Project Title: Catalyzing women's participation in agribusiness and post-COVID-19 recovery in Sao Tome and Principe

Project Number: award 00133968/output 00125689

Implementing Partner: Trade Directorate

Enforcement Agent: Trade Directorate

Start Date: 15-02-2021			End Date: 15-06-2022

Date of the Local Project Approval Committee (LPAC) Meeting: 15-02-2021

Brief Description

The project will promote inclusive growth and diversification by supporting the development of selected agribusiness value chains in high value niche crops, focusing especially on European markets and new export markets, including in the new African Continental Free Trade Area. The approach chosen by this project is that the development of value chains will be demand driven rather than supply driven, through partnerships with leading buyers and distribution networks that are active in highly segmented markets for bio and eco labeled agricultural products. In this context, the project is expected to generate significant employment and income opportunities, especially among women during this post covid-19 recovery phase. The project will also contribute indirectly to a number of desirable social protection and cohesion issues, such as the aforementioned employability and gender sensitivity, as well as the promotion of efficient management tools and access to finance, which are also central to UNDP's work in STP. Business environment The project will also promote the reduction of red tape and improve digital services provided by public administration, especially in the export sector, and introduce an arbitration centre as an alternative process for resolving commercial disputes, considering that the World Bank's Doing Business Report 2020 ranked STP 185th out of 190 countries in contract enforcement.

| Total resources required (USD): | 1.500.000 |
| --- | --- |
| Total resources allocated (USD): |  |
|  | UNDP TRAC: |  |
|  | Others:Reponses to COVID-19: |  |
|  | Government: | 0,00 |
|  | In-Kind: | 0,00 |
| Unfunded: | 0,00 |

Agreed by

| Government | UNDP |
| --- | --- |
| Eugénio António Sacramento da Graça State Secretary for Trade and Industry | Katarzyna Wawiernia Resident Representative |
| Date: 15-02-2021 | Date: 15-02-2021 |

# Purpose and Expected Output

- STP has achieved notable progress in terms of human development, especially driven by public investments in health and education. However, its economy shows the typical criticalities and dependencies of a small developing island state that underpin its limited capacity to generate business opportunities and create enough productive jobs. As a result, STP economic growth has not been inclusive. The arrival of Covid-19 has been further exacerbating this context of poverty and inequality.

- The government is mindful that, in order to develop this economic potential, as a small market the country has no choice but to reach out to foreign markets and investors - both regional and overseas - to expand its markets, while effectively strengthening the country current limited competitiveness.   It is also within this context that STP recently ratified and started the implementation of the African Continental Free Trade Area, with a view to accelerating its integration process with the African continent.

- Largely unexploited, agriculture is one of most promising sectors to generate business (especially for SMEs) and job opportunities (especially for women) for a more balanced and inclusive growth path.  However, limited investments in business know-how and capital, and the need to further accelerate governance reforms to easy the cost of doing business are all necessary conditions to unlock this potential.

- This project wants to contribute to reap part of this potential and address some of the most urgent bottlenecks. The project will promote inclusive growth and diversification by supporting the development of selected agribusiness value chains in high value niche crops, focusing especially on European markets and new export markets, including in the new African Continental Free Trade Area.  The focus of this project will be to empower women and SMEs to develop products that respond to the markets and buyer’s needs. This will be facilitated through two interlinked activities.

- First, the proposed project aims to identify markets (and especially export markets) and networks potentially interested in the agricultural products produced in STP, subject to the achievement of certain level of quality and standards required by the final markets.

- In parallel, it will contribute to tackle some of most pressing impediments to trade in the terms of governance, helping create a more predictable business operating environment, with more robust legal and regulatory frameworks, a reduction in "red tape" to improve the ease of doing business, and will encourage investors to choose STP..

- These two activities will have the dual impact of linking producers to markets and investors to producers, all in the context of increasing women's participation in the sector.

- Through its global networks and expertise, the project will build on on-going UNDP initiatives to boost the private sector. UNDP will provide targeted technical assistance to institutions working in key agribusiness sectors by capitalizing on the network of incubators and mentoring skills created by an on-going UNDP project promoting youth entrepreneurship that over the past two-years has mobilized more than 1000 young entrepreneurs and has become a flagship initiative for the GoSTP.

- UNDP will help identify value chains in export markets and tailor them to local potential to meet international market requirements. UNDP will also help identify potential importers and support in establishing business partnerships with local producers. It is hoped that this will orient the focus of the agribusiness sector in STP, directing it to meet the export market.

- Leading the Green Economy: Strategically, support for agribusiness (including processing/processing) is seen as an important catalyst for expanding STP's footprint in the emerging global Green Economy. The limited size and purchasing power of the domestic market has been a brake on making this shift. With support through the proposed RFF project, the best quality products with added value will be marketed in Europe and other target markets. The proposed project will provide significant opportunities for growth, investment, and livelihoods to help bring about this change. Particularly in STP where agriculture contributes significantly to GDP (about 10%) and leads the way in poverty reduction and employment opportunities, especially for women.

- Reduce bureaucracy: Another key objective of the project is to help reduce delays, inefficiencies, and lack of transparency in public administration related to "red tape". In particular, the project aims to alleviate the burden and lack of clarity of institutional and cumbersome export procedures by establishing a web portal for exporters that will connect investors and local producers. This initiative builds on the existing one-stop shop for establishing new companies that works successfully under the Ministry of Finance and Planning and allows for the establishment of a company in 5 days at a cost of US$200. On the other hand, expanding the use of ICT services focused on e-commerce, for example, will enable the collection, processing and sharing of data, as well as the standardization of procedures that will streamline digital certification on export/customs permits required in trade. Over time, these changes will be instrumental in adding new electronic activities and products (i.e. business creation, payment of duties and taxes). At an outcome level, it is hoped that streamlining trade regulations can create confidence and attract new financial flows.

- Create greater legal certainty: Agribusiness requires a conducive, stable and enabling business climate, just like any other business venture. To help foster these conditions in STP, this project will benefit from an ongoing UNDP project designed to support the Government to create a Dispute Arbitration Center, through a Public-Private Partnership with the Chamber of Commerce, to help build investor confidence. Resolving commercial disputes and legal conflicts are identified by the World Bank as the number one bottleneck to investment in the country. Using arbitration as an alternative mechanism to resolve commercial disputes and legal conflicts - notably export-related issues - through the court system will hopefully create efficiency, confidence and reduce risk for investors and potential importers.

- The establishment of the Arbitration Center (AC) is expected to improve formal economic activity among micro, small and medium enterprises (MSMEs).

- Main Objective: Based on STP´s COVID-19 livelihood and recovery priorities and the project´s Theory of Change (Figure 1 bellow), the main objective is to boost active participation in the embryonic agribusiness sector in Sao Tome and Principe and address the competitiveness in the countries business operating climate. The project will achieve this objective by delivering outputs in four key areas.

Figure 1: Theory of Change

| Key results: | Contributes to: | National Development Goal: |
| --- | --- | --- |
| Connecting local businesses with external markets and specialized business partners to identify specific demands for high value-added chains | Improving productivity and expanding the potential of bringing to market (and especially exportation markets) many of the high-value crops produced in STP especially by women and smallholder farmers | Promote more inclusive economic growth and diversification |
| Increasing the quality and standards of local agri-business productions |  |  |
| Reviewing legal frameworks on trade and agribusiness sectors and creating a Dispute Arbitration Centre. | Improving World Bank Ease of Doing Business Ranking, creating more favourable conditions for investment and expanding exportation potential. |  |
| Streamlining red-tape, inefficiency and lack of transparency in public administration including through digitalization to support local production and exports development along the identified value chains |  |  |

- The expected outputs of the project are the following:

- Increased capacity in business management, trade, and access to finance and technology by women and small farmers by:

a. Training agribusiness owners in export procedures and licensing

b. Building technical, technological, and managerial capacity of business owners, with a strong focus on women-led enterprises, using the existing business incubator network supported by the Ministry of Youth/UNDP

As the rehabilitation of the São Tomé incubator structure is still under way, the project will co-finance its completion

c. Increasing access to finance (credit, grants, innovation challenge)

d. Promoting technology transfer (production and commercialization) to promote the "greening" of the proposed value chains.

To achieve this result, an international consultancy will be hired to survey the needs of each of these companies to assess the challenges, opportunities, identify the specific technical, technological and organizational capabilities that need to be strengthened, as well as gaps along the value chain in order to develop their products and sell them internationally.  The services of this consultancy will extend to the other results

- Increased production of high-value crops, especially those produced by women and smallholder farmers, and promoted through access to new international markets by:

a. Supporting the certification process (e.g., Organic and/or Fair Trade).

b. Producing market intelligence that identifies value chains, markets and partners (distribution network and buyers) with the greatest potential, with business vision and marketing models based on principles of bio, eco, fair, responsible trade, etc.

c. Support organization and networking among local companies and with external partners to improve the approach to export markets (especially in terms of quality and standards), ensuring a gender balance in decision-making among women led local companies, including in joint logistics.

To achieve this result, an international consultancy will be contracted to carry out the training and subsequent certification along the value chain.

- Targeted technical support to overcome the country's bureaucratic barriers to export and trade:

a. Support for the establishment of a "one-stop-one" for exporters, an export helpdesk to guide companies on regulations and procedures for placing products on the international market

b. Development of a roadmap for exporters, streamlining export procedures specifically for the mostly women-operated agro-processing business.

c. Create a consultative mechanism between the exporting companies and the representatives of the institutions involved in exporting to share information, discuss opportunities and concerns, and address any eventual issue.

To achieve this objective, the Sydonia system of the Guichet Unico will be updated, associated to a portal where it will be possible to carry out simulations at the level of export costs, consult prices, etc. A national consultancy will be contracted to draw up the "exporter's guide or roadmap".

- Domestic barriers to agricultural exports have decreased through the adoption of dispute settlement mechanisms and expansion of e-governance services:

a. Improve the National Arbitration Centre (NAC) to resolve legal and commercial disputes, mitigate contract enforcement risks and improve the country's business environment.

b. Providing access to legal information and legal advice services to women-owned agribusiness SMEs.

This will be achieved through the rehabilitation of the NAC structure, the identification and training of arbitrators, the identification of pending commercial cases in the courts and forwarding them to the CNA, and the revitalization of the CNA through the establishment of new international partnerships.

Additionally, it is foreseen to hire national legal advisors (on retainer) to advise exporting companies on international trade issues

# Partnerships

The implementation of this project will be led by the State Secretary for Trade and Industry                                          , and coordinated with other key government stakeholders, namely:  Ministry of Justice, Public Administration and Human Rights, supporting the establishment of the arbitration Centre and  digitalization; Ministry of Youth and Entrepreneurship, supporting the training activities through the network of incubators and mentoring facilities; Ministry of Agriculture, supporting the identification of farmers and areas of production to enhance processors’ supply sources and also assuring alignment and coordination with on-going projects; Ministry of Finance and Planning, assuring the overall alignment with national strategies and policies. Working in tandem with the Secretary of State, UNDP will provide technical and coordination support in the execution of the project.

UNDP will further collaborate with the following donors and UN partners: i) mainly with IFAD  ii) AfDB, that holds the Lusophone compact with whom UNDP will engage to develop a specific line to support agri-processors; iii) FAO, that supports the improvement of agricultural production; and iv) Portugal/ EU that will be starting a new project in 2021 which will provide support to export products.  UNDP has already contacted key private sector operators in the agribusiness/processing sector such as Valudo (coconut oil producer and exporter), Agripalma (palm oil producer and exporter), Delicias das Ilhas (soap and dried fruits processer and occasional exporter), Coralo (chocolate maker and exporter), and Fluta Non (association of dried fruits and flours producers).  Building on these existing networks the project will connect nascent enterprises with more established agri-business ventures and institutional players.

Under the lead of the Chamber of Commerce, industry, Agriculture and Services the design and functioning of the Arbitration Center will be based on the Law governing arbitration, a consultative process with local women´s groups, government focal points, the agribusiness private sector, CSOs, and international partners. UNDP, in collaboration with the Chamber and key stakeholders, will provide training and information sessions to agrobusiness’s institutions on legal and commercial information related to the export agri-business.  In the area of digitalization, UNDP will work closely with the government´s Institute of Innovation and Knowledge and the private sector (e.g. national communication company), CSOs and international partners to expand the e-commerce footprint in the export arena.  This has become even more important as the new African Continental Free Trade Area comes into effect in January 2021- providing both risks and opportunities for the small island state which is dwarfed by many of its neighbours.

# Monitoring

UNDP will play a role in overall technical and financial oversight and quality assurance of the project. This will involve UNDP staff from the country office, Regional Bureau and Headquarters specific units. The quality assurance of the project is independent of the project management function.

UNDP will prepare and communicate the explanatory and financial reports in accordance with its reports on policies and procedures and operational guidelines. Also, UNDP, in its project quality assurance function, will feed data from the monitoring reports to the Atlas system, including:

- update of the related risks and problems encountered in Atlas at the end of each quarter.

- based on information entered in Atlas, a quarterly report from Atlas will be submitted to the IA;

- the monitoring plan will be updated regularly in Atlas to record the major follow-up actions.

Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk.

Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated into the project.

# Management Arrangements

The project will be implemented through the NIM implementation modality by the State Secretariat for Trade and Industry (SETI) as the National Implementing Partner (NIP).The UNDP office will provide specific support services for proper implementation as needed through its Administrative, Programmatic and Financial Units. Due to the nature of the project and the short implementation period, no additional structures will be set up disconnected from the implementing entities.

The UNDP office in Sao Tome and Principe will provide implementation support services, which include the following:

- Communications: to transmit project results through UNDP media such as social networks and website.

- Human resources: support with the recruitment, selection, hiring and administration of project staff contracts.

- Procurement: assistance in the procurement of good or services on behalf of the project, covering the entire procurement cycle.

- Finance: direct payment requests;

- Advice and technical support: for the proper implementation of the project according to rules and procedures, including contract management.

- Follow-up reporting and documentation of lessons learned: evidence-based reporting on results achieved compared to baseline and assessment; meeting substantive reporting requirements

- Advocacy: effective advocacy, media interaction, public information, and communication of the Project's activities as part of the broader communication and advocacy activities of UNDP and partner.

The institutional arrangements in relation to these services are reflected in the "Memorandum of Understanding" and the "Description of the services provided by the Country Bureau" both annexed to this Initiation Plan.

The release and allocation of funds will be in accordance with the tasks outlined in the annual workplans (AWP).

Throughout the implementation period, UNDP is committed to carry out the micro evaluation of the partner. This procedure is aimed at knowing the internal capacities for project management of the ministry's structure and serves to prepare an objective plan for project capacity building.

The Project will be subject to a final external and independent audit, carried out by an international audit firm. The reports and documents requested by the audit firm will be made available to them by both UNDP and Partner. The costs of the audit will be supported by the Project.

## Risks and assumptions

- The full risk matrix is attached to this PRODOC. However, the main risks that may affect the project are indicated in the following table along with the likelihood of their occurrence and the proposed mitigation measure:

| RISK | PROBABILITY | MITIGATION MEASURE |
| --- | --- | --- |
| Political Low political ownership, lack of support and high level commitment Government involvement in the improvement of Sao Tome and Principe's foreign trade | Moderate | Permanent involvement in project implementation of authorities and decision makers Negotiation with UNCTAD for the Creation of an Export Portal |
| Social Abandonment of companies that are not strategically prepared to reach the export market: "Leave them behind". | Moderate | Categorisation of companies (3 groups of companies) according to their organisation: - 1st category of companies: are more advanced companies in terms of organization: they will be given support in terms of the market requirement ( Fair Trade, Gluten Free, PGI, HCCP, Global Gap, etc.); - Second group of companies: these are the ones that have interesting products, but have not yet evaluated the production costs that are viable for the export market: this group will be the focus of the hired consultancy (CESO/Consultant Certification Rogério) - For the third group of companies, a growth plan will be created for them in order for them to benefit from other financing in the future (but they will not be left behind). |
| Financial Ability of firms to continue with the same post-project export strategies (self-sustainability) | Moderate | A programme is needed to accompany these companies post-project. |
| Technical Weak/Non Involvement of Partner Companies Applying to the Project. | Moderate | Signature of Full Engagement/Commitment of Candidate Companies to Support the Project. |

# Results Matrix

| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE | DATA COLLECTION METHODS & RISKS |
| --- | --- | --- | --- | --- |
|  |  |  | Value | Year |  |
| Output 1 Aumento da qualidade da produção local do agronegócio (incluindo o processamento) por mulheres e pequenos agricultores | 1.1 Number of Companies Strengthened and Well Positioned in the Market (Internal and External) | Project Reports | 0 | 2022 |  |
|  | 1.2 Number of Companies with a Well Established/Organised Growth Plan | Project Reports | 0 | 2022 |  |
|  | 1.3 Number of Companies with all Transformation Chains Equipped with Modern Equipment / Modern Technology | Project Reports | 0 | 2022 |  |
| Output 2 Aumento da produção de culturas de alto valor, especialmente as produzidas por mulheres e pequenos agricultores, e promovido através do acesso a novos mercados internacionais | 2.1 Number of Certified Companies (Organic, HCCP, Global Gap, Gluten Free) | Project Reports | 0 | 2022 |  |
|  | 2.2 Number of Trading Partners interested in Sao Tome and Principe products found and available to buy the products | Project Reports | 0 | 2022 |  |
|  | 2.3 Number of Companies Organized in Transformers/Agribusinesses Network: Joint Exports of Products | Project Reports | 0 | 2022 |  |
| Output 3 Apoio técnico orientado para a superação das barreiras burocráticas à exportação e ao comércio do país | 3.1 Single Export Desk Up and Running with Clear Regulations and Procedures Available to Exporters | Project Reports | 0 | 2022 |  |
|  | 3.2 Rationalised Export Roadmap with Procedures, Developed and Made Easy and Available to Exporters | Project Reports | 0 | 2022 |  |
| Output 4 Diminuição das barreiras domésticas às exportações agrícolas através da adopção de mecanismos de resolução de lítígios e expansão dos serviços de e-governação | 4.1 Arbitration Centre Created and Functioning | Project Reports | 0 | 2022 |  |
|  | 4.2 Legal information and advisory services to agribusiness SMEs provided by the arbitrators at the Arbitration Centre | Project Reports | 0 | 2022 |  |
|  | 4.3 Key government ministries related to agribusiness digitised | Project Reports | 0 | 2022 |  |
|  | 4.4 Computer literacy and ICT support in the agribusiness sector strengthened | Project Reports | 0 | 2022 |  |

# Monitoring And Evaluation

In accordance with UNDP’s programming policies and procedures, the project will be monitored through the following monitoring and evaluation plans:

| Monitoring Activity | Frequency | Action Envisaged | Resp |
| --- | --- | --- | --- |
| Monitoring progress | Quarterly | Collect information from the various project management reports and documents | UNDP/SSTI |
| Monitoring and Managing Risk | Quarterly | Raise the Companies' awareness of the Project's Objectives Encouraging social dialogue on national entrepreneurship issues | UNDP/ SSTI |
|  |  | Demonstration of successful agribusiness models, with community involvement for the credibility of the sector | UNDP/ SSTI |
| Lessons Learned | In the 2nd half of 2022 | Raise awareness among partners to learn lessons that can inform decision making. | UNDP/ SSTI |
| Quality Assurance Assessment | This is an initial short-term plan of the COVID-19 cooperation. It is therefore exempted | Areas of strength and weakness will be analysed by the Project Manager and used to inform decisions to improve project performance. | UNDP |
| Final Project Report | In the 4th Quarter 2022 | Recruitment of an independent national consultant for the final evaluation of the project, allowing quality concerns or other issues related to the operational performance of the project to be discussed at the project Steering Committee level for decision making. | UNDP |

# EXECUTION TIMETABLE AND BUDGET

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year | RESPONSIBLE PARTY |
| --- | --- | --- | --- |
|  |  |  |  | PLANNED BUDGET |
|  |  | Y1 |  | Funding Source | Budget Description | Amount |
| Output 1: Increased the quality of local agribusiness (including processing) production for by women and smallholder farmers by: Gender marker:01 | Activity 1 |
|  | 1.1 |  | UNDP/SSTI |  | " | 102000 |
|  |  |  | " |  |  |  |
|  | 1.2 |  | " |  |  | 70000 |
|  |  |  | " |  |  |  |
|  |  |  | " |  |  |  |
|  | 1.3 |  | " |  |  | 110000 |
|  | Sub-Total for Output 1 | 762000 |
| Output 2: Increased production of high-value crops, especially those produced by women and smallholder farmers, and promoted through access to new international markets by: Gender marker:02 | Activity 2 |
|  | 2.1 |  | " |  |  | 115000 |
|  | 2.2 |  | " |  |  | 57500 |
|  | 2.3 |  | " |  |  | 12000 |
|  | Sub-Total for Output 2 | 184500 |
| Output 3: Targeted technical support for overcoming the country’s bureaucratic barriers to export and trade established Gender marker:03 | Activity 3 |
|  | 3.1 |  |  |  |  | 105000 |
|  | 3.2 |  | " |  |  | 13000 |
|  | Sub-Total for Output 3 | 118000 |
| Output 4: Domestic barriers to Agri-exports decreased through adoption of modern dispute resolution mechanisms and expansion of e-governance services Gender marker:04 | Activity 4 |
|  | 4.1 |  | " |  |  | 187500 |
|  | 4.2 |  | " |  |  | 5500 |
|  | 4.3 |  | " |  |  | 40000 |
|  | 4.4 |  | " |  |  | 5000 |
|  | Sub-Total for Output 4 | 238000 |
| General Management Support & Monitoring |  |  |  |  |  | 197500 |
| TOTAL (USD) |  | 1,500,000 |

# Project Management and Governance Arrangements

70.	UNDP will carry out project implementation supervision (quality assurance) and will be responsible for submitting progress, financial and completion reports to the Steering Committee. UNDP will submit the necessary reports on the implementation of the Project in terms of funds used, activities implemented, results obtained and results achieved. The aim is to support the Steering Committee to ensure objective achievement and independent supervision and monitoring of project results, thereby ensuring compliance of project targets and management indicators from start-up to completion of activities.

71.	The following organisation chart illustrates the management structure

# Legal Context

This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Sao Tome and Principe and UNDP, signed on 26th March 1976 (date).   All references in the SBAA to “Executing Agency” shall be deemed to refer to “Implementing Partner.”

This project will be implemented by Secretariat of State for Trade and Industry (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

# Risk Management

- Consistent with the Article III of the SBAA [or the Supplemental Provisions to the Project Document], the responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner.  To this end, the Implementing Partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan.

- UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of the Implementing Partner’s obligations under this Project Document.

- The Implementing Partner agrees to undertake all reasonable efforts to ensure that no UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.

- The Implementing Partner acknowledges and agrees that UNDP will not tolerate sexual harassment and sexual exploitation and abuse of anyone by the Implementing Partner, and each of its responsible parties, their respective sub-recipients and other entities involved in Project implementation, either as contractors or subcontractors and their personnel, and any individuals performing services for them under the Project Document.

(a) In the implementation of the activities under this Project Document, the Implementing Partner, and each of its sub-parties referred to above, shall comply with the standards of conduct set forth in the Secretary General’s Bulletin ST/SGB/2003/13 of 9 October 2003, concerning “Special measures for protection from sexual exploitation and sexual abuse” (“SEA”).

(b) Moreover, and without limitation to the application of other regulations, rules, policies and procedures bearing upon the performance of the activities under this Project Document, in the implementation of activities, the Implementing Partner, and each of its sub-parties referred to above, shall not engage in any form of sexual harassment (“SH”). SH is defined as any unwelcome conduct of a sexual nature that might reasonably be expected or be perceived to cause offense or humiliation, when such conduct interferes with work, is made a condition of employment or creates an intimidating, hostile or offensive work environment.

- a) In the performance of the activities under this Project Document, the Implementing Partner shall (with respect to its own activities), and shall require from its sub-parties referred to in paragraph 4 (with respect to their activities) that they, have minimum standards and procedures in place, or a plan to develop and/or improve such standards and procedures in order to be able to take effective preventive and investigative action. These should include: policies on sexual harassment and sexual exploitation and abuse; policies on whistleblowing/protection against retaliation; and complaints, disciplinary and investigative mechanisms. In line with this, the Implementing Partner will and will require that such sub-parties will take all appropriate measures to:

  - Prevent its employees, agents or any other persons engaged to perform any services under this Project Document, from engaging in SH or SEA;

  - Offer employees and associated personnel training on prevention and response to SH and SEA, where the Implementing Partner and its sub-parties referred to in paragraph 4 have not put in place its own training regarding the prevention of SH and SEA, the Implementing Partner and its sub-parties may use the training material available at UNDP;

  - Report and monitor allegations of SH and SEA of which the Implementing Partner and its sub-parties referred to in paragraph 4 have been informed or have otherwise become aware, and status thereof;

  - Refer victims/survivors of SH and SEA to safe and confidential victim assistance; and

  - Promptly and confidentially record and investigate any allegations credible enough to warrant an investigation of SH or SEA. The Implementing Partner shall advise UNDP of any such allegations received and investigations being conducted by itself or any of its sub-parties referred to in paragraph 4 with respect to their activities under the Project Document, and shall keep UNDP informed during the investigation by it or any of such sub-parties, to the extent that such notification (i) does not jeopardize the conduct of the investigation, including but not limited to the safety or security of persons, and/or (ii) is not in contravention of any laws applicable to it. Following the investigation, the Implementing Partner shall advise UNDP of any actions taken by it or any of the other entities further to the investigation.

b) The Implementing Partner shall establish that it has complied with the foregoing, to the satisfaction of UNDP, when requested by UNDP or any party acting on its behalf to provide such confirmation. Failure of the Implementing Partner, and each of its sub-parties referred to in paragraph 4, to comply of the foregoing, as determined by UNDP, shall be considered grounds for suspension or termination of the Project.

- Social and environmental sustainability will be enhanced through application of the UNDP Social and Environmental Standards (http://www.undp.org/ses) and related Accountability Mechanism (http://www.undp.org/secu-srm).

- The Implementing Partner shall: (a) conduct project and programme-related activities in a manner consistent with the UNDP Social and Environmental Standards, (b) implement any management or mitigation plan prepared for the project or programme to comply with such standards, and (c) engage in a constructive and timely manner to address any concerns and complaints raised through the Accountability Mechanism. UNDP will seek to ensure that communities and other project stakeholders are informed of and have access to the Accountability Mechanism.

- All signatories to the Project Document shall cooperate in good faith with any exercise to evaluate any programme or project-related commitments or compliance with the UNDP Social and Environmental Standards. This includes providing access to project sites, relevant personnel, information, and documentation.

- The Implementing Partner will take appropriate steps to prevent misuse of funds, fraud or corruption, by its officials, consultants, responsible parties, subcontractors and sub-recipients in implementing the project or using UNDP funds.  The Implementing Partner will ensure that its financial management, anti-corruption and anti-fraud policies are in place and enforced for all funding received from or through UNDP.

- The requirements of the following documents, then in force at the time of signature of the Project Document, apply to the Implementing Partner: (a) UNDP Policy on Fraud and other Corrupt Practices and (b) UNDP Office of Audit and Investigations Investigation Guidelines. The Implementing Partner agrees to the requirements of the above documents, which are an integral part of this Project Document and are available online at www.undp.org.

- In the event that an investigation is required, UNDP has the obligation to conduct investigations relating to any aspect of UNDP projects and programmes in accordance with UNDP’s regulations, rules, policies and procedures. The Implementing Partner shall provide its full cooperation, including making available personnel, relevant documentation, and granting access to the Implementing Partner’s (and its consultants’, responsible parties’, subcontractors’ and sub-recipients’) premises, for such purposes at reasonable times and on reasonable conditions as may be required for the purpose of an investigation. Should there be a limitation in meeting this obligation, UNDP shall consult with the Implementing Partner to find a solution.

- The signatories to this Project Document will promptly inform one another in case of any incidence of inappropriate use of funds, or credible allegation of fraud or corruption with due confidentiality.

- Where the Implementing Partner becomes aware that a UNDP project or activity, in whole or in part, is the focus of investigation for alleged fraud/corruption, the Implementing Partner will inform the UNDP Resident Representative/Head of Office, who will promptly inform UNDP’s Office of Audit and Investigations (OAI). The Implementing Partner shall provide regular updates to the head of UNDP in the country and OAI of the status of, and actions relating to, such investigation.

- UNDP shall be entitled to a refund from the Implementing Partner of any funds provided that have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.  Such amount may be deducted by UNDP from any payment due to the Implementing Partner under this or any other agreement.  Recovery of such amount by UNDP shall not diminish or curtail the Implementing Partner’s obligations under this Project Document.

- Where such funds have not been refunded to UNDP, the Implementing Partner agrees that donors to UNDP (including the Government) whose funding is the source, in whole or in part, of the funds for the activities under this Project Document, may seek recourse to the Implementing Partner for the recovery of any funds determined by UNDP to have been used inappropriately, including through fraud or corruption, or otherwise paid other than in accordance with the terms and conditions of the Project Document.

Note:  The term “Project Document” as used in this clause shall be deemed to include any relevant subsidiary agreement further to the Project Document, including those with responsible parties, subcontractors and sub-recipients.

- Each contract issued by the Implementing Partner in connection with this Project Document shall include a provision representing that no fees, gratuities, rebates, gifts, commissions or other payments, other than those shown in the proposal, have been given, received, or promised in connection with the selection process or in contract execution, and that the recipient of funds from the Implementing Partner shall cooperate with any and all investigations and post-payment audits.

- Should UNDP refer to the relevant national authorities for appropriate legal action any alleged wrongdoing relating to the project, the Government will ensure that the relevant national authorities shall actively investigate the same and take appropriate legal action against all individuals found to have participated in the wrongdoing, recover and return any recovered funds to UNDP.

- The Implementing Partner shall ensure that all of its obligations set forth under this section entitled “Risk Management” are passed on to each responsible party, subcontractor and sub-recipient and that all the clauses under this section entitled “Risk Management Standard Clauses” are included, mutatis mutandis, in all sub-contracts or sub-agreements entered into further to this Project Document.

# ANNEXES

- Social and Environmental Screening Template [English] [French] [Spanish], including additional Social and Environmental Assessments or Management Plans as relevant. (NOTE: The SES Screening is not required for projects in which UNDP is Administrative Agent only and/or projects comprised solely of reports, coordination of events, trainings, workshops, meetings, conferences, preparation of communication materials, strengthening capacities of partners to participate in international negotiations and conferences, partnership coordination and management of networks, or global/regional projects with no country level activities).

- Risk Analysis. Use the standard Risk Register template. Please refer to the Deliverable Description of the Risk Register for instructions

- Capacity Assessment: Results of capacity assessments of Implementing Partner (including HACT Micro Assessment)

- Project Board Terms of Reference and TORs of key management positions

# ANNEXE 1 Social and Environmental Screening Template

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document at the design stage. Please refer to the Social and Environmental Screening Procedure and Toolkit for guidance on how to answer the 6 questions.

Project Information

| Project Information |  |
| --- | --- |
| Project Title | Catalyzing women's participation in agribusiness and post-COVID-19 recovery in Sao Tome and Principe |
| Project Number | 00133968/00125689 |
| Location (Global/Region/Country) | RBA/Sao Tome and Principe |

Part A. Integrating Programming Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Programming Principles in Order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the project mainstreams the human rights-based approach

Unlocking bottlenecks in the agribusiness sector is a key policy option to make the country's socio-economic development more sustainable and resilient to future shocks. Following the successful focus on increasing and improving agricultural production of quality products: cocoa, coffee, pepper, vanilla, coconut, palm, the next step should focus on transformation and value added. A vibrant private sector needs to be promoted. The sector is small, largely informal and lacks the skills and capital needed to seize opportunities and keep pace with population growth. It is also constrained by an overly bureaucratic business environment that often stifles commercial activity. Contract enforcement and inefficient commercial dispute resolution remain among the weakest business indicators, which combined with other bureaucratic processes such as those for import and export activities, severely undermine STP's business climate and ability to attract foreign direct investment (FDI).

Briefly describe in the space below how the project is likely to improve gender equality and women’s empowerment

Gender will be at the core of this project, offering equal opportunities to both male and female processors/processors. Largely untapped, agriculture is one of the most promising sectors to generate business (especially for SMEs) and employment opportunities (especially for women) for a more balanced and inclusive growth path. However, limited investments in know-how and business capital, and the need to further accelerate governance reforms to ease the cost of doing business are all necessary conditions to unlock this potential. This project aims to help reap some of this potential and address some of the most pressing bottlenecks. The project will promote inclusive growth and diversification by supporting the development of selected agribusiness value chains in high-value niche crops, focusing especially on European markets and new export markets, including in the new African Continental Free Trade Area. The focus of this project will be on building the capacity of women and SMEs to develop products that respond to markets and buyers' needs. This will be facilitated through two interlinked activities.

Briefly describe in the space below how the project mainstreams sustainability and resilience

Based on STP's COVID-19, livelihood and recovery priorities and the project's Theory of Change, the main objective is to drive active participation in the embryonic agribusiness sector in São Tomé and Príncipe and address competitiveness in First, the proposed project aims to identify markets (and especially export markets) and networks potentially interested in agricultural products produced in STP, subject to the achievement of a certain level of quality and standards required by end markets. In parallel, it will help address some of the most pressing governance impediments to trade by helping to create a more predictable business operating environment with more robust legal and regulatory frameworks, a reduction in "red tape" to improve the ease of doing business, and encourage investors to choose STP

Part B. Identifying and Managing Social and Environmental Risks

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Briefly describe the potential social and environmental risks identified in Annex 1- Risk Checklist (based on any "Yes" answers). If no risks have been identified, skip Question 4 and select 'Low Risk'. Questions 5 and 6 are not required for low risk projects. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5below before proceeding to Question 6 | QUESTION 6: What Social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for risk with Moderate and High Significance) |
| --- | --- | --- |
| Risk Description | Impact and Likelihood (1-5) | Significance (Low, Moderate, High) | Comments | Description of assessment and management measures as reflected in the Project design. If ESIA or SESA is required note that the assessment should considerer all potential impact and risk |
| Risk 1: Low political ownership, lack of support and high level commitment Government involvement in the improvement of Sao Tome and Principe's foreign trade | I = L = | Moderate | Permanent involvement in project implementation of authorities and decision makers Negotiation with UNCTAD for the Creation of an Export Portal | All stakeholders are involved and there is great ownership of the project by the lead partner The project has been working with the relevant t institutions already established. |
| Risk 2: Social: Abandonment of companies that are not strategically prepared to reach the export market: "Leave them behind". | I = L = | Moderate | Categorisation of companies (3 groups of companies) according to their organisation: - 1st category of companies: are more advanced companies in terms of organization: they will be given support in terms of the market requirement ( Fair Trade, Gluten Free, PGI, HCCP, Global Gap, etc.); - Second group of companies: these are the ones that have interesting products, but have not yet evaluated the production costs that are viable for the export market: this group will be the focus of the hired consultancy (CESO/Consultant Certification Rogério) - For the third group of companies, a growth plan will be created for them in order for them to benefit from other financing in the future (but they will not be left behind). | Verification will be possible when the training sessions begin on the part of the consultancies with the candidate companies who are partners in the project. |
| Risk 3: Financial: Ability of firms to continue with the same post-project export strategies (self-sustainability) | I = L = | Moderate | A programme is needed to accompany these companies post-project. | With regard to this challenge, monitoring is carried out in loco, together with the consultants hired and also the companies benefiting from the project |
| Risk 4: Technical :Weak/Non Involvement of Partner Companies Applying to the Project. | I = L = | Moderate | Signature of Full Engagement/Commitment of Candidate Companies to Support the Project. | With regard to this challenge, monitoring is carried out in loco, together with the consultants hired and also the companies benefiting from the project |
|  | QUESTION 4: What is the overall project risk categorization? |
|  | Select one (see SESP for Guidance) Comments |
|  | Medium Risk | ☐ | The risk will be minimised with the application of mitigation mitigation measures during the project. |
|  | Moderate Risk | ☐ |  |
|  | High Risk | ☐ |  |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |
|  | Check all that apply |  | Comments |
|  | Principle 1: Human Rights | ☐ | The project addresses the improvement of Human Rights, through the investment of all involved in the agribusiness/processing sector |
|  | Principle 2: Gender Equality and Women’s Empowerment | ☐ | The project will provide better business practices to women-led SMEs through capacity building |
|  | 1. Biodiversity Conservation and Sustainable Natural Resource Management | ☐ | The project has no impact on Biodiversity Conservation and Natural Resources Management |
|  | 2. Climate Change and Disaster Risks | ☐ | The project has no impact on Mitigation and Adaptation to Climate Change |
|  | 3. Community Health, Safety and Security | ☐ | The project impacts on community health through the challenge of responding to the Covid-19 pandemic. |
|  | 4. Cultural Heritage | ☐ | The project has no impact on cultural heritage, because its implementation consists in supporting small home-based units processing local products to reach the export market. |
|  | 5. Displacement and Resettlement | ☐ | The project has no impact on displacement and resettlement The project has no impact on displacement and resettlement. No new facilities will be built for beneficiary companies; the project will support the modernisation of equipment used along the value chain. |
|  | 6. Indigenous Peoples | ☐ | The project has no impact on indigenous peacocks |
|  | 7. Labour and Working Conditions | ☐ | The project has no impact on Pollution Prevention and Resource Efficiency |

Final Sign Off

Final Screening at the design-stage is not complete until the following signatures are included

| Signature | Date | Description |
| --- | --- | --- |
| QA Assessor |  | UNDP staff member responsible for the project, typically a UNDP Programme Officer. Final signature confirms they have “checked” to ensure that the SESP is adequately conducted. |
| QA Approver |  | UNDP senior manager, typically the UNDP Deputy Country Director (DCD), Country Director (CD), Deputy Resident Representative (DRR), or Resident Representative (RR). The QA Approver cannot also be the QA Assessor. Final signature confirms they have “cleared” the SESP prior to submittal to the PAC. |
| PAC Chair |  | UNDP chair of the PAC. In some cases PAC Chair may also be the QA Approver. Final signature confirms that the SESP was considered as part of the project appraisal and considered in recommendations of the PAC. |

### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principle 1: Human Rights | Answer (Yes/No) |
| P.1 Have local communities or individuals raised human rights concerns regarding the project (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 Is there a risk that duty-bearers (e.g. government agencies) do not have the capacity to meet their obligations in the project? | No |
| P.3 Is there a risk that rights-holders (e.g. project-affected persons) do not have the capacity to claim their rights? | No |
| P.4 adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| P.5 inequitable or discriminatory impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups, including persons with disabilities? | No |
| P.6 restrictions in availability, quality of and/or access to resources or basic services, in particular to marginalized individuals or groups, including persons with disabilities? | No |
| P.7 exacerbation of conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| P.1 Have women’s groups/leaders raised gender equality concerns regarding the project, (e.g. during the stakeholder engagement process, grievance processes, public statements)? | No |
| P.2 adverse impacts on gender equality and/or the situation of women and girls? | No |
| P.3 reproducing discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | No |
| P.4 limitations on women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| P.5 exacerbation of risks of gender-based violence? For example, through the influx of workers to a community, changes in community and household power dynamics, increased exposure to unsafe public places and/or transport, etc. | No |
| Principle 3: Environmental Sustainability and Resilience: Screening questions regarding risks associated with sustainability and resilience are encompassed by the Standard-specific questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 activities within or adjacent to critical habitats and/or environmentally sensitive areas, including (but not limited to) legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 risks to endangered species (e.g. reduction, encroachment on habitat)? | No |
| 1.5 exacerbation of illegal wildlife trade? | No |
| 1.6 introduction of invasive alien species? | No |
| 1.7 adverse impacts on soils? | No |
| 1.8 harvesting of natural forests, plantation development, or reforestation? | No |
| 1.9 significant agricultural production? | No |
| 1.10 animal husbandry or harvesting of fish populations or other aquatic species? | No |
| 1.11 significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.12 handling or utilization of genetically modified organisms/living modified organisms? | No |
| 1.13 utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.14 adverse transboundary or global environmental concerns? | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 areas subject to hazards such as earthquakes, floods, landslides, severe winds, storm surges, tsunami or volcanic eruptions? | No |
| 2.2 outputs and outcomes sensitive or vulnerable to potential impacts of climate change or disasters? For example, through increased precipitation, drought, temperature, salinity, extreme events, earthquakes | No |
| 2.3 increases in vulnerability to climate change impacts or disaster risks now or in the future (also known as maladaptive or negative coping practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| 2.4 increases of greenhouse gas emissions, black carbon emissions or other drivers of climate change? | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 construction and/or infrastructure development (e.g. roads, buildings, dams)? (Note: the GEF does not finance projects that would involve the construction or rehabilitation of large or complex dams) | No |
| 3.2 air pollution, noise, vibration, traffic, injuries, physical hazards, poor surface water quality due to runoff, erosion, sanitation? | No |
| 3.3 harm or losses due to failure of structural elements of the project (e.g. collapse of buildings or infrastructure)? | No |
| 3.4 risks of water-borne or other vector-borne diseases (e.g. temporary breeding habitats), communicable and noncommunicable diseases, nutritional disorders, mental health? | No |
| 3.5 transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.6 adverse impacts on ecosystems and ecosystem services relevant to communities’ health (e.g. food, surface water purification, natural buffers from flooding)? | No |
| 3.7 influx of project workers to project areas? | No |
| 3.8 engagement of security personnel to protect facilities and property or to support project activities? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 activities adjacent to or within a Cultural Heritage site? | No |
| 4.2 significant excavations, demolitions, movement of earth, flooding or other environmental changes? | No |
| 4.3 adverse impacts to sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.4 alterations to landscapes and natural features with cultural significance? | No |
| 4.5 utilization of tangible and/or intangible forms (e.g. practices, traditional knowledge) of Cultural Heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 temporary or permanent and full or partial physical displacement (including people without legally recognizable claims to land)? | No |
| 5.2 economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 risk of forced evictions? | No |
| 5.4 impacts on or changes to land tenure arrangements and/or community based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 areas where indigenous peoples are present (including project area of influence)? | No |
| 6.2 activities located on lands and territories claimed by indigenous peoples? | No |
| 6.3 impacts (positive or negative) to the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to screening question 6.3 is “yes”, then the potential risk impacts are considered significant and the project would be categorized as either Substantial Risk or High Risk | No |
| 6.4 the absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? Consider, and where appropriate ensure, consistency with the answers under Standard 5 above | No |
| 6.7 adverse impacts on the development priorities of indigenous peoples as defined by them? | No |
| 6.8 risks to the physical and cultural survival of indigenous peoples? | No |
| 6.9 impacts on the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? Consider, and where appropriate ensure, consistency with the answers under Standard 4 above. | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 the manufacture, trade, release, and/or use of hazardous materials and/or chemicals? | No |
| 7.4 the use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Montreal Protocol, Minamata Convention, Basel Convention, Rotterdam Convention, Stockholm Convention | No |
| 7.5 the application of pesticides that may have a negative effect on the environment or human health? | No |
| 7.6 significant consumption of raw materials, energy, and/or water? | No |

ANNEXE 2: OFFLINE RISK LOG

| Project Title: Catalyzing women's participation in agribusiness and post-COVID-19 recovery in Sao Tome and Principe | Award ID: 00133968 | Date: 15/02/2021 |
| --- | --- | --- |
| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| 1 | Low political ownership, lack of support and high level commitment Government involvement in the improvement of Sao Tome and Principe's foreign trade | February 2021 | Political | Enter probability on a scale from 1 (low) to 5 (high) P = 1 Enter impact on a scale from 1 (low) to 5 (high) I =1 | Permanent involvement in project implementation of authorities and decision makers (Secretary of State and Director of Trade) Negotiation with UNCTAD for the Creation of an Export Portal | UNDP/SSTI | Project Manager | December 2021 | Ongoing All stakeholders are involved and there is great ownership of the project by the lead partner The project has been working with the relevant t institutions already established. |
| 2 | Abandonment of companies that are not strategically prepared to reach the export market: "Leave them behind". | February 2021 | Social | Enter probability on a scale from 1 (low) to 5 (high) P = 1 Enter impact on a scale from 1 (low) to 5 (high) I =1 | Categorisation of companies (3 groups of companies) according to their organisation: - 1st category of companies: are more advanced companies in terms of organization: they will be given support in terms of the market requirement ( Fair Trade, Gluten Free, PGI, HCCP, Global Gap, etc.); - Second group of companies: these are the ones that have interesting products, but have not yet evaluated the production costs that are viable for the export market: this group will be the focus of the hired consultancy (CESO/Consultant Certification Rogério) - For the third group of companies, a growth plan will be created for them in order for them to benefit from other financing in the future (but they will not be left behind). | UNDP/SSTI | Project Manager | December 2021 | Verification will be possible when the training sessions begin on the part of the consultancies with the candidate companies who are partners in the project. |
| 3 | Ability of firms to continue with the same post-project export strategies (self-sustainability) | February 2021 | Financial | Enter probability on a scale from 1 (low) to 5 (high) P = 2 Enter impact on a scale from 1 (low) to 5 (high) I =3 | A programme is needed to accompany these companies post-project. | UNDP/SSTI | Project Manager | December 2021 | On going With regard to this challenge, monitoring is carried out in loco, together with the consultants hired and also the companies benefiting from the project |
| 4 | Weak/Non Involvement of Partner Companies Applying to the Project. | February 2021 | Technical | Enter probability on a scale from 1 (low) to 5 (high) P = 2 Enter impact on a scale from 1 (low) to 5 (high) I =3 | Signature of Full Engagement/Commitment of Candidate Companies to Support the Project. | UNDP/SSTI | Project Manager | December 2021 | With regard to this challenge, monitoring is carried out in loco, together with the consultants hired and also the companies benefiting from the project |

# Footnotes

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.

Prohibited grounds of discrimination include race, ethnicity, sex, age, language, disability, sexual orientation, gender identity, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender and transsexual people.

See the Convention on Biological Diversity and its Cartagena Protocol on Biosafety.

See the Convention on Biological Diversity and its Nagoya Protocol on access and benefit sharing from use of genetic resources.

Forced eviction is defined here as the permanent or temporary removal against their will of individuals, families or communities from the homes and/or land which they occupy, without the provision of, and access to, appropriate forms of legal or other protection. Forced evictions constitute gross violations of a range of internationally recognized human rights.

# Text boxes

Contributing to the UNDAF/CPD:

Employment and competitiveness are ensured through economic diversification, developing resilience to climate change, improving the quality of life of the poor and vulnerable in rural and urban environments, as well as access to finance and the market for young people and women

Indicative Product 1.1 & Investment in Gender:

Policies and programmes are adopted to stimulate competitiveness and employment, promote sustainable protection of the natural resources of neighbouring populations and green growth

Steering committee (governance mechanism)

Executive

RR/UNDP

SECRETARIAT OF STATE Development

CESA Portfolio

Trade Directorate

Project Management Team

UNDP + consultants + Secretariat of State