## Annual
IPMG Mechanism: Tasks | Months & Weeks
| January |  |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Updating NSP and preparing MTBP [footnote 1]
TechSec to discussions with ThG/IPMG Chairs for identifying funding priorities |  |  |  | x
Policy note to be submitted to SPC to inform on setting of budget sector ceilings | [5 empty] | x
Disaggregation of Budget Programmes ceiling allocations and funding priorities for each programme; discussion/decisions in ThGs | [9 empty] | x
IPMG reviews and decides on the celing allocations and funding priorities for each Programme | [12 empty] | x
Delivering final identified funding needs and allocation for first draft of the MTBP | [14 empty] | x
Reflection the comments by the MoF - Second phase of the MTBP preparation | [29 empty] | x
The IPMG reviews the final draft of allocations prior to submission to the relevant Ministry and Strategic Planning Committee (optional meeting) | [35 empty] | x
Reporting on IPA implementation [footnote 2]
IPA I Annual Report completion and consultation | [44 empty] | x
IPA II Annual Report completion and consultation | [14 empty] | x
Strategic programme monitoring
Regular consultations with national sector stakeholders on programme programmes' progress |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | [8 empty] | x |  |  |  | x |  |  |  |  | x |  |  |  | x
Regular consultations with DIPs on sector priorities, policies, financing and problematic isues |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x | [8 empty] | x | [8 empty] | x |  |  |  | x
First quarter monitoring report on implementation of sector strategies | [12 empty] | x
Semi-annual quarter monitoring report of implementation of sector strategies | [29 empty] | x
Third quarter monitoring report on implementation of sector strategic (this meeting is optional) | [40 empty] | x
Fourth quarter monitoring report on implementation of sector strategy | [49 empty] | x
IPMG/ThG meetings organisation [footnote 3]
TechSec/Chairs to prepare ThGs annual meeting calendear |  | x
TechSec/ThG Chairs to identify meeting topics and develop meeting agenda |  |  | x | x | [7 empty] | x | x | [15 empty] | x | x | [7 empty] | x | x
TechSec to prepare discussion paper on each meeting topic | [5 empty] | x | x | [8 empty] | x | [15 empty] | x | [8 empty] | x
ThG Chairs to send invitations to ThG meetings including meeting material/discussion papers (at least 2 weeks before the date of meeting) | [6 empty] | x | [8 empty] | x | [15 empty] | x | [8 empty] | x
Timing of ThG meetings | [8 empty] | 5 | 5 | [7 empty] | 5 | 5 | [14 empty] | 5 | 5 | [7 empty] | 5 | 5
ThG to prepare/submit draft ThG meeting minutes (withing 10 working days after the date of meeting) | [11 empty] | x | [8 empty] | x | [16 empty] | x | [8 empty] | x
ThG Chairs and Members to review/comment the minutes (within 10 working days from receiving) | [15 empty] | x | [7 empty] | x | [16 empty] | x | [8 empty] | x
After endorsing, TechSec to disseminate/post the minutes to the ministry website | [15 empty] | x | [7 empty] | x | [16 empty] | x | [8 empty] | x
TechSec and Chair to identify the IPMG meeting topics and develop the meeting agenda | [7 empty] | x | [8 empty] | x | [15 empty] | x | [8 empty] | x
IPMG Chair to submit meeting agenda to members (at least 10 days before the date of meeting) | [9 empty] | x | [8 empty] | x | [16 empty] | x | [8 empty] | x
TechSec to prepare discussion paper on each meeting topic | [10 empty] | x | [8 empty] | x | [16 empty] | x | [8 empty] | x
IPMG Chair to submit all meeting materials/documents to members (at least 5 days before the date of meeting) | [11 empty] | x | [8 empty] | x | [16 empty] | x | [8 empty] | x
Timing of IPMG meetings [footnote 4] | [12 empty] | 1 | [8 empty] | 1 | [16 empty] | 1 | [8 empty] | 1
TechSec to prepare/disseminate draft IPMG meeting minutes (within 7 days after the date of meeting) | [14 empty] | x | [7 empty] | x | [16 empty] | x | [8 empty] | x
IPMG members to provide comment/observation to the draft minutues (within 10 days from the submission) | [15 empty] | x | [7 empty] | x | [16 empty] | x | [8 empty] | x
IPMG Chair to provide the final version of the minutes (within 21 days after the date of IPMG meeting) | [16 empty] | x | [7 empty] | x | [16 empty] | x | [8 empty] | x
IPMG annual work plan (AWP) and Annual Progress Report (APR) [footnote 5]
TechSec prepares a draft of the AWP for the next year | [44 empty] | x
IPMG members circulate the AWP to the relevant actors within the entities they represent and seek their input into the endorsement process | [44 empty] | x
The IPMG considers and approves (amended as necessary) the AWP | [48 empty] | x
Upon endorsement by the IPMG, the Chair communicates the AWP to all sector stakeholders | [48 empty] | x
TechSec publishes the AWP on the relevant website | [49 empty] | x
TechSec to compile APR in direction of Chair | [51 empty] | x
Chair to table APR for endorsement in the first IPMG meeting of the calendar year | [12 empty] | x
Chair to submit the final version of the APR report to the SPC for consideration | [14 empty] | x
Following approval by the SPC, the Chair will provide all external stakeholders, including DIPs, with the final version of the APR. | [18 empty] | x
Footnotes: | 1) MTBP Operation Manual
2) To be completed (assesment of merging the IPA & IPMG processes)
4) IPMG meeting themes; First meeting - Strategic Monitoring & Budget Proposals; Second meeting - Budget Allocation Review; Third meeting - Free theme (Chair to decide) + budget execution to date review; Fourth meeting: IPA MC Preparation
3) & 5) Detailed guidelines and tools for IPMG/ThG meetings organisation are provided in the IPMG Mandate & Rules of Procedure, September 2016 (2nd draft), Chapters 3.2 and 5.3 and in Annexes 9-15
Legenda: |  |  | Working process
| x |  | Deadline/proposed timing of action
| 5 |  | ThG meetings (for an average of 5 ThGs unders each IPMG)
| 1 |  | IPMG meetings (typically 4/year, unless otherwise decided by SPC or sector lead Ministries)
Note on N37: Author: Strategic Monitoring + Budget Proposals
Note on W37: Budget Allocation Review
Note on AN37: Free Theme (Chair to decide) + Budget Execution review to date
Note on AW37: Preparation of IPAMC