United Nations Development Programme

Country: ARMENIA

Annual Work Plan

UNDAF Outcome 4: 	Environment and disaster risk reduction is integrated into national and local development frameworks

UNDP Outcome 4.1:	Armenia is better able to address key environmental challenges including climate change and natural resource management

UNDP Output 4.1.1:	National policies and tools for implementation of and compliance with international environmental agreements are developed and adopted

Implementing partner:                                Ministry of Nature Protection

Responsible Parties:                                  Ministry of Nature Protection

Agreed by Implementing Partner:

Name: 	Simon Papyan

Title:	First Deputy Minister of Nature Protection, EG PND   _____________________   _______________	                   				    signature	             date

Agreed by UNDP:

Name:	Dirk Boberg

Title:	UNDP Resident Representative a i                               _____________________   _______________	                                              signature	             date

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET (2012) |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount 2012 |
| Small Grants Programme |
| Output 1: National policies and tools for implementation of and compliance with international environmental agreements are developed and adopted Baseline: Established in 2009, the GEF Small Grants Programme is the main indicative financial instrument of UNDP CO that serves as fast, effective and friendly delivery mechanism to poor and vulnerable communities through NGO/CBO partner-grantees. As of December 2011, SGP has supported 11 community-based projects in the following GEF thematic areas: biodiversity, climate change, land degradation and persistent organic pollutants. The SGP-Armenian CPS paper is developed for the current GEF-5 Operational Phase of July 2011 - June 2014. Indicators Indicator 1: Number NGO/CBO projects funded or committed for funding by the SGP-Armenia Indicator 2: SGP good practices are replicated and/or scaled-up Targets Target 1: At least 10 new projects are commenced or committed through MOAs Target 2: At least 1 SGP good practice is replicated and/or scaled-up Related CP outcome: Armenia is better able to address key environmental challenges including climate change and natural resource management | Activity 1 GEF-5 Small Grant Programme implementation - Supporting NGOs/CBOs in new project concepts development and formulation - Oversight and monitoring of the SGP projects with NSC involvement | X | X | X | X | MNP | UNDP | 71400 – Contractual Services – Individuals (SGP Driver for 2012) 71300 – Local consultants 71600 – Travel 72100 – Contractual Services – Companies 72400 – Communication & Audio Visual Equipment 72600 – Grants 73400 – Rental and maintenance of other equipment 74200 – Audio visual and Printing Production Costs 74500 – Miscellaneous Expenses | $10,000.00 $3,000.00 $3,000.00 $2,000.00 $1,000.00 $22,400.00 $2,000.00 $2,600.00 $4,000.00 |
| Activity 1 Total: | $50,000.00 |
| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET (2012) |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount 2012 |
| Small Grants Programme |
| Output 1: National policies and tools for implementation of and compliance with international environmental agreements are developed and adopted Baseline: Established in 2009, the GEF Small Grants Programme is the main indicative financial instrument of UNDP CO that serves as fast, effective and friendly delivery mechanism to poor and vulnerable communities through NGO/CBO partner-grantees. As of December 2011, SGP has supported 11 community-based projects in the following GEF thematic areas: biodiversity, climate change, land degradation and persistent organic pollutants. The SGP-Armenian CPS paper is developed for the current GEF-5 Operational Phase of July 2011 - June 2014. Indicators Indicator 1: The CPS document is revised for the GEF-5 Operational Phase period (July 2010 – June 2014) Indicator 2: Number NGO/CBO projects funded or committed for funding by the SGP-Armenia Targets Target 1: The Country Programme Strategy for the GEF-5 Operational Phase is adopted by NSC and approved by CPMT Target 2: At least 5 new projects are commenced or committed through MOAs Related CP outcome: Armenia is better able to address key environmental challenges including climate change and natural resource management | Activity 2 New Projects Development/Monitoring | X | X | X | X | MNP | UNDP | 71400 – International Consultants 71200 – International consultants 71300 – Local consultants 71400 – Contractual Services – Individuals | $5,000.00 $5,000.00 $5,000.00 $35,000.00 |
| Activity 2 Total: | $50,000.00 |
| AWP GRAND TOTAL | $100,000.00 |

# Text boxes

During the year of 2012 UNDP Armenia will continue facilitating development of regulatory frameworks for strengthening environmental management to ensure implication of sustainable development practices. UNDP will further increase the capacity of NGO/CBOs through their involvement into the Small Grants Programme – a corporate Programme of GEF. The implementation of Activities of the AWP will be coordinated with activities of other portfolios of UNDP particularly the ones related to the Community Development issues. The AWP will be the instrument referred to as the Project Document in Article 1 of the SBAA between the Government of Armenia and UNDP, signed on March 8, 1995 and ratified on February 9, 2000.

2012 AWP budget:		$100,000.00

Total resources required           	_________

Total allocated resources:	_________

- Regular			$100,000.00

- Other:

  - GEF

  - Donor

  - Government	_________

Unfunded budget:		_________

In-kind Contributions

Programme Period:		2010-2015

CPAP Programme Component	Environment and disaster risk reduction is integrated into national and local development frameworks

Project Title:	The GEF Small Grants Programme

Atlas Award ID:		              00049734-00054966

Start date:		     	January 01, 2012

End Date			December 31, 2012

PAC Meeting Date		______________