# Annual Work Plan

# Annual Work Plan

Year: 2010

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Enhancing Dialogue and Trust Building in Armenia – (00059273 – 00074079) |
| CP Output 2.3.4 Confidence-building and dialogue process on all levels are developed and implemented Baseline: There are some indications for possible improvement of regional situation; the RoA Government recognized participatory processes as a priority. Nevertheless, no genuine participatory processes are applied to engage various strata of the society on development priorities on all levels. Indicators: (2010) Countrywide survey on social cohesion in Armenia conducted. (2010-2011) Number of participatory discussions on issues identified through survey. Targets: (2010) Baseline on social cohesion in Armenia is established through a first-ever countrywide survey. (2010-2011) Public policies are formulated in a more inclusive way through strengthened dialogue and participation at all levels. Related CP outcome: Communities and people have the capacities to claim their rights and participate in decision making processes. | Activity 1. Result: Baseline for situation on social cohesion in Armenia established in line with international standards Action 1.1 Survey on social cohesion in Armenia based on international standards (representative sample, etc.) is conducted, issues pertinent for various groups including women, minorities, vulnerable, etc., are diagnosed. Action 1.2. Survey findings are compiled and analyzed, options for concrete recommendations developed, mechanisms for dissemination of information including media channels identified. Action 1.3. Dialogue with the government on legal framework for implementation of main findings is initiated. |  | x | x | x | MTA 002184 | UNDP DGTTF 00012 -20001 | 72100 – Contractual Serv.-Companies Total Activity 1: | $45,000.00 $45,000.00 |
|  | Activity 2. Result: Broad public dialogue on social cohesion issues in Armenia is promoted and the policy level recommendations are developed and institutionalized Action 2.1 Bottom-up participatory mechanisms with special emphasis on engagement of women organizations, think tanks, vulnerable groups, etc., in the pilot region/province to discuss issues identified in the survey are developed and launched. |  | x | x | x | MTA 002184 | UNDP DGTTF 00012 -20001 | 71600 – Travel 72100 – Contractual Serv.-Companies 73400 – Rent.&Maint of Other Equip. 74200 – Audio Vis.&Print Prod. Costs 74500 – Miscellaneous Expenses Total Activity 2: | $2,000.00 $3,000.00 $1,500.00 $3,000.00 $500.00 $10,000.00 |
|  | Activity 3. Result: Programme Implementation, Monitoring and Evaluation Conduct effective coordination, administration and monitoring of project activities. Ensure full achievement of the project outputs. Prepare and submit all necessary reports as well as the project-management related documents, maintain regularly project’s risk/issue logs and the results matrices. Conduct regular monitoring visits and inform UNDP on observations. |  | x | x | x | MTA 002184 | UNDP DGTTF 00012 -20001 | 71400 – Contractual Serv.– Individ. 72400 – Commun., Aud.&Vis. Equip. 72500 – Supplies 73100 – Rental & Maint. – Premises 74500 – Miscellaneous Expenses Total Activity 3: | $1,500.00 $1,500.00 $300.00 $1,000.00 $700.00 $5,000.00 |
| 00059273 – 00074079 | GRAND TOTAL UNDP DGTTF 2010 |  |  |  |  |  |  |  | $60,000.00 |

# Annual Work Plan Budget Sheet

Year: 2011

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| CP Output 2.3.4 Confidence-building and dialogue process on all levels are developed and implemented Baseline: The situation on social cohesion in the Armenian society is assessed and diagnosed, main issues identified as a point of departure for improvement of dialogue processes on all levels. Indicators: (2010-2011) Number of participatory discussions on issues identified through survey. (2011) Number of recommendations on how to improve social fabric of the society. (2011) Number of policy level initiatives stemming from recommendations. Targets: (2010-2011) Public policies are formulated in a more inclusive way through strengthened dialogue and participation at all levels. (2011) At least 30% of recommendations developed through bottom-up participatory discussions are translated into policy level decisions and actions. Related CP outcome: Communities and people have the capacities to claim their rights and participate in decision making processes. | Activity 2. Result: Broad public dialogue on social cohesion issues in Armenia is promoted and the policy level recommendations are developed and institutionalized Action 2.1 (Continued from 2010) Round of participatory discussions in the pilot region/province of issues identified in the survey conducted and recommendations developed, media involvement is ensured. Action 2.2 Action plan for further country-wide replication of the pilot and implementation of recommendations developed and agreed upon locally and nationally; framework for implementation of main recommendation identified through discussions with the government at national and local level. | x | x | x | x | MTA 002184 | UNDP DGTTF 00012 -20001 | 71300 – Local Consultants 71600 – Travel 72100 – Contractual Serv.-Companies 73400 – Rent.&Maint of Other Equip. 74200 – Audio Vis.&Print Prod. Costs 74500 – Miscellaneous Expenses Total Activity 2: | $25,000.00 $6,000.00 $15,000.00 $3,000.00 $11,000.00 $2,000.00 $62,000.00 |
|  | Activity 3. Result: Programme Implementation, Monitoring and Evaluation Conduct effective coordination, administration and monitoring of project activities. Ensure full achievement of the project outputs. Prepare and submit all necessary reports as well as the project-management related documents, maintain regularly project’s risk/issue logs and the results matrices. Conduct regular monitoring visits and inform UNDP on observations. | x | x | x | x | MTA 002184 | UNDP DGTTF 00012 -20001 | 71400 – Contractual Serv.– Individ. 72400 – Commun., Aud.&Vis. Equip. 72500 – Supplies 73100 – Rental & Maint. – Premises 74500 – Miscellaneous Expenses Total Activity 3: | $22,000.00 $4,000.00 $500.00 $1,000.00 $500.00 $28,000.00 |
| 00059273 – 00074079 | GRAND TOTAL UNDP DGTTF 2011 |  |  |  |  |  |  |  | $90,000.00 |