United Nations Development Programme

Country: ARMENIA

Annual Work Plan

UNDAF Outcome 4: 	Promoting environmentally sound technologies and effective management of natural resources in accordance with the MDGs and PRSP.

Expected CP Outcome 6:	Conservation and sustainable use of natural resources is strengthened.

Expected CP Output 6.1:	Regulatory frameworks for strengthening environmental management and ensuring sustainable development are introduced.

Implementing partner:                                 Ministry of Nature Protection

Responsible Parties:                                   Ministry of Nature Protection

Agreed by Implementing Partner:

Name: 	Simon Papyan

Title:	First Deputy Minister of Nature Protection, EG PND   _____________________   _______________	                   				    				signature	               date

Agreed by UNDP:

Name:	Consuelo Vidal

Title:	UNDP Resident Representative                                   _____________________   _______________

signature	               date

# Annual Work Plan

Year: 2009

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Catalyzing Financial Sustainability of Armenia’s Protected Area System |
| Output 1: (i) information gathered and analyzed on the revenue situation and effectiveness of current PA system, including labor costs, other operating costs, maintenance, investment in conservation, and the like (ii) updated basic PA costing model used in the Feasibility Study to assess optimal/sustainable funding needs of the PAs, (iii) update of the current supply side of the equation with current (2009) budget information on key PAs, including amounts sourced from government, donors, and tourist and other revenues; (iv) detailed picture on the cost-effectiveness of business processes at the site level; (v) UNDP/GEF Financial Scorecard Finalized. | Activity 1: Updated baseline assessment of the financial gap and cost-effectiveness of the PA system in Armenia | X | X |  |  | MNP | GEF | 71300 – Local consultant 72100 – Contractual services-Companies 74500 – Miscellaneous Expenses GEF Subtotal: | $1,500.00 $5,500.00 $500.00 $7,500.00 |
| Activity 1 Total: |  |  |  |  |  |  |  |  | $7,500.00 |
| Output 1: (i) Project feasibility assessed, (ii) interventions carefully designed and budgeted Related CP outcome: Conservation and sustainable use of natural resources is strengthened | Activity 2: Feasibility analysis and budget | X | X |  |  | MNP | GEF | 71200 – International consultant GEF Subtotal: | $2,500.00 $2,500.00 |
| Activity 2 Total: | $2,500.00 |
| GEF Total | $10,000.00 |
| AWP GRAND TOTAL | $ 10,000.00 |

# Text boxes

Preparatory activities under this component of the PPG will contribute directly to the design of the Component I and II of the expected MSP and result in the following outputs: (i) information gathered and analyzed on the revenue situation and effectiveness of current PA system, including labor costs, other operating costs, maintenance, investment in conservation, and the like (ii) updated basic PA costing model used in the Feasibility Study to assess optimal/sustainable funding needs of the PAs, (iii) update of the current supply side of the equation with current (2009) budget information on key PAs, including amounts sourced from government, donors, and tourist and other revenues; (iv) detailed picture on the cost-effectiveness of business processes at the site level; (v) UNDP/GEF Financial Scorecard Finalized.

Total budget:			$20,000.0

Allocated resources:

- GEF (Grant)		$10,000.0

- Government (in kind)	$10,000.0

Programme Period:		2005-2009

CPAP Programme Component	Promoting energy efficiency and Environmental sustainability

Project Title:	Catalyzing Fin. Sustainability of Armenia’s PA System

Atlas Award/Project ID:		00057497-00071055

Period:				5 months