# Annual Work Plan Budget Sheet

Mobilizing Communities for Social Contract in Armenia

Year: 2011

| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| CP Outcome 2: Communities and people have the capacities to claim their rights and participate in decision making processes. Main CP OUTPUT 2.3.1 Mechanisms to ensure CS participation in the development, implementation and monitoring of strategic policies/programs at all levels developed. Project also contributes to CP OUTPUT 2.3.4 Confidence-building and dialogue processes on all levels are developed and implemented. Baseline: 1. Most citizens are poorly informed about local authorities and their responsibilities as well as local governance procedures. The Constitution provides for forms of direct democracy, such as referenda, public hearings and meetings, nevertheless, they are rarely applied at the local level. Local government activities are hampered by low citizen incentives and financial resources. 2. Participation of women and youth in political life and public policy making is extremely low, and transfer of capacities into Armenia inhibited. In particular, women’s participation in local governance is limited. 3. Border regions are not prepared for eventual improved cross border relationships. There is a weak confidence building mechanism in place in the conflict affected areas. Quality and number of initiatives is needs leveling-up. Indicators: 1. Freedom House Local Democratic Governance Rating improved. 2. At least 40% women’s participation in all project events: capacity building exercises in LSGs, and on community level. 3. At least 3 initiatives/policy statements formulated by youth and women in each targeted region. 4.Participation and representation of women in decision-making of local governance institutions increased by 20%. | Activity 1: National youth aspirations survey and Scenario based youth engagement module Result: Development of background material and public debate on the participation of youth in governance Sub-Activity 1.1: Updating of existing Armenian national survey on youth aspirations through the existing national youth platform (outsource) Sub-Activity 1.2: Debate on results of survey with parliament Sub-Activity 1.3: Production of a report based upon survey and parliamentary debate with national youth organizations Sub-activity 1.4: Development of Scenario based youth engagement module based on the survey results (2 workshops) |  | x | x | x | MTA | CPR TTF 26921 | 71300 - Local Consultants 71600 - Travel 72100 - Contractual Services Comp 72500 - Supplies 72700 - Hospitality 73100 - Rental & Maintenance-Premises 74200 - Audio Visual&Print Prod Costs Total Activity 1: | 10,000.00 2,000.00 20,000.00 1,000.00 2,000.00 3,000.00 2,000.00 $40,000.00 |
|  | Activity 2: Enhancing women’s and youth leadership Result: To bridge the gap between civil society and government on policy making, and provide an apparatus for discussion between citizens on key issues of Armenian citizenship. Sub-Activity 2.1: Establishment of facilitation training component for national civic leaders, including youth and women, in collaboration with key partners Sub-Activity 2.2: Consultations on the causes of women’s low political participation in Armenia. Sub-Activity 2.3: Development and implementation of a training module specifically designed to strengthen women’s leadership skills Sub-Activity 2.4: Development of a scenario based training module identifying the importance, impact and entry points for the engagement of young men and women in national policy making and national leadership Sub-Activity 2.5: Roll-out of training package in pilot regions |  | x | x | x | MTA | CPR TTF 26921 | 71300 - Local Consultants 71600 - Travel 72100 - Contractual Services Comp. 72500 - Supplies 72700 - Hospitality 73100 - Rental & Maintenance Premises 74200 - Audio Visual&Print Prod Costs 74500 - Miscellaneous Expenses Total Activity 2: | 5,000.00 5,000.00 30,000.00 5,000.00 5,000.00 3,000.00 5,000.00 2,000.00 $60,000.00 |
| 5.Situation analysis on implemented and ongoing confidence-building initiatives conducted and baseline developed 6. Strategic directions for future confidence-building activities outlined. | Activity 3: Development of baseline for future initiatives to work with local stakeholders on healing the conflicted past and looking into a more prosperous future Purpose: To develop a baseline for future peace and confidence-building initiatives and cross border cooperation between Armenia and neighboring countries Sub-Activity 3.1: Qualitative research on the implemented and on-going cross-border and confidence building initiatives in Armenia and neighboring countries and lessons learnt Sub-Activity 3.2: Organize “visionary” exercise in an open space format with key national and international stakeholders to identify strategic directions and routes for further effective confidence building initiatives. |  | x | x | x | MTA | CPR TTF 26921 | 71600 Travel 72100 Contractual Services Comp. 72500 Supplies 72700 Hospitality 74500 Miscellaneous Expenses Total Activity 3: | 2,000.00 5,000.00 2,000.00 5,000.00 500.00 14,500.00 |
|  | Activity 4: Programme Implementation, Monitoring and Evaluation Conduct effective coordination, administration and monitoring of project activities. Ensure full achievement of the project outputs. Prepare and submit all necessary reports as well as the project-management related documents, maintain project’s risk/issue logs and the results matrices. Conduct regular monitoring visits and inform UNDP on observations. |  | x | x | x | MTA | CPR TTF 26921 | 71300 - Local Consultants 71400 - Contractual Services Ind. 71600 - Travel 72200 - Equipment and Furniture 72400 - Communic & Audio Visual Equip 72500 - Supplies 72700 - Hospitality 73400 - Rental & Maintenance- Other eq. 74100 - Professional Services 74200 - Audio Visual&Print Prod Costs 74500 - Miscellaneous Expenses Total Activity 4: | 3,000.00 20,050.00 3,000.00 350.00 600.00 1,900.00 200.00 1,300.00 2,500.00 1,600.00 1,000.00 $35,500.00 |
| 2011 TOTAL BCPR - CPR TTR |  |  |  |  |  |  |  |  | $150,000.00 |

# Footnotes

Y2011 salary costs of PC, APC, PA and Driver are shared with other three projects of the AWP. Mobilizing Communities for Social Contract project  cost-share of salary budget  is  30% .