Basic Project Information

| Project Title: Barrier Removal to the Cost Effective Development and Implementation of Energy Efficiency Standards and Labeling Project (BRESL) |
| --- |
| UNDP Award ID | 48483 (Regional; PCs have their own IDs) |
| UNDP Project ID | 3327 (Regional; PCs have their own IDs) |
| Project Duration | January 2009 – June 2014 (extended to December 31, 2014 by 5th RPSC Resolution March 12, 2013, Langkawi, Malaysia) |
| Reporting Period | January 1 – December 31, 2013 |
| Total Approved Project Budget | USD 7,800,000 |
| Participating UN agencies | UNDP |
| Implementing Partners/ National collaborating agencies | National Development and Reform Commission (NDRC), China (Lead Country) Bangladesh Standards and Testing Institute (BSTI), Bangladesh Directorate General for Electricity and Energy Utilisation (DGEEU), Indonesia Ministry of Environment, Pakistan Department of Alternative Energy Development and Efficiency (DEDE),Thailand Ministry of Industry, Vietnam |
| International collaborating agencies |  |
| Cost-sharing third parties | International Copper Association |
| UNDP Contact officer | Shijun Liu (China); Sarwat Chowdhury (Bangladesh); Verania Andria (Indonesia); Saleem Ullah (Pakistan); Sutharin Koonphol (Thailand); Vu Thi Thu Hang (Vietnam) |
| Project websites | www.bresl.com; www.breslbd.org; www.bresl.or.id; www.bresl.net.pk; www.bresl.tgo.or.th; www.bresl.com.vn |

Executive Summary

As of December 31, 2013 or after four years and 10 months of implementation (since the Project Document signing in February 2009 by all six Participating Countries (PCs)), the BRESL Project has sustained its smooth project implementation and satisfactorily produced the expected outputs and results at the national and regional levels. It looks forward completing the whole project by December 31, 2014, which is the extended completion date considering that some PCs (Bangladesh and Pakistan) started later than the other PCs (China, Indonesia, Thailand and Vietnam) and that the pace of implementation varies among the PCs. China as the lead country and host of the Regional Project Management Unit (RPMU), has finished most of the activities and initiated the development of a project concept that will include future activities to sustain the regional and national ES&L program implementation ushered successfully by the BRESL Project. China, Thailand and Vietnam, with ongoing national energy standards and labeling (ES&L) programs when the project started, have continued to share their experiences and practices (while further enhancing own programs) to the other PCs (Indonesia, Bangladesh and Pakistan) which were just starting then to develop theirs in a very productive and purposeful south-south cooperation. Each PC has cooperated effectively and followed the overall strategies and activities diligently as stated in the regional and national Project Documents, including continuing advocacy, partnership, resource mobilization, close monitoring and follow-through and active co-financing and joint activities with various stakeholders in achieving project outcomes. This year 2013, marked the completion of the activities by the 7 TWGs (on Electric Fan, Compact Fluorescent Lamp (CFL), Ballast, Motor, Air Conditioner, Refrigerator and Rice Cooker) to guide national ES&L program development and implementation according to the needs of each PC for each of said Target Products in testing protocols, energy efficiency (EE) standards and labeling procedures. The TWGs also completed the 7 Feasibility Studies on Regional ES&L Harmonization which concluded that regional ES&L harmonization on testing protocols and EE standards is feasible for CFL, Electric Fan and Rice Cooker. The requirements of the major outputs of the 3 TWGs for the said feasible products on BRESL Specifications on testing protocol and EE standards have been completed and accepted by the Country Teams (CTs) for adoption following the recommended Action Plans which constitute initial major breakthroughs in the desired regional ES&L harmonization goals. Another major progress in achieving project outcome is the agreement on the Strategic Plan and the commitment among the CTs on the establishment of the BRESL Regional Energy Efficiency Standards and Labeling Network (REESLN) before the extended project completion date. Other national support activities for this year by the PCs are the continuance of strengthening policy support for energy efficient products, training and capacity development, establishing laboratory testing facilities to support regional harmonization of EE standards, information sharing of lessons learned and best practices, monitoring of project outcomes and adoption of labelling regulations. In summary, the BRESL Project has therefore satisfactorily accelerated the adoption and implementation of ES&L in the PCs, and in so doing already start bringing about energy savings from the use of energy efficient appliances/equipment. The project has also facilitated adoption of harmonization plans on test procedures and EE standards, laid the ground work for future cooperation in labeling procedures among the PCs and paved the way likewise for other interested developing countries in Asia when appropriate. The project looks forward to completing all activities by end of 2014.

- Background

Development Context

The development and implementation of energy-efficiency standards and labeling (ES&L) are among the most cost-effective types of policies and programs to mitigate global climate change. This is because ES&L programs have the potential to effect complete market transformation for different classes of energy-saving products, at a cost far below the cost of providing new energy supplies. Asia accounts for 28% of world energy use with the average rate of growth in energy use over the past decade at 3.7%, over double the 1.6% world average. Throughout this region, particularly in China, growth in the demand for electric power is requiring massive energy supply and extensive transmission and distribution networks. A significant percentage of the region’s total energy consumption is accounted for the energy consumption in the commercial, industrial and residential sectors (related to the use of appliances and equipment, motors and lighting). GHG emissions in the region will increase with economic growth, and these will have to be reduced if the global climate is to be stabilized. Clearly, focused efforts are needed to better utilize energy efficient technology and reduce energy consumption by these devices. Such programs, including ES&L however, are hindered by certain persistent barriers that continue to be addressed by the project. The six BRESL Participating Countries in Asia (Bangladesh, China, Indonesia, Pakistan, Thailand and Vietnam) have manifested interest in including ES&L programs in their national energy and environment development policies and priorities and are in the varying stages in setting up their institutional and legal platforms for pursuing the project goals consistent with this development context. The challenge lies in harmonizing the interests and plans in ES&L of countries involved or reaching mutual recognition of standards.

Project Objectives and Strategy

BRESL has the objective, aligned with GEF Operational Programme 5, to remove barriers to energy efficiency and energy conservation through ES&L. As it addresses and removes the barriers, it aims for the desired market transformation for energy-efficient appliances and equipment in the Asia region, complementing the initiatives of the participating countries. BRESL has been addressing the identified barriers through a combination of training and capacity-building, assessing and transmitting lessons learned, learning by doing, sharing work among countries to reduce the effort needed from each country, and technical assistance. Considering China’s and other countries’ advanced stage in their ES&L programs, majority of BRESL activities has also been addressing barriers that hinder governments from developing and implementing ES&L, with significant attention to also address manufacturers needs and the barriers that can hinder their support for ES&L efforts. For each of the seven (7) BRESL target products, the designated Technical Working Group (TWG) has completed its ES&L feasibility study, developed the ES&L implementation road map, and determined the action plans in carrying out the activities towards harmonization or mutual recognition of ES&L as a long-term strategy during the project and sustained by the governments after the project. With a major focus on capacity building as well as information and technical exchange, BRESL has helped to collectively eliminate ineffective practices, reduce financial barriers, and strengthen both policy formulation and enforcement. The free-flowing exchange is envisioned, with the help of UNDP, to facilitate cooperation and dialogue starting among the participating countries for them to appreciate and benefit from ES&L harmonization and/or mutual recognition and to promote trade of energy-efficient products within the region in the coming years.

2. Key Results

Project Outcomes

As of December 31, 2013 (or one year before the extended project completion date), the status/achievement of the BRESL Project in pursuit of the expected outcomes are as follows: At this stage of project implementation, the BRESL Project, has successfully developed a regional forum and technical working arrangements for dialogue, benchmarking, regional cooperation in ES&L experience exchange, feasibility studies for regional ES&L harmonization and/or mutual recognition of energy efficiency standards on 7 target products and appliances and action planning on how the ES&L program on national and regional levels will be pursued. It has catalyzed the further enhancement of the capacity and political will of the 6 BRESL PCs to develop, implement and mobilize resources for ES&L programs implementation on mutually beneficial and reinforcing south-south cooperation on the production, market development and trade for energy efficient products (Electric Fan, Electric Motor, Compact Fluorescent lamps (CFL), Electronic Ballast, Refrigerator, Air Conditioner and Rice Cooker. The countries (China, Thailand and Vietnam) with ongoing ES&L programs of varied levels of development (while progressively advancing their own national initiatives) have effectively shared experiences and results to the other PCs (Indonesia, Bangladesh and Pakistan) through the Project. The PCs have now recommended the action plans for regional harmonization of the BRESL Specifications for testing protocols and energy efficiency performance standards starting with three products (Fan, CFL and Rice Cooker) that were determined to be feasible for regional ES&L harmonization. All the PCs have considered and agreed that the TWG outputs are very useful for each country’s ES&L program development and implementation and that the country teams will continue to work towards their adoption into the national programs in consultation with stakeholders and government authorities in the formulation or updating of the necessary and applicable ES&L policy. The major project outcome on lowering energy consumption intensity of the target products used and traded within and among the PCs (and extended to other trading countries) has started to be materialize. Minimum energy efficiency performance standards (MEPS) have been adopted in some PCs. In support of the EE standards harmonization, the TWGs have endorsed the basic BRESL specifications for the harmonization of testing protocols for three products, namely, Fan, CFL and Rice Cooker which are in the process of finalization and submission to the PCs. On EE labeling schemes, at least 3 countries (China, Thailand and Vietnam) are in the process of implementing the newly adopted appliance and equipment energy efficiency labeling schemes at the national level. As recommended by the TWGs, however, regional harmonization of the labeling procedures among the PCs will not be pursued at this time because it is not feasible to do so considering present situation, on-going development and practice on ES&L in each PC. National ES&L programs are already operating in all PCs with plans to sustain these programs after the project completion by end of 2014 resulting from the policy and legal bases and institutional/organizational strengthening for the implementation of the ES&L programs that were developed and established through the project. The active policy and ample resources support of the respective governments of the PCs in the national ES&L programs that have been achieved thus far and aligned with regional thrusts. They have resulted in the integration of the principles of sustainability into the country policies and programs. This has definitely led to the opening of the markets in the BRESL countries and the region as a whole due to an increased trade and sale of energy-efficient appliances and products and the diffusion of technology through technical exchange and demonstration to maximize the economic and environmental benefits of new energy efficient technologies. The active participation and inputs by the private sector in each PC have been effectively solicited and mobilized in the development and implementation of the national ES&L programs leading to positive results towards desired outcomes. Through the project’s capacity building, manufacturer support and pilot demonstrations, the appliance and equipment manufacturers and support industries have advanced their production and marketing plans recognizing the great benefits, potentials and opportunities for ES&L in enhancing profitability and market sustainability. The framework for regional cooperation and mutual recognition agreements and product certification and posting procedures have been continually discussed and developed at the TWG level in line with the regional harmonization goals of the project. The PCs have reported qualitative increase in market share of energy efficient products targeted by the Project which can be verified by the planned market surveys which are planned to be completed before the project ends. Savings in energy consumption were also reported by the PCs in connection with the utilization of the targeted products in all the BRESL PCs which are also being verified as part of project M&E system and project completion activities. The above outcomes reflect the Project’s very significant and highly satisfactory achievements vis-a-vis the expected project outcomes resulting from the Project under the following five major ES&L components or programs consisting of complementary activities designed to remove barriers to achieve the project objectives: Policy-Making Program, Capacity Building Program, Manufacturer Support Program, Regional Cooperation Program and Pilot Projects. At the country level, the following summarizes the achievement of outcomes in each PC: China China has continued to support and lead the project while implementing its ongoing ES&L program in line with its national policies and priorities. It has also continued to share with the various PCs relevant ES&L implementation experiences and standards with the very valuable inputs of Chinese ES&L experts. China will encourage the stakeholders to adopt the TWG outputs in the revision of China’s national energy efficiency standards for CFL, Rice Cooker and Electric Fan towards the project’s regional harmonization objectives. It will coordinate the schedule for revision of relevant energy efficiency standards to consider TWG work plan time frame. In China, ES&L specifications of all the target products have been adopted except for the labelling specification of ballasts. It has also obtained very important breakthroughs in ES&L regulations, such as completion of the draft amendment of the Administration Regulation on China Energy Label which will provide a more solid legislation foundation for mandatory labelling program in China. The activities have effectively supported the realization of regional objectives of ES&L harmonization. Bangladesh The country has very significantly moved forward in its ES&L program development and implementation and strengthened testing and certification institutions with full support of the BRESL project and the Government and the shared ES&L experiences, templates and materials from the fellow BRESL PCs. In setting up its platform for ES&L program starting from almost nil, Bangladesh adopted BRESL Electric Fan Specification including testing protocols and EE performance standards to develop its own national standards. It has developed national EE performance standards also for other BRESL Target Products, such as Refrigerators, Air Conditioners, Electric motors and Electronic ballast with BRESL project support in terms of TWG activities. Looking forward, Bangladesh has continued to finalize the national standards for CFL including testing protocols and EE Performance Standards based on BRESL CFL specification in consultation with the stakeholders. It has also continued to encourage the stakeholders to increase the use of EE products through institutional strengthening, awareness campaign, formulation of appropriate government policies and standards and market surveillance of EE standard products and non-EE products through the Law Enforcement Authority. Through BRESL, it has also mobilized support for the Sustainable Energy Resources Development Act (SERDA), for BSTI institutional capacity enhancement on ES&L program implementation. Indonesia Indonesia has very significantly advanced its ES&L program for this year with active implementation of plans in various activities of the Project. Indonesia adopted BRESL testing protocols for Electric Fan, CFL, and Rice Cooker to develop national standards. It has continued to develop the corresponding MEPS for said products. In this connection, for Rice Cooker however, round robin tests will still be conducted with reference to TWG output. It also developed national EE performance standards for other BRESL Products such as Refrigerator, Air Conditioner, Electric Motors, and Electronic Ballast with BRESL project support. Among the specific outcomes include: (a.) established the necessary legal and regulatory basis for removing lowest EE technologies from the market and promoting high-efficiency technologies by proposing implementing policies for three BRESL appliances: CFL (revised), Refrigerator, and Air Conditioner to the implementing partner; by mandating 6 testing laboratories to conduct EE testing; by requesting manufacturers to comply with EE standards for 3 BRESL target products; by establishing a government accreditation program for appliance testing laboratories; and by accrediting 2 appliance testing laboratories; (b.) continued to build capacity for ES&L implementation; (c. ) provided support for manufacturers; (d.) provided support to TWG and REESLN activities; and (e.) initiated EE procurement program and pilot projects. Pakistan For this year, Pakistan already adopted the BRESL Electric Fan Specification as basis for its national standard. The revised Pakistan MEPS for CFL has been adopted in line with the BRESL Specification and will be made part of Pakistan National Standards along with the harmonized BRESL Testing Protocol after approval by the concerned government authorities. Significant development has been achieved in the ES&L policy area. The implementation of EE testing protocol and EE performance specifications for Fan and CFL will be undertaken after the adoption of revised PEEC Bill 2013 by the Parliament or approval of ES&L policy interventions by the Federal Cabinet. Pakistan has also developed labeling procedure and EE performance standards for electric motors, ballast and air conditioners under the BRESL project activities, in line with the TWG outputs. It has already undertaken awareness campaign for consumers on use of BRESL targeted EE products, through print and electronic media and has developed plans to rigorously pursue the campaign after approval ES&L policy interventions or the PEEC Bill 2013. Key outcomes achieved include: a.) Energy Efficiency Testing Protocols that have been adopted for all the six targeted appliances; b.) Minimum Efficiency Performance Standards (MEPS) that have been developed/ adopted/ notified for CFLs, Electronic & Magnetic Ballasts, Fans, Motors and Air conditioners; c.) MEPS for fans and CFLs that have been revised to harmonize with participating countries; d.) Energy Efficiency Labeling Procedure and Logo that have been approved by PSC. Energy Performance Rating Criteria has now been included in the procedure to harmonize with other participating countries and preparations are generally complete to launch the procedure through workshops; e.) Revised Pakistan Energy Efficiency Conservation (PEEC) Bill that has been submitted to MOWP for processing with Council of Common Interests and passage by Parliament; and f.) Amended ES&L Policy Summary that has been submitted to MOWP for Approval of Cabinet. Thailand Thailand adopted BRESL CFL Testing Protocol as basis for its national standard. For Electric Fans, the Testing Protocol and Performance Specification in terms of MEPS will be finalized based on BRESL Electric Fan Specification in consultation with key stakeholders. For CFL, since Thailand does not have MEPS for CFL, there is an opportunity for Thailand to adopt the BRESL CFL Specification. The National Standard Committee will be informed about the BRESL CFL MEPS and seek their advice on further harmonization. Thailand has continued to promote and encourage the awareness of ES&L application in BRESL target products through key stakeholders. Six technical reports were completed (Activity 1.1, 1.2a, 1.2b, 2.3, 3.2 and 4.2), three technical reports were revised (Activity 2.1b, 5.1a and 5.6), two technical reports are in the process of preparation (Activity 3.3 and 5.1b). Most of the activities have been completed except one activity under Activity 3.3 which is “Organizing of stakeholder consultation meeting on the policy recommendation” which is proposed to be conducted in Q1/2014. Three policy recommendations and one updated purchasing guideline are being prepared. These are 1) Policy recommendations on ES&L and CFP implementation (Activity 1.1, 1.2a and 1.2b) 2) Policy recommendation to promote high energy-efficient A/C manufacturing development (Activity 3.3) and 3) the updated purchasing guideline and policy recommendations for promoting high energy efficiency BRESL targeted products (Activity 5.1a). Vietnam Vietnam has significantly progressed in its ES&L program implementation with the assistance of BRESL project activities. The national standards for Fan, Rice Cooker and CFL testing protocols will be revised based on final BRESL Testing Protocols for said products in consultation with the local stakeholders in pursuit of regional harmonization goals. It has developed the plan to promote and disseminate the other TWG outputs to local stakeholders in the testing protocol adoption process. It has concluded its position to propose the harmonization of testing protocols for AC and Electric Motor in the next stage. More details on the national project outcomes are seen in the Annexes.

Activities and Outputs

The following highlights the progress in achieving the results and outputs of the different activities towards the desired outcomes as of December 31, 2013 in view of the accomplishments of the 6 PCs for this APR reporting period. Since 2013 is the fifth year of project implementation and most of activities have been finished in 2009-2012. For China, there are not many activities left for 2013 hence they focused on project completion and development of project framework for future activities for program sustainability and other areas for ES&L regional cooperation. Component 1: ES&L Policy-Making Program The Project has achieved very significant moves in developing and putting in place the policy and legal basis for ES&L program and implementation guidelines in support of the PCs plans and programs for all the PCs. By this time, the project has successfully and satisfactorily accomplished the requisite policies and regulations as needed in the respective country situations and priorities in line with the national programs and prepares the ground for regional harmonization activities in the pursuit of project objectives and goals. Activity 1.1 Strengthening of the Policy Context for Energy Standards and Labels The PCs have continued to strengthen the policy basis for national ES&L programs especially in the four (4) countries including China, Indonesia, Thailand and Vietnam that have new laws and regulations on ES&L in place and ES&L program fully operational. For 2013, BRESL has demonstrated successful south-south cooperation in the case of Bangladesh and Pakistan that have accelerated their legal and legislative process in adopting their own ES&L laws and regulations fitting their ES&L regimes. They have benefited directly from the project’s outputs, training and capacity building and from the shared experience of the other advanced PCs in terms of sharing ES&L materials, suggestions, technical documents and lessons learned. Activity 1.2 Adoption and Implementation of Energy Standards and Labeling Regulations In the recent TWG meeting held in Xiamen, the Country Teams have affirmed the finalization and adoption of the TWG outputs in the regional harmonization of testing protocols and EE standards for their own countries in Fan, CFL and Rice Cooker, while pursuing the ES&L requirements on a national basis for the other targeted products, namely Refrigerator, Air Conditioner, Ballast and Electric Motor. The PCs have proceeded to adopt their own labeling systems and procedures according to their needs considering that the practices vary among the PCs. Energy efficiency labeling is therefore not feasible to be harmonized in the region at this time. Bangladesh - It has conducted its “Policy Dialogue and Mass Awareness about Energy Efficient BRESL Products for Manufacturers, Importers, Traders and Consumers” in line with the proposed ES&L standards and the overall promotion of ES&L policy and planned standards for target products with the stakeholders. National Project Director already sent a Letter to Director, Standard Wing for 6 BRESL products Standard Mandatory, which was decided in the National Steering Committee Meeting (scan copy of letter is enclosed). China – EE standards and labeling specifications for all the target products have been adopted except for the labeling specification of ballasts. In 2013, China mainly focused on strengthening the ES&L policy context by improving government procurement program and introducing international new lessons and best practices of labelling programs by on-site investigation and surveys. Indonesia - Three (3) drafts of Ministerial Regulation for ES&L on AC, Refrigerator, and CFL (revised) had been submitted to DGNREEC and being processed by Legal Bureau of the of MEMR. Six (6) CFL testing laboratories had been legally appointed by DGNREEC – MEMR as official laboratory in Indonesia. Seven (7) CFL companies had implemented ES&L program with total of 201 models and its quantity of more than 171,2 million pcs of CFLs or about 40%-45% of Indonesia’s local market according to Indonesia’s lighting association (Aperlindo) data. Based on the result of procurement process, Ernst & Young consultant was appointed to conduct market survey including and develop survey protocol and evaluation. Duration of the contract is 6 months starting of November 2013. BRESL Project and National Accreditation Committee (KAN) has established accreditation program in 2013-2014 for Energy Efficiency that involved six (6) government-owned laboratories, two (2) Private and state-owned laboratories, and four (4) manufacturer laboratories. Two (2) AC’s laboratories and one (1) Refrigerator laboratory have been accredited by KAN. Two other laboratories are on accreditation process for 4 different product testing (CFL, Refrigerator, Fan and Rice Cooker). Surveilance guideline for CFL had been developed and integrated into Revision of CFL’s ES&L Ministerial Regulation. Pakistan - Energy Efficiency Testing Protocols have been adopted for all the six targeted appliances. Minimum Efficiency Performance Standards (MEPS) have been developed/ adopted/ notified for CFLs, Electronic & Magnetic Ballasts, Fans, Motors and Air conditioners. MEPS for fans and CFLs have been revised to harmonize with participating countries. Energy Efficiency Labelling Procedure and Logo have been approved by PSC. Energy Performance Rating Criteria has now been included in the procedure to harmonize with other participating countries. Preparations are generally complete to launch through workshops. Component 2: ES&L Capacity Building Program Almost all planned capacity building activities for all CTs have been completed this year 2013 as the project prepares to complete all commitments by year-end 2014. As a gauge of its success in the number of training and workshops conducted by each CT, the teams have been very successful in strengthening and enabling the public institutions to develop and implement the national ES&L programs in line with regional goals. The enhanced capacity of responsible agencies enabled them to build institutional and individual competence to secure on-the-ground development and implementation of pertinent policy and regulatory statutes and guidelines in the PCs and in strengthening the national testing and certification infrastructure. These were made possible through several regional and national training courses for various participants from the PCs and an in-depth immersion and capacity building for the Country Teams from the PCs in China and dissemination of relevant information materials and ES&L templates. In line with expected Component 2 outcomes for 2013, the Project has built capacity of each PC to conduct the planned activities with the professional services of the TWG experts and other contracted services. The national EE Experts were also hired to augment capacity of each PC CT in developing the national action plan in adopting the TWG outputs and initiate the implementation of the following: a.) coordination mechanisms, promotional strategies and approaches on the country’s participation in the regional EE performance standards and testing protocols harmonization and mutual recognition and other regional ES&L activities; b.) potential membership, promotion strategy, organizational structure of the BRESL REESLN establishment; c.) Identification of the barriers, needs, benefits, suggestions and inputs in the design of the next phase of the BRESL project; and, d.) recommendations on the development of data collection and reporting procedures. Activity 2.1 Training to Strengthen and Enable Public Institutions to Support Development and Implementation of ES&L Programs BRESL supported a number of training activities and workshops in conjunction with co-financed inputs and resources to enhance capacity of all the key stakeholders in various aspects of the national ES&L programs while considering specific country requirements and updated capacity needs assessment. Activity 2.2 Capacity Enhancement in the Development and Implementation of Standards and Labeling for the 6 Targeted Products This Activity involves mainly the tasks of the TWGs which have significantly and successfully augmented the CTs’ capacity in the development and implementation of ES&L plans for each of the seven (7) BRESL target products (adding rice Cooker to the former list of 6 targeted products The results of the TWG works are summarized in the outcomes listed above. Activity 2.3 Strengthening of National and Regional Testing and Certification Infrastructure In line with the Outputs of this activity for, For this year 2013, all the PCs have established their own ES&L development institutions for the national testing and certification taking into consideration the regional harmonization thrusts of BRESL. While the status of completion of establishing the national testing laboratories vary from PC to PC as well as across products, the CTs have progressed significantly in ES&L testing capability development and strengthening. The hardware and infrastructure requirements were sourced through co-financing support. The project looks forward in putting in place the ES&L certification program and institutional arrangements before the end of the Project. Activity 2.4 Strengthening of Data Collection and Reporting Procedures on Equipment Availability and Sales by Efficiency Level in Participating Countries For 2013, the CTs capability was augmented with the hiring of a National EE Expert for each PC, who will work in close coordination with the CT in finalizing and initiating the implementation of the plans for the data collection system and reporting procedures and the design and the development of the model data collection and reporting procedures. For the specific outputs per country for Component 2, the following outputs/developments related to establishing data collection and reporting procedures were submitted: Bangladesh Strengthening and enabling public institutions to support development and implementation of E S&L Program through: Run public awareness and behavior change campaigns Engaged private sector through development of voluntary standards for Green Star labeling, making it easier for consumers to choose high quality, low energy products. Advocated for mandatory standards to ensure all appliances meet minimum energy efficiency levels Demonstrated the effectiveness of energy efficient standards to government, driving their investment Continuation of the establishment of the country’s testing and certification infrastructure and the data collection and reporting procedures through BSTI, PMU, CSC and national consultants Note: Government already committed US$1.7 million to support further project roll out, for establishing testing facilities AC, Fridge, Fan, CFL, Electronic Ballast, and Electric Motor in BSTI. Which is significant given the five year project budget is only $0.65 million. China Approval and implementation of the revised motors standard and the newly developed ballasts standard. Except for ballast, the other 6 products have been covered by energy label system. Implementation Scheme of Efficiency Top-Runner Program in China Development and submission for approval of energy standard forsingle-cap fluorescent lamps, double-cap fluorescent lamps, high-voltage motors and rare earth permanent magnetic motors Evaluation report on the implementation effects of China Energy Label System Indonesia Involvement of six (6) technical experts in the ES&L activities to support the development of testing standard/protocols. Finalization of additional four (4) Technical Guidelines (Rice cooker, Electric Fans, Electronic ballast, Electric Motor). Training of thirty eight (38) testing practitioners from 14 institutions for implementation Energy Efficiency testing and training of nineteen (19) mid-management level from nine (9) manufacturer laboratories and university for ISO 17025. Participation in BRESL regional round robin testing for Electric Fan, Electric Motor and Rice Cooker. Facilitation of national implementation testing standards of 5 products: CFL, Air conditioner, Refrigerator, Rice Cooker and Electric Motor at 6 government laboratories, 5 manufacturer laboratories, 1 state-own company laboratories and 1 private company laboratory. Provision of 8 (eight) new testing equipment sets amounting to USD 225,000 composed of Power Analyzer, Programmable AC Power Source, Oscilloscope, Data Logger, M and Test package, Anemometer, Laser Level and Fan railing test support to six (6) government-owned and one (1) state-owned laboratories Training of testing laboratory practitioners to understand the adopted testing standards, to be able to identify precautions in testing processes and also to be able to assess the capacity of their laboratories for ES&L testing. Initiation of discussion on Mutual Recognition Agreement (MRA) between SIRIM Malaysia and Government of Indonesia which led to the conclusion that such arrangement could not be realized at present due to the stringent considerations of GoI on such international agreement; however, it is possible to have MRA among laboratories worldwide. Installation of a model of online data collection software in the BRESL website www.bresl.or.id which will allow that data collection be accessible and be filled out by registered users/ manufacturers themselves as an improvement to present practice that the data collection is only enabled for registered users and disabled for general viewer with the marked improvement on software security, access and restriction of data. Training/workshop for thirty nine (39) participants from 25 manufacturers on data collection, operation of the software and security access considering manufacturers concerns about data security and confidentiality to determine those data that should not be published in website. Data inputs for 201 CFL models from 7 different companies into data collection software. Pakistan Conduct of meetings with manufacturers/ dealers of Pumps and Motors in Gujranwala where more than 70 participants were apprised of the benefits of upcoming ES&L regime being launched by ENERCON/BRESL and where participants expressed their desire for more of such interactions which are now being planned. Development and maintenance of liaison arrangements with R&D Organizations, academia and associations of manufacturers to facilitate implementation of ES&L regime. Preparation and submission of proposal by PC-I and PCSIR Electrical Measurements & Testing Laboratory (EMTL) for seeking approval for funding to upgrade their facility/ laboratory for EE testing of BRESL targeted appliances, particularly motors, air conditioners and refrigerators so that the Ministry of Science & Technology (MOST) can be persuaded to expedite finalization/ establishment of requisite facility. Facilitation for PCSIR to participate in EE comparison tests of electric fans as arranged by RPMU China. Encouragement of the public/private sector through awareness campaigns and consultative meetings to gain support for establishing EE testing facilities thus resulting to the increase in manufacturers’ interest in the adoption/ launching of ES&L regime and to the formation of Working Group for Fans from the sector representatives for devising a strategy for adoption/ implementation of the regime starting in the electric fan product. Conduct of a study tour for personnel from public sector stakeholders regarding implementation of ES&L regime and EE Testing in Accredited Laboratories in China. Thailand Training for strengthening and enabling key stakeholders to support the development and implementation of the carbon footprint (CF) program where around 45% of trainees applied concepts and skills learned from the CF training course for evaluating the CF of their organizational and manufacturing processes. Capacity enhancement in the development and implementation of standards and labeling for the six targeted products and regional harmonization activities Completion of gap analysis and capacity assessment of local appliance testing and certification facilities in Thailand for BRESL products Participation in round robin test activity by testing laboratories where 3-phase induction motor samples were tested in the Thailand Institute of Scientific and Technological Research (TISTR) while the electric fan sample was tested in Electrical and Electronics Institute (EEI). Vietnam MOIT decision for 80 manufacturers/importers for labeling products Development of EE database and completion of a test version of database software and training activities for designated energy end users. Component 3: ES&L Manufacturer Support Program For 2013, significant progress was also achieved in Component 3 activities regarding technical support for local product manufacturers to help them develop efficient products and realize profit opportunities from efficient products. Following are related outputs of the activities: Activity 3.1 Product Technical Analysis and Reports The Product Technical Analysis Reports have been finalized as part of the TWGs outputs as basis for the findings in the Feasibility Study reports. Further work by the TWGs were completed on the three products (Fan, CFL and Rice Cooker) that were found feasible to be harmonized for EE testing protocols and standards which guided the drafting of the proposed BRESL specifications for testing protocols and EE standards. Activity 3.2 Educational Workshops for Manufacturers and Retailers on Impacts of Standards on Manufacturers and Retailers and Ways to Work with Standards to Increase Profitability All of the educational workshops planned for the project have been completed by the CTs for manufacturers and retailers on impacts of standards on manufacturers and retailers. As a result all CTs reported increased interest and participation in advocacy campaigns and actual implementation of ES&L activities at the national and company levels. Activity 3.3 Technical Assistance to Manufacturers The TWG Experts and national EE experts have started to plan out activities to provide specific technical assistance to manufacturers this year. The project is expecting to complete all planned technical assistance to manufacturers before the end of the project in December 2014. On a per-country basis, Component 3 outputs include the following: Bangladesh Product Technical Analysis & Reports done by CSC and national consultants Educational workshops for manufacturers and retailers (4 nos done) Core technician training and technical support to manufacturers (4 nos done) In this period 8 CFL, 1 EB and 3 Electric Fan have got EES&L Certificate from BSTI and Start Marketing. Beside this 2 CFL and 1 Electric Fan EES&L Certification is under process. Development a Model Pilot Project within 50 House Holds (HH) by replacing 3 non Energy Efficient bulbs, one E. Ballast for each HH and 3 non EE Electric Fan with energy star labelled of those appliances for creating awareness among the local people by using energy star label products China Several training workshops on ES&L for manufacturers have been organized considering that provision of technical assistance under Outcome 3 is difficult to achieve because of the proprietary attitude of manufacturers in improving their technology to produce EE products; however, these activities have stimulated them to consider improving their technologies to reach the MEPS and top energy grade. Conduct of ES&L training workshops on manufacturers of motors Workshops on energy label database and label registration procedure Training workshops on national subsidy program of air conditioners, refrigerators, motors Indonesia Participation in two additional training / workshops for manufacturers in China. Training of 30 personnel from manufacturers on energy efficiency, standardization and label Conduct of Market Study of AC, Refrigerator and Electric Motor with the assistance of the Ernst & Young consultant. Technical Assistance (TA) to 8 additional manufacturers resulting to a total of 30 local manufacturers adopting TA recommendations and 30 % local manufacturers satisfied with TA recommendations. Collection of sales data of EE labeling. Voluntary participation of 24 additional manufactures in the EE labeling for CFL, Air conditioner, and Refrigerator. Negotiation with 2 local banks/FIs into financing for facility improvements to accomodate EE product manufacturing. Pakistan Familiarization meetings with Manufacturers of Pumps and Motors on the benefits of upcoming Labeling Procedure being launched by ENERCON/ BRESL for possible technical assistance provision. Formation of a Working Group for Fans to facilitate adoption/ implementation of the regime in fan sector and identification of strategy for providing technical assistance to manufacturers. Consultative meetings with manufacturers/ associations for awareness regarding ES&L Regime. Thailand Completion of required reports Completion of consumer survey with results used in organizing domestic and international focus groups which do the ongoing integrated market demand analysis towards providing recommendations to manufacturers on marketing and technological support. Vietnam 500 CDs containing 20 templates for 10 kinds of labeled products. Component 4: ES&L Regional Cooperation Program In 2013, highly satisfactory results in regional cooperation activities were reported in promoting and implementing regional cooperation and harmonization of standards among the 6 PCs and in close cooperation with the key stakeholders. The activities mainly involved operation and maintenance of the national and regional website, sharing of best practices and lessons learned in a south-south cooperation scheme, organizational meeting for the establishment and membership recruitment for the REESLN, finalization of the TWG recommendations on the EE testing protocols and standards including the road map and action plan for the regional ES&L harmonization in 3 feasible target products. Measures to sustain the momentum in the achievements by individual PCs in development and implementation of their respective ES&L programs were discussed to form the basis of the next phase of the project. Activity 4.1 Project Web Site For 2013, the regional BRESL website www.bresl.com and the respective national websites among the six PCs continued to operate and be maintained for effective use and access by interested parties and stakeholders in line with the regional harmonization thrust of the project and individual PC implementation of respective ES&L national programs. The internet-based facility will also form the information hubs for the information networking and communication linkages among the PCs as well as serving as portals and repository of ES&L information and documents as part of the REESLN design and working arrangements. Activity 4.2 Lessons Learned Reports The project continued its activities related to the preparation of the Lessons Learned Reports. Activity 4.3 Regional Energy Efficiency Standards and Labeling Network (REESLN) During the 2013 REESLN Meeting which was held in Xiamen, China on 11 December 2013, the participants including representatives of the potential members, BRESL National Coordinators and EE Experts discussed the 3 draft REESLN Documents (Organizational Structure, By-Laws and Strategic Plan) and basically agree in principle. The CQM-PPC will take lead to finalize the required REESLN Documents which is planned to be finalized and ratified at the first REESLN Plenary meeting. Among the agreed points for REESLN organization are the following: In providing services for ES&L by the Pool of Experts, several experts may have different views or information. A Technical Working Group will be set up to avoid variations or conflicting positions. Funds to support the cost incurred in providing services will be sourced from BRESL. Additional funds could be explored from other sources and channels of support, WB, GTZ, bilateral arrangement, etc. Experts will render services in behalf of the Network and shall not deal directly with the Network clients The Network will focus initially on the 7 BRESL Target products and will be open to consider other products to be covered by the Network subject to an evaluation process initiated by the Steering Committee considering the demand for it. Manufacturers participation is highly encouraged is invited in the development of standards through the manufacturers association; the Network shall prevent some bias that can happen through the Working Groups. CQM-PPC will act as the initiating Secretariat during BRESL implementation; Selection of the permanent Secretariat will be decided by the majority vote of the partners and members. Activity 4.4 Regional ES&L Harmonization Initiative In this year, the TWGs have finalized the Feasibility Study Reports for the 7 products containing the ES&L Road Maps for the seven products. The feasibility study concluded that only three (3) products, viz. Fan, CFL and Rice Cooker, are feasible for regional ES&L harmonization starting with the testing protocols and EE standards. In summary, the TWGs concluded the following for each of the three selected products for harmonization: CFL All 6 PCs accepted the harmonization of the BRESL CFL Testing Protocol Bangladesh, China, and Pakistan agree to harmonize the MEPS in line with BRESL Specification while Indonesia, Thailand, Vietnam will refrain from harmonization at this time. China and Pakistan agree to harmonize the HEPS in line with BRESL Specification while Bangladesh decided to postpone the adoption for the time being. Indonesia, Thailand and Vietnam will refrain from harmonization at this time. Rice Cooker China and Indonesia already harmonized testing protocols for Rice Cooker in line with BRESL Specification. Vietnam intends to adopt the harmonized BRESL testing protocol when the testing protocols of Vietnam are revised (probably in 2014). By using proposed BRESL Testing Protocol, the laboratory comparison test among China, Indonesia and Vietnam laboratories was conducted following agreed arrangements and with satisfactory initial results. The further EE performance comparison test will be continued. The BRESL Specifications including the performance standards and testing protocol will be finalized by the end of February 2014 according to the result of the EE performance comparison test. Fan All 6 PCs adopted the Harmonization of BRESL Testing Protocol for electric fans except some reservations on the limit of ambient temperatures for Indonesia and Thailand. Thailand accepted testing protocols only for Table/desk fans and pedestal fans. Bangladesh, China, and Pakistan have Harmonized MEPS for electric fans in line with BRESL Specification while Indonesia, Thailand, Vietnam will refrain from harmonization for the time being. China and Pakistan have harmonized HEPS in line with BRESL Electric Fan Specification while Bangladesh, Indonesia, Thailand and Vietnam will refrain from harmonization for the time being. Activity 4.5 Preparation of a Plan for Regional Activities and Coordination after the GEF-Funded Project Ends RPMU has continued work on the UNDP/GEF project identification and development process for the next phase of the BRESL program. As recommended by the CTs, BRESL will give priority to the following products for the next round of regional cooperation and harmonization: air conditioner, motor, washing machine, LED lights, TV, electric iron, microwave oven, distribution transformers, refrigerators, ballast and others that may be further identified. BRESL will also give priority to the following activity areas for the next round of regional cooperation and harmonization: laboratory comparison test, acceptable testing tolerance for energy efficiency, compliance of EES&L, networking, public awareness campaign, training and capacity building, incentive policy in promotion of EE products, impact evaluation protocol for EES&L program, information dissemination, new EE technologies and other areas that may be further identified. For the whole of Component 4, each country has reported significant progress in all the related activities as follows: The harmonization of EE standards among participating countries is the key factor for the success of the project. The low possibility to harmonize the MEPS level is the barrier to achieve this outcome because each country has different situation of industrial level. BRESL needs to continue its support to the implementation process as well as monitoring & verification stage. The national activities and outputs related to preparation of the plan for future regional cooperation include the following: Bangladesh Development of the BRESL project website Completed one round robin testing for Fan Strongly participated in REESLN Finalization of the Feasibility Study Report for Fan, CFL & Energy Efficiency. China Information contents on EE standards and labeling programs posted in the www.energylabel.gov.cn and www.cnis.gov.cn . Inputs to PC support such as for a report made by Vietnamese experts on the result of the TWG Identification of means to further remove remaining barriers and issues to regional cooperation in ES&L related to 1.) language barrier, i.e. China’s laws/regulations, ES&L, testing protocols, and reports are in Chinese translation of which will require more resources such that related project deliverables have not been fully shared with other BRESL countries; and 2.) need to have a common methodology on calculation of energy savings and GHG emission as result of the project. Indonesia Participation by Regional Technical experts for lighting, home appliance, and energy efficiency in the regional TWG activities. Development of Model of database in support of the model of REESLN developed by BRESL – RPMU at the regional level. Technical exchange to accommodate TWG regional experts in developing testing protocols and specification for efficacy particularly for CFL Development of an action plan in line with the proposed regional BRESL follow-up project in ES&L Pakistan Development and maintenance of the BRESL Pakistan web-site. Provision of required inputs by BRESL Pakistan to TWG/ RPMU for Regional ES&L harmonization. Finalization of the Feasibility Study Report for Fans and circulation to all the in-country stakeholders for review and comments and final adoption. Development of Draft BRESL specifications for EE standards for fans by BRESL Pakistan as lead country for fans and facilitation of the finalization and adoption. Revision of MEPS for fans and CFLs to harmonize with the participating countries as discussed with PSQCA and PCSIR for resubmission to Technical Committee of PSQCA for adoption/ notification. Identification of 25 stakeholders from Pakistan for participation in REESLN activities with seven having applied for registration. Establishment of an information sharing network with Lites Asia based in China for data collection, R & D on global EE lighting products . Thailand Completion of reports on the development, implementation and enforcement of ES&L programs/projects in Thailand which identified the success and shortcomings of ES&L programs in the country through a SWOT analysis and provided recommendations for implementing more effective ES&L program. Vietnam Information contents on EE standards and labeling programs posted in the www.nhannangluong.com. Submission of reports made by Vietnamese experts on the result of the TWG. Submission of report of round robin testing for fan and electric motor. Component 5: ES&L Pilot Projects For 2013, each PC continued Component 5 activities related to ES&L pilot projects. Being a national initiative, the CTs continued to implement plans at the national level. Part of the expected outcomes for this component is the formulation and adoption of government procurement schemes for EE products and to design and model EE products databases and to showcase national EE consumer education schemes. Activity 5.1 Government Procurement (Bangladesh, Indonesia, Thailand, and Vietnam) For 2013, two (2) countries, namely: China and Vietnam, continued to implement government procurement plans for EE products while the other countries are still in the process of developing their government procurement schemes. In China, policy context for ES&L will be further strengthened. Government procurement program were evaluated, and best practices were identified, aiming at further improve the policy and removing the barriers of energy-efficient products promotion. Thai CT is recommending additional policies and guidelines on their Government Green Procurement Guidelines that is being completed. Currently, the guidelines for 5 BRESL products have been endorsed by Thai stakeholders for subsequent approval by the pertinent authorities. The report on evaluation on government procurement status on the electrical and electronic products has been delayed from Q2/2013 due to the literature review and analytical process which requires much effort, extensive time and human resources. This report is expected to be completed in Q1/2014. Activity 5.2 Database (and Web Site) of Energy-Efficient Equipment (Bangladesh and China) The activities related to the expected outputs continued to be implemented in China as the country which has an operational database and website for EE equipment. Other countries through their own initiative are still under the preparation process. Activity 5.3 Development of Consumer Education Schemes (Bangladesh, Indonesia and Pakistan) As a country initiative for this activity, all countries have completed Consumer Education Scheme in their own countries. Activity 5.4 ES&L Initiatives Financing (Indonesia) Indonesia continued the implementation of the activity with ongoing arrangements on ES&L initiative financing. Activity 5.5 Regional Harmonization Promotion (China) As lead country in this activity, China has continued promotional activities on regional ES&L harmonization with the help of China Country Team led by CNIS and CQM. All the PCs have continued to be very receptive to the harmonization plans on selected products and are prepared to resolve barriers that will be identified in order to achieve the objectives especially with the conclusions and recommendations during the successful 2nd 2013 TWG meeting in Xiamen. In another development, Thailand has continued to implement its complementary activity on implementing carbon footprint assessment and life cycle inventories in the manufacturing sector along with Activity 2.1 as a pilot activity with two manufacturing companies for lighting and air conditioner. Therefore, the activities and outputs for Component 5 are varied among the PCs as described below: Bangladesh (Ongoing activities) Bangladesh adopted BRESL Electric Fan Specification including testing protocols and EE performance standards to develop national standards Bangladesh finalized national standards for CFL including testing protocols and EE Performance Standards based on BRESL CFL specification in consultation with the stakeholders Bangladesh developed national EE performance standards for other BRESL Products, such as Refrigerators, Air Conditioners, Electric motors and Electronic ballast with BRESL project support in terms of TWG activities. China ES&L harmonization report by China experts of TWG of CFL, electric fan and rice cooker. For each of the BRESL target product, the designated Technical Working Group has completed the draft testing protocols and energy efficiency standards, and participated in several workshops towards the harmonization or mutual recognition of ES&L. Indonesia Initiation of the EE procurement program with the coordination of the Ministry of Environment. Provision of technical content to Fiscal Policy Agency, Ministry of Finance in developing Green Procurement which at this time it could not be implemented yet due to lack of energy efficient products that are endorsed by the MEMR. Start of pilot project for the implementation of EE in the local government buildings in Makassar, Province of South Sulawesi which has been actively participated in by local government, the implementing partner, BRESL Indonesia, in cooperation with ICED-USAID. Production of consumer education materials for public education. Participation in two exhibitions on ES&L by BRESL in coordination with local home appliances manufacturers and importers to facilitate awareness program in ES&L Program. Development and submission of 2 additional proposals/concepts to the government on ES&L Rebate, Tax Incentive, and Consumer Financing. Conduct of energy audit in the university building and assessment of the potential energy saving in the building in cooperation with the DGNREEC,. Participation in Focused Group Discussion on EE financing hosted by DGNREEC where BRESLintroduced a concept on Energy Efficiency Financing for rebate system. Pakistan Initiation of awareness campaigns on adopted MEPS. Initiation of awareness campaign regarding introduction of ES&L Regime in the country through meetings with manufacturers and their associations. Planning for more vigorous awareness campaigns and workshops for the launching of EE labelling program. Consultative meetings with universities/ academia to encourage them to promote ES&L program in Pakistan. Thailand Inclusion of the draft green procurement requirements for five BRESL products, A/C, refrigerator, electric fan, three phased induction motor and ballast in the government green procurement guideline which is being finalized for submission to the Green Procurement Promoting Subcommittee, including recommendations and suggestions for adding high EE criteria into the existing government green procurement guideline for BRESL products by the end of 2013. Conduct of seminar to provide knowledge on Low Carbon Society and Green Supply Chain Management for housing estates and high energy efficient appliances suppliers where the electricity consumption data of appliances used in housing estate are being collected in order to analyze and evaluate environmental impacts from GHG emission by comparing between existing and high energy efficient appliances. Implementation of a complementary program to ES&L, which is on establishing the carbon footprint program for participating companies to collect Life Cycle Inventory (LCI) and GHG accounting for carbon footprint assessment and provision of recommendations and suggestions to reduce carbon emission from the hot spot in their manufacturing process. Vietnam Report on marketing plan for electric fan and CFL. More details on the specific national project activities and outputs are seen in the Annexes.

Sustainability

National ES&L programs are already operating in all PCs with plans to sustain these programs after the project completion by end of 2014 resulting from the policy and legal bases and institutional/organizational strengthening for the implementation of the ES&L programs that were developed and established through the project. In summary, the following sustainability-related developments among the PCs include the following: Bangladesh – - For Project Sustainability Director General of BSTI already approved an Energy Efficiency Cell which comprised 5 Members of BSTI; Physical Wing, Standard Wing and Certification Marks (CM) Wing-Headed by Deputy Director, CM. - Designation of SREDA and BSTI to handle the ES&L responsibility; training of BCSIR and BUET as appliance testing centers; actively linking SREDA with the industry sector; resource mobilization for BSTI facility improvement; established 6 voluntary standards and 3 mandatory standards; application by numerous manufacturers for ES&L accreditation; adopting of the developed standards by manufacturers are new products with project’s assistance in R&D capacity building and established partnerships to support sustainable country ES&L program. China – In addition to close monitoring and adaptive management, the project partners were encouraged to continuously advocate and encourage the government policy makers to support ES&L regional cooperation and harmonization. Since the BRESL is designed as a capacity-building project with solid legal and institutional bases, the successful putting up of new energy efficiency standards and labels will also mean institutional structural growth with a capacity to effectively sustain the ES&L program. The responsible government agency with the ES&L mandate will play a significant role in the implementation of the national activities under BRESL. ES&L activities will be mainstreamed into the country’s EE program. BRESL should already encourage establishing schemes for these agencies to continue to lead in the ES&L efforts and GHG emission mitigation activities. Periodic monitoring and evaluation shall be institutionalized even after BRESL. This will bring sustainability of the project with desired benefits in the long run. Indonesia – The activities of BRESL Indonesia project were coordinated and integrated into the program of Directorate General of New Renewable Energy and Energy Conservation (DGNRE-EC). It is expected the integration will ensure the sustainability of the project, because the implementing partner mostly working on energy conservation. Ministry of Energy and Mineral Resources (MEMR) plan to implement ES&L into 10 (ten) home appliances product by 2016. To ensure the plan can implemented, BRESL, DGNREEC and stakeholders had initiated to establish a forum that connecting all stakehoders related to ES&L project. The forum named as “Communication forum of Energy Efficiency Testing Laboratory” that launched by Director of Energy Conservation – DGNEREC, MEMR on Nov 28, 2013. The objective of the communication forum is to continuing the BRESL program. The leading institution of the forum is P3TKEBT laboratory (Center of R&D for Electricity, New Energy Renewable and Energy Conservation) - MEMR and advised by MEMR, Ministry of Industry and Ministry of Trade. The members of communication forum are 17 testing laboratories. The program of the forum are devided by 4 components; (1) Standard & Testing Method, (2) EE training, (3) Capacity Building (4) workshop and (4) EE testing Research and Development. Thailand – To ensure that the outcomes and lessons learned derived from the implementation of project activities will be brought into the concrete practices, BRESL project working team has prepared policy recommendations on ES&L, carbon footprint, green government procurement and market based assistance for A/C to be presented to relevant government agencies. Vietnam – N.A.

Partnership Effectiveness

The active policy and ample resources support of the respective governments of the PCs in the national ES&L programs that have been achieved thus far and aligned with regional thrusts have resulted in the integration of the principles of sustainability into the country policies and programs. This partnership has definitely led to the opening of the markets in the BRESL countries and the region as a whole due to an increased trade and sale of energy-efficient appliances and products and the diffusion of technology through technical exchange and demonstration to maximize the economic and environmental benefits of new energy efficient technologies. Each PC has established effective partnership to support its own resource mobilization and to augment GEF project funds and resource inputs by project partners to enhance institutional capability. The following are partnership achievements to support ES&L programs in each PC: Bangladesh – Government Partnership has been established for creating testing laboratory of 3 products (AC, Refrigerator & E. Motor) at BSTI through DPP approval Partnership is continuing with more than 50 Manufacturer of 6 BRESL Products for their capacity building and policy making opinions. Partnership is continuing with Associations like BEMMA, BEA, CAB for market share surveillance, data collection and consumer awareness. China – BRESL has yet to prove its development effectiveness as it realizes that the goals and target benefits through a regional partnership strategy. BRESL is composed of able and committed stakeholders and partners, viz. the six ES&L-related agencies representing the participating governments in the project, the International Copper Association, ELI Quality Certification Institute, and the UNDP Country Offices of the BRESL PCs. The active and direct involvement of the partners has been fostering closer cooperation in achieving goals in a symbiotic way. Countries that are more advanced in ES&L cater to the needs of those countries that are still developing their own. For example, China started its ES&L program way ahead of the others and has accumulated extensive knowledge and experience that it can share with the other PCs. It takes lead in the development, and later, regional harmonization or mutual recognition of ES&L. Bangladesh and Pakistan shortened their learning curve and adopt accepted ES&L practices into their own situation and needs. Thailand, Indonesia and Vietnam also benefit by accelerating their ES&L development and at the same time provide assistance to each other and to Pakistan and Bangladesh by also sharing their own experiences. In that way, the regional approach becomes an effective development strategy and at the same time magnifies the ES&L benefits and environmental impacts in wider and sustained regional basis. There is sufficient reason to believe that accountability and responsibility for managing and achieving project outputs are happening and BRESL has already reached it partnership stability and is already geared to achieving more and better results through 2014. Indonesia – In implementing the project activities, BRESL Indonesia formed partnerships with several parties to increase the effectiveness of the project including (a.) Japan Partnership Fund (JPF) for providing grant to strengthen testing facilities and for conducting trainings in Indonesia and Japan and also for conducting several testings; (b.) National Accreditation Commitee (KAN) of Indonesia for joint activities in accrediting testing laboratories; (c.) USAID – ICED Project for a pilot project for energy efficiency implementation in the city of Makassar’s selected government offices; (d.) Private laboratories and manufacturers for conduct of several trainings and testing of target products. Thailand - For activity 5.1b, Sena Development PCL, Supalai PCL and Pruksa Real Estate are the pilot real estates in the promotion of high energy efficient appliances. For activity 5.6, Thai Energy Conservation Co., Ltd. And United Technology Development Co., Ltd. are companies that participated in ES&L-complementary on implementing CF in manufacturing. Cooperation among the working team, experts, specialists, and partnership agencies were observed to be effective.

Cross-cutting Issues

As an important part of the entire BRESL project, the project is now addressing relevant cross-cutting issues pertaining to environmental sustainability, gender equality, poverty alleviation, improving trade ties and developing global partnership for development. The project has paid ample attention to related cross-cutting issues as gender and south-south cooperation. On gender aspects, the project has encouraged the participation of women in community training on energy efficiency awareness and application. Women play a very important role in applying energy efficiency concepts as end-users particularly their constant presence and decision making in the household where the utilization of the target products mostly happens. It also promotes gender equality because of non-gender discrimination in the use of standard products. In Indonesia, for example, the technicians of most of EE performance testing laboratories are men, maybe because the electricity sector is perceived as for male sector. However, most of the manufacturer workers are women and the marketing chain also dominated by women. In addition, most of the users of the home appliances are women. It put women in the unique position as influencer for the decision on the purchasing of home appliances On the south-south cooperation; BRESL has espoused this approach in the development and application of ES&L best practices and learning experiences between and among countries. The countries (China, Thailand and Vietnam) with ongoing ES&L programs of varied levels of development (while progressively advancing their own national initiatives) have effectively shared experiences and results to the other PCs (Indonesia, Bangladesh and Pakistan) who are in the process of developing and establishing their ES&L programs through the Project. Most primary among these issues is regarding environmental sustainability by directly reducing GHG and regarding improving trade of energy efficient products and appliances that will redound to economic savings. Most PCs have proceeded to have follow-up related ES&L projects drawing from the BRESL experiences that will further multiply and expand the BRESL initiatives.

3. Project Management and Oversight

Implementation status

The year 2013 saw very significant and highly satisfactory accomplishment in line with desired outputs for the year while also catching up with delays in the achievement of some project outputs, work completion on the project activities both at the national and regional levels experienced in the past year 2012. The PCs have continued to implement their respective national activities in line with national priorities and regional commitments and has also accelerated compliance with the MTR recommendations particularly the putting in place of the testing and certification procedures and institutions using harmonized standards. The project continued with the necessary preparations for the development and implementation of the prescribed quantitative monitoring of electricity savings and the corresponding GHG emission reduction; establishing system of monitoring market share of energy efficient products; annual data collection system; operational government procurement systems and pilot demonstration of ES&L best practices as the project completes all output commitments before the project ends in December 31, 2014. The project has delivered satisfactory results and very significant progress in achieving the expected outcomes. All the activities are implemented smoothly and are expected to be completed up the extended completion date at the end of December 2014. With the work of the TWGs, the harmonization action plans for the EE standards on testing protocols and EE performance standards for the 3 feasible products: Fan, CFL and Rice Cooker, have progressed significantly with the BRESL specifications agreed at the recently concluded 2013 2nd TWG Meeting in Xiamen. Adoption of the TWG outputs and the subsequent Implementation of these harmonized standards by the PCs need close cooperation and coordination through the country Teams. Each Country Team, with guidance by the National Project Steering Committees under the leadership of the RPMU, has satisfactorily implemented related activities to accelerate project progress and catch up with delays by effective adaptive management. The project has actively involved all stakeholders in effective consultative and participative approach considering national ES&L policy needs and priorities. In China, being the Host Centre for the RPMU, after reorganization of the designated executing agency (CSC) and change of Financial Manager (from CICETE to NECC), BRESL China project implementation got on the right track and proceeded smoothly and rapidly and contributed effectively in RPMU operations. Aggressive progress has been obtained mainly in 2009-2012. Some subcontracts have been finished and the corresponding outcomes have been replicated into daily management of ES&L. Some subcontracts which are tightly linked with national energy saving policies have been almost finished under guidance of the government. BRESL have demonstrated greater impact and impetus on China ES&L infrastructure establishment, capacity building, and policy and system perfection. In 2013, BRESL China is sustaining the national efforts in ES&L policy context and legislation basis, and as a whole, at the regional level, the project is being implemented smoothly. Internally, the PCs have Project Steering Committees, or Project Board in the case of Indonesia that monitors and evaluates the Project implementation through Project Board or PSC Meeting mechanism. Externally, UNDP also conduct project audits. In addition independent government inspection body (e.g. BPKP for Indonesia and similar bodies for other PCs) also conducts annual audit for monitoring and evaluation of the project implementation. The management of succesful project implementation was also influenced by external and internal barriers. The BRESL project is continuously seeking to remove both barriers, but some concerns, for example in Indonesia, were encountered to be a sort of external barriers which are beyond BRESL project scope such as: (1) the project could not interfere with setting of the testing fees that vary widely among laboratories; (2) the differences of Financial Institution policies on supporting Energy Efficiency Projects; and (3) the limited testing space and technicians in existing laboratories. In summary, the expected project outputs and indicators for this APR 2013 have been met. The project is being implemented on track and as planned toward achieving all the targets expected by end of the project. The project budget was planned and disbursed reasonably and consistently with the regulations of UNDP Budget resources have been allocated as planned in the reporting period. The actual GEF Fund expenditure of each Participating Country is shown in the APRs of the PCs as annexed herewith. Each PC has further increased the level of co-financing actualized to the project which is a strong manifestation of serious commitment and cooperation towards successful project completion. The China Government has provided a large amount of co-financing in the form of EE products subsidy. The estimated co-financing amount was reported to be US$ 1.2 million for Bangladesh, US$ 6,300 Million for China, US$ 1,236,158 for Indonesia, US$ 716,000 for Pakistan, US$ 12,820,527 for Thailand and US$ 918,000 for Vietnam by middle of 2013.

Human Resource Management

The enhancement of manpower complement of RPMU has brought in very significant improvement in the day-to-day planning and implementation of project activities and oversight in accomplishing expected project outputs for the year. RPMU has also successfully addressed the concern related to the completion of the hiring of the TWG experts and National EE experts which is very necessary in accomplishing very critical project tasks. Although there was a delay in the hiring process, the composition o f the teams were completed in time for the holding of the 2nd 2013 TWG Meeting side-by-side with the REESLN Organizational Meeting on December 11- 13, 2013 in Xiamen. RPMU has coordinated effectively the participation also of the Project Managers/Coordinators in said meetings thus completing the representation of each country in very important reporting and deliberations on critical matters about the finalization and adoption of the TWG outputs and the REESLN organization as they are introduced in each PC’s ES&L program and along the line of the desired regional cooperation, harmonization and mutual recognition of the endorsed EE testing protocols and standards for the BRESL target products. For Indonesia, the lack of trained laboratory technicians is experienced. For Thailand, the project consultant, Thailand Environment Institute has changed the project working team. Thus, the human resources are amply provided and can be sustained as needed with the implementation up to project completion.

Monitoring and Evaluation

Monitoring and evaluation (M&E) has continued to be implemented as a very important management function. Regular reporting through the UNDP/GEF prescribed M&E tools such as this APR, annual PIR, budget and expenditure analysis, quarterly reports, mid-term review and other M&E activities have all been satisfactory complied with by the project. In addition to these, BRESL PCs have established specific M&E practices at the national and industry levels: Bangladesh Revised M&E Plan with provisions for continuous monitoring, BSTI visits the market and factory twice a year to assess the standards of available products certified by BSTI. Adoption of international standards and harmonization with five other participating countries. Activity tracking to be undertaken by Counterpart Expert of BSTI, National Expert of BRESL and International Consultant from RPMU. ENERGY EFFICIENCY CELL has been designed & approved by Director General BSTI to continue to provide Certification & Star Label activities for new Manufacturers for sustainability of BRESL objectives. US$ 1.7 million has been approved for establishing 3 Testing Labs ( For A/c, Refrigerator & E Motor) with required spaces in BSTI as a Government Co-financing for scaling up Testing Protocol. For Community Level ownership Mass Awareness Campaign will be continuing through Training/Workshop and Television advertisement with maximum budget of AWP- 2015 upto June 2015. China - During daily project implementation, China CCT set a strict M&E system to monitor the progress of the activities and ensure the quality of project outcomes. All the undertakers of subcontracts were required to develop their own M&E plans which will be submitted to China CCT to serve as M&E tool. Based on that, China CCT required the undertakers to prepare and submit quarterly reports and meeting minutes/investigation summaries in order to fully keep abreast of the project progress and to evaluate whether the subcontracts are proceeding and adhering to committed schedules. Besides, routine meetings with the subcontract undertakers were held to discuss the project implementation and existing problems. The implementing agency NDRC, UNDP, NECC, and related experts were also invited to give guidance and suggestions. For acceptance of the first batch of subcontractors, several experts were invited to hear the report of undertakers, and then formal resolution/decisions were made after serious discussion. Besides, the project has been subjected to the mid-term review (MTR) as completed in 2012. By establishing and executing strict M&E system, the project activities were on track to committed outcomes, their outcomes and related information were timely collected, and the compliance between project actual deliverables with defined targets were effectively ensured. Indonesia - Besides the Quarterly Project Monitoring Report, BRESL has regular Project Meetings to evaluate the project implementation and discuss the follow up action plan. On the government side, BPKP acting as government internal audit agency conducted overall project review once a year on behalf of the GoI and UNDP. The M&E arrangements provide clear and unbiased advice to the implementation of all project activities. The project audit and project evalution show that the project implementation is still on track.

Risk management

The RPMU and the PCs have continued to assess the project’s risk profile this year and to identify mitigation measures to manage. They have reported the issues and risks factors and risk management measures in the preparation of Annual Work Plans and Project Implementation Review. RPMU noted however that the PCs should be encouraged to pay needed attention in reporting completely in the Risk Management tab in the APR/PIR and in UNDP’s ATLAS risk log for the project that requires that critical risks that may affect the project success are identified and what risk management measures to address them were undertaken in the reporting period. The RPSC in its 5th Annual Meeting has also reviewed the project implementation risks and discussed possible adjustments or adaptive management to mitigate the identified risks. In summary, each PC has identified the following risks that continued to be addressed this year as follows: Bangladesh – While there remains to have broad-based support for ES&L from manufacturers and trained technical professionals, however manufacturers fear loss of market share and loss of competitiveness if they improve standards ahead of their competitors. Initial investment cost remains a problem from the perspective of manufacturers. Information and promotional campaigns are still limited to expand the reach in the entire population. Independent testing and accreditation of products to improve efficiency are still very limited with only BSTI providing accreditation services; thus the government is unable to cope with the quantity of accreditation applications. Political unrests and public mass action have affected project timeline and contingency planning took up significant project time. Any risks arise are being minimized through Idea Exchange Meeting with Manufacturers, Country Team (CT), TAG and NPSC members. Besides, UNDP will provide more coordination and help to prevent any high-level risks that may happen in the future. China – Among the external project concerns that were experienced by China CCT in varied degrees included: a.) unclear or changing government priorities and policies; b.) economic and political changes that affected the pace of implementation of activities and availability of co-financing resource inputs; and c.) long lead-time in government approving new guidelines and activities that are in the process of installing EES&L programs. As agreed in the RPSC Meeting, China CCT together with other BRESL Country Teams and RPMU are also encouraged to employ strategies for more effective implementation of BRESL activities, to make use of synergy with ongoing and upcoming ES&L projects/programs in all BRESL countries and to ensure that the staffing is maintained to ensure continuity of project operation and decision making. Besides, UNDP has and will provide more coordination and help for China CCT to prevent any high-level risks that may happen in the future. Indonesia – In managing risks on the ES&L Program, the BRESL project has identified 3 possible barriers on the implementation of ES&L labelling: (a.) large differences in testing fees that may lead to varied distribution of testing loads in the laboratories; (b.) manufacturers or laboratories argue that investment return / return on capital of EE equipment are difficult to be achieved due to there are no yearly re-certification and surveillance EE testing; and (c.) less participation from Financial Institution on supporting ES&L Program due to the absence of technical specification regulation and guideline for Financial Institutions to develop their internal policies favourable to ES&L. To address these barriers, the project has given recommendations to stakeholders by facilitating Non-tax revenue meeting that describe and detail the testing component, so that every party can figure out the base price of testing expenses. For the financial Institution issues, the project is also working with Fiscal Policy Agency-Minstry of Finance, Ministry of National Planning, and Financial institution to formulate the concept of Green Financing scheme. Pakistan – Identified key remaining risks include the following: non-availability of accredited laboratory facilities for testing of appliances for their energy performance; non- responsive attitude of manufacturers, especially fans; and lukewarm responsiveness of the government towards ES&L policy and implementation. These are being addressed through upgrading of PCSIR and PC1 laboratories to cater for energy performance testing; comprehensive awareness programs, workshops and seminars and more institutional support for capacity building. Thailand – Ineffective regional coordination and collaboration with regional organizations – Participating countries may continue to carry out ES&L activities on their own losing the potentials for synergetic work towards wider achievement of ES&L harmonization objectives. The mitigation actions could be that regular meetings of the Regional PSC to exchange work programmes and implementation plans and that meeting plans should be prepared in advance to ensure participation of participating countries.

Communication and advocacy

In line with the Project’s communication and advocacy strategy and plan, it continued to implement arrangements for the preparation and implementation of the BRESL Regional and National Annual Work Plans and enhancement of communication and advocacy among the country teams, as well as other project stakeholders. The project significantly achieved this year the marked improvement in the level of participation by the country teams and relevant government institutions and private organizations in advocating and rendering support ES&L national program implementation as well as regional cooperation and harmonization. Considering the varying needs and situations in ES&L by the stakeholders in the respective countries, such communication and advocacy strategies and plans have gained very significant grounds and satisfactory success this year. The RPMU has continued to coordinate with the CTs of the BRESL countries in achieving the regional objectives of the project and constantly guiding the individual Country Teams in project implementation to achieve expected outputs at the national and regional levels through improved coordination. RPMU noted each PC’s advocacy-related outputs this year while continuing the usual communication and advocacy activities. Bangladesh – It has completed 2 workshops involving consumer groups, traders, and manufacturers for advocacy about how to reduce sub-standard product from entering the market and protect the consumers. It also devised some communication and advocacy campaigns through festoons, banners and brochures with energy saving slogans. It updated the information in the project and UNDP websites and published news on project activities in the country’s Energy and Power Magazine. As a part of mass awareness campaign, BRESL Posters have been posted throughout 7 division of Bangladesh. BRESL Project send awareness SMS through mobile almost 4,50000 people which has a very good response. A Computer Graphics Animation through TV commercial is prepared and it was broadcasted 9 TV Channel from January 2014 to till now with the help of Ministry of Information. And it is a continuous process. Another new TV commercial (35 seconds slot) has been prepared and this TV commercial will be broadcasted through 6 Private TV Channels from February 2015 by BRESL own fund. For creating mass awareness about BRESL products Two (2) Advertisement (one energy star label and one energy efficiency standard) related was published in the 2 English and 4 Bengali Daily Newspaper on 21-04-2014, 05-05-2014, China – Since China CCT was encouraged to continuously advocate and encourage the government policy makers to support ES&L regional cooperation and harmonization, to employ strategies for more effective implementation of BRESL activities and to make use of synergy with ongoing and upcoming ES&L projects/programs in their respective countries, effective communication and advocacy issues have been experienced in the reporting period. Firstly, China CCT constructed its own China Project Steering Committee (CPSC) which is composed of officers from NDRC, NECC and AQSIQ. CPSC has continued to discuss and make critical decisions regarding project direction. Since the CPSC members are all from government, the synergy of project activities with national policies were ensured. Secondly, China CCT sent project bulletins and reported project progress reports to NDRC and other government agencies from time to time. Finally, China CCT has conducted frequent communication with RPMU. In the future, the communication and advocacy activities will be further strengthened to greatly enhance the acceptance and cooperation regarding developing and implementing ES&L programs until completion. Indonesia – For better communication and coordination in the development and implementation of the ES&L program, communication and advocacy have been implemented to encourage involvement of the key stakeholders, to ensure sustainability of the program, and to raise awareness of the public on the ES&L program. Audience of communication mostly come from related government agencies, industry associations, EE appliances manufacturers, and other relevant institutions. Awareness is mostly directed to government officials, women, youth, school/university, home appliances users. The messages for the communication include ES&L program which involves many parties, and thus coordination is needed for implementation. In addition, using energy-efficient appliances that will save energy, save money, and save the environment have been communicated by the project. Pakistan – Communication with stakeholders is done through interactive meetings, soft & hard material and advocacy/ awareness among stakeholders is being created through print and electronic media, and consultative meetings. Thailand – The BRESL working team has communicated with the implementing partners on regular basis to ensure the effective operation of the project and to immediately solve emerging problems.

4. Financial Management (Bangladesh)

The budget for the year 2014 is $174,848, and the accumulated annual expenditure by the end of the year 2014 was about $ 148,848, with the delivery rate of 100% (Final CRD is not provided, the final CDR will be get in Feb 2015). After that rest of the amount will be adjusted in AWP 2015.  Till now the AWP 2015 is $93537.

|  | Source of Fund | Budget | Expenditure |
| --- | --- | --- | --- |
| Expenditure Vs. Approved project budget by source of funding | UNDP | $ 174848 | 174848 |
|  | Government Cost Sharing | 0 | 0 |
|  | Third Party Cost-sharing | 0 | 0 |
|  | Other (please specify) | 0 | 0 |
|  | Total | 174848 | 174848 |

| Output | Activities | Source of Funding | Budget Description | Annual Budget | Annual Expenditure | Note |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (USD) | (USD) |  |
| Output 1 | 1.1 | GEF | Strengthening of the Policy Context for ESL. | 7766 | 0 |  |
|  | 1.2 | GEF | Adoption and Implementation of Energy Standards | 1232 | 0 |  |
| Sub-total-1 |  |  |  |  | 8,998.00 |  |
| Output 2 | 2.1 | GEF | Training to Strengthen and Enable Public Institutions to Support Development and Implementation of ES&L Programs | 0 |  |  |
|  | 2.2 | GEF | Training to Strengthen and Enable Public Institutions to Support Development and Implementation of ES&L Programs | 8,000 |  |  |
|  | 2.3 | GEF | Strengthening of National and Regional Testing and Certification Infrastructure | 10,000 |  |  |
|  | 2.4 | GEF | Strengthening of Data Collection and Reporting Procedures on Equipment Availability and Sales by Efficiency Level in Participating Countries | 2,000 |  |  |
| Sub-total-2 |  |  |  |  | 20,000.00 |  |
| Output 3 | 3.1 | / | Product Technical Analysis and Reports | 10500 | 10,500.00 |  |
| Output 4 | 4.1 | GEF | Website | 0 |  |  |
|  | 4.2 | GEF | Interviews | 0 |  |  |
|  | 4.3 | GEF | REESLN | 0 |  |  |
|  | 4.4 | / | REESL Harmonization | 0 |  |  |
|  | 4.5 | GEF | BRESL phase 2 | 0 |  |  |
| Sub-total-4 |  |  |  |  | 0 |  |
| Output 5 | 5.1 | / | Government Procurement | 3300 | 0 |  |
|  | 5.2 | / | Database (and Web Site) of Energy-Efficient Equipment | 43500 | 0 |  |
|  | 5.3 | / | Development of Consumer Education Schemes | 9400 | 0 |  |
|  | 5.4 | / | ES&L Initiatives Financing | 0 | 0 |  |
|  | 5.5 | / | Regional Harmonization Promotion | 0 | 0 |  |
| Sub-total-5 |  |  |  |  | 56,200.00 |  |
| Output 6 |  | GEF | Project management | 79,150 | 79,150 |  |
|  | Total (1+2+3+4+5+6) | 174,848 | 174,848 |  |

5. Management recommendations

Among the key recommendations noted per country are the following: China – (a.) Strengthen sharing of project information and deliverables. As the leading country of BRESL, China hopes to provide more technical support to other countries. However, because of communication limit, the needs of other countries are not well understood. The progress of all the BRESL countries should be circulated around from time to time; (b.) Cut short and simplify approval procedures of project implementation. Regarding project implementation of BRESL China, the dual approvals of NDRC and RPMU are necessary. The process always takes a long time. The procedure should be cut short and simplified, and China CCT should be given more flexibility; and (c.) Further strengthen communication and advocacy efforts. A systematic communication and advocacy plan should be developed and adequately resourced. The corresponding efforts should be strengthened by involving government officers in BRESL China decision making regarding project direction, hearing routine reporting and sharing project information and outcomes by bulletins dispatched by China CCT, etc. Indonesia – (a.) On implementation of ES&L programs, to avoid delayed and unbalance of volume testing process in certain laboratories due to existing differences on testing fees, the project should conduct policy meetings, discussions and communication forum to review, revise, approve and validate testing fees (non-tax revenue) for relevant institutions; (b.) On initiative financing, conduct a comprehensive quantitative review of the future energy saving and GHG mitigation potential from the use of energy-efficient appliances associated with the implementation of ES&L program and develop an incentive/rebate scheme based on the cost-benefit analysis; (c.) On promoting ES&L, with concern on low purchasing power and high preference on low-priced non-EE products, to promote ES&L by continuing consumer education and combining with financial incentive program to attract and affect on consumer mindset. Pertinent data, information, and inputs system and website should be developed for all stakeholders including the implementing partner and the relevant associations of producers and manufacturers of energy saving home appliances; and (d.) On government procurement, to create fiscal space to allow governments to expand social services and meet other critical infrastructure investment priorities using energy efficiency investments in public facilities leading to attractive economic stimulus, local jobs and reduced future operating costs. Government procurement in the pilot project should be a stimulus for expanding the program of EE. Pakistan – a.) Project organogram realigned to fulfil the project requirements due to non-availability of experts in ES&L field; b.) Reiterate request to Government and UNDP on Project Bank Account being non-operational since April 2013, due to non-availability of signatories as either of the two signatories i.e. National Project Director or National Project Coordinator was not on board; and c.) Closer cooperation and speedy interaction with TWG members to address delayed and inconsistent inputs from TWG members. Thailand - The BRESL PSC meeting suggested to the BRESL working team to revise and improve the policy recommendations before presenting to the PSC again within Q1/2014. After that the completed policy recommendation should be officially presented to relevant agencies. Furthermore, the BRESL working team should seek the way to push the policy recommendation to be the concrete implementations through related agencies. Vietnam - a.) The capacity of testing labs and monitoring & verification must be improved and conducted frequently. MOST needs to invest in improving the capacity of testing labs as well as building more capable testing labs to meet the demand of the market. In addition, the testing experts should be trained and shared experiences with other colleagues. Beside, MOIT also needs to pay more attention to the monitoring and verification activities after mandatory phase came into effect by conducting compliance surveys in different areas and enhancing market surveillance of labeled products. BRESL can assist both MOIT and MOST in improving capacity of testing labs through training for technical experts and implementing M&V activity nationwide; b.) A management software of labeling applications database should be prepared and applied for the officers at MOIT. The management of database of energy labeling applications will be the difficulty for MOIT when hundreds of applications submitted for approval. Additionally, there are many kinds of equipment and appliances needs to be classified and managed in a systematic way.

6. Annexe/s

Bangladesh 2013 APR China 2013 APR Indonesia 2013 APR Pakistan 2013 APR Thailand 2013 APR Vietnam 2013 APR

# Text boxes

Annual Progress Report

Barrier Removal to the Cost Effective Development and Implementation of Energy Efficiency Standards and Labeling Project (BRESL)

January 2014