Jamaica

Annual Progress Report

| Country: | BAHAMAS |
| --- | --- |
| Reporting period: | 01 January 2011 – 31 December 2011 |
| Project number and title: | PIMS 3212 CC EA SNC Bahamas - Enabling Activities for the Preparation of The Bahamas’ Second National Communication to the UNFCCC |
| Project Duration: | 63 months (October 2006 – December 2011) |
| Donors: |  |
| Implementing Partner: | Bahamas Environment, Science & Technology (BEST) Commission |
| Responsible Parties: | National Climate Change Committee |
| Overall Project Coordinator: | Philip S. Weech |
| Date: | 30 June 2012 |
| Current year Approved Budget: | US$126,201.63 |
| Total annual advance: | US$48,934.62 | Total annual expenditure: | US$90,337.44 |
| Annual expenditure to date: | US$90,337.44 | Annual Delivery: | 71.2% |

Table of Contents

I.	Executive Summary	4

II.	Resources and Expenditure	4

III.	Activities and Achieved Results	6

IV.	Implementation Constraints/Challenges, Risks, Lessons Learnt & Recommendations	8

V.	Partnerships and Sustainability	8

Annex I: Annual Work Plan 2011	10

Annex II: Combined Delivery Report	18

Annex III:  Assets Inventory	20

# Executive Summary

The external auditor finished the audit of the project from inception to the end of 2010, and provided the audit report in early June 2011. The audit was conducted along the lines outlined in the guidance document provided by the UNDP Jamaica Office. The V&A and mitigation have been finalised and compiled into the first compilation of the National Communication The Public Education and Outreach (PEO) Subcommittee concluded the PEO strategy. The comic strip booklet, targeting middle school children, was finalised. Quotes for printing the booklet are being received. Delivery is expected in the first half of 2012. The terms of reference for The Bahamas SNC editor were drafted, but not yet circulated. Discussions with UNDP on funding the work on the editor continue. The compiled drafts of the Second National Communication is expected to be submitted to Cabinet for endorsement in the first half of 2012 and the end of 2012.

# Resources and Expenditure

| Resource and Expenditure Report - 2011 |
| --- |
|  | COMMITTED (US$) as per the cost sharing | RECEIVED (US$) | EXPENDITURE (US$) | Remaining Funds (US$) Received – Total Expenditure |
| DONOR |  |  | Period Prior to 2011 | 2011 | TOTAL, i.e. Prior to 2011 + 2011 |  |
| GEF | 405,000 | 382,045.44 | 278,798.37 | 90,337.44 | 369,135.81 | 12,909.63 |
| TOTAL | 405,000 | 382,045.44 | 278,798.37 | 90,337.44 | 369,135.81 | 12,909.63 |

# Activities and Achieved Results

| Expected Outputs & Indicators (including annual targets) | Planned Activities | Planned Budget | Expenditure (US$) | Achieved Results | Progress Towards Achieving Outputs |
| --- | --- | --- | --- | --- | --- |
| Output 1 – National Circumstances Targets/Indicators: 1.1.5 National circumstances chapter drafted | National Circumstances chapter drafted | 7,575.00 | 6,400.00 | Final draft of the National Circumstances chapter completed. Chapter still needs to be published as a part of the SNC. | Completed. |
| Output 2 – V&A Targets/Indicators: 2.1.3 Climate baseline developed; 2.1.4 Environmental and socio-economic baseline developed; 2.1.2 Data and information collected; and 2.1.3 Training materials adapted 2.1.4 Define a range of options applicable to The Bahamas 2.1.5 Develop adaptation response measures | BahamasSimCLIM model developed. | 151,000.00 | 120,267.18 | Climate baseline developed through BahamasSimCLIM model. | Completed. |
|  | BahamasSimCLIM model developed. |  |  | Environmental and socio-economic baseline developed through BahamasSimCLIM model. |  |
|  | BahamasSimCLIM model developed. Draft V&A chapter developed. |  |  | Data and information collected and input into BahamasSimCLIM model. First draft of V&A chapter completed and circulated for review and comments by PSC. |  |
|  | BahamasSimCLIM training workshop completed. |  |  | Training materials adapted and delivered during BahamasSimCLIM training workshop. |  |
|  | Draft V&A chapter developed. |  |  | First draft of V&A chapter completed and circulated for review and comments by PSC. |  |
|  | Draft V&A chapter developed. |  |  | First draft of V&A chapter completed and circulated for review and comments by PSC. |  |
| Output 4 - Mitigation Targets/Indicators: 4.1.2 Identify and evaluate least-cost mitigation options for The Bahamas with emphasis on the energy sector 4.1.4 Assign members with the relevant skills to explore regulatory and legislative options | Work in the energy sector undertaken using LEAP model. | 49,000.00 | 15,914.51 | Work has begun with the LEAP model. | The output has not yet been completed if the cosultants have not yet completed the chapter |
|  | Appropriate technical officers have been engaged to assist in completion of this project component for the energy sector. |  |  | Team has begun work on determining mitigation options for the energy sector. |  |
| Output 5 – Other relevant information | Terms of reference completed. | 7,000.00 | 0.00 | Local consultants engaged to complete this chapter. | The output has not yet been completed if the cosultants have not yet completed the chapter |
| Output 6 – Constraints, gaps and related needs | Terms of reference completed. | 12,000.00 | 0.00 | Local consultants engaged to complete this chapter. | The output has not yet been completed if the cosultants have not yet completed the chapter. |

# Implementation Constraints/Challenges, Risks, Lessons Learnt & Recommendations

| Implementation Constraints/Challenges | Significance | Response/Action |
| --- | --- | --- |
| The project can be negatively impacted if disbursements are not made in a timely manner. This can significantly impact the end date of the project which has shifted forward with each annual report. If disbursements can be made in a timely manner, the project can be successfully completed by the end of 2011. | High |  |
| Risks | Significance | Response/Action |
| As with many Small Island Developing States, The Bahamas has issues related to capacity and resources - both of which are limited and have many priorities competing for their attention and commitment. Climate change will have to compete as well. Economy is dependent on touristic development with large-scale projects existing or planned in coastal areas. | Medium - High | The outputs of the project will enable the National Climate Change Committee to increase awareness of this important issue amongst all sectors of society, particularly decision-makers. There has been engagement with Government agencies on this issue through various workshops and meetings. |
| Awareness and understanding of climate change is limited across all sectors of society. | Medium | A part of the project will be to increase awareness and understanding of climate change through outputs such as V&A assessment, GHG inventory and mitigation options report. Members of Climate Change Committee have participated in events to increase public awareness of this issue and are currently working to refine the PEO Strategy to identify activities that can be completed in this calendar year. |
| As a low-lying SIDS, The Bahamas is faced with the reality that they can do their best to adapt, but climate change as a threat cannot be addressed without commitment of countries with high GHG emissions. | High | The Bahamas Government has been active and vocal on this issue at UNFCCC meetings including COPs. |
| Lessons Learnt and Recommendations: Positive: Progress is slowly being made, reporting is more regular, structure of the project has improved to provide more guidance to those involved. Communication has improved with Implementing Agency. Negative: Disbursements differed from the approved 2010 annual budget by $91,397.45. This is a significant amount which means that planned activities had to be delayed, thus negatively impacting project implementation. Disbursements need to more closely align with cash advance requests made during quarterly reports to aid timely project implementation. |

# Partnerships and Sustainability

| Key Partnerships | Impact on/Contribution to Project Activities |
| --- | --- |
| Executing Agency, Project Steering Committee, Project Coordinator, National Technical Team and GHG Team Leader interact through regular meetings and communication | Regular interaction has improved project efficiency and stakeholder engagement. |
| V&A Team Leader has worked in partnership with persons in relevant sectors including energy, agriculture, tourism, housing and population settlement, water resources and forestry. | This has facilitated completion of the V&A component of the project with partners assisting with provision of much needed data and information. |
| Sustainability Significance Response/Action |
| V&A Assessment training completed. LEAP Modelling completed GHG mitigation, analysis and development of alternatives completed. A cadre of trained national have benefitted from training and capacity development through project activities. |

# Annex I: Annual Work Plan 2012

| Expected Outputs (including indicators and annual targets) | Planned Activities | Timeframe | Responsible Party | Planned Budgets |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| Output 1 Targets/Indicators: Publication of National Circumstances chapter | Main Activity Description |
|  | 1.1.5 Draft national circumstances sections that would be respectively relevant to each thematic area |  |  | X |  | NCC, BEST, Local consultants | GEF | 71400 Contractual services | 1,175.00 |
| Output 2.1A Targets/Indicators: Procedures for assessing vulnerability. The compiled SNC will also require an Executive Summary which will draw upon all major elements at the SNC. This is the final phase of the V&A Mitigation analysis. | Main Activity Description |
|  | 2.1.2 Assess current vulnerability of climate change for sectors under the priority area | X |  |  |  | V&A Team Leader | GEF | 71300 Local consultants | 3,000.00 |
|  | 2.1.3 Develop a climate baseline for the priority area by taking into consideration the baseline developed under stocktaking exercise | X |  |  |  | V&A Team Leader | GEF | 71400 Contractual services | 9,863.66 |
| Output 2.1B Targets/Indicators: Procedures for identifying and evaluating adaptation options | Main Activity Description |
|  | 2.1.2 Collect and synthesize the necessary data and information | X |  |  |  | V&A Team Leader | GEF | 71600 Travel | 3,388.00 |
|  | 2.1.3 Adapt training materials as needed for use in The Bahamas | X |  |  |  | V&A Team Leader | GEF | 71200 International consultants | 78.96 |
|  | 2.1.4 Define a range of options applicable to The Bahamas | X |  |  |  | NCC, BEST, V&A Team Leader, Local consultants | GEF | 71200 International consultants | 2,000.00 |
|  |  |  |  |  |  |  |  | 71400 Contractual services | 3,000.00 |
|  |  |  |  |  |  |  |  | 71600 Travel | 2,000.00 |
|  | 2.1.5 Develop adaptation response measures | X |  |  |  | V&A Team Leader | GEF | 71200 International consultants | 2,000.00 |
|  |  |  |  |  |  |  |  | 71300 Local consultants | 2,402.20 |
|  |  |  |  |  |  |  |  | 71400 Contractual services | 3,000.00 |
| Output 4 Targets/Indicators: Development of national mitigation options | Main Activity Description |
|  | 4.1.1 Define the range of possible mitigation options within the country | X |  |  |  | International expert, NCC, Local experts | GEF | 71600 Travel | 1,933.29 |
|  | 4.1.2 Identify and evaluate least-cost mitigation options for The Bahamas with emphasis on the energy sector | X |  |  |  | International expert, NCC, Local experts | GEF | 71200 International consultants | 3,420.01 |
|  |  |  |  |  |  |  |  | 71405 Service contracts - individuals | 3,000.00 |
|  |  |  |  |  |  |  |  | 71600 Travel | 2,500.00 |
|  | 4.1.3 Analyze the GHG Inventory to identify potential areas for reduction of sources and enhancement of sinks | X |  |  |  | International expert, NCC, Local experts | GEF | 71200 International consultants | 2,500.00 |
|  |  |  |  |  |  |  |  | 71400 Contractual services | 3,892.50 |
|  | 4.1.4 Assign members with the relevant skills to explore regulatory and legislative options | X |  |  |  | International expert, NCC, Local experts | GEF | 71200 International consultants | 2,500.00 |
|  |  |  |  |  |  |  |  | 71400 Contractual services | 7,000.00 |
|  | 4.1.5 Participate in activities adapted to the mitigation options facing Caribbean nations | X |  |  |  | International expert, NCC, Local experts | GEF | 71400 Contractual services | 6,000.00 |
|  |  |  |  |  |  |  |  | 71600 Travel | 339.69 |
| Output 5 Targets/Indicators: Development of other relevant information chapter | 5.1.1 Collect and synthesize information relevant to the Article 6 activities | X |  |  |  | BEST, NCC, Local consultants | GEF | 71400 Contractual services | 2,250.00 |
|  | 5.1.2 Collect, synthesize and provide the information on steps taken to integrate climate change into socio-economic and environmental policies | X |  |  |  | BEST, NCC, Local consultants | GEF | 71400 Contractual services | 2,250.00 |
|  | 5.1.3 Collect, synthesize and provide information on the research and systematic observation systems | X |  |  |  | BEST, NCC, Local consultants | GEF | 71400 Contractual services | 2,250.00 |
|  | 5.1.4 Collect, synthesize and provide information on ongoing programs and projects relevant to climate change and National Communication process | X |  |  |  | BEST, NCC, Local consultants | GEF | 71400 Contractual services | 2,250.00 |
|  |  |  |  |  |  |  |  | 74210 Printing & publications | 3,000.00 |
| Output 6 Targets/Indicators: Development of constraints, gaps and related needs chapter | 6.1.1 Review the status of the constraints and gaps from previous studies | X |  |  |  | NCC, Local consultants | GEF | 71200 International consultants | 300.00 |
|  |  |  |  |  |  |  |  | 71405 Service contracts - individuals | 500.00 |
|  | 6.1.2 Identify new constraints and gaps for each thematic area and elaborate needs to overcome and fill them | X |  |  |  | NCC, Local consultants | GEF | 71200 International consultants | 1,000.00 |
|  |  |  |  |  |  |  |  | 71405 Service contracts - individuals | 1,000.00 |
|  | 6.1.3 Identify new constraints and gaps related to Article 6 activities | X |  |  |  | NCC, Local consultants | GEF | 71200 International consultants | 1,000.00 |
|  |  |  |  |  |  |  |  | 71405 Service contracts - individuals | 1,000.00 |
|  | 6.1.4 Summarize constraints, gaps and needs identified; draft a synthesis report | X |  |  |  | NCC, Local consultants | GEF | 71200 International consultants | 200.00 |
|  |  |  |  |  |  |  |  | 71405 Service contracts - individuals | 1,000.00 |
|  | 6.1.5 Distribute synthesis report for comments and reflect in the document |  | X |  |  | NCC, Local consultants | GEF | 71405 Service contracts - individuals | 500.00 |
|  | 6.1.6 Finalize report as a chapter in the SNC |  | X |  |  | NCC, Local consultants | GEF | 71405 Service contracts - individuals | 500.00 |
| Output 8 Targets/Indicators: SNC Production | 8.1.1 Compile draft SNC | X | X | X | X | BEST, NCC, PC, Local consultants | GEF | 71405 Service contracts - individuals | 3,000.00 |
|  | 8.1.2 Circulate draft for comments; review and incorporate them | X | X | X | X | BEST, NCC, PC, Local consultants | GEF | 71405 Service contracts - individuals | 3,000.00 |
|  | 8.1.3 SNC document endorsed by NCC | X | X | X | X | BEST, NCC, PC, Local consultants |  |  |  |
|  | 8.1.4 Finalize SNC | X | X | X | X | BEST, NCC, PC, Local consultants | GEF | 71405 Service contracts - individuals | 3,000.00 |
|  | 8.1.5 Publish SNC | X | X | X | X | BEST, NCC, PC, Local consultants | GEF | 74210 Printing & publications | 5,500.00 |
|  | 8.1.6 Prepare e-copies of SNC in CD-ROMs | X | X | X | X | BEST, NCC, PC, Local consultants | GEF | 74210 Printing & publications | 500.00 |
|  | 8.1.7 Official submission of SNC to UNFCCC COP | X | X | X | X | BEST, NCC, PC, Local consultants |  |  |  |
| Output 9 Targets/Indicators: Project management | Project management | X | X | X | X | BEST, NCC, PC | GEF | 71400 Contractual services | 5,700.00 |
|  |  |  |  |  |  |  |  | 72200 Equipment and furniture | 35.00 |
|  |  |  |  |  |  |  |  | 72500 Supplies | 2,901.65 |
|  |  |  |  |  |  |  |  | 74100 Professional services | 3,123.98 |
|  |  |  |  |  |  |  |  | 74500 Miscellaneous | 1,147.69 |
| Output 10 Monitoring & Evaluation (Reporting) | Monthly Activities Report | X | X | X | X |  |  | 74210 Printing & publications | 2,700.00 |
|  | Quarterly Report and Work-Plan Update |  |  |  |  |  |  | 74100 Professional services | 0.00 |
|  | Annual Project Reporting |  |  |  |  |  |  | 74110 Audit fees | 11,600.00 |
| Total | 126,201.63 |

# Annex II: Combined Delivery Report

(This will be supplied by the UNDP Finance Unit, to be endorsed by authorized/responsible officer of the Implementing Partner)

| Annex III: Assets Inventory |
| --- |
| Project Title: include relevant info |  |  |  |  |  |  |  |  |
| Award Number: 000 |  |  |  |  |  |  |  |  |  |
| Project Number: 000 |  |  |  |  |  |  |  |  |  |
| Date of Report: |  |  |  |  |  |  |  |  |  |  |
| Asset Profile 1 - Vehicles |
| S/N | Country Code | Business Unit | Item Description | Make & Model | Quantity | Location | Tag Number | Date acquired | Value | Custodian | Remarks |
| 1 |  |  | Vehicle |  |  |  |  |  |  |  |  |
| 2 |  |  | Vehicle |  |  |  |  |  |  |  |  |
| 3 |  |  | Vehicle |  |  |  |  |  |  |  |  |
| 4 |  |  | Vehicle |  |  |  |  |  |  |  |  |
| Asset Profile 2 - Furniture |
| 5 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| 6 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| 7 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| 8 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| Asset Profile 3 - Electrical |
| 9 |  |  | Electrical Equip. or Computer |  |  |  |  |  |  |  |  |
| 10 |  |  | Electrical Equip. or Computer |  |  |  |  |  |  |  |  |
| 11 |  |  | Electrical Equip. or Computer |  |  |  |  |  |  |  |  |
| 12 |  |  | Electrical Equip. or Computer |  |  |  |  |  |  |  |  |
| Asset Profile 4 - Heavy Machinery |
| 13 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| 14 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| 15 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| 16 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| Asset Profile 5 - Non Capitalized Items |
| 17 |  |  | Other (less than 1,000 $) |  |  |  |  |  |  |  |  |
| 18 |  |  | Other (less than 1,000 $) |  |  |  |  |  |  |  |  |
| 19 |  |  | Other (less than 1,000 $) |  |  |  |  |  |  |  |  |
| 20 |  |  | Other (less than 1,000 $) |  |  |  |  |  |  |  |  |
| Project Manager |  | Programme Officer |  |  |  | Deputy Resident Representative |  |
| Date and Signature |  | Date and Signature |  |  |  | Date and Signature |  |  |  |

# Comments

This is to reflect the planned activities and budget for 2011

$1,175 in 2011 AOP

No activities planned for this outcome in 2011 AOP

$0 in 2011 AOP

$33,085.49 in 2011 AOP

$12,000 in 2011 AOP

$7,000 in 2011 AOP

Please indicate how this will support the sustainability of the initiative.

This appears to be the 2011 not 2012 workplan.

This table needs to be completed and signed.

Signature required.

# Text boxes

Project Management:	Prepared by: ______       	Date:            7 January 2011 _

Approved by: _                                                	Date: ___

UNDP Resource Persons:	Name, Programme Advisor – Governance, E & E, Poverty						Name, Programme Analyst – Governance, E & E, Poverty