Cover Page

Country: Bosnia and Herzegovina

Programme Title: Mainstreaming Environmental Governance: Linking Local and National Action in BiH

UNDAF Outcome(s):

Outcome 1: Strengthened accountability and responsiveness of government to

pro-active citizens.

Names and signatures of national counterparts and participating UN organizations

| UN Organizations | National Partner |
| --- | --- |
| Ms. Christine McNab, United Nations Resident Coordinator Office of the UN Resident Coordinator Date & Seal | Mr. Mladen Zirojevic Minister Ministry of Foreign Trade and Economic Relations, Council of Ministers BiH Date & Seal |
| Mr. Peter van Ruysseveldt Deputy Resident Representative United Nations Development Programme / United Nations Volunteers Date & Seal |  |
| Mr. John Noisette Chief, Corporate Services Service United Nations Environment Programme Date & Seal |  |
| Ms. Fernanda Guerrieri Deputy Regional Representative, Subregional Coordinator for Central and Eastern Europe Food and Agriculture Organization of the United Nations Date & Seal |  |
| Mr. Engelbert Ruoss Director, Regional Bureau for Science and Culture in Europe (BRESCE) United Nations Educational, Scientific and Cultural Organization Date & Seal |  |

Contents

1.   Executive Summary	6

2.   Situation Analysis	8

3.   Strategies including lessons learned and the proposed Joint Programme	13

4.   Results Framework	18

5.   Management and Coordination Arrangements	27

6.   Fund Management Arrangements	30

7.   Feasibility, risk management and sustainability of results	32

8.   Accountability, Monitoring, Evaluation and Reporting	35

9.   Ex Ante Assessment of Cross-cutting Issues	39

10. Legal Context or Basis of Relationship	41

Annex A:  Annual Work Plan 2007, 2008 & 2009	43

Annex B: Detailed Budget	55

GLOSSARY

AA		- Administrative Agent

ALD		- Appointment of Limited Duration

BiH		- Bosnia and Herzegovina

CARDS	- Community Assistance for Reconstruction, Development and Stabilisation

CDM		- Clean Development Mechanism

CEMAT	- European Conference of Ministers responsible for Regional Planning

CO		- Country Office

CPAP		- Country Programme Action Plan

CSO		- Civil Society Organisations

CTA		- Chief Technical Advisor

DEX		- Direct Execution/implementation

DNA		- Designated National Authority

EC		- European Commission

ESDC		- European Spatial Development Scheme

ESDP		- European Spatial Development Perspective

EU		- European Union

EWS		- Early Warning System

FAO		- Food and Agriculture Organisation

FBiH		- Federation of Bosnia and Herzegovina

FME		- Funding Mechanism for Environment

GHG		- Green House Gases

ILDP		- Integrated Local Development Programme

IPA		- Instrument for Pre-accession Assistance

JI		- Joint Implementation

JP		- Joint Programme

JPD		- Joint Programming Document

LAG		- Local Action Group

LEAP		- Local Environment Action Plan

MAB		- Man and the Biosphere European network of Biosphere Reserves

MDG		- Millennium Development Goals

MEA		- Multilateral Environmental Agreements

MoFTER	- Ministry of Foreign Trade and Economic Relations

MoU		- Memorandum of Understanding

MTDS		- Medium-Term Development Strategy

NEAP		- National Environmental Action Plan

NGO		- Non Governmental Organisation

NHDR		- National Human Development Report

NSC		- National Steering Committee

ODA		- Overall Development Assistance

PMC		- Programme Management Committee

PRSP		- Poverty Reduction Strategy Programme

REC		- Regional Environmental Centre

RMAP		- Rights-based Municipal Assessment and Planning

RS		- Republic of Srpska

SBAA		- Standard Basic Assistance Agreement

SIDA		- Swedish International Development Agency

SoE		- State of Environment

UN		- United Nations

UNCT		- United Nations Country Team

UNDAF		- United Nations Development Assistance Framework

UNDP 		- United Nations Development Programme

UNECE 	- United Nations Economic Commission for Europe

UNEP		- United Nations Environmental Programme

UNESCO	- United Nations Education Science and Culture Organisation

UNRC		- United Nations Resident Coordinator

UNV		- United Nations Volunteers

# 1.	Executive Summary

Bosnia and Herzegovina (BiH) is renowned for its natural beauty, biodiversity and ecology, but this is being damaged through a lack of environmental management and effective delivery of environmental services. The proposed joint programme is designed to address and overcome the significant barriers faced in effectively delivering environmental services and management at the local level in Bosnia and Herzegovina (BiH). This requires a multi-level approach integrating responsive local government, improved local delivery, and national level process development, reflected in the three programme outcomes:

- Improved local level environmental planning;

- Enhanced management of environmental resources and delivery of environmental services; and

- Increased national environmental awareness and action, localizing and achieving the MDGs.

Key to driving forward the delivery of MDGs in BiH will be two funding windows, one supporting the implementation of Local Environmental Action Plan priority projects at local level, and a second providing assistance for innovative proposals that link environmental management and poverty reduction, and provide lessons to inform further policy development at national level. These funding mechanisms will take into consideration the work done in this field so far by others and will align its functioning with other initiatives by the World Bank and EC, providing parallel co-financing and further enhancing the innovation potential of the programme.

The proposed Programme is to be jointly implemented by FAO, UNDP, UNEP, UNESCO and UNV, and will address and overcome barriers to delivering environmental services and management at the local level in BiH. Interventions centre around providing capacity and support for developing Local Environmental Action Plans for 30 municipalities (a legal requirement and the sole planning tool for local environmental implementation), providing seed funding/co-financing for implementing local environmental management and service delivery priorities, raising the awareness and national level support for environmental action through an environmental innovation fund, and developing effective systems for capturing environmental data.

The joint programme will support and improve local management of environmental resources and service delivery through improving local level environmental governance and developing replicable models for local level environmental planning. The experiences and knowledge base generated will inform and support national level planning and policy development. This will help secure the achievement of MDGs 1, 6, 7 and 8 in BiH. The proposed programme offers an innovative approach to strengthening the capacities for mainstreaming environment issues into policy planning, resource management and service delivery in BiH, reviving the environment sector which is critically stagnant and threatens to become one of the most serious obstacles on the country’s road to European integration.

The programme highlights the links between environment and poverty, in a country with a highly inequitable growth pattern, with an approach based on the principles of social inclusion, a cross cutting issue that is a concern of all the UN agencies in the country.  Social inclusion sharpens the MDG framework in the context of EU pre-accession countries such as BiH.

Design and implementation has and will involve the participation and partnership of central and local government, demonstrated by their commitment to co-finance various activities. The UN agencies involved in this proposal will bring their specific technical and management skills to the Programme. The budget for the programme is $5,500,000 and implementation will be over three years.

2.	Situation Analysis

Background

Bosnia and Herzegovina is emerging from a post-war conflict era. The country’s macro-economic stability has been maintained, inflation is less than 1%, and the growth rate is an estimated 6.2 percent (2006). Agreement has been reached on a single economic space and according to UNDP Early Warning System reports, a growing number of people in all ethnic groups now see their future linked to the state of BiH. However, significant outstanding challenges remain. In the current national context, the Common Country Assessment identified the main challenges to be: weak governance, poor environmental protection, decreasing access to and quality of basic education and health services, inadequate social protection and continued risk posed by over 1 million landmines and unexploded ordinance. Until recently environmental management and governance issues have been largely overlooked due to more pressing post-conflict issues, coupled with a lack of capacity and institutional development at a state level. The UN/ECE Environmental Performance Review and the functional review of the Environmental Sector detail serious failings in environmental policy, legislation, and implementation functionality. There is no state level environmental policy or national level regulatory framework, although a National Environmental Action Plan (NEAP) has been adopted at the entity level. State level administrative mandate and capacity are both limited. The legislative functions are also weak: laws specifically targeting the environmental sector do not exist at the state level. Monitoring of the state of the environment does not provide regular or reliable data on environmental indicators. Public information and education are also lacking.  These represent serious challenges to currently mainstreaming environmental governance, and are expanded on below.

Legal-Institutional Framework

With up to three levels of autonomy (State, Entity, Cantons) and up to four administrative levels (State, Entity, Cantons, Municipalities) the country’s environmental administration, and notably its regulatory, executive and control aspects, are very complex. This necessitates enormous cooperative efforts resulting in cost-inefficiencies, considerable delays, gaps in administrative coverage and unequal application of standards.

The environment is not expressly mentioned in the Constitution (neither in the competencies of the State of BiH or the Entities). According to Article III.3c, all governmental functions and powers not expressly assigned by the Constitution to the institutions of BiH shall be Entity responsibilities. This means that the Entities regulate environmental issues through their laws, regulations and standards. A draft state environment framework law is under preparation with assistance from the EU. The only significant exception to this is the 2003 Law on the Ministries and Other Administrative Bodies of BiH, which assigns responsibilities for environmental protection to the Ministry of Foreign Trade and Economic Relations (MoFTER). This gives MoFTER responsibility for the definition of policy, fundamental principles, coordination of activities and harmonizing the plans of the Entities governmental bodies and institutions at the international level in agriculture, energy, environmental protection, and the development and the exploitation of natural resources.

In principle all institutions and administrative units in the environmental field have mandates based on legal provisions. Competencies and functions are also detailed in secondary documents such as rule books, however anomalies occur. A great part of the secondary legislation necessary for the implementation of the primary environment related legislation has not been elaborated yet, so competencies are not clearly defined. In some cases secondary by-laws are adopted on entity level, but not enforced, as institutional and human capacity for enforcement is inadequate.

Additionally, the great number of laws, the multitude of regulating bodies and the differences in spatial provision create confusion. There are some positive aspects to the institutional framework: the Inter-entity Steering Committee for the Environment, established in 1998, is a reasonably effective mechanism providing for coordination and communication. It consists of eight members and deals with environmental issues delegated to it by the Entities. In the past, secretariat services had been provided by the local office of the Regional Environmental Centre (REC) but currently there is a lack of an appropriate support system.

Policy Environment

The main policy document on environmental issues is the National Environment Action Plan (NEAP) prepared  with  World  Bank  support  by  ministry officials,  scientists  and  NGOs, and adopted in 2003  in  both  Entities.  It  identifies  8  priorities: water resource management and waste water treatment, sustainable development in  rural areas, environmental   management   (information   systems, integral  planning and education), protection of biological and landscape diversity, waste and waste management, economy and sustainable  development,  public  health  and  de-mining.  Although the NEAP led to numerous  project  proposals  it  fell short  of  a  proper  action  plan  as  it  did  not designate responsible actors. It provides orientation, but remains at the level of general direction and has had little effect on the distribution of functions and the structure of public administration.

More impact is attributed to the Mid-Term Development Strategy of BiH 2004-2007. It is a general document addressing most economic and social issues, which covers also environment and water. Although, it follows the priorities listed by NEAP, it is more concrete in designating the necessary follow-up. An overall strategy for the environmental sector, however, is yet to be written. The preparation of a number of strategies and plans is required by law. However, none of the required documents have been adopted so far.

Environmental Information

The monitoring of the state of environment in BiH does not provide regular, comprehensive and reliable information on the state of water, waste-water, air, solid waste, soil and nature protection,   radiation   and   noise/vibration   at   the   state,   entity   and   municipal   level.   A comprehensive monitoring network does not exist.  Monitoring  activities  are  fragmented  and  in  the complex  institutional structure  environmental  information  does  not  flow  satisfactorily.  Information is usually stored within each institution that collects it, not reaching others.

There is a need for comprehensive and systematic environmental information management. With support from EU CARDS, a structure for such a system has been developed, but implementation has not been effective, leaving significant gaps in terms of environmental data management, environmental statistics and reporting, including to international bodies. BiH is currently failing in its environmental reporting obligations.

With regard to access to environmental information, the norms of the Aarhus Convention are anchored in the Entities’ legislation. Much of the necessary secondary legislation is however not yet in force.  Although Government offices do recognize their duties and have designated officials, NGOs state that the information received from the public agencies is often not fully satisfactory.  Delay in replies and lack of skilled staff are identified as causes. In reality there is little access to reliable environmental information for citizens, central or local tiers of government.

Environmental Finance

Effective environmental management is not possible without efficient financing of environmental protection and economic support instruments. In BiH, environmental finance issues are still in a very rudimentary stage. There appears to be an almost complete de-linkage between municipal level budget cycles and financing, and environmental planning. Entity budgets earn some income from economic instruments related to the use and pollution of the environment, e.g. special taxes, concessions and other fees, etc. These funds are spent for various public functions, but very little funding supports environmental protection.

Additional fundraising and the establishment of efficient overall financial and project management systems is needed for environmental policy implementation. BiH is working towards establishing environmental funds in both Entities. Currently, each entity has adopted an Environmental Fund Law. These laws have not been yet implemented; there are no management structures or flow of revenues. These laws need also further elaboration, on objectives, priorities and type of activities, which has been assisted by a EC technical assistance project.

Local Development/Environment Planning

Environmental Planning at the local level is mainly organized through a Local Environmental Action Plan (LEAPs), which is an effective tool to help communities undertake environmental planning, and provides a solid basis for further coordinated action. Development and adoption of LEAPs is a legal obligation in Republic of Srpska (Law on Environmental Protection of RS, Article 51.), and in Federation of BiH, municipalities express their own willingness to develop a LEAP. However, cantons are obliged to adopt cantonal environmental action plans (Law on Environmental Protection of FBiH, Article 49). Of the 148 municipalities in BiH (64 in RS and 84 in FBiH), approximately 30% have already developed and adopted LEAPs. Most of the LEAPs have been developed with support from different donors (EC, SIDA, Netherlands), with facilitation assistance from national organisations such as the Regional Environmental Center (REC) for BiH, and others. REC BiH has made a significant contribution to the process of developing LEAPs in BiH by organizing seminars and workshops, and providing technical assistance in plan development. However the quality of LEAPs varies significantly, and in most cases the direct link to municipal budgetary and investment planning is missing. The implementation of LEAPs is currently limited because of the lack of human and institutional capacities, low public environmental awareness and lack of resources.

Environmental Governance, Poverty and MDG Linkages

The 2003 National Human Development Report (NHDR) on MDGs in BiH concluded that poverty reduction is the number one priority for BiH, with environmental management and governance being fundamental issues that need addressing if poverty is to be reduced and MDG 1, 6, 7 and 8 achieved. This has been backed up more recently by the BiH Medium-Term Development Strategy (MTDS – equivalent to PRSP), which identifies poverty as the main problem in BiH, and the 2007 NHDR on Social Inclusion. Key issues identified include a lack of environmental policy and legislation; poorly developed environmental management and implementation capacities; little public participation in environmental decision-making; and a lack of reliable information and data. BiH has serious environmental problems in the areas of water, forestry, health, land management (including abandoned land and land mines), contaminated land and waste management. Despite the documented importance given to the environment in poverty reduction, surprisingly little donor attention has been paid to it: the 2006 UNDP donor mapping exercise found that only 0.6% of ODA (€2.7m) was allocated to environmental protection.

The lack of donor interest in environmental governance and management is in part due to serious administrative and institutional issues that have made progress difficult. The mandate of the state level administration is limited, as is their capacity. The multiple tiers of administration (up to four levels: BiH, FBiH, cantons, municipalities) create complex regulatory, executive and control systems. This, coupled with a lack of mutually recognized central coordination, results in a lack of application of standards and gaps in administrative coverage.

European Integration

The European Commission BiH Delegation website states that ‘Environmental planning … is inadequate, and recent neglect of environmental considerations has left visible and invisible scars.’ The European integration process requires major changes in environmental management. EU environmental policy legislation covers a wide range of sectors and represents the most extensive and most expensive part of implementation of the Acquis communautaire. Currently the capacities of BiH authorities to move this process forward on their own are extremely limited. Unusually complex governance structures and constitutional arrangements result in a lack of a coherent policy and planning framework in the environmental field. Poor governance and jurisdictions divided between the two Entities without an effective coordination role at the national level further enhance the problem. However, recently there have been some positive signs. It is particularly encouraging that the new Government (from February 2007) has proclaimed environment as one of its priority areas and has committed to work on resolving the mounting environmental problems.

From 1 January 2007, the EU is using a new financial tool for promoting modernisation, reform and alignment with the EU’s legal order, the Instrument of Pre-Accession (IPA). This will entirely replace previous assistance instruments, with priorities based on the Multi-Annual Indicative Plan. The EC multi-annual financial framework allocates IPA funds €62.1 Million for BiH in 2007 for transitional assistance and institution building, growing to €106 Million by 2010, with matching funding available. Strengthening environmental institutions and governance are objectives of IPA support. Currently IPA funds cannot be released to BiH, and there is a defined need to provide support for institutional development.

Kyoto Protocol and CDM

The procedure for Kyoto Protocol ratification in BiH is in it’s final stage of finalization, but there is a low level of awareness and knowledge of its mechanisms among the government, public, and private sector. The Government lacks both the human capacity and financial resources to initiate the implementation process and has already approached UNDP for assistance. There is a clear commitment to commence the implementation activities on the Government side in order to become eligible to participate and host GHG reduction projects under the Clean Development Mechanism (CDM). Beyond ratifying the Kyoto Protocol, BiH still needs to establish appropriate legal and institutional frameworks, namely Designated National Authority (DNA) and CDM approval procedures.

3.	 Strategies including lessons learned and the proposed Joint Programme

Background

The issues of environment have been identified in the key national strategic planning documents as high priority.  For example, the MTDS is built around the key goals of: 1) creating conditions for sustainable and balanced economic development, 2) reducing poverty and 3) acceleration of the EU integration process. The key environment related priorities identified in the MTDS are: i) strengthening the legal and institutional framework; ii) improvement of  the system of funding and capacity in this sector (through the establishment of environmental funds) and encouraging local level implementation; and iii) strengthening environmental statistics.

Through the current UNDAF for BiH, the UNCT in BiH has clearly committed itself to support BiH’s progression towards European Integration, and environment is one of the priority areas for support. This proposed programme responds to the BiH UNDAF Outcome Number One: “Strengthened accountability and responsiveness of government to pro-active citizens”, as the UNDAF attributes the poor environmental protection in BiH to the lack of environmental policy, legislation and its implementation, poor public participation in environmental protection and sustainable development, and unsustainable rural and urban development.

The MDGs, MTDS and European accession processes have common features: governance reform, poverty reduction and provision of basic services, to which this programme directly responds.

This Programme has three closely aligned and mutually supportive outcomes, designed to deliver significantly improved local management of environmental resources and service delivery (outcome II of the thematic window). This will in turn contribute to a reduction in poverty and vulnerability by helping secure MDG 1, 6, 7 and 8.  The three outcomes have been identified jointly by the UN Country Team and the Government of BiH as priority areas, where interventions can produce concrete and significant results in the life of the programme.

Lessons Learned

The experiences of UNCT in BiH have shown that the issue of integrating the centralized and bottom-up processes of Government are both critically important and, at the same time, extraordinary difficult. As the multiple administrative and organisational layers complicate any integration effort, focus has to be directed to building linkages and information flows, to ensure that policy developments are effectively interpreted and implemented at the local level and, conversely, that local level implementation experiences feeds into and influences policy development.

This programme specifically builds on the experiences, learning and accumulated knowledge of the participating UN agencies in supporting local governance reform, with a particular focus on participatory planning processes and social inclusion. Support and capacity building for local level delivery of environmental services are currently being successfully delivered in BiH, on a limited scale, through several area-based development programmes and rights-based assessment and planning projects. These have captured experiences and knowledge, providing an evidence-base to inform, influence and support policy and legislative developments. The proposed programme builds on these experiences and skills, directing them towards environmental governance reform. This will build a solid platform for delivering the MDGs, European accession and sustainable development opportunities for a vibrant BiH.

Some of the key lessons learnt and issues identified based on the agency experiences in BiH, which have been taken in consideration when designing this programme, are related to: the need to mainstream the LEAP processes into a participatory planning process and to integrate them with the municipal budget cycles and processes; the risk of focusing on developing only state level institutions (although this is an accession requirement it is most likely several years away before state level institutions might have any real power); the distinct lack of understanding about environmental service provision and the valuing of environmental services; a lack of data for climate change and environmental monitoring; ineffective environmental resource management; and low levels of awareness regarding environmental management. The risk management section details how lessons have been built into the programme design.

Proposed Joint Programme

The strategic approach is to utilise the extensive skills and operational experiences of the UN joint implementation team to work with local and national partner organizations, drawing on their skills and capabilities, further enhancing them where appropriate to build their capacity. While the specific roles for individual UN agencies and partner organisations are highlighted in Annex A, the overall role of the UN agencies in this programme will be capacity building and providing technical assistance, moderation, and management of the programme. In order to further improve national capacity there will be an emphasis on developing in-country civil society and private sector skills, as well as the skills of public sector workers, through learning-by-doing, sub-contracting activities to local partners, and joint implementation.

As the UN agency with the most significant capacity at country level, UNDP will be the programme lead agency with the responsibility for achieving Joint Programme Outputs. With its strong implementation capacities and cooperation partnerships, UNDP will ensure quality and effective delivery of local level interventions. Given its strong mandate in environmental policy, UNEP will provide technical cross-programme coordination for environmental management issues at the national level. Within the Programme, FAO will use its experience in supporting and strengthening the management of natural resources as well as assessment and mitigation of environmental risks. UNESCO will have a key role in providing organizational support for all the activities related to the protection of the natural heritage. The relevant UN agencies will also provide assistance to environmental governance and capacity development as well as assistance to the development of the legal framework and assessment of the local environmental needs. Through all these activities, volunteerism in local environmental management will be actively promoted, building on work UNV has already done in this field.

The strategic orientation of the Joint Programme is designed to address and overcome barriers to effectively delivering environmental services and management at the local level in BiH. This will be achieved through delivering three integrated outcomes, addressing local and central (state and entity) level environmental governance issues.

A main conceptual pillar of the project is its emphasis on mainstreaming environmental issues into the broader development agenda with a particular emphasis on poverty alleviation as expressed in the MDGs. This is reflected in the integrated planning approach but also informs indicator development, the selection criteria for participating municipalities and the award of innovation grants. Moreover, planning and other participatory processes will ensure that the poor and other socially excluded groups are targeted and have an effective voice.

The project will pursue an integrated approach to local development planning, ensuring that the LEAPs evolve from stand-alone action plans into more holistic strategic instruments. Various models and approaches to strategic planning have been tried and tested in BiH over the recent years, and cover a broad spectrum of focuses, time frame and participation. This project component will be closely linked to the second phase of the RMAP project, the Integrated Local Development Programme (ILDP). A possible modality is to offer a joint ILDP/LEAP package to selected municipalities, with mutual representation in the two project governance structures. Participatory planning methods will be used to ensure social inclusion of vulnerable groups. The skills and experiences on integrated situation analysis, community mobilization and public participation of UN Volunteers (UNV) are incorporated into implementation of the Joint Program.

Linking Local Entity and National level Capacity Building

Effective local-level environmental management can only be sustainable if it is supplemented by, and integrated with, a set of strategic interventions at the entity and national levels (multilevel governance). Many of the activities (under all 3 outcomes, but particularly 1 and 2) focus on strengthening the planning and environmental services delivery processes at the local (municipal) level, building local level capacities, and ensuring that the benefits of this programme reach directly the people of BiH. To date, this has been problematic within BiH due to difficulties with the complex entity/national level institutional setup.  The need to initiate capacity building activities at entity and national levels is fully acknowledged, and one of the key objectives of the programme is to facilitate the process of national level priority setting, policy making, and the development of environment services delivery financing mechanisms, as realistic and promising entry points.

At the local level, the focus will be on strengthening the capacities of  the  authorities concerned, communities and CSOs to organize and conduct modern participatory prioritization and planning processes, network effectively, raise funds and implement the priority environment actions deriving from the plans. This is discussed in more detail in section 4, and in the Year 1 action plan.

The entity and national level capacity building strategy of the programme derives from the country realities, as described earlier in section 2. In the specific context of BiH it is not realistic to approach the development of  capacities only though activities focused on supporting national level institutions; It is essential to work, in parallel, at the entity and national levels, ensuring that there is both buy-in to the process of national level capacity building, and sufficient capacity within the entity institutions themselves.

The approach of the programme is to ensure activities deliver tangible, needs-based environmental improvements that directly benefit the country and it’s population, but also effectively transfer knowledge to entity level and national partners, building their capacities. This, in turn, will help to ensure the long-term sustainability of the programme outcomes.

A key goal is to achieve effective knowledge development, building national capacities and competency. The overall approach to delivering this is a ‘learning by doing’ approach. At the beginning of the programme there will need to be a leading, coaching and monitoring role by the UN Agencies involved, with a gradual transfer of responsibilities to national partners later in the implementation stage. The approach will support the delivery of a coordinated package of targeted capacity building, advocacy and advisory activities, which will be designed on the results of reviews and capacity needs assessments.

At the national level, capacity building will be focused on the relevant authorities. Key skills will be developed in: managing data collection; planning (review of the legal framework and related advocacy activities, new frameworks of indicators, and State of the Environment Report); prioritising actions; the implementation of targeted capacity building packages for key staff; electronic linking; and public access to information. Capacity building will be reinforced by gaining practical experience through active participation in the set up and management of the national level Funding Mechanism for innovative environment projects (under activity 3.4.1.).

These actions will contribute significantly to enhancing the general absorption capacity of the institutions, while contributing to removing and reducing barriers to effective environmental management and mainstreaming.

Building Capacity

Capacity building will be focused on improving:

a) Institutional Capacity. Although recent years have seen some improvements in terms of the authorities’ ability to perform basic environmental policy and management functions, serious gaps remain. Some of them will be addressed in the context of ongoing and planned EU support, particularly at the state level. This project will target a number of well-defined challenges:

- International Multilateral Environment Agreement Obligations: To address some of the shortcomings in the  administration  of  international  obligations, it is necessary to have a national strategy for international environmental cooperation, including a set of costed implementation priorities, clarification  of  internal   institutional responsibilities,  and  due  reporting  to  the  decision-making  and  supervisory  state  and  entity bodies.

- Inter-Entity Steering Committee: The project will  assist in the setup of a permanent executive secretariat to facilitate the Committee’s ongoing business, in particular the follow-up and monitoring of decisions and recommendations and the preparation of policy briefs and technical discussion papers. It will also explore options for transforming the Committee into an enhanced body such as a State Commission.

- Climate Change: BiH has not yet fully assessed and addressed the implications and opportunities under various climate change regimes including mitigation and adaptation options. The project will focus on institutional support for Clean Development Mechanism (CDM) implementation and the development of an adaptation strategy for select sectors such as agriculture, forestry and water resources.

b) Information Systems and Knowledge Management: The complex distribution of roles and responsibilities for environmental management has hampered the establishment of a comprehensive environmental information system. The project will assist in the implementation of some of the measures proposed in the EU functional review, with emphasis on:

- Indicator Development:  A core set of indicators will be compiled and developed, taking into account Bosnia’s international obligations and national/local circumstances, with particular emphasis on linking environmental indicators to the broader development agenda and poverty alleviation priorities.

- State of the Environment Report:  The development of a state-level SoE Report will for the first time provide a comprehensive picture of basic environmental data and trends for both Entities.

- Public Access to Information: The project will assist in the development of more transparent and participatory processes through capacity development for government and civil society officials to prepare for the implementation of the Aarhus Convention. In addition, local pilot projects will be carried out and good practices compiled and disseminated.

c) Finance and Economic Incentives: The project will establish a grant facility- “Funding Mechanism for Environment” (FME). More information is given in section 4, outcomes 2 and 3. The grant facility will be set up in the Project Management Unit, and managed by a dedicated staff member of that Unit. The focus, priorities, criteria for selection of projects and all other key decisions for the facility will be steered through a participatory process organized by the Fund Steering Committee, in which the members of the Inter-Entity Steering Committee for the Environment, CSOs and other stakeholders will have a leading role and the overall responsibility for decisions on grants and other strategic issues.

# 4. Results Framework

In order to help  secure the achievement of MDGs 1, 6, 7 and 8 in BiH there must be support for change and development at both the local and national level simultaneously, in a strategically and operationally aligned manner. The three outcomes of the programme are designed to overcome the barriers to effective environmental resource management and service delivery, through local planning and action, supported by national level awareness raising and actions providing a more enabling environment. The general problems in the fields of environmental policy and legislation, capacities, public participation in decision making on environmental issues, monitoring and analysing environmental data and a lack of economic incentives require a programme designed to address these issues at multiple levels. The 3 project outcomes are designed to achieve this necessary synergy.

The design of the programme is based on the need to have effective national level coordination and prioritization mechanism for the environment sector, not only as the central focal point for the many international treaties that BiH is party to, but also for the sake of the future EU accession process. In parallel, there is a focus on local environmental service delivery, where action can be rapidly implemented to secure the agreed results.

Outcome 1: Improved local level environmental planning

Within many municipalities environmental governance is very low on the planning agenda, and is not viewed as a cross-cutting theme or an important component in regional sustainable development. This is not symptomatic of a lack of interest or perceived importance of environmental governance: it is due to a lack of capacity to address the issues. Therefore, there will be a focus on developing effective participatory environmental planning methods (building on highly regarded social inclusion processes already implemented by UNDP across BiH), using multi-stakeholder decision support methods to identify and prioritise environmental management and delivery requirements.

This will support the design and development of Local Environmental Action Plans (LEAPs) in 30 Municipalities throughout the country. LEAPs are a legal requirement in both Entities, and underpin the development of local environmental governance capacity. Some municipalities are more advanced in their environmental planning and service delivery than others. Our approach to building capacity will be to work with municipalities in clusters of 4-5, with an ‘environmental champion’ municipality, that has already developed a LEAP, providing support and guidance to municipalities that are not so advanced. This co-learning will be supported by external capacity building.

The selection of the municipalities to be supported by this programme will be made under the overall steering of the Programme Management Committee. The PMC will, together with the Programme Manager, organize a consultative process and define detailed criteria for selection of Municipalities. The criteria will reflect: the strategies, results and experiences of other similar initiatives in field of local level planning; the level of expressed interest, enthusiasm and capacities of individual municipalities; the real needs of population on local level and potentials for synergies; potential for clustering municipalities around a ‘champion’ or early adaptor municipality; and joint effort and cross-fertilization with other similar ongoing initiatives.

A deeper understanding of the key environmental issues facing BiH, their relationship to sustainable development, social inclusion and poverty reduction, and  how to plan and action activities to improve environmental governance will be built at the municipality level. At the same time, the programme will identify an appropriate strategy and produce recommendations on how to best feed the LEAP process outputs into the entity and BiH level strategies. The role of entity ministries of environment will be crucial in achieving this as they have both the legal mandate to enforce development of LEAPs, and an obligation to follow up on their implementation. Therefore, they are in a position to link the LEAP process and outcomes with the entity and national level planning process, and this programme will support them in developing these linkages.

Outcome 2: Enhanced management of environmental resources and delivery of environmental services

In many municipalities there is an extremely low capacity for the effective management of environmental resources or the delivery of environmental services. This, in turn, hinders sustainable economic development and deepens and embeds chronic poverty amongst the vulnerable. Environmental governance and planning are ineffectual without the appropriate means for implementation.

The UNCT agencies will utilise their experiences in delivering effective environmental resource management through capacity building and technical assistance across municipalities. A multi-agency approach will be taken to improving environmental service delivery mechanisms. This will be particularly focused on better provision of environmental services, energy, drinking water, sanitation, river and groundwater pollution, waste management and depletion of underground water.

A “Funding Mechanism for Environment” (FME) will be established, envisaged to be operating on basis of a co-financing scheme. There will be two separate funding windows, namely:

  - support to the implementation of LEAP priority projects

  - assistance to the financing of larger-scale innovation projects

The first  one will directly support achievement of the Outcome 2 though provision of just over USD1 million in grants for implementation of the priority projects identified though the LEAP process. Local communities and municipalities interested in benefiting from the grants will provide a minimum co-financing of 50% of the total project value, demonstrating both the importance of the project, and the necessary commitment to ensure sustainability.

Grants will be targeted at activities which will solve the most pressing problems at the local level which are identified during LEAP preparation. Activities will also have to be designed to develop stronger relationship between local stakeholders (municipalities, CSO, private sector) who will be encouraged to jointly apply for funds. Thirty grants ranging from $30 000-70 000 will be awarded.

This window of the grant facility will:

a)	Directly benefit the communities and population at ground level though financing of their priority projects;

b)	Improve the level of capacities for environmental project prioritization and development, by stimulating community participation in planning, project development, implementation and monitoring activities;

c)	Increase the local level project development and management knowledge, thus effectively increasing absorption capacity on that level

Outcome 3: Increased national environmental awareness and action, localizing and achieving MDGs.

This outcome is designed to ensure that local level developments, lessons and best-practices are used to inform and influence policy development and mobilize awareness of environmental issues, thereby encouraging a more pro-active approach. Additionally, incentives in testing and implementing innovative approaches in environmental resource management and service delivery are expected outcomes, to be supported through the innovative national level funding mechanism to be set up under the FME.

Closely connected to the support to local action, an environmental database will be developed, to capture reliable information on environmental indicators, to support informed decision-making processes. A detailed understanding of the gaps in the legal and institutional framework will be gained, with special focus on links between environment and poverty. A State of Environment Report and implementation of a capacity building package targeted at environment ministries will further contribute to achieve this Objective. This will assist with assessing the existing legal-institutional framework and environment documents in order to produce new "road map" recommendations for MoFTER. This in turn will support advocacy activities, and allow the development of a new comprehensive indicator framework including data sources.

An assessment of the needs in capacities to be developed will be conducted for MoFTER, the Inter-entity Environmental Committee and entity environmental Ministries. This will then be used to develop a capacity building strategy on priority areas (such as environmental monitoring and reporting, MEA obligations, mainstreaming). These activities will be carried out in close cooperation with government institutions, helping them to develop their capacity. Additionally, regional exposure visits/study tours for key national stakeholders, as well as targeted workshops will further strengthen capacities.

The second funding window, at national level, FME innovation, will grant ca.10 awards of up to $90,000 for projects that go beyond the municipal level and which adopt and promote innovative approaches. The Fund Management and the Steering Committee will further develop criteria for innovation award applications but one of the key aims will be to facilitate innovative approaches linking environment protection and poverty reduction. Furthermore, submissions of inter-municipality and sub-regional projects will be sought as environmental issues do not usually follow administrative boundaries. Project proposals that deal with new and emerging environmental issues will be encouraged including those that propose inter-sectoral solutions, such as interventions across the agriculture, energy, water management, and human security sectors. For example, ecosystem services delivered by public-private partnerships would be welcome.  The innovation awards will support activities that contribute to the achievement of the MDGs and contribute best practice examples in support of further policy development at national level.

In consultations with the key donors in BIH, this component of the programme has been highly regarded for its innovative approach. Donor representatives have expressed their unanimous support for setting up this funding mechanism.  They agree that the lack of national capacity and weaknesses in functional institutional frameworks have discouraged them from investing in the environment sector, despite the obvious need for support. Most of the key donors have expressed a readiness to reconsider their policy if the Innovation Fund provides a functioning financing mechanism at national level. A successful national level Innovation Fund should result in significant co-financing for the Fund itself, and lead to a significant increase in the level of investments in the wider environment sector in BIH over the next few years.

The rationale for setting up the Innovation Fund is to establish an incentive mechanism for the state and entity level governments to start working together in order to translate environmental obligations under international conventions into actual environmental solutions and actions. As the BiH state level institutions have limited constitutional competencies in the field of environment, and given that a strong role of the State is a requirement for EU accession, the establishment of such an incentive mechanism is essential as the first step in towards effectively integrating the efforts of the key players in this sector.

The FME Innovation Fund will be setup with the following key objectives

- To provide a strong incentive for the national level players (state and entity governments) to work together on technical, non-political issues related to functioning and strategic management of the fund. The Fund will provide a practical platform, through which there will be demonstration of the direct advantages of working together. This will form a basis on which future, more formal, national priority and policy setting mechanisms can be based on.

- Ensure full national ownership, participation and transparency – the Fund management structure and modus operandi will be based on full national ownership, guaranteed through the role that national stakeholders will have in the participatory fund management mechanisms, including the Fund Steering Committee. The Committee will be the key mechanism though which the national level stakeholders (representatives of state and entity authorities, Brcko District, civil society, academia and others) will steer the Fund and make decisions on key issues (strategic focus, priorities, criteria for selection of projects, grant awarding, implementation arrangements). Details of Fund set up arrangements will be determined though a consensus building participatory process. This will help to mitigate most of the political risks which this activity bears.

- Maximize links between achieving environment and poverty related MDGs. The Innovation Fund will put emphasis on supporting projects that offer innovative solutions in linking achievement of environment related MDG with achievement of effective poverty reduction throughout the country. For the first time in BiH, focus will be put on identifying and addressing the priority environmental problems that have biggest impact on the poor and vulnerable groups. These will include projects with high economic impact, such as climate change related flooding, droughts, forest fires and similar. By addressing such problems through, for example, irrigation projects or forest fire warning systems, direct impact on achievement of both poverty and environment protection related MDGs will be maximized.

- Increase national absorption capacity – the experience of the most recent expansion of EU is that the capacity of a country to absorb the levels of funding that are available to an EU accession country is one of the most significant bottle necks in the process. This is likely to be particularly true for BiH due to its governmental structures. It is imperative that BiH urgently and quickly builds it’s absorption capacity in anticipation of the EU accession process, which is one of the very few goals that all in BiH share unanimously. Therefore, the capacity to set policy, prioritize, manage and implement funds, which will be built at relevant national level institutions though participation in the management of the Innovation Fund will significantly strengthen the currently very limited absorption capacity in the environment field.

In it’s functioning the Innovation Fund will be using the public call for proposal modality, where decision making will be done though a transparent, participatory process, particularly the selection of the innovation projects to be funded. Details on priorities, process and criteria will be determined tough the inclusive process of joint decision making by the UN agencies and key national stakeholders, in the inception phase of the project. Beneficiaries of the activity will be primarily the national level stakeholders, as primary target of the capacity building activities, but also wider population of the areas where the innovation projects will be implemented bringing both improvements in environmental service delivery and reduction of poverty for the most needy parts of BiH population.

This national financing mechanism will take into consideration prior work done in this field (for example, establishment of the Entity level Environmental Funds) and will align and integrate its functioning with other similar initiatives. The other initiatives in this field, such as those financed by the World Bank and EC, can be seen as parallel co-financing driving the process in the same direction, which will further enhance the positive effects of the programme Innovation Fund. The grant facility to be set up by this UN programme will provide incentives to move this process ahead, and provide an excellent opportunity to pilot the co-financing and grant mechanisms in BiH’s environment sector.

Although the funds available for this component of our programme are relatively limited, with total of USD 900,000 available for approximately 10 innovation grants, we believe that once the mechanism is functioning and demonstrates success in supporting innovative projects in the environment sector, there will be interest and support from donors and international financial organizations. Donors will be able to use it directly as an effective delivery mechanism for their assistance, and to align their ongoing activities as parallel funding for the Innovation Fund projects.

One significant strength of the Innovation Fund will be that the priorities, project selection criteria, project selection and awarding will be conducted though a fully participatory, transparent and accountable process, in which key national and international stakeholders will have an opportunity to participate and contribute to aligning it with the real national needs and priorities.

The FME steering committee will involve representatives of State and Entity level Government, the District of Brcko, and the Inter-Entity Coordination Committee, with the intention of supporting MOFTER in responding effectively to the demands of their role in coordinating activities in the environment sector in BiH.

The flexibility of this approach will enable the Innovation Fund to be well-positioned to support innovative solutions in linking environmental issues and poverty reduction. The focus will be on identifying the environmental problems that have the largest economic impact, such as climate change related flooding, droughts, forest fires, and particular those that impact on the poor and vulnerable populations. By addressing such problems through, for example irrigation projects or forest fire warning systems, direct impact on achievement of both poverty reduction and environment protection related MDGs will be maximised.

Support for implementation of Kyoto protocol

Additionally to the above described activities, the Objective 3 programme will support the national authorities in identification of the best options and strategies for implementation of the Kyoto protocol, in ways that will most effectively enable BiH to become an active member and benefit from the development mechanisms existing under the protocol.

As an Annex 1 country, where current emissions are on much lower levels than those in 1990, BiH can benefit greatly from participation in the Clean Development Mechanism (CDM). To qualify for that a country has to ratify the protocol and set up a complex legal and institutional framework for monitoring and certification of emissions and reductions known as the Designated National Authority. This programme will contribute to this process, working in close coordination with other initiatives and projects, including the GEF project ‘development of the BiH Initial National Communication to the UN Framework Convention on Climate Change’ implemented by UNDP.

Table 1: Summary of Results Framework – Spanish MDGs Achievement Fund Environment – Bosnia and Herzegovina

UNDAF Outcome:  No. 1: Strengthened accountability and responsiveness of government to pro-active citizens

| Expected Results (Outputs) | SMART Outputs and Responsible UN Organization | Reference to Agency priority or CP | Implementing Partner | Indicative activities for each Output | Resource allocation and indicative time frame |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Y1 | Y2 | Y3 | Total |
| JP Outcome 1. Improved local level environmental planning |
| Output 1. Strengthened capacity of municipalities and CSOs to manage and participate in long-term sustainable environmental planning and management process Indicator 1.1 Number of local coordinators trained in facilitation of local environmental planning and programming process and LEAP formulation Baseline: 0 Target: 30 Indicator 1.2 Number of civil servants trained in environmental planning and programming for including LEAP into budgetary formulation processes Baseline: 0 Target: 90 (3 per municipality) Indicator 1.3 Number of members of Local Action Group trained in LEAP planning and implementation Baseline: 0 Target: 150 (5 per municipality) Indicator 1.4 Number of LEAPs developed Baseline: 30 Target: 60 Indicator 1.5 Number of participants actively participated in LEAPs development process Baseline: 0 Target: 300 (30 per municipality) | 1.1 Effective local level participatory environmental planning mechanisms strengthened. | UNDP | UNDP / UNV | 1.1.1 Design, testing and choosing of context specific, poverty focused participatory planning method; Publishing the guidelines on participatory and inclusive planning method; Training needs assessment of local planning coordinators; Training of local planning coordinators; Establishing network of local development coordinators. | 388,322 | 133,960 | 121,224 | 643,507 |
|  | 1.2 Cross-cutting environmental governance methodology integrated into local participatory planning processes. | UNEP | UNEP | 1.2.1 Assessment of local environmental needs using participatory planning approaches. | 152,629 | 66,579 | 57,089 | 276,298 |
|  |  |  | UNDP / UNV | 1.2.2 Assessment of local integrated good governance training needs; Training of civil servants responsible for municipal budget formulation on integrated participatory planning; Exchange of experts, civil servants and leaders of NGO groups through mentor program. | 86,632 | 67,645 | 55,128 | 209,406 |
|  |  |  | FAO | 1.2.3 Data collection and input on land use planning to local integrated development processes. | 46,579 | - | - | 46,579 |
|  | 1.3 Strengthened capacity of 30 municipalities for environmental programming and planning. | UNDP | UNEP | 1.3.1 Develop selection criteria for environmental, social and poverty-reduction cost-benefit analysis; Publishing best case studies. | 61,535 | - | - | 61,535 |
|  |  |  | UNV | 1.3.2 Analysis of best practices on integrated assessment and planning; Training needs assessment of 30 municipalities; Training for 30 municipalities on environmental planning, climate change adaptation, waste management, biodiversity protection, and renewable energy; Study trip to neighboring countries to collect knowledge on environmental management on local level (Hungary, Slovenia, Estonia). | 49,376 | 102,866 | - | 152,243 |
|  | 1.4 Thirty (30) Local Environmental Action Plans defined and agreed by municipal stakeholders. | UNDP | UNDP / UNV | 1.4.1 Development of LEAPs as part of local integrated planning process; Training of media representatives on local and environmental development issues – establishing the network of journalists; Bankable Project preparation and management training for local stakeholders. | 48,696 | 69,497 | 54,867 | 173,061 |
| JP Outcome 2. Enhanced management of environmental resources and delivery of environmental services |
| Output 2. Secured understanding of the necessity of sustainable management of natural resources within local communities and improved link between local and state/entity level policies Indicator 2.1 Number of grants distributed for LEAP’s priority project implementation Baseline: 0 Target: 30 Indicator 2.2 Percentage of grant matching funds provided by municipalities/other donors Baseline: N/A Target: 50% Indicator 2.3 Number of projects implemented Baseline: 0 Target: 30 Indicator 2.4 Number of developed and implemented preventive poverty risk actions Baseline: 0 Target: 30 locations Indicator 2.5: Number of innovation grants provided and projects implemented; Baseline: 0 Target: 10 | 2.1 Improved management of environmental resources in 30 municipalities. | UNDP | UNDP / UNV | 2.1.1 Implement key enhancements in the management of natural resources using multi-agency best-practice approaches; Working with competent authorities for creation of long term natural resources management plans as part of local integrated development plans. | 27,017 | 56,819 | 3,606 | 87,443 |
|  |  |  | FAO | 2.1.2 Assisting canton/entity authorities to update the databases of natural resources; Making databases of natural resources available for experts and public at municipal and canton level for integrated planning and appropriate implementation. | 24,420 | 95,836 | 64,411 | 184,669 |
|  |  |  | UNEP | 2.1.3 Promoting sustainable use of natural resources. | - | - | 17,336 | 17,336 |
|  | 2.2 Priority actions identified in LEAPs addressed in 30 municipalities. | UNDP | UNDP | 2.2.1 Establish national funding mechanism for co-financing of LEAP priority projects and deliver thirty (30) grants ranging from $ 30,000-70,000 for the project implementation support; Setting the criteria for selection of the projects in participatory manner- discussing and agreeing these with stakeholders; M&E/ supervision of projects supported by FME fund; Publishing the best case studies after the implementation of priority actions. | - | 1,136,073 | 18,636 | 1,154,710 |
|  | 2.3 Improved environmental, energy, water and sanitation services in 30 municipalities for the poor. | UNDP | UNDP / UNV / UNESCO | 2.3.1 Build capacity for implementing poverty focused actions for biodiversity protection, clean energy, water supply and sanitation proposals; Poverty mapping at local level in order to identify vulnerable communities and factors of vulnerability; Exchange of experiences of experts, heads of units, NGOs private sector via mentor programs; Organizing pilot recycling stations and promoting recycling via public campaigns, information and demonstration days, mobile recycling demonstration utilities; Public campaign on eco-labels, domestic (organic food), European (eco-flower),international (FSC); Organizing training on biodiversity protection, renewable energy, water supply, water supply and sanitation, waste management and recycling. | 51,934 | 51,934 | 158,383 | 262,253 |
| JP Outcome 3. Increased national environmental awareness and action, localizing and achieving MDGs |
| Output 3. Strengthened capacity of state to manage local socio-economic development and engage key national partners - capacity of government in designing and implementing public investment budget strengthened Indicator 3.1: Use of Operational Environmental Information System; Baseline: Rudimentary and disconnected data Target: Environmental Information system is fully functional, continuously updated and actively used – 50 visits per day Indicator 3.2: DNA established and number of CDM projects; Baseline: Number DNA, number CDM projects Target: DNA fully functional, 10 CDM projects in operation Indicator 3.3: State of the Environment Report; Baseline: 0 (No comprehensive state-level SoE) Target: 1 | 3.1 Documentation of the legal and institutional background for environmental governance at entity and state level. | UNEP | UNEP | 3.1.1 Conduct desk review of existing legal-institutional framework, produce "road map" recommendations for MoFTER's position and advocacy activities; Organize high-level validation workshop and advocacy campaign. | 52,644 | 25,928 | 21,639 | 100,212 |
|  | 3.2 Reliable environmental indicators (linked with poverty reduction) to inform entity and state policy development. | UNEP | UNEP / FAO | 3.2.1 Review existing NEAP indicators and produce new comprehensive framework; Produce comprehensive new indicator framework including data sources. | 45,570 | 35,149 | - | 80,720 |
|  | 3.3 Increased public access to environmental information. | UNEP | UNEP | 3.3.1 Identify gaps (particular emphasis on environment-poverty linkages); Link, modify and update existing environmental databases/information sources in accordance with indicator framework; Conduct gap analysis for comprehensive environmental information system; Organizing stakeholder workshop on content and priorities for pilot State of the Environment Report; Select drafting team and advisory committee for SoE; Draft State of the Environment Report; Launch and disseminate report; Develop rights-based guidelines for improved access to environmental information; Advocacy campaign on information access. | 37,744 | 103,141 | 102,463 | 243,349 |
|  | 3.4 Expanded access to environmental finance. | UNDP | UNDP | 3.4.1 Establish national funding mechanism for innovative projects linking environment and poverty; Establish governance structure and selection criteria for seed/innovation grants; Award grants (10) grants in average value of $ 90,000 for project implementation support and monitor/evaluate implementation. Develop implementation strategy for Kyoto Protocol; Analyze and identify options for the CDM institutional and legal framework; Assist in the establishment of the Designated National Authority (DNA); Conduct training workshop on CDM programme/project cycle; | 54,962 | 524,785 | 522,946 | 1,102,695 |
|  | 3.5 Greater implementation of environmental governance actions demonstrating innovation, poverty reduction and social inclusion approaches and addressing the achievement of MDG 6, 7 and 8 through improved service delivery. | UNEP | UNEP | 3.5.1 Develop capacity needs assessment for MoFTER, the Inter-entity Environmental Committee and entity environmental Ministries; Develop capacity building strategy for MoFTER on priority areas such as environmental monitoring and reporting, MEA obligations, mainstreaming, etc.; Conduct regional exposure visits/study tours for MoFTER and members of the Inter-Entity Environment Committee. | 10,819 | 30,349 | 30,349 | 71,518 |
|  | 3.6 Lessons and best practices from effective delivery documented and used to inform policy development. | UNEP | UNEP | 3.6.1 Establish project website; Develop electronic network linking municipalities and national authorities; Forming the database and network of national and international experts, who are able to answer to all requests from local stakeholders on priority issues; Produce lessons learned notes capturing experiences and challenges from innovation projects; Develop sectoral guidelines for the delivery of environmental services. | 58,100 | 41,098 | 35,550 | 134,749 |
| Joint Programme | Management (UNDP) | 118,290 | 108,017 | 107,732 | 334,040 |
|  | Monitoring and Evaluation (UN RC BIH) | 42,494 | 41,210 | 79,826 | 163,531 |
| TOTAL | 1,357,774 | 2,690,895 | 1,451,192 | 5,499,863 |

# 5.  Management and Coordination Arrangements

The overall ownership and responsibility for this programme rests with the Government of Bosnia and Herzegovina. Oversight and strategic guidance will be provided through the National Steering Committee (NSC) of the MDG-F UN Joint Programme, consisting of non-implementing parties (representative of the Government of BiH, Government of Spain, and the UN RC). Operational coordination will be through the Programme Management Committee (PMC), chaired by the UN RC, with representatives of Participating UN Agencies, Government counterparts and other invitees (Programme Manager, experts, key stakeholders, National Authorities, Donors). The PMC will ensure that other donors and key stakeholders (particularly the World Bank, EC and Sida) are closely involved with the Programme and have opportunities to coordinate and harmonise approaches with Government and other Programmes. The PMC will be directly responsible for making all major management decisions for the programme, and will be consulted when the Programme Manager requires guidance. This would include approval of the programme and any ongoing approval for programme revisions. It will also review on a semi-annual basis the programme’s progress (for additional detail refers to the monitoring and evaluation section). The delivery of programme activities to achieve results rests with UN Agencies and implementation partners.

The roles and responsibilities for the implementation of the programme will be in line with the UN Joint Programming methodology and it’s pass-through modality, which is based on principals of complementarity, coherence, comparative advantages of every participant, and clearly prescribed minimum requirements for ensuring proper accountability for programmed activities and use of resources.

Considering the limited capacities to ensure delivery of the programmed activities in the quality and quantity needed to achieve this programme’s goals and objectives, this programme will be implemented under direct management of the UN Agencies (modality earlier referred to as Direct Execution/implementation-DEX). This is an approach which UNDP BiH has been applying and has fine-tuned during the last couple of years in a number of projects and programmes implemented in several thematic areas. At the core of this approach is ensuring that delivery is overseen directly by the Agencies, and concerted effort is made to build-in governmental oversight and local management input. The use of this modality is motivated by its high potential for maximum cost-effectiveness alongside flexible capacity development of local institutions.

The overall coordination and management structure is outlined in the organizational chart below.

Figure 1: Coordination and Management Structure

This structure ensures the active and substantive involvement of the Ministry of Foreign Trade and Economic Relations (MOFTER) through the PMC. This is critical as MOFTER is the body with the overall coordination mandate in the environment sector at the State level. The relevant Entity level ministries (the  Ministry of Environment and Tourism of the Federation of BiH, and the Ministry of Urban Planning, Construction and Ecology of the Republika Srpska), will both participate in the PMC, as well as in many specific implementation mechanisms for individual programme activities. The purpose is to enable building of sustainable national capacity through learning by doing, via direct and substantive involvement of the Government and specialized NGOs in implementation of this project.

Any modifications to the activities set out in the Joint Programme Document, including as to their nature, content, sequencing or the duration thereof shall be subject to mutual agreement in writing between the relevant Participating UN Organization and the NSC.

The National Programme Manager (NPM) will be engaged to manage the programme on a day-to-day basis and will ensure the best possible coordination of the activities of the different Agencies. His/her primary responsibility will be to ensure that the programme delivers results that contribute to achievement of the project objectives. The programme support function, built in the programme management unit, will provide administrative and operational support to management and the programme team. This function will also act as a repository for lessons learned and a central source of specialist expertise. As the functions of the NPM will include demanding and crucial day-to-day obligations, such as human resource, administrative and financial management, coordination, reporting and many others, the NPM needs to be supported by a Chief Technical Advisor (CTA). The CTA will be an experienced international environmental expert, who will support the NPM with substantive expert advice related to specific technical aspects of activities. The CTA is there to ensure that the strategic orientation, key strategic and operational decisions and all activities are implemented to the highest technical standards and with the best impact on achievement of the programme goals.

As described earlier, this programme will be implemented in accordance with the UN Joint Programming methodology, which is used when two or more UN Agencies develop a joint programme and intend to deliver a set of activities defined by a common work plan and related budget. In case of this joint programme, the Donor (MDG-F) and the participating UN organizations have agreed to channel the funds through one participating UN organization and to apply the “pass-through modality” of fund management. This management option, and the standardised instruments it uses, has been approved by all ExCom agencies. Their use in operationalizing joint programmes without alterations does not require any further approvals from headquarters.

It has been agreed that each participating UN organization will take appropriate measures to publicize the joint programme and to give due credit to the other participating UN organizations. Information given to the press, to the beneficiaries of the joint programme, all related publicity material, official notices, reports and publications, shall acknowledge the role of the host government, the donors, the participating UN organizations, the Administrative Agent and any other relevant parties. In particular, the Administrative Agent will include and ensure due recognition of the role of each participating UN organization and national partner in all external communications relating to the joint programme.

# 6.  Fund Management Arrangements

UNDP will act as the Administrative Agent (AA), in charge of channeling the programme resources. UNDP has by far the strongest both programmatic and operational support capacities in country of the UN agencies, with: i) Country presence; ii) Financial and administrative capacity to interface between donor(s) and participating UN organizations and iii) Thematic, functional and geographical area of expertise in the area covered by the programme.

In accordance with the pass-through modality, the programmatic and financial accountability rests with the participating organizations and their (sub-) national partners, who will be managing their respective components of the Joint Programme. UNDP, as AA, will be responsible, among other duties, to:

- negotiate and sign a Letter of Agreement with the donor(s) in respect of the joint programme, based on agreement of the joint programme coordination mechanism identified at country level

- sign a Memorandum of Understanding with the participating UN organization. Each UN organization participating in the joint programme will programme and manage activities and funds in line with its established regulations and rules.

In terms of budget preparation, each UN organization will prepare a separate budget, consistent with its procedures, and covering the mutually agreed parts of the programme that it will be managing. Budget formats should to the extent possible be harmonized. The AA will prepare a consolidated budget for approval by the joint programme coordination mechanism.

On behalf of the Participating UN Organizations, the Administrative Agent shall:

- Receive contributions from donors that wish to provide financial support to the Joint Programme through the Administrative Agent;

- Administer such funds received, in accordance with this Memorandum of Understanding including the provisions relating to winding up the Joint Programme Account and related matters;

- Subject to availability of funds, disburse such funds to each of the Participating UN Organizations in accordance with instructions from the Joint Programme Steering Committee, taking into account the budget set out in the Joint Programme Document, a copy of which is attached hereto as, as amended in writing from time to time by the Joint Programme Steering Committee;

- Compile financial reports produced by each of the Participating UN Organizations into a consolidated report, and distribute such financial reports together with consolidated programme reports produced by the Participating UN Organizations, as further described in the Joint Programme Document, to each donor that has contributed to the Joint Programme Account and to the Joint Programme Steering Committee;

- Provide final reporting, including notification that the Joint Programme has been operationally completed;

- Perform such other activities as the Participating UN Organizations and the Administrative Agent may agree on additionally.

The AA will establish a Joint Programme Account administered in accordance with the regulations, rules, directives and procedures applicable to it, including those relating to interest.  It shall be subject exclusively to the internal and external auditing procedures laid down in the financial regulations, rules, directives and procedures applicable to the AA.

In accordance with the UN Joint Programming rules applicable to the pass-through modality, the AA shall be entitled to allocate one percent (1%) of the amount contributed by donor(s), for its costs of performing the AA’s functions.  At the same time, each UN organization participating in the joint programme will recover indirect costs in accordance with its financial regulations and rules and as documented in the Memorandum of Understanding signed with the AA. The rate of recovery has been agreed to be equal for all the UN organizations participating in the joint programme in amount of 7%.

Each of the participating UN organizations will prepare reports in accordance with its financial regulations and rules and operational policy guidance. Reports will be shared with the Joint Programme coordination mechanism in accordance with the relevant MoU. To the extent possible, reporting formats should be harmonized. The AA shall prepare consolidated narrative progress and financial reports consisting of the reports submitted by each participating UN organization, and shall provide those consolidated reports to each donor that has contributed to the joint programme account, in accordance with the timetable established in the Letter of Agreement.

# 7.  Feasibility, risk management and sustainability of results

Feasibility

Feasibility for this programme has been assessed through an integrated process of expert consultation (see Figure 1) coupled with developing a baseline of capacity development assets and needs and determining if and how these can be addressed. This process has ensured that the programme is both needs-based and effectively coordinated with wider development activities in the environmental sector from the Government of Spain, World Bank, European Union, Sida, and the Government of the Netherlands, which represent the main donors in this sector. We have obtained and acted on advice of programme managers and technical experts from these donors, and incorporated them into programme design.

The feasibility of the project is ensured via cost-effective implementation of activities using the best available skills, knowledge and experiences of national and local experts and service providers, supported by appropriate TA from UN agency staff, operating to build local capacities and capabilities. The Joint Programming integrates centralized and bottom-up processes, and is designed on the specific strengths and experiences of the participating UN agencies.

Risks and Risk Management

Three key areas of risk have been identified and managed in the design of this Programme:

Lack of ongoing, long term political and government support for the programme implementation. At both state and entity level, Government commitments for this programme have already been confirmed, including possibilities to cost share the programme. Highly participatory process of project identification, concept note development and implementation strategy, together with ongoing consultations on  ownership of programme development and implementation with key government stakeholders have already taken place and will continue throughout the proposal development and programme implementation.

BiH Constitutional reform that can transfer more responsibilities from entity to state level. At this time this risk does not pose a large threat to the programme implementation as the programme is designed to deliver at municipal level, as well as to build state level capacities. Through this approach the programme largely mitigates the risk of shifting power between the state and Entities, as environmental responsibilities and mandates at municipal level are expected to remain the same. Increased responsibilities at the state level will, in terms of this project, increase absorption capacities and, therefore, enable more efficient delivery of results.

Inadequate programme implementation. The strategy to overcome this risk includes careful selection of project team members and the appropriate M&E framework to be put in place. A long term, complex programme, such as the one proposed, will need an efficient and committed management. The experts that will work on the implementation must have a good understanding of the environment sector in BiH. Furthermore, the programme design will aim to minimize risks through careful apportionment of activities between UN agencies and national partners.

Specific risks for Joint Programme implementation, and mitigation measures, are given in Table 2. The main specific risks are inadequate communication and cooperation between local, canton, Entities and state; weak capacity at local and national level;  inadequate capacity and skills for planning and implementing environmental management at the local level and entity/state levels; weak local level environmental planning mechanisms; lack of data for climate change and environmental monitoring; and ineffective  environmental resource management. There is a distinct lack of understanding about environmental service provision and the valuing of environmental services; poor delivery of environmental services; and low levels of awareness regarding environmental management, CDM/JI and climate change.

Table 2. Risk assessment

| Risk | Probability | Impact | Risk owner | Mitigation |
| --- | --- | --- | --- | --- |
| Lack of support for further empowering MOFTER | High | Low | MoFTER | Work at developing linkages and capacities for environmental governance at multiple levels |
| Problems of UN agencies integrating working practices and administrative systems | Low | Medium | Un Agencies (UNDP as managing agent) | Pass-through management approach. Effective joint programming approach and real engagement of each agency during design phase |
| Resistance at entity level on state level policy and institutional development | Medium | Low | MoFTER | European accession process has positive influence to cooperation between Entities and state via harmonization of legislation: environmental innovation fund incentive for cooperation |
| LEAPs written and actioned, but implementation limited | Medium | High | Municipalities | LEAPs combined with rights-based and participatory planning processes integrated with municipal budget cycles, and supported through implementation fund |
| Inadequate Capacity and skills for planning and implementing environmental management, at the local level | Low | High | Municipalities | Tailored capacity building addressing specific local needs, needs are effectively assessed with strong feedback inclusion from participants |
| Inadequate Capacity and skills for planning and implementing environmental management, at the state level | Medium | Medium | MoFTER | Capacity building on environmental planning and management |
| Lack of data for climate change and environmental monitoring and inadequate cooperation between institutions working on environmental monitoring | Low | Medium | Environmental Monitoring Institutions UN agencies (UNEP) | Assess the gaps in data for climate change and environmental monitoring; find additional information sources; encourage diverse environmental monitoring institutions to cooperate and exchange information via including them to drafting Committee of SoE Report |
| Ineffective environmental resource management and poor delivery of environmental services | Medium | Medium | Municipalities | Strengthen the capacities of local authorities on effective environmental resource management via integrated planning and additional fund-raising skills for implementation of action plans, which increases the efficiency environmental resource management and delivery of environmental services |
| Low levels of awareness regarding environmental management, CDM/JI and climate change | High | Low | MoFTER, entity ministries, private sector | Implement media campaign on climate change in mainstream media in order to get decision makers, opinion leaders and political scene aware of climate change and its adoption measures. Keep the highlights of the implementation of projects granted from Innovation Fund and LEAP Implementation Fund at local level visible in mainstream media |

Sustainability of Results

If BiH is to continue improvements in environmental management and service delivery, action will be required both outside this programme and after it has finished. Sustainability of results will be ensured by establishing a regulatory framework and financial mechanism for environmental planning and implementation, and building capacity. The Government has indicted it will cost share these activities by at least 25%. At a local level, interventions will be combined with the UNDP municipal governance programme, which will assist in institutionalizing the LEAP process and ensuring budget allocations together with the entity ministries. The environmental innovation fund will be established to provide long-term support to environmental management, with the potential for this being a key mechanism for the World Bank to provide soft loans at a municipal and cantonal level.

A central tenet of the approach, and key to sustainability, is to utilise, lever and further build national capacity. Within the field of environmental management the overall level of national capacity is not high, with notable exceptions (particularly REC), which will be utilised to their full. The multi-agency approach allows the Programme to pull in staff with high levels of regional experience and cutting edge sectoral knowledge from FAO, UNEP and UNESCO. These staff will work with local counterparts from Government and the CSO/NGO community to ensure their skills are transferred effectively. Sustainability in knowledge transfer from international experts to national experts and institutions will be ensured through a mentoring and coaching approach. In case of repeating joint programme implementation activities (such as needs assessment, training delivery, capacity building, and human resource development) a ‘coach team’ of international and national experts will be formed. The main technical responsibility will lie with international experts at the early stages of the programme, shared at the middle stages, and with national expert at the final stages of the project, with international experts only backstopping the implementation.

# 8.  Accountability, Monitoring, Evaluation and Reporting

Although the project will follow the standard UNDP procedures for reporting, monitoring and evaluation, for which implementation agencies will be responsible on a day-to-day basis, the office of the Resident Coordinator will have also have an important monitoring and evaluation role, This additional oversight role of the Resident Coordinator office, will ensure the overall compliance with this Programme Document and Annual Work Plans. The monitoring, evaluation and reporting will include following up on management actions, keeping track of progress benchmarks, visiting project sites to contact beneficiaries and contractors, interpreting progress and technical reports, and processing budget revisions.

Monitoring: assesses the performance and progress of the project, at this level focusing on outputs. Based on the Annual Work Plan and Budget of each output, UNDP, jointly with UNEP and FAO, will monitor the project's progress. The annual review of a joint programme will be implemented collectively by national partners and participating UN organizations. Annual review results will be in a single report, thus reducing transaction costs. A common format for reporting based on results-based annual programme level reporting will be used as far as possible.

Media monitoring will be undertaken for media related activities. Mission reports, project publications and the JP website will be effective tools for sharing information. Indicators measuring both qualitative and quantitative processes, outputs, and outcomes have been included in the Programme Monitoring Framework (Table 3).

Reporting: Each project component will develop monthly work plans and progress reports. These will form the basis for the programme officer's Quarterly Report. An Annual Project Report by the Project Management to the UNDP CO will provide critical information and lessons learnt regarding the effectiveness of the implementation strategy and the delivery of outputs. This will include both technical and financial review and will provide the opportunity to review progress, achievements as well as challenges which will feed into the detailed work plan of the next year. Key results and findings will be shared with the members of the JP Steering Committee, donors and interested institutions to ensure transparency and to seek feedback.

Validation: Monthly field visits of the programme officer and consultations with the Project Management Team will verify whether the reported progress is accurate or not. In a participatory way, with the management team, the Resident Coordinator office and the National Steering Committee, implementation will be discussed and lessons learned incorporated in future activities.

| Table 3: Programme Monitoring Framework (PMF) |
| --- |
| Expected Results (Outcomes & outputs) | Indicators (with baselines & indicative timeframe) | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| 1. Improved local level environmental planning 1.1 Effective local level participatory environmental planning mechanisms strengthened. 1.2 Cross-cutting environmental governance methodology integrated into local participatory planning processes. (UNDP-led multi-agency approach). 1.3 Strengthened capacity of 30 municipalities for environmental programming and planning (UNDP). 1.4 Thirty (30) Local Environmental Action Plans defined and agreed by municipal stakeholders (UNDP). | Indicator 1.1 No. of local coordinators trained in facilitation of local environmental planning and programming process and LEAP formulation Baseline: 0 Target: 30 | Training evaluation and reports | Immediately after each training event participants fill the evaluation sheets Training provider complete training report after training | UNDP | Evaluations sheets are not filled by participants ( the requirement to have evaluation sheets and training report should be part of ToR of training provider |
|  | Indicator 1.2 No. of civil servants trained in environmental planning and programming for including LEAP into budgetary formulation processes Baseline: 0 Target: 90 (3 per municipality) | Training evaluation and reports | Immediately after each training event participants fill the evaluation sheets Training provider complete training report after training | UNDP | Evaluations sheets are not filled by participants ( the requirement to have evaluation sheets and training report should be part of ToR of training provider |
|  | Indicator 1.3 No. of members of Local Action Group trained in LEAP planning and implementation Baseline: 0 Target: 150 (5 per municipality) | Training evaluation and reports | Immediately after each training event participants fill the evaluation sheets Training provider complete training report after training | UNDP | Evaluations sheets are not filled by participants ( the requirement to have evaluation sheets and training report should be part of ToR of training provider |
|  | Indicator 1.4 No. of LEAPs developed Baseline: 30 Target: 60 | Municipal Council decision on LEAP adoption | Local legal acts on Municipal Council decisions, once a year | UNDP | LEAP development process will take longer tima than planned ( to agree the process, steps and deadlines from very beginning of the process |
|  | Indicator 1.5 No. of participants actively participated in LEAPs development process Baseline: 0 Target: 300 (30per municipality) | Number of calls for participation per medium Participant lists of local LEAP development forums | Archive of call for participation, advertisements in newspapers. Participants will register their participation in LEAP forums, after each event immediately | UNDP | Low interest to participate in local environmental planning – to increase the interest via implementing small visible pilot projects |
| 2. Enhanced management of environmental resources and delivery of environmental services 2.1 Improved management of environmental resources in 30 municipalities. 2.2 Priority actions identified in LEAPs addressed in 30 municipalities. 2.3 Improved environmental, energy, water and sanitation services in 40 municipalities for the poor. | Indicator 2.1 No. of grants distributed for LEAP’s priority project implementation Baseline: 0 Target: 30 | MoUs/Contracts with municipalities/ grant-holders signed | From archive of grant decision making Board, once a year | UNDP | Risk not to have MoUs/Contracts is very low, as this is the basis for grant transfer |
|  | Indicator 2.2 % of grant matching funds provided by municipalities/other donors Baseline: N/A Target: 25% | Co-financing agreements signed | From archive of grant decision making Board, once a year | UNDP | Risk not to have co-financing agreements is very low, as this is the basis for grant transfer |
|  | Indicator 2.3 No. of projects implemented Baseline: 0 Target: 30 | Project Monitoring Reports, Annual Review Report | Field visits, twice a year | UNDP | Risk is unprofessionally implemented projects ( to provide project management training to Grant-Holders |
|  | Indicator 2.4 No. of developed and implemented preventive poverty risk systems Baseline: 0 Target: 30 | Project Monitoring Reports, field reports | Field visits, twice a year | UNDP | Risk is that less attention has been paid to poverty prevention ( to include poverty prevention requirements to ToR of service provider |
| 3. Increased national environmental awareness and action, localizing and achieving MDGs 3.1 Documentation of the legal and institutional background for environmental governance at entity and state level. 3.2 Reliable environmental indicators (linked with poverty reduction) to inform entity and state policy development. 3.3 Increased public access to environmental information. 3.4 Expanded access to environmental finance. 3.5 Capacity development for greater implementation of environmental governance actions demonstrating innovation, poverty reduction and social inclusion approaches and addressing the achievement of MDG 6, 7 and 8 through improved service delivery. 3.6 Lessons and best practices from effective delivery documented and used to inform policy development. | Indicator 3.1: Use of Operational Environmental Information System; Baseline: Rudimentary and disconnected data Target: Environmental Operational Environmental Information system is fully functional, continuously updated and actively used – 50 visits per day | Environmental Information System Track Record, which includes user statistics e.g. number of users, size of databases, number of different projects using the database | From website logs on user statistics, once a month | UNEP | Summary of assumptions and risks for each result The risk is that Information system is programmed without keeping user statistics ( to include user statistics component to software development service provider |
|  | Indicator 3.2: DNA established and No. of CDM projects; Baseline: No DNA, no CDM projects Target: DNA fully functional, 10 CDM projects in operation | Project Monitoring Reports, Annual Review Reports | National legal documents once a year, DNA website once a month | UNDP | The risk is in lack of capacities to establish and operate DNA professionally ( adequate training needs assessment and training of responsible authorities |
|  | Indicator 3.3: State of the Environment Report; Baseline: 0 (No comprehensive state-level SoE) Target: 1 | Report | Report | UNEP | No major risks identified |
|  | Indicator 3.4: No. of innovation grants provided and projects implemented; Baseline: 0 Target: 10 | Project Monitoring Reports, Annual Review Reports | National legal documents once a year | UNDP | Risk is unprofessionally prepared project proposals and inadequate criteria for project selection ( providing training on project proposal and working out criteria of project selection in open participatory and transparent manner in close cooperation with key-stakeholders via consensus building process |

9. Ex Ante Assessment of Cross-cutting Issues

In the development of this programme full attention has been paid to considering and building on the findings and recommendations of the prior assessments and analyses of the environment sector in BiH, conducted by relevant partner organizations, such as the EC’s “Functional Review of the Environmental Sector in Bosnia and Herzegovina”, the World Bank supported “National Environment Action Plan”, the “Environmental Performance Review” report by UNECE and UNDP’s “Environmental Policy in South-Eastern Europe”.

The key cross-cutting issue that has been identified and clearly highlighted by most of the assessments and analyses thus far is the issue of weak capacity for effective environmental management at all levels, making capacity building the central element for the designed programme. The programme will address this problem with specific activities aimed at capacity building at both the local and national levels.

Since the signature of the EU Treaty in Maastricht, in 1992, which clearly integrates the concept of sustainable development, the EU Environmental Strategy (see in particular the Sixth Environment Action Programme of the European Community) is oriented towards the achievement of such a goal by assuring in particular:

- a better integration of environmental concerns in policies and territorial development (principle of integration);

- a more effective participation of all socio-economic actors involved in the planning and implementation of such development (principle of subsidiary)

While neglected in the past, land use planning and management decisions (having a clear influence on the environment) are directly effected today by such an orientation. The European Spatial Development Perspective (ESDP), adopted in 1999, is intended to ensure a more balanced and sustainable development of the European territory, in accordance with the basic objectives of Community policy. It is considered as an essential instrument which can help improve the coordination of Community policies as well as better direct and/or limit their territorial impact (spatial effects). In this context, the importance of national and local efforts directed to the implementation of sustainable territorial development is increasingly recognized, and the wise use of proper methodological and conceptual frameworks to foster integrated planning procedures warmly encouraged (see in particular the CEMAT). To this end, huge experimental efforts in a network of ‘pilot areas’ to test innovative territorial development approaches are still urgently needed.

Such a need is particularly urgent in Central and South-Eastern European countries, where the tendency of focusing on the quantitative aspects used to be a typical environmental protection policies approach in most of the centralised economies (today in a EU approximation process at various stages); a need to reverse this trend tends to emerge from the most recent analyses, demanding a deep revision of the main governmental policy documents and a reorganisation of the legal and institutional frameworks. In such a context, the speed and the intensity of local territorial dynamics call for the identification and implementation of appropriate mechanisms of trans-scale governance, so that the network of local actors able to foster local sustainable development initiatives could be better inter-related with the national and the international levels. Again, local planning and management processes are expected to play an essential role in this view.

The European Spatial Development Scheme (ESDC) clearly refers to the principle of Environmental Integration, assuming environment as a transversal criteria for the elaboration and implementation of corresponding plans at the various subordinated levels. Efforts undertaken at the local level in that very direction have therefore to be encouraged, for the conduction of which reference methods and techniques (such as Strategic Environmental Impact Assessment) are still to be defined.

In particular, a more rational use of natural and cultural resources (including biodiversity and traditional landscapes) is encouraged within the ESDC. Such a goal is to be achieved through the extension of the European network of Protected Areas and Ecological Corridors, and by o assuring that cultural and natural heritages are taken into consideration as fundamental assets in local territorial development planning and management processes.

In the frame of its environmental programmes (the Man and the Biosphere – MAB Programme in particular) in the SEE Region, UNESCO ,through its Regional Bureau for Science and Culture in Europe (UNESCO-BRESCE) established in Venice, has undertaken a programme of activities aiming at the promotion of the safeguarding of cultural and natural heritage in South Eastern Europe and in the Mediterranean region, as part of a larger environmental integration effort which transversally involves all the key development activities and well reflect the multi-faceted mandate of the Organization.

At the local level, the process of national capacity building will be linked and integrated with the process of local environmental action planning. It is important to highlight that the environmental planning process will not be a stand alone exercise, but rather it will be integrated with other local level planning process, reflecting in this EU's more advanced orientations towards Environmental Integration into sectoral policies and spatial planning at all levels as a major tool for achieving sustainable development in the Region. It will adopt the best practices and approaches of other participatory and human rights based methodologies for local level planning, such us REC/EC LEAP development methodology, UNDP’s Rights-based Municipal Assessment and Planning (RMAP) project, and the future Integrated Local Development Planning Programme. In this way full integration of human rights-based approaches will be assured, and ensuring that other cross-cutting issues (gender and participation of vulnerable groups) are addressed through the planning process. It will also take advantage of experience gained in networks addressing similar questions such as the Man and the Biosphere (MAB) European network of Biosphere Reserves supported by UNESCO.

At the national level a set of specific capacity building activities will be undertaken, which will start with a focused review of the existing legal and institutional framework and national level capacity needs assessment, serving as the basis for the development of a capacity building strategy for the state level Ministry in charge of Environment (MOFTER), the entity level Ministries of Environment and the Inter-Entity Coordination Committee for Environment. The development of national capacities in priority areas, such as environmental monitoring and reporting, MEA obligations, transparent and effective planning and prioritization and similar, will significantly enhance the mainstreaming of environmental issues into all sector policies and other aspects of life in BiH.

# 10.  Legal Context or Basis of Relationship

The United Nations Development Assistance Framework in BiH  (UNDAF) for the period 2005-2008, signed  by the Government of Bosnia and Herzegovina and the UN Country Team in BiH in June 2005, represents the basis for the activities of all the UN development agencies in BiH and. This Joint Programme will contribute significantly to achievement of the UNDFAF Outcome 1: “Strengthened accountability and responsiveness of government to pro-active citizens”.

As far as individual agencies are concerned, in general all of their individual cooperation and/or assistance agreements that they have with the Government of Bosnia and Herzegovina and which are the legal basis for their relationships between the Government will apply for each of the UN Organizations participating in this Joint Programme. Each agency’s activities under this Joint Programme will be governed by the respective applicable basic and other agreements of the agency.

Specifically, all of the activities of UNDP in Bosnia and Herzegovina are legally grounded in the Standard Basic Assistance Agreement (SBAA) between the Government of Bosnia and Herzegovina and UNDP, signed on 7th December 1995 and the current Country Programme Action Plan (CPAP) for period 2005-2009, as agreed and signed by the Government and UNDP on 3rd June 2005.  Specifically, the outputs of this Joint Programme will contribute significantly to achievement of the CPAP Outcome 4.2. “Strengthened national capacity in sustainable environmental management”.

UNEP as a United Nations organization will participate in the implementation of the MDG-F project with the agreement of the Government of Bosnia and Herzegovina through activities within is core mandate. The mandate and objectives of UNEP are set out in General Assembly resolution 2997 (XXVII) of 15th December 1972 and subsequent amendments adopted by the United Nations Conference on Environment and Development (Report A/CONF.151/26/Rev.1 (Vol. I), para. 38.22), as well as in the Nairobi Declaration on the Role and Mandate of the United Nations Environment Programme adopted at the nineteenth session of the UNEP Governing Council. The legislative sources and relevant Governing Council declarations and decisions mandate UNEP to act as the authority for environmental issues at the global and regional levels for the United Nations system. To that end, UNEP is mandated to catalyze and coordinate the development of environmental policy consensus by keeping the global environmental situation under review and bringing emerging environmental issues to the attention of the international community and Governments for action.  UNEP’s  mandate encompasses: i) assessing global, regional and national environmental conditions and trends, ii) Developing international and national environmental instruments, iii) Strengthening institutions for the wise management of the environment, iv) Facilitating the transfer of knowledge and technology for sustainable development, and v) Encouraging new partnerships and mind-sets within civil society and the private sector.

The work of FAO and its relation with its members is governed by the “Basic Text” (including the FAO Constitution and rules and regulations for its functioning), undersigned by all member nations. The ongoing programme of work is discussed and decided by the Governing Bodies, i.e. different Committees, the FAO Council and the FAO Conference, which meets every two years to decide on the next biennium’s Programme of Work and Budget. FAO’s technical assistance is provided to all the member nations on request of the Governments through Regular Programme funds and Extra-Budgetary funds.

As an inter-governmental Organization, FAO is present in all member nations of Europe (http://www.fao.org/world/regional/REU/about/about_members_en.html). Even though there is not an official Representation of FAO in BiH, its presence is assured by Project Offices.

Among the general documents related to statute, the function and mandate of UNESCO and its relations to the Member States, the cooperation of UNESCO with Bosnia and Herzegovina is established on the basis of following two documents:

The agreement between Bosnia and Herzegovina and UNESCO, dated 30 August 1995 related to the UNESCO’s assistance to Bosnia and Herzegovina and the Memorandum of Cooperation between UNESCO and Bosnia and Herzegovina in UNESCO’s filed and competences signed on 13 December 1995. Accordingly UNESCO, from its Regular Programme sources as well from Extra-Budgetary sources, provides a constant assistance to Bosnia and Herzegovina in all fields of its competences.

UNV is a UNDP administered programme and is such governed by all legally binding agreements entered into effect by UNDP and the government of Bosnia and Herzegovina on its behalf.

# Annex A:  Annual Work Plan 2007, 2008 & 2009

Note 1: 	Although MoUs between UNDP and Municipalities are not yet endorsed, both the 'Implementation Support Fund (2.2.1)' and the 'Innovation fund (3.4.1)' will be co-financed between 30 to 50%.

Note 2: 	The World Bank has shown interest to finance municipal level public budgeting and has expressed interest to combine activities with this programme as parallel funding.

Note 1: 	Although MoUs between UNDP and Municipalities are not yet endorsed, both the 'Implementation Support Fund (2.2.1)' and the 'Innovation fund (3.4.1)' will be co-financed between 30 to 50%.

Note 2: 	The World Bank has shown interest to finance municipal level public budgeting and has expressed interest to combine activities with this programme as parallel funding.

Note 1: 	Although MoUs between UNDP and Municipalities are not yet endorsed, both the 'Implementation Support Fund (2.2.1)' and the 'Innovation fund (3.4.1)' will be co-financed between 30 to 50%.

Note 2: 	The World Bank has shown interest to finance municipal level public budgeting and has expressed interest to combine activities with this programme as parallel funding.

# Annex B: Detailed Budget

# Footnotes

Specifically, addressing indicators 3,23,25,26,27,28,29,30,31,34,35,41

Central bank of BiH 2006 Annual Report, p.12

Environmental performance reviews: Bosnia and Herzegovina In: Environmental Performance Reviews Series (ECE), no. 20 / ECE, Geneva (Switzerland); EC Functional Review of the Environmental Sector in Bosnia and Herzegovina Final Report, April, 2005;

The 3rd Draft of the State Law on Environment is currently under review: there has been no state level environmental law enacted for the last 5 years.

See EC Functional Review Box 5a for an overview of the policy gaps

REC publication “The Way towards Sustainable Development of Local Communities” prepared by Andrea Bevanda-Hrvo, Mustafa Šuvalija, REC for Bosnia and Herzegovina, 2006.

The Results Framework maps activities with MDG indicators. Specific data for each indicator can be found at http://mdgs.un.org/unsd/mdg/data

UNDP, 2006, Donor Mapping Report, Donor Coordination Forum of Bosnia and Herzegovina

Commission Staff Working Document, Bosnia and Herzegovina 2006 Progress Report

COM (2006) 649

The entire body of European laws is known as the acquis communautaire. This includes all the treaties, regulations and directives passed by the European institutions as well as judgments laid down by the Court of Justice. The term is most often used in connection with preparations by pre-accession and candidate countries to join the union.

Directorate for European Integration, 2006, EU integration strategy of Bosnia and Herzegovina, Bosnia and Herzegovina council of ministers.

Instrument for Pre-accession Assistance (IPA) Bosnia and Herzegovina Multi-Annual Indicative Planning Document 2007 – 2009

During Programme design the EC stated that the MDG-F Mainstreaming Environmental Governance programme would be key in early developments of strengthening environmental institutions, and would provide important developments to be built on during the pre-accession process.

The main guidance document specific to the environmental sector is the National Environmental Action Plan BiH, March 2003, and the outcomes of the joint programme have been mapped against the main action points.

Examples include the EU-funded Local Action Groups (LAGs), UNDP RMAP’s rights based local development strategies, the World Bank sponsored community development plans, etc.

Chiefly: failure  of fulfilling reporting obligations; the omission of designation of a national focal point; and the non-execution of monitoring duties

# Text boxes

REVISED STANDARD JOINT PROGRAMME DOCUMENT

Sources of funded budget:  (MDG-F)

- UNDP/UNV		USD 4,119,362

- UNEP			USD 905,000

- FAO			USD 311,917

- RCO			USD 163,532

PROGRAMME MANAGEMENT UNIT

PROGRAMME MANAGEMENT COMMITTEE

Representatives of: UN RC, Participating UN Agencies, Government counterparts and other  invitees     ( Programme Manager, experts, key stakeholders, National Authorities, Donors)

National Programme Manager

Chief

Technical

Advisor

UN Resident Coordinator

Office direct oversight

Operations Associate

Finance &

Admin

Assistant

Driver/

Interpreter

International

UN

Volunteer

OPERATIONAL

SUPPORT UNIT

National

UN

Volunteer

3-5 Municipal

Environment

Coordinators

Municipal

Level

Activities

.…

….

UNEP

Staff and

Consultants

UNEP

Specific

Activities

National

UN

Volunteer

3-5 Municipal

Environment

Coordinators

Municipal

Level

Activities

National

UN

Volunteer

3-5 Municipal

Environment

Coordinators

Municipal

Level

Activities

FAO

Staff and

Consultants

FAO

Specific

Activities

UNESCO

Staff and

Consultants

UNESCO

Specific

Activities

TA

Coordination

NATIONAL STEERING COMMITTEE

of the MDG-F UN Joint Programme

Representatives of: Government of BiH, Government of Spain, UN RC.

Total estimated budget*:

Out of which:

1. Funded budget:	USD 5,499,863

2. Unfunded budget:

* Total estimated budget includes both programme costs and indirect support costs

Programme Duration:  3 years,

Anticipated start/end dates: Sept. 2009 – Sept. 2011

Fund Management Option(s): pass-through

Managing or Administrative Agent: UNDP BiH