United Nations Development Programme

Country: Bosnia and Herzegovina

PROJECT DOCUMENT

| Project Title: | Bosnia and Herzegovina’s First Biennial Update Report (FBUR) |
| --- | --- |
| UNDAF Outcome(s): | Outcome 3: By the end of 2014, Government meets requirements of EU accession process and multi-lateral environment agreements (MEA), adopts environment as a crosscutting issue for participatory development planning in all sectors and at all levels, strengthens environmental management to protect natural and cultural resources and mitigate environmental threats. |
| UNDP Strategic Plan Environment and Sustainable Development Primary Outcome: Expanding access to environmental and energy services for the poor |
| Expected CP Outcome(s): Strengthened national capacities to integrate environmental and energy concerns into development plans at all levels and systems for effective implementation of the sectoral priorities |
| Expected CPAP Output (s): State-level Government in coordination with Entity Government is enabled to respond to its international environmental obligations including EU accession obligations |
| Executing Entity/Implementing Partner: RS Ministry of Spatial Planning, Construction and Ecology |  |

Agreed by (Government):

Date/Month/Year

Agreed by (Executing Entity/Implementing Partner):

Date/Month/Year

Agreed by (UNDP):

Date/Month/Year

Table of Contents

Acronyms	4

Situation analysis	5

Strategy	6

Project Results Framework	9

Total budget and workplan	11

Management Arrangements	14

Monitoring Framework and Evaluation	16

Legal Context	19

Appendix A: Summary report of the self-assessment exercise	21

A.1 	Methodological approach	21

A.2 	Findings	21

A.3 	Stakeholder Involvement Matrix	27

Appendix B: Technical components of the project proposal	33

B.1	Description of components and activities	33

B.2	Detailed Workplan	41

Appendix C: Terms of Reference	50

Appendix D: Endorsement letters	53

Acronyms

BD		Brčko District

BiH		Bosnia and Herzegovina

CC		climate change

CoP		Conference of Parties

EBRD		European Bank for Reconstruction and Development

FBiH		Federation of Bosnia and Herzegovina

FBUR		First Biennial Update Report

GEF		Global Environmental Facility

GHG		Greenhouse Gas

HMI		Hydro-meteorological institutes

IC		International Consultant

IFI		International Financial Institution

INC		Initial National Communication

IPCC		Intergovernmental Panel on Climate Change

LEDS 		Low Emission Development Strategy

LUCF		Land Use Change and Forestry

MRV		Measurement, Reporting and Verification

NAMA		National Appropriate Mitigation Actions

NCSP		National Communications Support Programme

PA		Project Assistant

PM		Project Manager

RS		Republika Srpska

SNC		Second National Communication

SRES		[IPCC] Special Report on Emissions Scenarios

UNDP		United Nations Development Programme

UNDAF	United Nations Development Assistance Framework

UNFCCC	United Nations Framework Convention on Climate Change

WB		World Bank

WMO		World Meteorological Organization

- Situation analysis

Bosnia and Herzegovina belongs to the lower middle income countries with GDP of USD 4337 (2010) and population of app 3.8 million inhabitants. It has a total surface area of 51,209.2 km2, consisting of 51,197 km2 of land and 12.2 km2 of sea. Of the total land area, 5% is lowlands, 24% hills, 42% mountains, and 29% karst regions. The climate varies from a temperate continental climate in the northern Pannonian lowlands along the Sava River and in the foothill zone, to an alpine climate in the mountain regions, and a Mediterranean climate in the coastal and lowland area of the Herzegovina region in the south and southeast.

It is a sovereign state with a decentralized political and administrative structure consisting of two Entities: the Republic of Srpska (RS), the Federation of Bosnia and Herzegovina (FBiH) and and Brčko District. The Federation of Bosnia and Herzegovina is sub-divided into 10 Cantons. Decision-making involves the Council of Ministers, the two Entities and Brčko District.

Bosnia and Herzegovina (BiH) became a member of the United Nations Framework Convention on Climate Change (UNFCCC) on December 6, 2000, and the Kyoto Protocol was ratified on April 22, 2008. Following the ratification of the UNFCCC, BiH has made a serious effort to establish appropriate political, institutional and legal frameworks to meet the commitments of the convention. Based on mutual agreement of both of the relevant entities, the BH Focal Point for the UNFCCC is the Ministry of Spatial Planning, Civil Engineering and Ecology of Republic of Srpska (RS).

The Initial National Communication (INC) of BiH to the UNFCCC was submitted in 2010. Technical assistance and coordination was provided by UNDP BiH according to the guidance provided in “Instructions for the Preparation of National Communications of the Member Countries not Involved in Annex I to the Convention” (17/CP.8), the corresponding Operational Program of the GEF, and relevant documents from Bosnia and Herzegovina. The Project Board, which included the state and entity level governments, actively followed and supported the INC preparation process.

The Second National Communication (SNC) has been prepared using similar arrangements and the same comprehensive representation.  The SNC has been finalized by the project team and adopted by entity government.  Final adoption by Council of Ministers is awaited.  The SNC has advanced the state of climate modelling, impacts assessment, and policy analysis in Bosnia and Herzegovina, and it has also established a measurement baseline for public awareness and outlined key capacity needs. Furthermore, work on the SNC has enhanced the individual capacity of climate researchers in Bosnia and Herzegovina in government, academia, and NGOs, and it has strengthened the organizational capacity of the UNFCCC focal institution in Bosnia and Herzegovina, the Ministry of Spatial Planning, Civil Engineering and Ecology of RS.  Finally, the INC and the draft SNC have served as an important source of information for the country’s draft Climate Change Adaptation and Low Emission Development Strategy.

In order to fulfill new obligations resulting from the Cancun and Durban COP decisions related to the submission of national communications and biennial update reports, support from the Global Environment Facility is needed to continue to develop existing technical and institutional capacity and to continue the efforts to integrating climate change into government activities.

The First Biennial Update Report (FBUR) of Bosnia and Herzegovina will provide an update of the country’s Second National Communication, which is to be submitted during the initial phase of the FBUR project, with an emphasis on updating greenhouse gas inventories.  The FBUR project aims to encourage the incorporation of climate-related policies and programs into the work of the state and entity level governments.  At the same time, the projects must take into consideration the complex political environment, the lack of overarching economic and sectoral development policies at the state and entity levels, and the shortage of organizational capacity in Bosnia and Herzegovina at present. Therefore, the proposed project to prepare the FBUR will be implemented in line with UNDP’s standard National Implementation Methodology (NIM) implementation, using the same implementation arrangements as the SNC preparation project to support continuity and efficiency while moving to increase government capacity to oversee climate policy and programs.

- Strategy

Project rationale

Overall, this project will contribute to meeting countries obligations towards signed multi-lateral environment agreements (MEA), adopting environment as a cross-cutting issue for participatory development planning in all sectors and at all levels and to strengthening environmental management to mitigate environmental threats. This is a national priority listed in the UNDAF Outcome 3, 2010-2014 period. The capacity development activities under this project focus on enhancing the capacity of the state and entity institutions in the area of GHG inventory and climate change mitigation.

Within this framework, this project will specifically enable Bosnia and Herzegovina to prepare its First Biennial Report to the Conference of Parties. It will also contribute to development and enhancement of national capacities to fulfill the country’s commitments to the Convention on a continuing basis, and it will enhance general awareness and knowledge of government planners on issues related to climate change and reduction of greenhouse gas emissions, thus enabling them to take such issues into account in the national development agenda.

Country ownership

Authorities of Bosnia and Herzegovina and the various domestic stakeholders are very motivated to support and implement the project as GHG levels and climate change issues are becoming more and more prominent in various sectors and at the top level. Also, governments are very keen on keeping the close relationship with researchers and broad stakeholders participation. Further integration of climate changes into sectoral strategies is seen as a way towards sustainable developments.

Furthermore, the preparation of the FBUR is mandated under the UNFCCC, and the Government has an interest in maintaining its commitments to international agreements and being fully engaged in the UNFCCC process.

The Implementing Partner for this project will be the BiH UNFCCC Focal Point, which is the Ministry of Spatial Planning, Construction, and Ecology of the Republic of Srpska (RS). The project will be implemented in line with UNDP’s standard National Implementation Methodology (NIM) implementation, with UNDP supporting the Implementing Partner as needed in the provision of procurement, recruitment and contracting processes upon request.   NIM implementation has been proposed on the basis of an agreement among environmental authorities in Bosnia and Herzegovina, and it has been used successfully to address significant delays in preparing the Initial National Communication and to support the timely preparation of the Second National Communication. The Implementing Partner, under close supervision of the UNDP BIH Country Office will hold the overall responsibility for the production of outputs/implementation of activities envisaged. The management of project funds will be carried out according to UNDP financial rules and regulations, based on a work plan with a detailed budget.

The Project Board will involve the representation of the Council of Ministers through the Ministry for Foreign Trade and Economic Relations, which oversees environmental issues at the country level. It will also include two entity-level ministries (the Ministry of Spatial Planning, Construction, and Ecology of RS and the Federal Ministry of Environment and Tourism for FBiH), and the government of the Brcko District through its Utilities Department.

Project objective, outcomes and outputs/activities

The long term objective of the project is to assist Bosnia and Herzegovina in deepening the mainstreaming and integration of climate change into country and sectoral development goals and to enable the entity and state level government to respond to international environmental obligations by strengthening and giving continuity to the institutional and technical capacity development that has been initiated and sustained by the National Communications process.

The immediate objective of the project is to assist Bosnia and Herzegovina in the preparation and submission of its First Biennial Update Report to the Conference of the Parties to the UNFCCC for the fulfilment of its obligations to the Convention under Dec. 1/CP. 16 par. 60 and Dec 2/CP. 17 par. 41 and its Annex III.

The project objective will be achieved with the fulfillment of the following outcomes, which are in line with the GEF’s climate change mitigation strategic objective (SO-6) under GEF-5: Enabling Activities: Support enabling activities and capacity building under the Convention. The outcome is: Completed climate change enabling activities under the UNFCCC.

The project expected outcomes are:

- Updating GHG inventory

- Analysis of mitigation actions and their effects

- Updating national circumstances and other information

- Establishment of domestic measurement, reporting and verification arrangements

1.	Outcome 1: Updating GHG inventory

This activity will result in an updated GHG inventory with the additional of several sectors not covered in the draft SNC.  It will cover years 2010 and 2011. Data and estimates will be documented and archived in a way that adheres to IPCC Good Practice Guidelines and ensures accessibility and continuity for future reports. A capacity of public institutions in charge of GHG inventory update will be strengthened via trainings which will, amongst other include training in use of UNFCCC NAI software.

- Analysis of mitigation actions and their effects

This activity will result in an updated chapter on measures to mitigate climate changes. It includes updated analysis of low-cost measures to reduce emissions intensities in selected key sectors, estimation of baseline scenarios for emissions from each sector given any changes in state or entity-level policies and programs; quantification of potential emission reductions for each measure/mitigation scenario through the year 2040; estimation of a feasible timeline for implementation of each measure/mitigation scenario; identification of key obstacles and constraints, and what would be required to overcome them.  A description on the country arrangements to enable the implementation of NAMAs including the establishment of a NAMA Registry for Bosnia and Herzegovina is also part of this activity. Support will be provided to  identifying NAMA development potential in different sectors and to understand the different types of financing and co-financing that will be involved in various projects.

- Updating national circumstances and other information

This outcome includes an update of the country characterization in terms of geography, demography, natural resources, climate and education, social and cultural aspects, as well as macroeconomic parameters, employment, income and services. It will also include the characterization of the specific sectors such as energy, transport, agriculture, forestry...In particular, the update will describe how national circumstances may affect Bosnia and Herzegovina’s ability to deal with mitigating and adapting to climate change. Gender disaggregated data will be considered whenever data collection allows for this.

Under the proposed project, an initial study of capacity and technology needs in the field of climate change will be carried out with a special emphasis on capacity and technology necessary to maintain high-quality GHG inventories. The study will include a review of financial, technological and capacity needs and constraints of institutions responsible for activities related to GHG inventory data gathering, analysis and storage.

This Activity will also result in the preparation, translation, editing, submission, launch, and further dissemination of the FBUR according to the guidelines contained in Annex II of Dec. 2. CP 17.

- Establishment of domestic measurement, reporting and verification arrangements

Under this activity, an assessment will be conducted regarding the different options and possibilities for the domestic MRV according to the guidelines to be developed, considering current circumstances and capabilities. The project will study the experience to date with the relatively recent measurement and reporting experiences of the Designated National Authority of BiH for the Clean Development Mechanism (DNA BiH), which is the most relevant experience in the country to date.  Also, the project will assess the potential scope and implications of measurement and reporting under the European Union’s Emissions Trading System (EU ETS), as BiH is currently a potential candidate country for accession to the EU.

It is also expected that the project outcomes and activities will strengthen individual and organizational capacity in government and civil society to address climate change issues in Bosnia and Herzegovina and to establish important linkages between climate change issues and country priorities such as accession to the European Union.

Sustainability and Replicability

The project approach will build on the work done under development of national communications and will involve the key national experts and institutions responsible for its compilation in order to maintain continuity in the process, and additional experts and institutions will be involved as needed. This work is directly aligned with the CPAP, which stresses commitments to international accords, addressing environmental problems and applying GEF funding in BiH.

The project will address sustainability by developing both individual and organizational capacity in BiH. The engagement of national experts will allow them to strengthen their experience in climate change issues and linkages between key socioeconomic development issues and climate change. The involvement of many organizations, ranging from hydrometeorological services to universities and research institutes, will also provide those groups with best practice techniques and training materials for their employees.

Finally, designated project activities in each area of the FBUR will include coordinated data archiving to support continuity and make the BUR process more efficient.

- Project Results Framework:

| This project will contribute to achieving the following Country Programme Outcome as defined in CPAP or CPD: Strengthened national capacities to integrate environmental and energy concerns into development plans at all levels and systems for effective implementation of the sectoral priorities |
| --- |
| Country Programme Outcome Indicators: |
| Primary applicable Key Environment and Sustainable Development Key Result Area (same as that on the cover page, circle one): 1. Mainstreaming environment and energy OR 2. Catalyzing environmental finance OR 3. Promote climate change adaptation OR 4. Expanding access to environmental and energy services for the poor. |
| Applicable GEF Strategic Objective and Program: |
| Applicable GEF Expected Outcomes: |
| Applicable GEF Outcome Indicators: |
|  | Indicator | Baseline | Targets End of Project | Source of verification | Risks and Assumptions |
| Project Objective Preparation of the First Biennial Update Report | FBUR Submitted to UNFCCC | BiH has completed its national inventory for the period 1990-2001. | The FBUR will be endorsed and submitted to the UNFCCC. | UNFCCC documentation; government records | Risk: Insufficient attention to climate change issues on the part of the government due to other pressing concerns will hinder project implementation. Risk rating: Low. Assumption: political support and consensus for the BUR process will continue. |
| Outcome 1 GHG inventory 2010-2011 completed | The GHG inventory capacity for data collection and analysis process maintained and strengthened GHG inventory 2010-2011 completed | Inventory for the period 1990-2001 carried out by independent consultants Not all emissions from industrial and waste sectors covered Several gases not measured Need for enhanced QA/QC and uncertainty assessment | GHG data collection systematized, institutionalized within Federal and RS Hydrometeorological institutes Emissions from mineral extractions, solvents, waste waters etc. included in FBUR Estimates of fluoric gases and/or measurements included in FBUR Improved QA/QC programme and uncertainty assessment provided in FBUR. | Project documentation Government reports Expert review (NCSP) FBUR | Risk: enterprises may be unwilling or unable to provide data in necessary areas. Risk rating: Medium. Assumption: enterprises and government agencies will be willing and able to share data on their emissions with the project team |
| Outcome 2 Mitigation actions and their effects described | Updated and strengthened chapter on Mitigation Registration of BiH NAMAs enabled | Business as Usual scenario and two mitigation scenarios till 2025 developed under SNC project No NAMA created for BiH | Business as Usual scenario and at least two mitigation scenarios through the year 2040 with clear, documented assumptions included in the FBUR Updated list of NAMAs with quantitative and qualitative assessments of their potential impacts and relative importance. | Project documentation UNFCCC NAMA registry Government reports Expert review (NCSP) FBUR | Risk: Government not able to reach agreement on NAMA approving process. Risk rating: Low. Assumption: state and entity ministries agree on NAMA approving methodology |
| Outcome 3 National circumstances and other information updated | Updated account of National Circumstances prepared and capacity to collect and manage information strengthened Study on financial, technology and capacity building needs and support received FBUR prepared, translated and edited, submitted and disseminated | NC described in SNC, but information on technology, finance and capacity needs, require further elaboration | The National Circumstances chapter of the FBUR has updated and strengthened data. Information on financial, technology and capacity building needs and support updated | Project documentation Government reports Expert review (NCSP) FBUR | Risk: statistical agencies may be unwilling or unable to provide data in necessary areas. Risk rating: Medium. Assumption: statistical agencies will be willing and able to share data on their emissions with the project team |
| Outcome 4 Domestic measurement, reporting and verification arrangements established | Domestic MRV arrangements established | No system in place for MRV of mitigation activities. | MRV system established and mainstreamed into capacity building and environmental monitoring | Project documentation Government reports Expert review (NCSP) FBUR | Risk: Government not able to reach agreement on MRV arrangements. Risk rating: Low. Assumption: state and entity ministries agree on MRV arrangements |

Total budget and workplan

| Award ID: | 00075853 | Project ID(s): | 00087531 |
| --- | --- | --- | --- |
| Award Title: | Country Name Project Title |
| Business Unit: | BIH 10 |
| Project Title: | Country Name Project Title |
| PIMS no._______ | 5250 |
| Implementing Partner (Executing Agency) | Republic of Srpska Ministry of Spatial Planning, Civil Engineering and Ecology |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount (USD) 2013 | Amount (USD) 2014 | Amount (USD) 2015 | Total (USD) | See Budget Note: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: GHG inventory 2010-2011 | UNDP | 62000 | GEF | 71200 | International Consultants | 2,000 | 15,000 |  | 17,000 | Training for local partners in data gathering and analysis and software (UN NAI) use |
|  |  |  |  | 71300 | Local Consultants | 2,000 | 67,000 |  | 69,000 | Data collection, analysis and storage |
|  |  |  |  | 71400 | Contractual services - individual |  | 3,000 |  | 3,000 | PM’s engagement in inventory development and software training |
|  |  |  |  | 72100 | Contractual Services - Companies |  | 15,000 |  | 15,000 | GHG evaluation |
|  |  |  |  | 71600 | Travel |  | 4,000 |  | 4,000 | int consultant, local travel related to data collection |
|  |  |  |  | 72800 | IT Equipment |  | 12,000 |  | 12,000 | Equipment for GHG inventory development for HMI, statistics |
|  |  |  |  |  | Total Outcome 1 | 4,000 | 116,000 |  | 120,000 |  |
| OUTCOME 2: Mitigation actions and their effects described | UNDP | 62000 | GEF | 71200 | International Consultants |  | 13,000 |  | 13,000 | International consultant (NAMA and mitigation scenarios revision) |
|  |  |  |  | 71300 | Local Consultants | 3,000 | 56,000 |  | 59,000 | Mitigation experts (all sectors) |
|  |  |  |  | 71400 | Contractual services - Individual |  | 4,000 |  | 4,000 | ’NAMA development and training |
|  |  |  |  | 72100 | Contractual Services- Companies | 8,000 | 12,000 |  | 20,000 | data collection and data surveys in priority areas |
|  |  |  |  | 71600 | Travel |  | 4,000 |  | 4,000 | int consultant, local travel related to data collection |
|  |  |  |  |  | sub-total GEF |  |  |  |  |  |
|  |  |  |  |  | Total Outcome 2 | 11,000 | 89,000 |  | 100,000 |  |
| outcome 3: National circumstances and other information updated | UNDP | 62000 | GEF | 71200 | International Consultants |  | 5,000 |  | 5,000 | technical editing and profession review of FBUR |
|  |  |  |  | 71300 | Local Consultants | 2,000 | 9,000 |  | 11,000 | local experts-national circumstances |
|  |  |  |  | 71300 | Local Consultants |  | 5,000 |  | 5,000 | Local experts-support received to enable FBUR preparation |
|  |  |  |  | 71300 | Local Consultants |  | 5,000 |  | 5,000 | Local consultant - Financial, technology and capacity building needs and support received |
|  |  |  |  | 71300 | Local Consultants |  | 4,000 |  | 4,000 | translation and proofreading |
|  |  |  |  | 71400 | Contractual services - Individual |  | 2,000 | 2,000 | 4,000 | FBUR compilation and promotion |
|  |  |  |  | 74200 | Audio Visual &Print Prod Costs |  | 3,000 | 13,000 | 16,000 | Submission, publication and promotion |
|  |  |  |  |  | Total Outcome 3 | 2,000 | 33,000 | 15,000 | 50,000 |  |
| OUTCOME 4: Domestic MRV arrangements established | UNDP | 62000 | GEF | 71200 | International Consultants |  | 19,000 |  | 19,000 | Int consultant |
|  |  |  |  | 71300 | Local Consultants |  | 28,000 |  | 28,000 | introduction of MRV system in local institutions |
|  |  |  |  | 71600 | Travel |  | 3,000 |  | 3,000 | int consultant, local travel related to MRV establishment |
|  |  |  |  |  | Total Outcome 4 |  | 50,000 |  | 50,000 |  |
| Project management unit | UNDP | 62000 | GEF | 71400 | Contractual services - Individual |  | 25,950 | 2,000 | 27,950 | part time PM and PA |
|  |  |  |  | 72100 | Contractual Services - Companies |  | 2,800 | 200 | 3,000 | office utilities, fuel, communication costs |
|  |  |  |  | 72500 | Office Supplies |  | 1,000 | 50 | 1,050 | office supplies, stationary, sundries |
|  |  |  |  |  | Total Management |  | 29,750 | 2,250 | 32,000 |  |
|  |  |  |  | PROJECT TOTAL | 17,000 | 317,750 | 17,250 | 352,000 |  |

| Summary of Funds: |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Total |
|  |  |  |  | GEF | 17,000 $ | 317,750 $ | 17,250 $ | $ | 352,000 $ |
|  |  |  |  | Donor 2 Federal Fond for Environmental Protection | $ | 30,000 $ | $ | $ | 30,000$ |
|  |  |  |  | Donor 3 RS Ministry for Spatial Planning Construction and Ecology (in-kind) | 3,000$ | 12,000$ | 1,000$ | $ | 16,000$ |
|  |  |  |  | TOTAL | 20,000$ | 359,750 $ | 18,250 $ | $ | 398,000 $ |

- Management Arrangements

The project will be implemented in line with UNDP’s standard National Implementation Methodology (NIM) implementation, with UNDP being available to support the Implementing Partner though the provision of procurement, recruitment and contracting processes upon a request of the Implementing Partner. UNDP will provide procurement and contracting services in accordance with the relevant UNDP rules and regulations, policies and procedures for procurement, human resources management and RBM guidelines. Direct project costs will not be charged against the GEF-financed project budget for these services.

It is foreseen that the Implementing Partner for this project will be the BiH National UNFCCC Focal Point, which is the Ministry of Physical Planning, Construction, and Ecology of Republic of Srpska.

The Implementing Partner, under close supervision of the UNDP BIH Country Office will hold the overall responsibility for the production of outputs/implementation of activities envisaged. The management of project funds will be carried out according to UNDP financial rules and regulations, based on a work plan with a detailed budget.

The overall coordination of the project will be the responsibility of a Project Board (PB), which will be constituted of representatives of all the key national stakeholders. The Project Board plays a critical role in project monitoring and evaluations by quality assuring these processes and products, and using evaluations for performance improvement, accountability and learning. The Project Board is the main platform for stakeholders active involvement, provision of strategic advice and guidance to the project management and experts on key aspects of the self-assessment process.

Mandate of the Project Board will be to:

- Provide strategic guidance to the project;

- Support project implementation, including bottlenecks resolution;

- Monitor project implementation, discuss and assess project results.

The Project Board will meet every four months or more frequently if necessary. It will be composed of the representatives from concerned ministries, municipalities and UNDP Country Office in BiH. The Project Board will consist of one representative of the each of the following organizations:

1. Ministry of Spatial Planning, Construction and Ecology of Republic of Srpska (Implementing Partner/Chair of the Project Board)

2. Ministry of Foreign Trade and Economic Relations of Bosnia and Herzegovina (member)

3. Ministry of Tourism and Environment of the Federation of BiH (member); and

4. Brcko District Government (member)

5. UNDP BiH (member)

The Project Board ensures that required resources are committed and arbitrates on any conflicts within the project or negotiates a solution to any problems with external bodies. Based on the approved Annual Work Plan, the Project Board can also consider and approve the quarterly plans (if applicable) and also approve any essential deviations from the original plans.

Project revisions that involve changes to project goal, or substantial modification of project outputs, will be agreed in writing by members of the Project Board by calling an ad hoc session, or by collecting (including through email) written opinions of the PB members. Revisions will then have to be approved by UNDP/GEF NCSP.

A Project Manager and Project Associate will ensure day-to-day management and oversight for the project as a whole, will be responsible for achievement of projects goals and the reporting on the resources allocated.

The Project Board and Project Manager will additionally ensure that all key national stakeholders are informed and involved in the important aspects of the self-assessment process through a number of consultations, workshops and working meetings which will bring together all the interested parties throughout the project lifespan.

- Monitoring Framework and Evaluation

The project will be monitored through the following M& E activities.  The M& E budget is provided in the table below.

Project start:

A Project Inception Workshop will be held within the first 2 months of project start with those with assigned roles in the project organization structure, UNDP country office and where appropriate/feasible regional technical policy and programme advisors as well as other stakeholders.  The Inception Workshop is crucial to building ownership for the project results and to plan the first year annual work plan.

The Inception Workshop should address a number of key issues including:

- Assist all partners to fully understand and take ownership of the project.  Detail the roles, support services and complementary responsibilities of UNDP CO and RCU staff vis à vis the project team.  Discuss the roles, functions, and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for project staff will be discussed again as needed.

- Based on the project results framework and the relevant GEF Tracking Tool if appropriate, finalize the first annual work plan.  Review and agree on the indicators, targets and their means of verification, and recheck assumptions and risks.

- Provide a detailed overview of reporting, monitoring and evaluation (M&E) requirements.  The Monitoring and Evaluation work plan and budget should be agreed and scheduled.

- Discuss financial reporting procedures and obligations, and arrangements for annual audit.

- Plan and schedule Project Board meetings.  Roles and responsibilities of all project organisation structures should be clarified and meetings planned.  The first Project Board meeting should be held within the first 2 months following the inception workshop.

An Inception Workshop report is a key reference document and must be prepared and shared with participants to formalize various agreements and plans decided during the meeting.

Quarterly:

- Progress made shall be monitored in the UNDP Enhanced Results Based Managment Platform.

- Based on the initial risk analysis submitted, the risk log shall be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Reports (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc...  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

Bi-annual progress:

Status Survey Questionnaires to indicate progress of key project activities and identify challenges  as well as technical support needs will be carried out twice a year, typically in February/March and August/September period.

Periodic Monitoring:

A detailed schedule of project reviews meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for Steering Committee Meetings, (or relevant advisory and/or coordination mechanisms) and (ii) project related Monitoring and Evaluation activities.

Day to day monitoring of implementation progress will be the responsibility of the Project Coordinator, Director or CTA (depending on the established project structure) based on the project's Annual Work plan and its indicators. The Project Team will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

Periodic monitoring of implementation progress will be undertaken by the UNDP-CO through quarterly meetings with the project proponent, or more frequently as deemed necessary. This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

End of Project:

During the last three months, the project team will prepare the Project Terminal Report. This comprehensive report will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results.

Audit clause:

Audit on project will follow UNDP Financial Regulations and Rules and applicable Audit policies.

Learning and knowledge sharing:

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

Communications and visibility requirements:

Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo.   The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.  Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

M& E workplan and budget

| Type of M&E activity | Responsible Parties | Time frame |
| --- | --- | --- |
| Inception Workshop and Report | Project Manager UNDP CO, UNDP GEF | Within first two months of project start up |
| Measurement of Means of Verification of project results. | UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members. | Start, mid and end of project (during evaluation cycle) and annually when required. |
| Measurement of Means of Verification for Project Progress on output and implementation | Oversight by Project Manager Project team | Annually prior to ARR/PIR and to the definition of annual work plans |
| Periodic status/ progress reports | Project manager and team | Quarterly |
| Project Terminal Report | Project manager and team UNDP CO local consultant | At least three months before the end of the project |
| Audit | UNDP CO Project manager and team | Yearly |
| Visits to field sites | UNDP CO UNDP RCU (as appropriate) Government representatives | Yearly |

Legal Context

Standard text has been inserted in the template. It should be noted that although there is no specific statement on the responsibility for the safety and security of the executing agency in the SBAA and the supplemental provisions, the second paragraph of the inserted text should read in line with the statement as specified in SBAA and the supplemental provision, i.e. “the Parties may agree that an Executing Agency shall assume primary responsibility for execution of a project.”

If the country has signed the Standard Basic Assistance Agreement (SBAA), the following standard text must be quoted:

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA [or other appropriate governing agreement] and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

If the country has not signed the SBAA, the following standard text must be quoted:

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together the instrument envisaged in the Supplemental Provisions to the Project Document, attached hereto.

Consistent with the above Supplemental Provisions, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

The following standard text for a global/ multi country and regional projects should be included:

This project forms part of an overall programmatic framework under which several separate associated country level activities will be implemented. When assistance and support services are provided from this Project to the associated country level activities, this document shall be the “Project Document” instrument referred to in: (i) the respective signed SBAAs for the specific countries; or (ii) in the Supplemental Provisions attached to the Project Document in cases where the recipient country has not signed an SBAA with UNDP, attached hereto and forming an integral part hereof.

This project will be implemented by the agency (name of agency) (“Implementing Partner”) in accordance with its financial regulations, rules, practices and procedures only to the extent that they do not contravene the principles of the Financial Regulations and Rules of UNDP. Where the financial governance of an Implementing Partner does not provide the required guidance to ensure best value for money, fairness, integrity, transparency, and effective international competition, the financial governance of UNDP shall apply.

The responsibility for the safety and security of the Implementing Partner and its personnel and property, and of UNDP’s property in the Implementing Partner’s custody, rests with the Implementing Partner. The Implementing Partner shall: (a) put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried; (b) assume all risks and liabilities related to the Implementing Partner’s security, and the full implementation of the security plan. UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The Implementing Partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

#### Appendix A: Summary report of the self-assessment exercise

A.1 	Methodological approach

The stocktaking analysis was used to determine the current baseline for activities under the FBUR and to identify needs and priorities.  The analysis paid particular attention to areas that might require new information or approaches and to the current system of data collection and BUR preparation with a view to regularizing that process for subsequent BURs.

The following main tools have been used for the stocktaking: (i) desk review of relevant documents; (ii) interviews with stakeholders; (iii)  meetings with more than 20 experts from public institutions, NGOs, academia, who were involved in compiling inventory and mitigation parts of INC and SNC; (iv) consultative meetings arranged through the SNC and CC Adaptation and Low Emission Development Strategy finalization.

Overall, the stocktaking exercise involved a variety of stakeholders from different ministries, other public institutions, NGOs, academia, and international organizations active in Bosnia and Herzegovina, including all of the 30 national experts involved in the compilation of the inventory and mitigation parts of INC and SNC.

A. 2 	Findings

General Findings related to the BUR  process

Baseline and issues identified

- There is a need for more coordination amongst the primary government stakeholders. Team leaders from relevant governmental institutions to carry the GHG inventory process forward

- A lack of sectoral data and socioeconomic data have introduced difficulties in aspects of the report ranging from GHG inventories to mitigation scenarios and estimates of climate change impacts and effects of mitigation measures.

- Considerable capacity also exists to measure and evaluate mitigation measures, although assistance is required in implementing a cost-benefit analysis.

- More capacity building within the Agency for Statistics and statistical institutes in dealing with climate change / environment-related statistics is necessary. This includes training in data collection methodology and continuing training in statistical packages linked to the GHG inventory.

- Awareness of climate change issues should be constantly strengthened.

- There is a need for international cooperation in activity data, emission factors and capacity development in modelling. This cooperation is a cost-effective approach to enhancing data and capacity already available in BiH.

Priorities under the FBUR

- There is a need to discuss and develop institutional arrangements that will allow BiH to prepare the biennial update reports on a regular basis.

- Within this process, there is a need to support training for partners to undertake key components of the BUR work, such as ongoing data collection, analysis, and archiving.

- Work should continue on increasing the transparency of the reporting and analysis that supports the BUR.  Steps such as strengthening data collection, economic analysis, quality control and quality assurance, and reporting formats will all feed into this effort.

- There is an absence of both NAMAs and the national arrangements needed to support their development, selection, and implementation that should be addressed as soon as possible.

- On a related note, there is a need to identify and assess different options for MRV that will be appropriate for BiH and to mainstream MRV into environmental monitoring at the state and entity level.

GHG Inventories

Baseline and issues identified

- Inventory data were collected for the base year of 1990-2001.

- The SNC team developed emission factors for coal combusted in BiH, which enhanced the quality of the inventory.  These emission factors will continue to be refined.

- Regional cooperation will be necessary in the further development of emission factors.

- Key source analysis should be strengthened

- A lack of activity data and their availability presents a significant challenge to the compilation of the inventory.

- The GHG inventory covering the above period did not include all gases, and it will be important to provide more comprehensive reporting in the FBUR.

- There is a need to coordinate data storage and management.

- There is a need to undertake information dissemination in order to increase awareness of the findings from the compilation of the inventory.

Priorities and new areas for work under the FBUR

- The inventory should be updated for 2010 and 2011.

- The FBUR inventory should cover CO2, CH4 and N2O and -- conditional on data availability -- HFCs, PFCs, SF6, CO, NOx, NMVOCs, and SOx

- Provide training in NAI software

- Estimates of the key sources.

- Identify new sources of activity data where available, particularly for gases not covered in the SNC, and develop corresponding methodology protocols for measurement

- Emission factors should be refined (and additional factors developed where necessary), utilizing regional resources where possible.

- Sensitivity analysis should be strengthened

- Uncertainty levels should be both described and estimated quantitatively.

- Documentation and archiving of measurements, analysis, and supporting research should be a priority.

- All inventory-related activities should be brought in line with IPCC Good Practice Guidelines, and a QA/QC program established during SNC development should be improved where necessary.

- Identification of gaps in the applicability of the IPCC Guidelines for National GHG Inventories

- Institutional arrangements with HMIs, sectoral ministries and statistical institutions should be strengthened;

- Training and support for the development of technical capacity for compiling the inventory

- Inventory findings should be disseminated in addition to the report in the FBUR.

Mitigation Analysis

Baseline and issues identified

- The Climate Change Adaptation and Low Emission Development Strategy identified four key sectors for mitigation:

  - electric power production

  - district heating

  - buildings

  - transport

- These sectors remain the most important. While the discussion of the electric power production sector is quite strong, the key to strengthening the mitigation chapter in the FBUR will be to enhance the analysis of the other three “key” sectors with additional data and analysis

- Economic analysis of the mitigation measures should include more quantitative information

- The potentially important role of local governments is not sufficiently addressed in national communications.

Priorities and new areas for work under the FBUR

- Baseline and mitigation scenarios until 2040 for abatement of GHG emission will be further developed.

- Training, capacity building and awareness rising on NAMAs should be provided under this project.

- Analysis of mitigation measures should include research of local government activities and provide a description of the potential for mitigation at the local level.

- In the FBUR, the project team should work closely with branch ministries in order to determine the status of sectoral policies and to analyse new strategies that will become available during the course of the project,

- Training and capacity strengthening should be undertaken in the area of conducting mitigation analysis and to improve the analysis in key sectors while acknowledging shortcomings in data.

Establishment of domestic measurement, reporting and verification arrangements

Baseline and issues identified:

- There is no domestic MRV for mitigation activities.

- There is a need to determine the institutional arrangements for MRVs in close coordination with the activities on developing an institutional framework for NAMAs and when developing the NAMAs themselves.

Priorities and new areas for work under the FBUR:

- Reporting on and supporting the development of institutional arrangements and a framework for domestic MRV

- Training and capacity strengthening to support the mainstreaming of MRVs into overall environmental monitoring at the entity level and the coordination of monitoring at the state level.

Other information required by the UNFCCC and subsequent CP decisions

Baseline and issues identified:

- National Circumstances: The national circumstances section of the SNC is largely still relevant in terms of geographic and other descriptive data related to land and natural resources.

- National Circumstances: The lack of current, reliable socioeconomic data continues to be a problem.  The census is to take place in Sept 2013 and it is not very likely that its data will be available for this report.

- Public awareness: baseline information on public awareness or knowledge of climate change was conducted under SNC.

- Government institutions are not conducting public outreach or education activities in the area of climate change, although this was identified as a need in the INC, and NGO activity is limited.

- Training: There has not been any type of general training for government officials on climate change.

- One need that was identified during consultations was to continue initial efforts to make the NC findings accessible to high-level decision-makers and to provide training and outreach to this important target group.

- Research, monitoring, and systematic observation:  There is a need to qualitatively prioritize research in climate change.

Priorities and new areas for work under the FBUR:

- National Circumstances: Update relevant sections of the chapter on National Circumstances, and ensure that socioeconomic data used in that chapter reflect the most recent available data (including those from statistical agency surveys)

- Assess technological, financial and capacity needs for inventory development

Updated information on technology needs and technology support received.

A.3	Risk log

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Government bodies do not pay sufficient attention to climate change issues due to other pressing concerns | Jun 2013 | Strategic | FBUR will not be given proper importance nor will its finding and recommendation be given due attention. P = 3 I = 2 | UNFCCC focal point, UNDP and the project team shall provide additional information on importance of climate changes and their link with GHG levels and also on importance of mitigation activities and their cause-effect link with adaptation measures. | Project Board, Project Team | UNDP | Sept 2013 | No change |
| 2 | Government institutions, public and private companies may be unwilling to provide data | Jun 2013 | Operational | Data gathering and processing will be made very difficult. P = 2 I = 4 | Representatives of all relevant institutions/companies will be involved in the process from the very beginning. Support from the ministries of environment will be given to the project implementation and communicated properly to relevant stakeholders. | Project Board Project team | UNDP | Sept 2013 | No change |
| 3 | Government institutions, public and private companies may be unable to provide data for inventory and NAMA’s development due to insufficient technical and human capacity. | Jun 2013 | Operational | Completion of FBUR paragraphs will require additional time and effort from the project team. P = 3 I = 4 | The project team shall provide necessary technical assistance in data gathering and processing, as well as in NAMA development. International experts will be recruited as needed. Strengthening technical capacities and knowledge of the relevant institutions and their experts will be conducted during the project tenure via various trainings, information and lessons learnt exchange. | Project team | UNDP | Sept 2013 | No change |
| 4 | Governments on state and entity levels are not able to reach an agreement on MRV and NAMA approving process. | Jun 2013 | Organizational | No agreement will hinder NAMA development and MRV process. P = 2 I = 3 | Relevant stakeholders will be involved in setting up institutional arrangements for MRV and NAMA approving process from the very beginning. Training will be provided on NAMA preparations and NAMA importance to relevant institutions/ companies/ NGO’s. | Project Board, UNDP, Project team | UNDP | Sept 2013 | No change |

A.4 	Stakeholder Involvement Matrix

| Name of institutions / stakeholders consulted | Stakeholder interests, official position or mandate | Relevance to climate change / Reasons for inclusion | Modality of involvement/ Role in the self-assessment process |
| --- | --- | --- | --- |
| Inter entity environment body | Responsible for environmental issues which require consolidated approach of both entities | Involves relevant person from ministries in charge of environment | Individual consultations Review and endorsement of the SNC and Climate Change Adaptation and Low Emission Development Strategy Review and endorsement of the FBUR project proposal |
| BiH Ministry of Foreign Trade and Economic Relations | Responsible for coordinating policies and measures in the field of the environment. | Location of GEF Operational Focal Point Member of Project Board | Individual consultations, ongoing dialogue Participation and active work in INC/SNC Project Board, Participation in preparation for COPs Formal review and endorsement of the FBUR project proposal |
| RS Ministry of Spatial Planning, Construction, and Ecology | Responsible for environmental policies and measures in RS, including environmental measures that may mitigate CC | Location of UNFCCC focal point. Sectoral development policies in these areas will influence the findings of the FBUR and should be informed by findings of the FBUR Implementing partner for the FBUR project, Chair of the Project Board | Individual consultations, ongoing dialogue Participation and active work in INC/SNC Project Board Participation in preparation for COPs Formal review and endorsement of the INC Formal review and endorsement of the FBUR project proposal |
| Federal BiH Ministry of Environment and Tourism | Responsible for coordinating entity-level policies and measures in the environmental area | Sectoral development policies in these areas will influence the findings of the FBUR and should be informed by findings of the FBUR Member of Project Board | Individual consultations, ongoing dialogue Participation and active work in INC/SNC Project Board Participation in preparation for COPs Formal review and endorsement of the FBUR project proposal |
| Brčko District Department of Communal Works | Responsible for coordinating policies and measures in the environmental area in Brcko District | Responsible for environmental policies and measures in BD, including environmental measures that may mitigate CC Member of Project Board | Individual consultations, ongoing dialogue Participation and active work in INC/SNC Project Board Participation in preparation for COPs |
| Hydro-meteorological Institute of RS | Entity body Authorized to create GHG inventory for RS Collects climatic data necessary for studying climate variability, for trend analysis, and for long-run modeling. Conducts modeling and participates in WMO research programs. | Climatic data are essential to the FBUR Data provider | Individual consultations Participation of individual experts in preparation of the GHG inventory of INC and SNC Review and inputs of individual experts in the FBUR project proposal development process |
| Hydro-meteorological Institute of F BiH | Entity body Collects climatic data necessary for studying climate variability, for trend analysis, and for long-run modeling. | Climatic data are essential to the FBUR Data provider | Individual consultations Participation of individual experts in preparation of the GHG inventory of INC and SNC Review and inputs of individual experts in the FBUR project proposal development process |
| BiH State Statistical Agency | State level Responsible for state-level statistics, data aggregation and analysis | Responsible for aggregating economic and demographic data and that will support modeling and scenario development and for environmental statistics Data provider | Individual consultations |
| Entity statistical institutes | Entity level Responsible for collecting data and providing it to the BiH statistical agencies | Responsible for collecting economic and demographic data that will support modeling and scenario development and for the collection of environmental data Data provider | Individual consultations |
| F BiH Ministry of Energy, Mining, and Industry | Entity level Responsible for coordinating policies and measures in energy, mining, and industry | Sectoral development policies in these areas will influence the findings of the FBUR and should be informed by findings of the FBUR | Individual consultations Formal review and endorsement of the SNC and CC Adaptation and LEDS |
| F BiH Ministry of Agriculture, Water-Management, and Forestry | Entity level Responsible for coordinating policies and measures in agriculture, water-management and forestry | Sectoral development policies in these areas will influence the findings of the FBUR and should be informed by findings of the FBUR | Individual consultations Formal review and endorsement of the SNC and CC Adaptation and LEDS |
| RS Ministry of Land Use, Forestry, and Water Resources | Entity level Responsible for coordinating policies and measures in land use, forestry, and water resources | Sectoral development policies in these areas will influence the findings of the FBUR and should be informed by findings of the FBUR | Individual consultations Formal review and endorsement of the SNC and CC Adaptation and LEDS |
| State and Entity Ministries of Transport | *Responsible for coordinating policies and overseeing the transportation sector | Sectoral development policies in these areas will influence the findings of the FBUR and should be informed by findings of the FBUR | Individual consultations Formal review and endorsement of the SNC and CC Adaptation and LEDS |
| Entity Ministries of Health | Different bodies Responsible for coordinating (state) and implementing (entity) health policies and measures | Information sharing | Individual consultations Formal review and endorsement of the SNC and CC Adaptation and LEDS |
| Entity Ministries of Education | Different bodies Responsible for coordinating (state) and implementing (entity) health policies and measures Oversee universities and research institutions | Individual consultations Data provider | Individual consultations Formal review and endorsement of the SNC and CC Adaptation and LEDS |
| Local Governments | Municipal bodies Oversee city management | Owners of water supply systems Owners of heat supply systems Managers of municipal waste systems (in some cases) Oversee development of urban master plans Local development policies will influence the findings of the FBUR and should be informed by findings of the FBUR Data provider | Individual consultations |
| Chambers of Commerce | Associations Promote business development and networking; serve as a constituency for lobbying on issues | Good conduit for information about CC that should be transmitted to the private sector | Individual consultations |
| Faculties of Natural Sciences (Banja Luka and Sarajevo) | Universities, research institutions | The highest educational institutions in the field of ecology, physics, chemistry Data provider | Participation of individual experts in preparation of the GHG and mitigation parts of INC and SNC Review and inputs of individual experts in the FBUR project proposal development process |
| Faculties of Machine Engineering (Banja Luka and Sarajevo) | Universities, research institutions | The highest educational institutions in the field of mechanical engineering, heating and cooling engineering, energy efficiency, renewable energy sources Data provider | Participation of individual experts in preparation of the GHG and mitigation parts of INC and SNC Review and inputs of individual experts in the FBUR project proposal development process |
| Faculties of Agriculture (Banja Luka and Sarajevo) | Universities, research institutions | The highest educational institutions in the field of agriculture Data provider | Participation of individual experts in preparation of the GHG and mitigation parts of INC and SNC |
| Faculty of Forestry (Banja Luka) | Universities, research institutions | The highest educational institutions in the field of forestry management Data provider | Participation of individual experts in preparation of the GHG and mitigation parts of INC and SNC |
| Faculty of Technology (Banja Luka) | Universities, research institutions | The highest educational institutions in technology and industrial management Data provider | Participation of individual experts in preparation of the NC parts of INC and SNC |
| Environmental NGOs | NGOs Provide information, training, and awareness-raising related to environmental issues, such as urban planning, water quality, and renewable energy | Can serve as a resource for public outreach related to the SNC and to raising awareness among the public about climate change-related issues. | Individual consultations Participation of individual experts in preparation of NC, GHG and mitigation parts of INC and SNC |
| European Commission | *Multilateral organization *Provides technical assistance and benchmarking in institutional reform | PHARE and CARDS programs have supported sustainable development *Provides support for legislation that will indirectly strengthen mitigation and adaptation efforts | Individual consultations Desk reviews |
| World Bank | IFI The International Bank for Reconstruction and Development (IBRD) has numerous investment projects. | The WB has projects in many areas directly related to climate change mitigation and adaptation, including transport infrastructure, health sector infrastructure, protected areas, forest and solid waste management. | Individual consultations Desk reviews |
| EBRD | IFI The EBRD, a regional development bank, is the largest institutional investor in Bosnia-Herzegovina. | Lending portfolio includes projects in electricity and electricity distribution infrastructure; road, rail, and air transport infrastructure; gasification; and waste water management. 46% of the projects are in the area of municipal and environmental infrastructure, 15% in agribusiness, manufacturing, and other industries, and 14% in the energy sector. | Individual consultations Desk reviews |
| USAID | US Development Agency | Various projects in the field of energy efficiency | Individual consultations Desk reviews |
| GIZ | German International Cooperation | Various projects in the field of energy efficiency at the municipal level | Individual consultations Desk reviews |

#### Appendix B: Technical components of the project proposal

B.1	Description of components and activities

Project Outcome: to enable Bosnia and Herzegovina to prepare and submit its First Biennial Update Report to the Conference of the Parties to the UNFCCC for the fulfilment of its obligations under the Cancun and Durban CoP decisions and to strengthen its reporting capacity in support of obligations under Dec. 1/CP. 16 par. 60 and Dec 2/CP. 17 par. 41 and its Annex III. The project will also result in increased capacity to produce subsequent BUR that meet all guidelines established by the CoP and that can serve as a source of information for national policies and measures in climate change and in key economic and social sectors.

GEF Outcome/UNDP Activity 1: GHG National Inventory for 2010 and 2011 elaborated.

GEF Output/UNDP Activity 1.1: Activity data collected for 2010 and 2011 as per Revised 1996 Guidelines with additional activity data collected in the agriculture and transport sectors.

Activity 1.1.1: Establish a working group on GHG emissions inventory. Responsible party: PM

Activity 1.1.2: Review activity data and emission factors for the agricultural sector, including LUCF data.  Responsible party: inventory expert.

Activity 1.1.3: If appropriate, develop a country-specific emission factor or emission factors in the BiH agriculture sector and use these factors to refine the calculation of emissions. Responsible party: inventory expert.

Activity 1.1.4: Review activity data for energy sector: PM, inventory expert.

Activity 1.1.5: Develop more detailed bottom-up analysis of energy use in the transport sector;  collect road transport data that are disaggregated by vehicle type, and any other additional data that are available for other modes of transportation. Responsible party: inventory expert.

Activity 1.1.6: Review activity for industrial processes: Responsible party: PM, inventory expert.

Activity 1.1.7: Review available data on the application of solvents and where available, include more specific information on the application of solvents. Responsible party: PM, inventory expert.

Activity 1.1.8: Review activity data in the waste sector  and include more detailed information where applicable. Responsible party: PM, inventory expert.

Activity 1.19: Incorporate the new data and emission factors in the GHG national inventory for 2010 and 2011 for the FBUR and provide appropriate documentation and description in the text of the FBUR. Responsible party: PM, inventory expert.

GEF Output/UNDP Activity 1.2: Strengthened institutional arrangements with key partners for specific sub-sectors (energy, industrial processes with mineral products and metal production, solvents, agriculture, LUCF, waste including wastewater, and waste incineration)

Activity 1.2.1: Strengthen cooperation and conclude any necessary agreements with governments and industries to collect higher quality and more detailed data in the energy sector (el. energy production, transport, buildings sectors): PM, inventory expert.

Activity 1.2.2: Strengthen cooperation and conclude any necessary agreements with governments and industries to collect data in specific industrial subsectors (mineral products and metallurgy, solvents). Responsible party: PM, inventory expert.

Activity 1.2.3: Strengthen cooperation and conclude any necessary agreements with governments and service providers in the waste sector, including wastewater treatment and waste incineration. Responsible party: PM, inventory expert.

Activity 1.2.4: Collect new activity data as necessary. Responsible party: inventory expert.

Activity 1.2.5: Incorporate the new data and emission factors in the GHG national inventory for 2010 and 2011 for the FBUR and provide appropriate documentation and description in the text of the FBUR.  Responsible party: PM, inventory expert.

GEF Output/UNDP Activity 1.3: Country-specific emission factors for coal updated and fully documented.

Activity 1.3.1: Review the current emission factors for coal that are used in the INC and SNC and make suggestions as to appropriate revisions.  Responsible: PM, inventory expert.

Activity 1.3.2: Incorporate revisions into the 2010 and 2011 GHG inventory of the FBUR. Responsible party: inventory expert.

GEF Output/UNDP Activity 1.4: Activity data collected for additional greenhouse gases (SF6, HFCs, PFCs) and indirect GHGs.

Activity 1.4.1: Establish a measurement system for all new sources to be referenced in the FBUR. Responsible party: inventory expert.

Activity 1.4.2: Identify existing sources of data for fluoric gas emissions (PFCs, HFCs, SF6) and collect activity data or develop estimates as necessary. Responsible party: inventory expert.

Activity 1.4.3: Identify possible sources of data for indirect GHGs and collect activity data or develop estimates as necessary. Responsible party: inventory expert.

Activity 1.4.4:  Incorporate new data into 2010-2011 GHG inventory. Responsible party: PM, inventory expert.

GEF Output/UNDP Activity 1.5: Worksheets, summary tables, uncertainty management for 2010 and 2011 GHG emissions elaborated, including a strengthened key category analysis.  Responsible party: inventory expert.

Activity 1.5.1: Review and update the current QA/QC Plan for the GHG inventory. Responsible parties: inventory expert, GHG inventory management expert.

Activity 1.5.2: Develop a quantitative analysis of key sources (for the year 2010) and conduct a sensitivity analysis as guided by IPCC Good Practice Guidelines. Responsible party: inventory expert.

Activity 1.5.3: Undertake a quantitative uncertainty assessment as guided by IPCC good practice guidelines. Include estimates on the significance of missing data in the discussion of uncertainty. Responsible party: inventory expert.

GEF Output/UNDP Activity 1.6: 2010-2011 inventory report published using UN NAI software.

Activity 1.6.1: Prepare a draft inventory of anthropogenic greenhouse gas emissions by sources and removals by sinks for 2010 and 2011 using the CRF and UN NAI software. Responsible party: GHG inventory management expert.

Activity 1.6.2: Circulate the inventory for internal and external review as part of QA/QC plan. Responsible party: PM, inventory expert.

Activity 1.6.3: Incorporate comments received from the review process and finalize the inventory to be submitted as a part of the FBUR. Responsible party: PM, inventory expert.

Activity 1.6.4: Archive the measurement plan for all sources and archive additional data and procedures as per IPCC Good Practice Guidelines and update the Manual of Procedures. Responsible party: PM, inventory expert, GHG inventory management expert , PA.

GEF Output/UNDP Activity 1.7: Updated summary information tables of previous inventories as necessary.

Activity 1.7.1: Re-visit the data from the INC and SNC and make any revisions necessary given the additional activity data collected and estimates made. Responsible party: inventory expert.

Activity 1.7.2: Re-visit the data from the INC and SNC and make any revisions necessary given the new country-specific emission factors developed (if any). Responsible party: inventory expert.

Activity 1.7.3: Re-visit the data from the INC and SNC and make any revisions necessary given data on new gases (if possible). Responsible party: inventory expert.

GEF Output/UNDP Activity 1.8: Training and capacity development for key partners to support continuous, on-going inventory data collection, analysis, and archiving.

Activity 1.8.1: Assess training activities in support of the BUR process to date and identify specific training needs for enterprises and/or government agencies in data collection (particularly for identified key sources and for activity data from industrial processes).  Responsible parties: PM, project experts as needed.

Activity 1.8.2: Procure and implement training in NAI software for inventory experts. Responsible parties: PM, GHG inventory management expert project experts, PA.

Activity 1.8.3: Procure and implement training for enterprises and/or agencies on data collection as necessary. Responsible parties: PM, GHG inventory management expert project experts as needed, PA.

GEF Outcome/UNDP Activity 2: Mitigation actions and their effects, including associated methodologies and assumptions, and progress of implementation are described as per the guidelines.

GEF Output/UNDP Activity 2.1: Information provided on the national arrangements to enable the identification, registration, and implementation of nationally appropriate mitigation activities (NAMAs).

Activity 2.1.1: Collect information on good practice in institutional arrangements for NAMAs in NAI countries.  Responsible parties: PM, mitigation expert.

Activity 2.1.2: Hold briefing sessions and consultations with the project board agencies and other stakeholders in order to gather input on the optimal institutional arrangements regarding NAMAs. Responsible parties: PM, mitigation expert, NAMA development expert.

Activity 2.1.3: Produce recommendations on the operations of a NAMA Designated National Authority (DNA) and submit to the UNFCCC focal point. Responsible parties: PM, mitigation expert, International expert, NAMA development expert.

Activity 2.1.4: Conduct a training needs assessment for a NAMA DNA and develop a training plan. Responsible parties: PM, International expert, other experts as needed.

Activity 2.1.5: Provide text on the progress towards national arrangements for the FBUR. Responsible parties: PM,  International expert, NAMA development expert.

GEF Output/UNDP Activity 2.2: Baseline and mitigation scenarios to the year 2040 for abatement of GHG emissions developed (energy, agriculture, transport, forestry, and waste sectors).

Activity 2.2.1: Review software, licenses, hardware, and training needs (if any) to support the updating of the mitigation scenarios. Responsible party: PM, mitigation expert.

Activity 2.2.2: Collect all relevant available macro-economic data and any new sectoral data, particularly in priority areas (district heating, energy, etc.) and identify any changes necessary in the assumptions for the business-as-usual scenario. Responsible party: mitigation expert.

Activity 2.2.3: Process the collected data, format them for entry, and enter them as required by the software utilized.  Responsible party: mitigation expert (scenarios development).

Activity 2.2.4:  Cross check scenario outputs to the year 2040 for consistency in sectors and time lines with data from other chapters. Ensure that model outputs include quantitative estimates of the impacts of both policies and measures. Responsible party: PM and mitigation expert (scenarios development).

Activity 2.2.5: Write up the scenarios and the outputs and accompanying analysis in tabular and text format for inclusion in the FBUR. Responsible parties: mitigation expert (scenarios development).

Activity 2.2.6: Circulate the write-up on mitigation for internal and external review and comments. Responsible party: PM, PA.

Activity 2.2.7: Receive comments and incorporate them into the FBUR. Responsible party: PM, PA.

GEF Output/UNDP Activity 2.3: Guidelines developed for the identification and selection criteria for NAMA projects.

Activity 2.3.1:  Draw upon the recommendations in the report drafted under 3.1.1. to propose draft guidelines for the identification and selection criteria for NAMA projects and to identify the capacity needs that would have to be met in order to carry out the guidelines effectively. Responsible party: CC policy expert, NAMA development expert.

Activity 2.3.2: Submit the draft guidelines to the Project Board and external reviewers and incorporate their feedback where appropriate. Responsible party: PM, PA.

Activity 2.3.3: Provide the draft guidelines to the UNFCCC focal point Responsible party: PM

Activity 2.3.4: Summarize work under this activity in the FBUR.  Responsible party: PM, project experts.

GEF Output/UNDP Activity 2.4:  At least three NAMAs developed (description, financial analysis, expected GHG emission reduction and monitoring plan included).

Activity 2.4.1: Conduct a workshop to introduce NAMAs to potential project developers and funders.  Responsible party: PM, NAMA development expert.

Activity 2.4.2: Support the NAMA DNA in announcing a call for NAMAs in strategic sectors and in screening submissions and working with the developers and investors in promising projects. Responsible party: PM, NAMA development expert.

Activity 2.4.3: Consider the potential for policy and program NAMAs as appropriate. Responsible party: PM, NAMA development expert.

Activity 2.4.4: Provide the necessary project development support for at least three selected NAMAs (assistance with financial analysis, emissions estimates, and monitoring plans). Responsible party: PM, NAMA development expert.

Activity 2.4.5: Provide a summary of progress on the NAMAs in the FBUR and in a public or on-line forum. Responsible party: PM, NAMA development expert.

GEF Outcome/UNDP Activity 3: National Circumstances and other information reviewed and updated

GEF Output/UNDP Activity 3.1: Updated information on features of Bosnia and Herzegovina’s geography, population, natural resources, climate and economy that may affect its ability to deal with mitigating and adapting to climate change.

Activity 3.1.1: Review existing information and check for any new developments in terms of relevant information (e.g. environmental funds, sectoral strategies, etc.), including data collected for other UN conventions. Responsible party: Project Manager (PM), Project Officer / Technical Assistant (PA).

Activity 3.1.2: Confirm links with state and entity-level statistical agencies and sectoral ministries to obtain revised demographic data and updated socioeconomic data from statistical agency reports. Responsible party: PM, PA.

Activity 3.1.3: Collect data and information from different sources as they become available in the course of project implementation, including initial census data if available. Responsible party: PM, PA, CC policy expert.

Activity 3.1.4: Fill data gaps, update and add the new information to the National Circumstances section of the FBUR. Responsible party: PM, PA, CC policy expert.Activity 1.1.5: Circulate the National Circumstances section of the FBUR for comments, receive comments, and incorporate them into the draft chapter. Responsible party: PM, PA.

Activity 3.1.6: Finalize the National Circumstances section of the FBUR. Responsible party: PM, PA.

GEF Output/UNDP Activity 3.2: Description of Bosnia and Herzegovina’s national development objectives, priorities and circumstances, and the specific needs and concerns arising from the adverse effects of climate change.

Activity 3.2.1: Check for any new developments in terms of relevant information on development objectives, priorities, and circumstances. Responsible party: PM, PA.

Activity 3.2.2: Combine these findings with other data from activities 1.1.1 and 1.1.2 and feed into the new National Circumstances section of the FBUR as per Activity 1.1.4. Responsible party: PM, PA.

Activity 3.2.3: Review data for the National Circumstances section to ensure that, wherever possible, gender disaggregated data have been included and analysed; make any necessary edits. Responsible party: CC policy expert, PM, PA.

GEF Output/UNDP Activity 3.3: Description of institutional arrangements relevant to the preparation of the national communications and biennial update reports on a continuous basis.

Activity 3.3.1: Hold consultations with the project board and other stakeholders in order to gather suggestions on the optimal institutional arrangements in the near, medium, and long term for preparing the BURs, with special attention to the collection, analysis, and archiving of activity data for the GHG inventories. Responsible party: PM, PA.

Activity 3.3.2: Draft a description of existing and planned arrangements for the preparation of the BURs to be included in the text of the FBUR. Responsible party: PM, CC policy expert.

GEF Output/UNDP Activity 3.4: Description of level of support received to enable the preparation of the BUR.

Activity 3.4.1: Use the project monitoring and evaluation plan to document the level of support received to enable the preparation of the BUR, including both grant assistance and “soft” assistance” (training and informational resources).  Responsible party: PM, CC policy expert, PA.

Activity 3.4.2: Draft text describing the level of support received for inclusion in the FBUR and for reporting and leaning processes at the UNDP country, regional, and global level. Responsible party: PM, PA.

GEF Outcome/UNDP Activity 3.5: Financial, technology and capacity building needs and support received.

Activity 3.5.1: Conduct a needs assessment for the development of the GHG inventory that considers the technology, financial, and capacity needs.   Responsible party: CC policy expert-needs and constraints.

Activity 3.5.2: Coordinate the findings and recommendations with experts working on Activities 3.3 and 3.4. Responsible party: CC policy expert.

Activity 3.5.3: Summarize the needs assessment for the FBUR and convey the results to relevant agencies. Responsible party: PM, CC policy expert-needs and constraints.

Activity 3.5.4.:  Review and report on any activities in the area of financial resources, technology transfer, capacity building and technical support received from the GEF, Annex II Parties, and other developed countries Parties, the GCF and multilateral institutions for activities related to climate change.  Responsible party: PM, CC policy expert.

Activity 3.5.5.: Update and synthesize information on how BiH is addressing activities related to technology transfer and access to environmentally sound technologies and know-how. Responsible Party: PM, CC policy expert.

Activity 3.5.6.: Report on status of technology needs. Responsible party: PM, relevant experts.

GEF Output/UNDP Activity 3.6: First Biennial Update Report published and submitted according to the guidelines contained in Annex III of Dec.2/CP.17,

Activity 3.6.1: Compile a complete draft of the FBUR with the structure and scope of the report designed as guided by relevant CoP decisions.  Responsible parties: PM, PA.

Activity 3.6.2: Circulate the draft for comments and review at the country level and incorporate them. Responsible parties: PM, experts, PA.

Activity 3.6.3: Endorse the document by the Project Board. Responsible party: PM

Activity 3.6.4: Finalize the FBUR. Responsible party: PM.

Activity 3.6.5: Commission translation and technical editing of the FBUR where necessary. Responsible parties: PM, PA.

Activity 3.6.6: Publish the FBUR in English and local language and prepare electronic copies of the FBUR in CD-ROM format. Responsible parties: PM, PA.

Activity 3.6.7: Oversee official submission of the FBUR to the CoP of the UNFCCC as necessary. Responsible party: UNFCCC focal point, PM

Activity 3.6.8: Organise a conference and presentations on FBUR methodology, findings and lessons learnt

GEF Output/UNDP Activity 3.7.:  Project financial and progress reports prepared and submitted.

Activity PM 3.7.1.: Compile documentation that conforms with UNDP-GEF requirements and CO specifications.  Responsible parties: PM, PA.

Activity PM 3.7.2: File regular reporting documents as required by UNDP-GEF and/or UNDP BiH, with corresponding updates in the Atlas Risk Log if necessary. Responsible parties: PM, PA.

Activity PM 3.7.3: Oversee financial transactions and commission financial review / audits as per regulations.  Responsible parties: monitoring and evaluation expert, UNDP BiH.

GEF Outcome/UNDP Activity 4: Domestic Measurement, Reporting and Verification arrangements are supported.

GEF Output/UNDP Activity 4.1: Identification and assessment of different options and possibilities for domestic MRV according to the national circumstances and capabilities of Bosnia and Herzegovina and taking into account the characteristics of mitigation actions and current international best practice.

Activity 4.1.1:  Prepare an overview of international recommendations and MRV practices that are currently in place for non-Annex I countries that includes: (1) a specific analysis of advantages and disadvantages (institutional, economic, etc.) for BiH; and (2) ways in which monitoring can be mainstreamed into more general environmental monitoring.  Responsible party: CC Policy - MRV expert.

Activity 4.1.2: Present the overview to the project board and relevant agencies to review its results.  Responsible party: CC Policy - MRV expert.

GEF Output/UNDP Activity 4.2: Support given to the process of development of the state and entity level institutional arrangements and framework for domestic MRV.

Activity 4.2.1: Draw upon the overview produced in Activity 5.2 to produce recommendations on the establishment of guidelines for MRV and submit these guidelines to the UNFCCC focal point. Responsible party: CC Policy - MRV expert.

Activity 4.2.2: Conduct a training needs assessment regarding MRV (and its implications for environmental monitoring more generally) and develop a training plan. Responsible party: CC Policy - MRV expert.

Activity 4.2.3: Carry out training as necessary to support the MRV activities in state and entity agencies. Responsible party: PM, CC Policy - MRV expert.

Activity 4.2.4: Provide text on the progress towards a framework for MRV for the FBUR.

Responsible party: CC Policy - MRV expert.

GEF Output/UNDP Activity 4.3: Support given to mainstreaming MRV into capacity building in environmental monitoring at the state and entity level.

Activity 4.3.1:  Use the findings from the report prepared under Activity 5.1.1 to provide specific recommendations to state and entity government agencies about how to mainstream MRV into environmental monitoring. Responsible party: CC Policy - MRV expert.

Activity 4.3.2: Identify specific capacity building measures in environmental monitoring that will benefit sectoral and/or project-based MRV. Responsible party: CC Policy - MRV expert.

Activity 4.3.3: Communicate the measures to the project experts supporting the preparation of the FBUR. Responsible party: PM, CC Policy - MRV expert.

Activity 4.3.4 Summarize MRV recommendations and activities in the FBUR.  Responsible party: PM.

B.2	Detailed Workplan

2013 2014 2015 Oct Nov Dec Jan Feb Mar Apr May Jun Jul Aug Sep Oct Nov Dec Jan Outcomes/Activities 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 Outcome 1: Updated GHG 2010 & 2011 inventory prepared Activity data collected for 2010 and 2011 1.1.1 Establish a working group on GHG emission inventory 1.1.2 Review activity data and emission factors for agriculture and LUCF 1.1.3 Develop country specific emission factors in agriculture 1.1.4 Review activity data for energy sector 1.1.5 Collect detailed and segregated data in transport sector 1.1.6 Review activity data for industrial processes 1.1.7 Review activity data for solvents use 1.1.8 Review activity data in the waste sector 1.1.9 Incorporate new data in the 2010-2011 GHG inventory 1.2 Strengthen institutional arrangements with key partners for specific sub-sectors 1.2.1 Strengthen cooperation and conclude agreements with governments and industries to collect data in energy sector 1.2.2 Strengthen cooperation and conclude agreements with governments and industries to collect data in industrial sub-sectors 1.2.3 Strengthen cooperation and conclude agreements with governments and industries to collect data in specific waste sub-sectors 1.2.4 Collect new activity data for all sectors 1.2.5 Incorporate new data in the 2010-2011 GHG inventory 1.3 Country specific emission factors for coal updated and documented 1.3.1 Review current emission factors for coal 1.3.2 Incorporate revision into 2010-2011 GHG inventory 1.4 Activity data collected for additional GHG and indirect GHG 1.4.1 Establish measurement system for all new sources 1.4.2 Identify sources of fluoric gas emissions, collect data and develop estimates if necessary 1.4.3 Identify sources of indirect gas emissions, collect data and develop estimates if necessary 1.4.4 Incorporate new data into 2010-2011 GHG inventory 1.5 Worksheets, summary tables, uncertainty management for 2010-2011 elaborated 1.5.1 Review ad update current QA/QS 1.5.2 Develop quantitative analysis of key sources and conduct sensitivity analysis 1.5.3 Undertake quantitative uncertainty assessment 1.6 2010-2011 inventory report published 1.6.1 Prepare a draft inventory using UN NAI software 1.6.2 Circulate inventory for internal and external review 1.6.3 Incorporate comments and finalize inventory 1.6.4 Archive data and update Manual of Procedures 1.7 Update summary information tables of previous inventories as necessary 1.7.1 Re-visit data from INC and SNC and make any revisions necessary given the additional activity data collected 1.7.2 Re-visit data from INC and SNC and make any revisions necessary given the new country specific emission factors developed 1.7.3 Re-visit data from INC and SNC and make any revisions necessary given data on new gases (if applicable) 1.8 Training and capacity development for key partners to support continuous data collection, analysis and archiving 1.8.1 Assess training activities in support of the BUR process and identify specific training needs 1.8.2 Implement training in NAI software 1.8.3 Implement training for enterprises and/or agencies Outcome 2: Mitigation actions, their effects and progress implementation described 2.1 Information provided on national arrangements to enable identification, registration and implementation of NAMAs 2.1.1 Collect information on good practice in NAI countries 2.1.2 Consult stakeholders in order to gather input on optimal institutional arrangements 2.1.3 Produce recommendations on the operation on NAMA DNA 2.1.4 Conduct a training needs assessment for a NAMA DNA and develop a training plan 2.1.5 Provide text on the progress for the FBUR 2.2 Mitigation scenarios to 2040 developed 2.2.1 Review software, licenses, software and training needs to support the updating of mitigation scenarios 2.2.2 Collect all relevant available macro-economic data and any new sectoral data and identify any changes necessary in the BAU scenario 2.2.3 Process the collected data in the software utilized 2.2.4. Cross check scenario outputs to the year 2040 with data from other chapters 2.2.5 Write up the scenarios and outputs and accompanying analysis 2.2.6 Circulate mitigation chapter for internal and external review 2.2.7 Receive comments and incorporate them into FBUR 2.3 Guidelines developed for the identification and selection criteria for NAMA projects 2.3.1 Draw upon the recommendations in the report drafted under 2.1.1. to propose draft guidelines for the identification and selection criteria for NAMA projects and to identify the capacity needs that would have to be met in order to carry out the guidelines effectively 2.3.2 Submit draft guidelines for to the internal and external review 2.3.3 Provide the draft guidelines to the UNFCCC focal point 2.3.4 Summarize work under this activity for FBUR 2.4 At least three NAMAs developed 2.4.1 Conduct a workshop to introduce NAMAs to potential project developers and funders 2.4.2 Support the NAMA DNA in announcing a call for NAMAs in strategic sectors and in screening submissions and working with the developers and investors in promising projects 2.4.3 Consider the potential for policy and programme NAMAs 2.4.4 Provide the necessary project development support for at least three selected NAMAs 2.4.5 Provide a summary of progress on the NAMAs in FBUR Outcome 3: National circumstances and other information reviewed and updated 3.1 Updated information on features of Bosnia and Herzegovina’s geography, population, natural resources, climate and economy that may affect its ability to deal with mitigating and adapting to climate change 3.1.1: Review existing information and check for any new developments 3.1.2: Obtain revised demographic data and updated socioeconomic data from statistical agency and institutes reports. 3.1.3: Collect data and information from different sources as they become available in the course of project implementation, 3.1.4: Fill data gaps, update and add the new information to the National Circumstances section of the FBUR. 3.1.5: Circulate the National Circumstances section of the FBUR for comments, receive comments, and incorporate them into the draft chapter. 3.1.6: Finalize the National Circumstances section of the FBUR. Responsible party: PM, PA. 3.2.: Description of Bosnia and Herzegovina’s national development objectives, priorities and circumstances, and the specific needs and concerns arising from the adverse effects of climate change 3.2.1: Check for any new developments in terms of relevant information on development objectives, priorities, and circumstances. 3.2.2: Combine these findings with other data from activities 3.1.1 and 3.1.2 and feed into the new National Circumstances section of the FBUR as per Activity 3.1.4. 3.2.3: Review data for the National Circumstances section to ensure that, wherever possible, gender disaggregated data have been included and analysed; make any necessary edits. 3.3: Description of institutional arrangements relevant to the preparation of the national communications and biennial update reports on a continuous basis. 3.3.1: Consultations with the project board and other stakeholders in order to gather suggestions on the optimal institutional arrangements in the near, medium, and long term for preparing the BURs 3.3.2: Draft a description of existing and planned arrangements for the preparation of the BURs to be included in the text of the FBUR. 3.4: Description of level of support received to enable the preparation of the BUR. 3.4.1: Document the level of support received to enable the preparation of the BUR, including both grant assistance and “soft” assistance” (training and informational resources). 3.4.2: Describing the level of support received for inclusion in the FBUR and for reporting and leaning processes at the UNDP country, regional, and global level. 3.5: Financial, technology and capacity building needs and support received. 3.5.1: Conduct a needs assessment for the development of the GHG inventory that considers the technology, financial, and capacity needs 3.5.2: Coordinate the findings and recommendations with experts working on Activities 3.3 and 3.4. 3.5.3: Summarize the needs assessment for the FBUR and convey the results to relevant agencies 3.5.4.: Review and report on any activities in the area of financial resources, technology transfer, capacity building and technical support received from the GEF, Annex II Parties etc. 3.5.5.: Update and synthesize information on how BiH is addressing activities related to technology transfer and access to environmentally sound technologies and know-how. 3.5.6.: Report on status of technology needs. GEF Output/UNDP Activity 3.6: First Biennial Update Report published and submitted 3.6.1: Compile a complete draft of the FBUR with the structure and scope of the report designed as guided by relevant CoP decisions 3.6.2: Circulate the draft for comments and review at the country level and incorporate them 3.6.3: Endorse the document by the Project Board 3.6.4: Finalize the FBUR 3.6.5: Commission translation and technical editing of the FBUR where necessary 3.6.6: Publish the FBUR in English and local language and prepare electronic copies of the FBUR 3.6.7: Oversee official submission of the FBUR to the CoP of the UNFCCC as necessary 3.6.8 Organise a conference and presentations on FBUR methodology, findings and lessons learnt 3.7.: Project financial and progress reports prepared and submitted. 3.7.1 Compile documentation that conforms with UNDP-GEF requirements and CO specifications 3.7.2 File regular reporting documents as required by UNDP-GEF and/or UNDP BiH 3.7.3 Oversee financial transactions and commission financial review / audits as per regulations Outcome 4: Domestic Measurement, Reporting and Verification arrangements are supported 4.1 Identification and assessment of different options and possibilities for domestic MRV 4.1.1 Prepare an overview of international recommendations and MRV practices that are currently in place for non-Annex I countries 4.1.2 Present the overview to the project board and relevant agencies 4.2 Support given to mainstreaming MRV into capacity building in environmental monitoring at the state and entity level 4.2.1 Draw upon the overview produced in Activity 4.2 to produce recommendations on the establishment of guidelines for MRV and submit these guidelines to the UNFCCC focal point 4.2.2 Conduct a training needs assessment regarding MRV and develop a training plan 4.2.3 Carry out training as necessary to support MRV 4.3 Support given to mainstreaming MRV into capacity building in environmental monitoring at the state and entity level 4.3.1 Provide specific recommendations to state and entity government agencies about how to mainstream MRV into environmental monitoring based on findings from the report prepared under Activity 5.1.1 4.3.2 Identify specific capacity building measures in environmental monitoring that will benefit sectoral and/or project-based MRV 4.3.3 Communicate the measures to the project experts 4.3.4 Summarize MRV recommendations and activities in the FBUR Project Management 5.1 Project Inception Activities 5.1.1 Establish technical teams 5.1.2 Update the composition of the Project Board 5.1.3 Organize a project Inception Workshop 5.1.4 Key experts identified and mobilized 5.1.5 Organize a scoping meeting 5.2 Project management activities 5.2.1 Identify and hire appropriate local experts 5.2.2 Establish regular team meetings 5.2.3 Finalize timetable for all outputs 5.2.4 Procure equipment and office facilities as needed 5.2.5 Conduct an initial overview of data, parameters, time bounds for consistency 5.2.6 Coordinate training to be provided and oversee experience sharing 5.2.7 Include project stakeholders and experts on PB and convene it at least 4 times 5.2.8 Prepare press releases on an as-needed basis and respond to public queries 5.2.9 Compile and file regular reporting documents for UNDP and GEF, incl. PIRs, and QORs 5.2.10 Compile and distribute a lessons-learned note (LLN) on the FBUR process

#### Appendix C: Terms of Reference

ToR – Project Manager

In consultation with the Project Board, the Project Manager (PM) is responsible for day-to-day management, co-ordination and supervision of the implementation of the above project. Specifically, his\her responsibilities are but not limited to the following:

- Supervises and ensures the timely implementation of the project relevant activities as scheduled in the working plan

- Prepares a detailed work plan for the project and draft terms of reference for the subcontracts (in consultation with the Project Board and UNDP);

- Compiles the scope and content of the overall FBUR report and relevant sections in consultation with Team Leaders;

- Develops the scope of the work and TORs and other procurement documentation required to identify and facilitate recruitment of experts and consultants;

- Identifies and hire/subcontract the national experts and institutions (in consultation with the Project Board and UNDP);

- Supervise project support staff national consultants who are recruited to provide technical assistance

- Organizes and supervise the workshops and training needed during the project;

- Liaises with the relevant ministries, national and international research institutes, NGOs, and other relevant institutions in order to involve their staff in project activities, and to gather and disseminate information relevant to the project;

- Prepares periodic progress reports of the project;

- Control the expenditures and otherwise ensure adequate management of the resources provided for the project;

- Summarizes and synthesizes the results of the project;

- Identifies the follow up activities and mobilizes other resources at the extend possible;

- Identifies and ensures synergy of the FBUR with other relevant ongoing / new projects.

- Finalizes the FBUR along with government personnel and national experts;

- Ensures that the FBUR process is in the line with guidance provided by the CoP of the UNFCCC and contributes to the improvement of the UNFCCC reporting process.

- Collaborates with all relevant stakeholders and the Project Board and other partners to ensure their involvement in the FBUR

- Follow the process of international negotiations in the UNFCCC and respective decisions related to reporting of non-Annex 1 Parties and particularly in relations to NAMA’s, the Registry, MRV and BUR’s.

Qualifications and Experience

- Preferably master’s degree in environment and development related studies and other related disciplines;

- Good understanding of environment/development issues in BiH as well as the three thematic areas under investigation;

- At least 5 years experience relevant to the project;

- Excellent communication (Written and Oral) Skills;

- Demonstrated experience in project management;

- Expertise in putting together costed, results-oriented action plans;

- Demonstrated experience in working with government, donors and the United Nations system;

- Substantial involvement in the preparation of the initial National Communication is an asset

- Substantial knowledge of methodologies for inventories (IPCC Revised 1996 Guidelines and Good Practice Guidance, LEAP etc)

- Familiarity with international negotiations and processes under the UNFCCC preferred

- A demonstrated ability in managing projects, and in liaising and co-operating with all project personnel including government officials , scientific institutions, NGOs, and private sector;

- Excellent knowledge of English.

ToR for Project Assistant

The Project Assistant will work under the direct supervision of the Project Manager and provide assistance to project implementation in the mobilization of inputs, the organization of training activities and financial management and reporting.

The Project Assistant will be responsible for the following duties:

Manage the day to day operations of the Project implementation unit, particularly with respect to the provision of technical services and support

- Assist the Project Manager in the implementation of technical and operational activities for the preparation of the outputs of the BUR.

- Review technical and support information on climate change studies, projects and initiatives that may contribute to the Project activities.

- Prepare the terms of reference for the international and local consultants and experts to be hired for the implementation of the project

- Assist the Project Coordinator in the selection process of the consultants to be hired by the Project according to the rules and procedures established by UNDP.

- Participate in the planning, organization and execution of Project activities.

- Organize and coordinate seminars, training activities, workshops, site visits and other exchange and facilitation events for stakeholders.

- Organize and coordinate information exchanges internationally and between participating institutions.

- Participate in the edition of the BUR report.

- Compile and/or prepare the documentation necessary for the procurement of services, good and supplies under the project

- Prepare administrative, technical and financial reports.

- Perform the procurement of services, good and supplies authorized by the Project Coordinator.

- Prepare the payment’s request as authorized by the Project Coordinator

- Assist the Coordinator to monitor disbursements in accordance to the Project Budget and Disbursement Plan.

- Maintain the Project’s files and supporting documentation for payments.

- Undertake other administrative/ financial duties as requested by the Project Coordinator

- Other duties which may be required

Qualifications and Experience

- University Degree, training in business and/or administration desirable (finance or accounting)

- At least five years administrative experience

- Good organizational skills

- Good computer skills, including spread-sheets and database

- Languages: High proficiency in English

# Footnotes

For UNDP supported GEF funded projects as this includes GEF-specific requirements

Objective (Atlas output) monitored quarterly ERBM  and annually in APR/PIR

All outcomes monitored annually in the APR/PIR.  It is highly recommended not to have more than 4 outcomes.

Summary table should include all financing of all kinds: GEF financing, cofinancing, cash, in-kind, etc...

IPCC. “Good Practice Guidance and Uncertainty Management in National Greenhouse Gas Inventories” (2001): 8.10.

# Text boxes

Programme Period:		      Oct 2013–Jan 2015

Atlas Award ID:			00075853

Project ID:			00087531

PIMS #				5250

Start date:		     	01 Oct 2013

End Date			              31 Jan 2015

Management Arrangements		NIM

PAC Meeting Date			13 Sep 2013

Brief Description

This project aims to enable Bosnia and Herzegovina to prepare and submit its First Biennial Update Report to the Conference of the Parties to the UNFCCC for the fulfilment of its obligations to the Convention under Dec. 1/CP. 16 par. 60 and Dec 2/CP. 17 par. 41 and its Annex III. The FBUR will update and strengthen information provided regarding national circumstances, greenhouse gas inventories, climate change mitigation and information on financial, technology and capacity building needs. The project will also create a set-up for domestic measurement, reporting and verification arrangements and increase the capacity to produce subsequent BURs.

Total resources required           	USD 398,000_____

Total allocated resources:		USD 398,000_____

- Regular			________________

- Other:

  - GEF			USD 352,000_____

  - Government	________________

  - In-kind			________________

  - Other			USD 30,000______

In-kind contributions		USD 16,000______

Project Manager

Project Board

Senior Beneficiary:

Ministry of Spatial Planning, Construction and Ecology RS)

Executive:

UNDP, BiH

Senior Supplier:

Other State and Entity Level Ministries

Project Assurance

UNDP RSC (Bratislava)

NCSP (New York)

Project Support

Project Organisation Structure

Inventory team

MRV Team

Mitigation team