**United Nations Development Programme**

**Country: Republic of Belarus**

**Project Document**

|  |  |
| --- | --- |
| **Project Title** | **Policy Support to the Launch of the Country Programme Document 2016-2020** |
| **UNDAF Outcome(s):** | By 2020, effective partnerships will have been strengthened between the state, civil society and private sector, ensuring reconciliation of their interests  By 2020, vulnerable groups and the population at large will have equal access to high-quality healthcare, education and social protection services that effectively address their needs |
| **Expected Country Programme Outcome(s):** | By 2020, state institutions ensure responsive, accountable and transparent governance to enable citizens to benefit from all human rights in line with international principles and standards.  By 2020, vulnerable groups and the population at large have equal access to quality health, education and social protection services that effectively address their needs, including comprehensive post-Chernobyl development |
| **Expected Output(s):** | 1) Provide advocacy support to the establishment of a National Human Rights Institution;  2) Outline a Technical Assistance Facility and provide policy advice through the National Human Development Report.  3) Support to gender mainstreaming work in the CPD.  4) Support to mainstreaming of social inclusion of people with disabilities in the CPD.  5) Provide partnership support to the CPD launch. |
| **Executing Entity:** | Ministry of Economy of the Republic of Belarus |
| **Implementing Agencies:** | United Nations Development Programme (UNDP) |

Total resources required $165,000

Total allocated resources: $165,000

* Regular \_\_\_\_\_\_\_\_\_
* Other:
  + UNDP $165,000

Unfunded budget: \_\_\_\_\_\_\_\_\_

In-kind Contributions \_\_\_\_\_\_\_\_

Programme Period: 2016-2020

Key Result Area (Strategic Plan):

1. Growth and development are inclusive and sustainable, incorporating productive capacities that create employment and livelihoods for the poor and excluded.

Atlas Award ID: \_00096449\_\_\_\_

Start date: May 2016

End Date December 2016

**Brief Description**

The UNDP in Belarus is launching its new Country Programme Document for 2016-2020. To support the implementation of the programme, several cross-cutting issues will be addressed through a number of targeted measures, in particular, with respect to human rights, gender mainstreaming, capacity development, social inclusion and partnership building. On human rights, the CO will provide advocacy support to the establishment of a National Human Rights Institution; on gender mainstreaming, an analysis of gender aspects in the current and prospective projects will be conducted along with the recommendations for improvement; on capacity development, measures will be taken to conceptualize a technical assistance facility and promote the recently launched National Human Development Report; on social inclusion, disability mainstreaming across the programme portfolios will be promoted; and on partnership building, a massive partnership building campaign will be conducted around SDGs.

Agreed by (Executing Entity):

Agreed by (UNDP):

# Work Plan

**Year: 2016**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **EXPECTED OUTPUTS**  *And baseline, indicators including annual targets* | **PLANNED ACTIVITIES**  *List activity results and associated actions* | **TIMEFRAME** | | | | **RESPONSIBLE PARTY** | **PLANNED BUDGET** | | |
| Output 1 – Provide advocacy support to the establishment of a National Human Rights Institution | Conduct a study on the feasibility of establishing a National Human Rights Institution in Belarus and disseminate the results |  |  | X | X | UNDP | UNDP |  | USD 15,000 |
| Output 2 – Outline a Technical Assistance Facility and provide policy advice through the National Human Development Report | Draft a concept of a Technical Assistance Facility for UNDP in Belarus to support national development process  Translate, publish and promote the National Human Development Report 2015 |  | X | X | X | UNDP | UNDP |  | USD 15,000 |
| Output 3 – Support to gender mainstreaming work in the CPD | Conduct gender screening of the current and planned portfolio on projects, disseminate the results |  | X | X |  | UNDP | UNDP |  | USD 10,000 |
| Output 4 – Support to mainstreaming of social inclusion of people with disabilities in the CPD | Conduct disability screening of the current and planned portfolio of projects, disseminate the results |  | X | X | X | UNDP | UNDP |  | USD 10,000 |
| Output 5 – Provide partnership support to the CPD launch | Organize a partnership building campaign around the SDGs |  |  | X |  | UNDP | UNDP |  | USD 115,000 |
| TOTAL |  |  |  |  |  |  |  |  | USD 165,000 |