Agreed by UNDP Resident Representative

| UNDP Resident Representative In Belarus Mr. Sanaka Samarasinha | Signature | Date: day/month/year |
| --- | --- | --- |

INITIATION   PLAN

for a GEF Project Preparation Grant (PPG)

- Brief Description of Initiation Plan:

During the initiation plan period, a number of studies and stakeholder consultations will be undertaken with the view to further develop the approved PIF into a fully formulated project document. The final output of the initiation plan will be a UNDP-GEF project document and GEF CEO endorsement document ready for submission to UNDP and GEF. Regular consultations (working meetings) will be carried out among the key PPG stakeholders to ensure that the PPG phase delivers the full size project document reflecting the country’s priorities in the respective fields and is in line with UNDP and GEF requirements.

UNDP Belarus will lead the project development process and manage the PPG budget. The PPG Atlas budget is presented in the Section III. “Total Budget and Work Plan”. UNDP Belarus will be responsible for the selection and recruitment of PPG consultants (local and international), developing TORs, arranging travel and meetings, maintaining project disbursements.

Quality assurance and technical advice for the full project development will be provided by the UNDP GEF Regional Technical Specialist (Istanbul, Turkey).

A PPG working group will be established to guide, review and endorse PPG outcomes. The Ministry of Environment and Natural Resources of Belarus will oversee project preparation from the Government side.

- Project preparation activities:

- Component A:  Technical review

  - Baseline studies:  This activity will involve data collection and review on the national legislative controls on the area of PCBs and POPs in general. Further it will be looking at the recent and current actions being taken in the country on sound PCB management and clarifying on the PCB inventory to enable the precise design of the future GEF project.

  - Studies to address any opportunities/risks identified during an environmental and social screening of the project proposal. The pre-screened risks are presented in the respective PIF. A detailed report will be prepared by UNDP during the PPG stage.

  - Identification of specific sites for intervention: The project team will plan for several field visits to the project stakeholders from the industry during the project preparation based on the findings on the initial mission and the PIF. Public and non-governmental stakeholders will be involved in the work on the project formulation as per usual UNDP procedures to allow as wide participation and decision-making as possible.

  - Integration with development plans, policies, budgets and complementary projects:  POPs inventory - prepare plan for the update of PCB/obsolete pesticides/ODP Inventory (all potential owners, definition of a sampling plan with priorities, analysis of phased out and in-use equipment); Sampling and testing of randomly selected equipment for better setting of baseline; Prepare scenarios for the future innovative solutions for the phasing out and sound management of PCB contaminated equipment and waste.

  - Completion of GEF focal area tracking tool:  the GEF Chemicals Tracking Tool will be prepared along with the FSP package during the submission time to the GEF.

  - Stakeholder consultations during technical review:  Mobilize and engage stakeholders during project design. Negotiate partnerships with on-going projects to align their activities and the project to build synergies.  Document these consultations.

- Component B:  Institutional arrangements, monitoring and evaluation

The outputs of Component A will be used as technical input to Component B for the formulation of the UNDP-GEF project document.

  - Finalization of project results framework:  Further define the results framework with appropriate objective-level and outcome-level quantitative and qualitative SMART indicators, and end-of-project targets.  Special attention will be made to include socio-economic and sex disaggregated indicators.

  - Definition of monitoring and evaluation (M&E):  A detailed M&E work plan will be developed, including clear identification of responsibilities and accountabilities, as well as an appropriate M&E budget. The plan will be based on the standard template provided in the UNDP-GEF project document template that reflects the mandatory requirements of the GEF M&E Policy.

  - Define sustainability plan:  The sustainability plan will outline the principles and guidelines for ensuring the long-term sustainability of project achievements. It will also outline an exit strategy, seeking the continuation of key activities/achievements without the need of long-term international financing.

  - Definition of management arrangements:  The organisational structure governing the project will be decided.  This will include identification of the project board.

  - Stakeholder consultations during Component B:  Involve key agencies in the development of the project strategy to ensure a strong national ownership. In close collaboration with key government representatives and other stakeholders ensure full participation in the development of the project results framework and ensure agreement on the project objectives and outcomes.  Undertake consultations to secure agreement(s) on project implementation arrangements, including roles, responsibilities, and accountabilities of lead and partner agencies.  Document these consultations.

- Component C:  Financial planning and co-financing investments:

- Prepare a detailed multi-year budget following the standard template provided in the UNDP-GEF project document template that reflects the mandatory requirements of the GEF M&E Policy.

- Explore multilateral and bilateral co-financing opportunities: Undertake series of consultations with partners to ensure a coherent and sustainable financing package for the project including post- GEF grant phase.

- Ensure completion of required official endorsement letters:  An official endorsement letter will be prepared by the GEF Operational Focal Point of the Government.  A co-financing guarantee will be collected from participating government institutions, bilateral development partners, multilateral development partners and NGOs who wish to provide cash or in kind contributions to the project.

- Stakeholder consultations during Component C:  Intensive stakeholder consultations will be conducted to identify storage facilities of PCB equipment, obsolete pesticides and ODP pending disposal or decontamination, assess the potential cost for this utilization; Environmentally sound technologies or services for PCB, obsolete pesticides and ODP disposal identified and assessed (collect technical and cost information from stakeholders, GEF, UNDP and other relevant databases, collecting logistical information etc.).

- Component D:  Validation workshop

An initial and a validation workshop will gather representatives from all relevant stakeholders to present, discuss and validate the final draft project document. Working meetings with stakeholders will be organised to discuss the required and proposed by the project measures to deal with the hazardous wastes under question.

Total Budget and Work Plan:

| Award ID: | 00095561 |
| --- | --- |
| Award Title: | GEF-6 Belarus POPs Legacy and Sustainable Chemicals Management Project |
| Business Unit: | UNDP Belarus CO |
| Project Title: | GEF-6 Belarus POPs Legacy and Sustainable Chemicals Management Project |
| Project ID: | 00099575 |
| Implementing Partner (Executing Agency) | UNDP |
| GEF Outcome/Atlas Activity | Responsible Party/ | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount US$ | Notes Notes |
| Project preparation grant to finalize the UNDP-GEF project document for project “GEF-6 Belarus POPs Legacy and Sustainable Chemicals Management Project” | UNDP | 62000 | GEF TRUSTEE | 71200 | International Consultants | 48,000 | 1 1 |
|  |  |  |  | 71300 | Local Consultants | 108,000 | 2 |
|  |  |  |  | 71600 | Travel | 25,000 | 3 |
|  |  |  |  | 72500 | Supplies | 4,000 | 4 |
|  |  |  |  | 75700 | Trainings | 15,000 | 5 |
|  |  |  |  |  | PROJECT TOTAL | 200,000 |  |

BUDGET NOTES:

1. GEF FINANCING FOR AN INTERNATIONAL TECHNICAL SPECIALIST TO WORK TOGETHER WITH LOCAL CONSULTANTS, UNDP CO AND NATIONAL COUNTERPARTS ON DEVELOPING THE GEF ENDORSEMENT DOCUMENT, THE UNDP PROJECT DOCUMENT AND THE RESPECTIVE TRACKING TOOLS.

2. GEF FINANCING FOR LOCAL CONSULTANCY REVIEWING REGULATORY FRAMEWORK AND IDENTIFICATION OF GAPS OF THE MANAGEMENT OF POPS, PARTICULARLY OBSOLETE PESTICIDES, PCBS AND OZONE DEPLETING SUBSTANCES, ALONG WITH DEVISING AN EFFECTIVE STRATEGY AND CONCRETE ACTIVITIES TO TACKLE THESE GAPS IN LINE WITH THE APPROVED PIF.

3-INCLUDES ABOUT 15,000 LOCAL DSA AND TRAVEL COSTS RELATED TO FIELD WORK, AND 10,000 RELATED TO COMPENSATION OF MISSIONS OF INTERNATIONAL CONSULTANT

4-INCLUDES PROCUREMENT OF STATIONARY, OFFICE SUPPLIES, FIELD CLOTHING, LABORATORY TESTS, MAP PROCUREMENT UNDER VARIOUS ASSIGNMENTS OF LOCAL CONSULTANTS TO ENABLE THEM TO IMPLEMENT THEIR TASKS AS PER TORS

5-INCLUDES TWO WORKSHOPS – INITIAL AND VALIDATION, AND FOUR WORKING MEETINGS WITH NATIONAL STAKEHOLDERS.

Annex 1:  GEF CEO PIF approval letter

Annex 2:  Summary of Consultants Financed by the Initiation Plan

| Summary Tasks to be Performed | Daily Rate, USD | # working days |
| --- | --- | --- |
| Local Consultants |  |  |
| Consultant on Chemicals Management Policy – National Team Leader |  | 75 |
| Consultant on PCBs |  | 50 |
| Consultant on POPs |  | 50 |
| Consultant on ODS |  | 35 |
| Consultant on Human Health |  | 30 |
| Consultant on Chemicals Monitoring |  | 40 |
| Consultant on Environmental Legislation |  | 25 |
| Assistant |  | 51 |
| International consultants |  |  |
| Project Development Specialist |  | 48 |

# Text boxes

Total budget:		 US$ 200,000

Allocated resources:

- GEF		 	US$ 200,000

Country Programme Component: Growth and development are inclusive and sustainable, incorporating productive capacities that target employment and create livelihoods for vulnerable groups

ATLAS Project Award: 		00095561

ATLAS Project ID: 		00099575

PIMS Project ID: 			5532

Management Arrangement: 	DIM

Project Title:  Initiation Plan - GEF-6 Belarus POPs Legacy and Sustainable Chemicals Management Project

Country: Belarus

Initiation Plan Start Date: 1 May 2016

Initiation Plan End Date: 31 August 2017