UNITED NATIONS DEVELOPMENT PROGRAMME

UNITED NATIONS DEVELOPMENT PROGRAMME

INCEPTION REPORT

UNDP/GEF Project

"Initial Implementation of Accelerated HFCF Phase Out in the CEIT Region"

Republic of Belarus

Full sized project

November 2013

MINSK

PROJECT OVERVIEW

TABLE OF CONTENTS

A.	PROJECT UPDATE	5

1.	PROJECT OVERVIEW	5

3.	PROJECT UPDATE ANALYSIS	6

3.1.	Project Implementation Period	6

3.2.	Stakeholder Analysis	6

3.3.	Project Goal, Objectives, Outcomes and Outputs/Activities Overview	6

3.4.	Project Indicators, Risks and Assumptions	6

3.5.	Revised Detailed Work Plan and Budget	7

3.6.	Schedule For Project Reviews, Reporting and Evaluation	7

B.	INCEPTION WORKSHOP RECOMMENDATIONS AND PROJECT FOLLOW-UP	8

4.	Cooperation with Stakeholders	8

5.	Lessons Learned from Previous Project Implementation	8

C.	ANNEXES	10

Annex I.	10

INCEPTION WORKSHOP AGENDA	10

Annex II.	12

INCEPTION WORKSHOP PARTICIPANTS LIST	12

Annex III	17

INCEPTION WORKSHOP MINUTES	17

Annex IV.	23

ANNUAL DETAILED WORK PLAN 2013	23

LIST OF ACRONYMS AND ABBREVIATIONS

| ADWP | Annual Detailed Work Plan |
| --- | --- |
| CEIT | Countries with Economies in Transition |
| GEF | Global Environmental Fund |
| HFCF | Hydrochlorofluorocarbons |
| MNREP | Ministry of Natural Resources and Environment of the Republic of Belarus |
| MP | Montreal Protocol |
| UNDP | United Nations Development Programme |
| PB | Project Board |
| PSC | Project Steering Document |

# PROJECT UPDATE

## PROJECT OVERVIEW

The UNDP / GEF Project "Initial Implementation of Accelerated HFCF Phase Out in the CEIT Region" is a response to the obligations incurred by Belarus as CEITs (non-Article 5) under the phase out schedule for HCFC of the Montreal Protocol (MP), as amended by the Copenhagen amendment and Decision XIX/6. The Project is implemented by the United Nations Development Programme (UNDP) with the Ministry of Natural Resources and Environment Protection of the Republic of Belarus acting as the Executing Entity. The Global Environmental Fund (GEF) finances the project.  The total allocated resources (budgeted amount) is US$2,200,000.

The Project aims to speed up the phase out of facilitate phasing out ozone depleting substances, particularly hydrochlorofluorocarbons ( HCFCs) and their substitution with modern alternative substances in accordance with the respective Belarus’ obligations under the Montreal Protocol, along with strengthening the system of import control and management of HCFCs in Belarus. The project targets support to the adoption of the fully completed HCFC phase-out strategy (with selected legislative options to control HCFC import/use), capacity building and supply of analytical and servicing equipment/tools for the Environmental Inspectorate and Customs Departments and refrigeration technicians, technological conversions for solvents and rigid foams, modernization of HCFC re-use scheme in the country and demonstration of alternative technologies in refrigeration equipment and A/C sectors, pilot small-scale ODS destruction, the current absence of effective regulatory instruments and need to support ongoing institutional development.

- PROJECT INCEPTION ACTIVITIES

Project implementation started in August 2013. During the period passed since that time the following steps were undertaken:

- UNDP in Belarus established the Project Implementation Unit (PIU) including the following positions: the Project Manager, Scientific Coordinator and Administrative/Finance Assistant. The appointments to the said positions were done following UNDP rules and resulting from open competitive procedures.

- MNREP provided premises for Project Office located in Minsk at the address: Room 111, 16 Komsomolskaya Str., 220030. Phone/fax: +375 (17) 306 04 52. UNDP in Belarus fully equipped the office with furniture, computers and other office machines under the Project funds. Procurement of the office furniture and equipment was conducted following UNDP procurement rules and procedures and within the allocated budget.

- The Project team has revised the detailed work plan and the project budget provided in the Project Document. Because of late actual project start date most activities are shifted in time schedule to later period. Project Procurement Plan for the period till end-2013 was developed and approved accounting for the revised Detailed Annual Work Plan.

- The project has initiated procurement of six (6) sets of audio and visual aids for the training institutions that will provide premises for training workshops and seminars to be conducted within the Project framework.

- Two representatives of the National Partner: one from the MNREP and the second one from non-governmental organization, - participated in the Thematic Meeting on HPMPs: Progress in Implementation of Prioritized Activities and Opportunities/Barriers in Introduction of Low or Zero GWP alternatives to HCFCs,- conducted by the Multilateral Fund for the Implementation of the Montreal Protocol and UNEP in Bishkek, Kyrgyzstan in the period of 24-26 September 2013. Besides, Programme Analyst, Project Manager and Scientific Coordinator participated in the Regional Project Inception Workshop, which took place in Bratislava on 04 November – 05 November 2013.

- Members of the Project Steering Committee (PSC) including representatives of Ministry of Environment, UNDP and main stakeholders were assigned and informed on Project current status. The first PB meeting will take place in December 2013.

- Inception Workshop was held on October 25, 2013 at the Business Center “Stolitsa” (Viktoria Hotel) in Minsk. The workshop was aimed at introducing the Project to the main stakeholders and ensuring clear understanding by the project team, governmental officials, customs officers and cold industry professionals of the specific project instruments and in what way they could contribute to the national efforts on implementation of the obligations under the Montreal Protocol undertaken by the Government of the Republic of Belarus.

Annex I presents the detailed Workshop Agenda.  32 people included the Government Ministries, State Entities and UNDP Focal Points, the Project National Coordinator, Project Implementation Unit staff, senior staff specialists of the industrial enterprises, educational and scientific research institutions, non-governmental organizations dealing with ODS consumption and phase out issues as well as mass media representatives participated in the workshop. The list of participants is provided in Annex II.

## PROJECT UPDATE ANALYSIS

### Project Implementation Period

The Project is designed as full-size project for 3-years implementation period. However, the registered project duration period is 20/05/2013 – 19/08/2015, which is, only 27 months long. Actually, the Project started in August 2013.

### Stakeholder Analysis

The project will be implemented in close coordination and collaboration with relevant government institutions, regional authorities, industries, public and local authorities and NGOs, as well as with other related relevant projects in the region through enhanced networking. List of main stakeholders and their roles is presented in Project Document (article 1.3. Stakeholder Analysis, p. 18). Most stakeholder representatives participated in the Inception Workshop (refer to the List of Participants, Annex II). They evidenced their proper understanding of the Project goal, purposes and objectives as well as their interest in Project implementation.

### Project Goal, Objectives, Outcomes and Outputs/Activities Overview

The Project design, viz. its goal, objectives, outcomes and outputs/activities framework as presented in the Project Document need no corrections as at the current status.

### Project Indicators, Risks and Assumptions

The Strategic Results Framework provides an overview of impact and process indicators for project implementation along with their corresponding means of verification, and as such it forms basis for the Project’s M&E system.

Potential risk in timely project implementation is identified because of the shortened implementation period as mentioned in article 4.1 above. In order to mitigate such risk the Project Implementation Schedule, Work Plan and Budget are revised correspondently as described further in this Report.

### Revised Detailed Work Plan and Budget

PIU has revised Detailed Work Plan and budget for 2013 -2015. Lower budget in year 2013, is due to less activity level in the upstart period. The total amount allocated for each project output/outcome activities remains without any change as seen in the below table:

Table 1.

| Project Outcome/Activity | Amount planned by years, USD |  |  |  |  |  | Total funds (USD) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Year 2013 |  | Year 2014 |  | Year 2015 |  |  |
|  | Pro Doc | 1st rev. | Pro Doc | 1st rev. | Pro Doc | 1st rev. | Pro Doc = 1st rev. |
| OUTCOME 2: HPMP, National Level Capacity Strengthening and HCFC Phase Out Investment | 879,800 | 27,000 | 658,000 | 1,204,000 | 427,200 | 734,000 | 1,965,000 |
| OUTCOME 3: M & E | 0 | 0 | 15,000 | 15,000 | 20,000 | 20,000 | 35,000 |
| OUTPUT 4: Project Management Component (PMC) | 77,000 | 42,900 | 64,000 | 90,000 | 59,000 | 67,100 | 200,000 |
| TOTAL FOR NATIONAL COMPONENT (W/O PMC) | 879,800 | 27,000 | 673,000 | 1,219,000 | 447,200 | 754000 | 2,000,000 |
| PROJECT TOTAL: | 956,800 | 69,900 | 737,000 | 1,309,000 | 506,200 | 821,100 | 2,200,000 |

The revised detailed annual work plan for 2013 is presented in Annex IV. It is approved by the MNREP and the UNDP.

### Schedule For Project Reviews, Reporting and Evaluation

Accounting for the revised Project Implementation Schedule (see article 4.6 above) the following schedule for Project reviews, reporting and evaluation is introduced:

| Activity (per quarter) | Year 2013 |  |  |  | Year 2014 |  |  |  | Year 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | I | II | III | IV | I | II | III | IV | I | II | III | IV |
| Inception workshop |  |  |  | Oct |  |  |  |  |  |  |  |  |
| Inception report |  |  |  | Nov |  |  |  |  |  |  |  |  |
| GEF quarterly reports |  |  | Oct |  | Jan | Apr | Jul | Oct | Jan | Apr |  |  |
| Providing data to MNREP for progress report to Mineconomy |  |  |  |  | Jan |  | Jul |  | Jan |  | Jun |  |
| Annual progress report |  |  |  |  | Jan |  |  |  | Jan |  |  |  |
| TPR |  |  |  |  | Jan |  | Sep |  | Jan |  |  |  |
| PIR |  |  |  |  |  |  | Aug |  |  |  | Aug |  |
| Mid-term Evaluation |  |  |  |  |  |  |  | Nov |  |  |  |  |
| Final Evaluation |  |  |  |  |  |  |  |  |  | June |  |  |
| Terminal Report |  |  |  |  |  |  |  |  |  |  | Aug |  |

Conclusions: The proposed changes and/or updates have no significant impact on Project design as a whole. Therefore, no necessity to revise project document is revealed as at the current status.

# INCEPTION WORKSHOP RECOMMENDATIONS AND PROJECT FOLLOW-UP

The project document was basically approved by the inception workshop on 25 October 2013. Comments and recommendations are provided in Annex III, Minutes).

The workshop applauded the project start and recommended to launch its main activities as soon as possible. The stakeholders awaited the Project to start in 2012. Now there is critical need to make all efforts possible to make up for the lost period.

PIU has revised detailed work plan and budget for the period 2013-2015. According to the revised ADWP the project team’s work during the first year will basically focus on administrative issues, such as project office management activities, planning and selecting technical experts who will develop detailed technical specifications on the basic equipment to be procured in the next year.

## Cooperation with Stakeholders

The workshop highlighted importance of close cooperation of the Ministry of Natural Resources and Environmental Protection, the Ministry of Trade, the Ministry of Food and Agriculture, the State Customs Committee, other governmental entities as well as non-governmental organizations,  private and public sector enterprises involved in project implementation. The workshop applauded the initiatives and recommendations referring improvement of national regulation and legislation system in the field of HCFC import and trade control that were announced by a number of participants. However, the MNREP needs them to be submitted in the written form in order to push them further for governmental approval.

PIU could act as an intermediary agent for collecting all the proposals, initiatives, recommendations, etc. referring the issues related to the project act, summarizing them and providing for MNREP consideration.

## Lessons Learned from Previous Project Implementation

The workshop recommended to the project team to take advantage of the lessons learned from previous project aimed at CFC phasing-out in the country. As an example, some items of the new equipment purchased under the previous project is not in operation at the moment because of lack of post-warranty service and spare parts. In other cases, it is not used because there is no relevant standards in the country according to which it would be calibrated and/or certified. PIU will take due notice of the said lessons and pay due attention to the said issues while purchasing the tools and equipment under the project funds.

Lessons learned from implementation of the previous are as follow: (i) procurement of the equipment and tools shall be linked to the requirements of  Gosstandard of the Republic of Belarus, e.g. measuring tools and systems are to be certified in Belarus; (ii) when organizing training special attention shall be paid to the choice of trainees so that the targeted specialists undergo training but not those who are in no way related to the subject; (iii) the previous project failed to reach the technicians working at various enterprises (about 3 thousand people) since there’s no reester and no records on personnel engaged in cold industry sector; (iv) while purchasing equipment it is necessary to provide conditions for its post-warranty service and maintenance in order to prolong its total life cycle duration; (v) the targeted recycling indicators were not achieved because of low consumers’ activity in returning freon for recycling caused by certain reasons (time and costs burden); instead of planned 20 tons there were actually only 12 tons returned though the installed recycling equipment is in perfect operating conditions; thus, it is obvious that there’s need in specific law governing the behavior of HCFC consumers. The present project will be more successful if it accounts for the lessons learned from the previous one.

# ANNEXES

## Annex I.

## INCEPTION WORKSHOP AGENDA

| AGENDA |  |  |
| --- | --- | --- |
| 9:00 – 9.30 | Registration of the participants |  |
| 09:30 – 09:50 | Workshop Opening. Welcome Speech. | Sergei ZAVYALOV, Head of Air and Water Resources Management Division, Ministry of Nature and Environment of the Republic of Belarus Igor TCHOULBA Programme Analyst, UNDP in Belarus Maksim Surkov Programme Specialist, Regional Bureau fir CIS and Europe, Bratislava |
|  | Part 1: Background Analysis and Project Strategy |  |
| 09:50 – 10:10 | International Obligations of the Republic of Belarus on Ozonedepleting Substances (HCFCs) Phase-Out and Implementation Strategy | Sergei ZAVYALOV, Head of Air and Water Resources Management Division, Ministry of Nature and Environment of the Republic of Belarus |
| 10:10 – 10:30 | Capacity Strengthening and HCFC Phase-Out in the Region | Maksim Surkov Programme Specialist, Regional Bureau fir CIS and Europe, Bratislava |
| 10.30- 10.50 | GEF/UNDP Project “Initial Implementation of Accelerated HCFCs Phase-Out in CEIT Region | Liudmila TRATSEVSKAYA Project Manager, UNDP in Belarus |
| 10:50 – 11:10 | Coffee Break |  |
|  | Part 2: Совершенствование системы подготовки и переподготовки специалистов по обслуживанию холодильного оборудования, сотрудников таможенных органов и служб экологического контроля и надзора |  |
| 11:10 – 11:20 | Improvement of HCFC Import Control Measures System | Oleg FEDOTOV Head of Administration State Customs Committee of the Republic of Belarus |
| 11.20 - 11.30 | Training in HCFC Consumption Control Methods On the Basis of National Training Center | Vladimir GERASIMOV Director, National Training Center of Environment Staff |
| 11:30 – 11:45 | APIMH Association Approaches to Compulsory Certification System Creation and Refrigerating Equipment Service Technicians Training | Vasilij VOLKOV Deputy Chairman, Association of Microclimate And Cold Industry Enterprises (APIMH) International Cold Academy Associate Member |
|  | Part 3: Demonstration Projects Implementation |  |
| 11.45 -12.10 | Rational Use of HCFC Ozone Safe Alternatives. Implementation of Demonstration Projects Aimed at HCFC Phase-Out. | Aleksandr BAMBIZA Project Scientific Coordinator, UNDP in Belarus |
| 12.10-12.20 | Foam Agent Production Technology Update at “MAZ-Kupava” Works | Viktor VASILIVSKIJ Deputy General Director, Chief Engineer MAZ-Kupava, OOO |
| 12.20-12.30 | Conversion to New Solvents Composition | Sergei AVDEICHUK Chief Engineer, David-Gorodok Electromechanical Plant |
| 12.30-13.30 | DISCUSSIONS: Implementation of Demonstration Projects on Cold Equipment Substitution with Use of Alternative Technologies, Creation of HCFC Regenerating Infrastucture, Re-Use and Utilisation. Proposals on the Appropriate Project Document Amendments (if required) | Workshop Participants (voluntary speakers) |
| 13.30 | SUMMARY AND WORKSHOP CLOSING |  |

## Annex II.

## INCEPTION WORKSHOP PARTICIPANTS LIST

| Nr. | Entity, position | Name | Contact Details |  |
| --- | --- | --- | --- | --- |
| MINISTRY OF NATURAL RESOURCES AND ENVIRONMENT |  |  |  |  |
|  | Project National Coordinator, Head of Air and Water Resources Management Division | SERGEI ZAVYALOV | Phone: e-mail: | (017) 200-60-48 2006048@tut.by |
|  | Consultant | NATALIA KLIMENKO | Phone: e-mail: | (029)604-6-179 klimenko.natasha@tut.by |
| UNITED NATIONS DEVELOPMENT PROGRAMME |  |  |  |  |
|  | Programme Specialist, Regional Bureau for Europe and CIS in Bratislava | MAKSIM SURKOV | Phone: e-mail: | +421-2-59337-423 maksim.surkov@undp.org |
|  | Programme Analyst, UNDP Belarus | IGAR TCHOULBA | Phone: e-mail: | (017) 210-40-63 igar.tchoulba@undp.org |
|  | Project Manager, Project Implementation Unit, UNDP Belarus | LIUDMILA TRATSEVSKAYA | Phone: e-mail: | (017) 306-04-52 (044) 575-60-44 liudmila.tratsevskaya@undp.org |
|  | Scientific Coordinator, Project Implementation Unit, UNDP BELARUS | ALEKSANDR BAMBIZA | Phone: e-mail: | (017) 306-04-52 aleksandr.bambiza@undp.org |
|  | Administrative and Finance Assistant, Project Implementation Unit, UNDP Belarus | GALINA BOLSHAKOVA | Phone: e-mail: | (017) 306-04-52 (029) 671-86-40 galina.bolshakova@undp.org |
| STATE CUSTOMS COMMITTEE |  |  |  |  |
|  | Head of Department | OLEG FEDOTOV | Phone: | (017)218-90-71 |
| TORGTEKHNIKA, UNITARY ENTERPRISE |  |  |  |  |
|  | Deputy Chief Engineer | SEGEI STAKHNO | Phone: | (017) 226-32-43 |
| BELTORGPROGRESS, RPO |  |  |  |  |
|  | Chief Engineer | NIKOLAI BRUSHKOV | e-mail: | direktor@torgprom.by |
| BELARUSIAN REPUBLICAN UNION OF CONSUMER SOCIETIES “BELKOOPSOUZ” |  |  |  |  |
|  | Head, Technical Development and Transport Department | ROSTISLAV ERMOLENKO | Phone: e-mail: | (017) 226-91-07 techno@bks.by |
| «ANEROMKHOLOD», UNITARY ENETRPRISE |  |  |  |  |
|  | Chief Engineer | VIKTOR NOVIKOV | Phone: e-mail: | (017)210-23-91 office@anerom.by |
| AUTOMOBILE TRAILERS AND BODIES PLANT «MAZ-KUPAVA», JSC |  |  |  |  |
|  | Deputy General Director, Chief Engineer | VIKTOR VASILЕVSKIJ | Phone: | (017) 343-56-98 |
| «DAVID-GORODOK ELECTROMECHANICAL PLANT», JSC |  |  |  |  |
|  | Chief Engineer | SERGEI AVDEICHUK | Phone: Phone: e-mail: | (0165)51- 2 -68 (029) 315-18-97 david@brest.by |
| «KHOLODON», CJSC |  |  |  |  |
|  | General Director | VLADIMIR LUKONIN | Phone: e-mail: | (029)622-7-890 |
| «KHLADAGENT», PRIVATE ENTERPRISE |  |  |  |  |
|  | Director | VASILILIJ PIPIK | Phone: e-mail: | (029) 252-75-26 hladagent@tut.by |
|  | Deputy Director | DMITRIJ AKULICH | Phone: e-mail: | (029) 540-21-62 hladagent@tut.by |
| «LAMINAR», SCIENTIFIC AND PRODUCTION PRIVATE UNITARY ENTERPRISE |  |  |  |  |
|  | Director | ALEKSAND BOROZDIN | Phone: e-mail: | (029)610-06-10 info@laminar.by |
| ASSOCIATION OF MICROCLIMATE AND COLD INDUSTRY ENTERPRISES (APIMH) |  |  |  |  |
|  | Deputy Chairman, International Cold Academy Associate Member | VASILIJ VOLKOV | Phone: e-mail: | (017) 392-98-72 vasilii_volkov@mail.ru |
|  | Deputy Director | EKSTERINA CHERNOSHEI | Phone: e-mail: | (029) 607-99-71 apimh@tut.by |
| «GASPROMTRANSGAS BELARUS» JSC |  |  |  |  |
|  | Head of Environment Protection Administration | DMITRIJ ABRAMOVICH | Phone: e-mail: | (029) 691-99-98 dim_ab@tut.by |
| BELARUSIAN NATIONAL TECHNICAL UNIVERSITY |  |  |  |  |
|  | Head of Chair | VIKTOR BASHTOVOJ | Phone: e-mail: | (029) 326-17-23 bashv@rambler.ru |
| «NATIONAL CENTER OF VOCATIONAL ADVANCED TRAINING, THE MINISTRY OF NATURAL RESOURCES AND ENVIRONMENT» STATE EDUCATIONAL ENTERPRISE |  |  |  |  |
|  | Director | VLADIMIR GERASIMOV | Phone: | (029) 691-06-14 |
| MINSK STATE VOCATIONAL SCHOOL NO. 8 OF PROCESSING INDUSTRY, EDUCATIONAL ENTERPRISE |  |  |  |  |
|  | Director | VLADIMIR MAKEDON | Phone: | (044) 551-30-51 |
| «POLOTSK COMMERCE AND TECHNOLOGY COLLEGE OF THE BELARUSIAN REPUBLICAN UNION OF CONSUMER SOCIETIES» EDUCATIONAL ENTERPRISE |  |  |  |  |
|  | Teacher | VLADIMIR TIKHONENKO | Phone: | (0214) 42-54-26 |
| «INSTITUTE OF POWER AND NUCLEAR RESEARCH-SOSNY OF THE NATIONAL ACADEMY OF SCIENCES OF BELARUS” STATE ENTERPRISE |  |  |  |  |
|  | Senior Staff Scientist, Professor, Doctor of Technical Sciences, International Cold Academy Member | BORIS TIMOFEEV | Phone: | (029) 556-83-45 |
| «EKOLOGIA» BELARUSIAN RESEARCH CENTER" NATIONAL UNITARY ENTERPRISE |  |  |  |  |
|  | Senior Staff Scientist | OLGA VAVILONSKAYA | Phone: e-mail: | (017) 247-65-43 olgavavilonskaya@mail.ru |
|  | Junior Research Scientist | EKATERINA LUSHNOVA | Phone: | (017)247-65-43 |
| «NATIONAL SCIENTIFIC RESEARCH CENTER OF OZONE SPHERE MONITORING» BELGOSUNIVERSITY ENETRPRISE |  |  |  |  |
|  | Director | LEONID TURNYSHEV | Phone: Phone: e-mail: | (017) 212-53-12 (029) 256-41-2 turishevln@tut.by |
| «MICROCLIMATE AND COLD» JOURNАL EDITORIAL OFFICE |  |  |  |  |
|  | Chief Editor | ANDREI KIREENKO | Phone: e-mail: | (029) 335-51-00 prodby@mail.ru |
| «BELTA» UNITARY ENTERPRISE |  |  |  |  |
|  | News Writer | MARIA DMITRIEVA | Phone: e-mail: | (029) 665-62-21 maree.journalist@mail.ru |
| «PEOPLE NEWSPAPER» JSC |  |  |  |  |
|  | Reviewer | ELENA YASNO | Phone: e-mail: | (017) 287-10-60 a_yasno@ng.by |

## Annex III

## INCEPTION WORKSHOP MINUTES

The Agenda of the Inception Workshop is included in Annex I. There were 32 participants present at the workshop. The participants included the Government Ministries, State Entities and UNDP Focal Points, the Project National Coordinator, Project Implementation Unit staff, senior staff specialists of the industrial enterprises, educational and scientific research institutions, non-governmental organisations dealing with ODS consumption and phase out issues as well as mass media representatives. The list of participants is provided above.

INTRODUCTIONS

Mr. Sergei Zavyalov, Head of Air and Water Resources Management Division, Ministry of Nature and Environment of the Republic of Belarus and Project National Coordinator opened the workshop by welcoming all the participants. He highlighted the active role of the Government of the country in ozone layer protection at the global level, the achievements in this field resulted from implementation of the previous projects as well as significance of the forthcoming targets. He recalled the difficulties for the country to solve problems with the national HFCF Phase-Out Strategy development, and stressed the importance and value of everybody present at the seminar in helping to solve these problems. The Project is launched in due time and is considered to be very supportive to the national strategy of HFCF phase-out in accordance with the country’s obligations under the Montreal Protocol and its four consequent amendments.

Mr. Maksim Surkov, Programme Specialist, UNDP Regional Bureau in Bratislava gave an introduction on how this project forms part of the regional portfolio and pointed out the significance of the project for implementation by all the involved countries: Belarus, Ukraine, Tajikistan and Uzbekistan. He mentioned that almost two years had passed since the Project approval date. Main delays were caused by the situation in the Ukraine, the country had lost much of its potential capacity during this period. He expressed his much hopes for proper communication between the countries in the region and wished success to the project.

Mr. Igar Tchoulba, Programme Analyst, UNDP in Belarus highlighted in his welcome speech that the project is aimed primarily at solving the current problems and he actually hopes for active involvement of everybody present at the seminar in today’s discussions and in project implementation as a whole.

After the introductory remarks all participants of the Inception Workshop introduced themselves by name and represented organization.

PART A: CURRENT SITUATION ANALYSIS AND PROJECT STRATEGY

“International Obligations of the Republic of Belarus on Ozone Depleting Substances (ODS) /HCFCs Phase-Out and Implementation Strategy”

Mr. Sergei Zavyalov, Head of Air and Water Resources Management Division, Ministry of Nature and Environment of the Republic of Belarus.

Ozone layer protection issues have always been under the care of the Government of the Republic of Belarus. The country has never produced but consumed ODS, and as such it signed a number of international agreements on ozone layer protection, the most important of which are the Vienna Convention (March 1985) and the Montreal Protocol (1987) with four consequent amendments: London 1990, Copenhagen 1992, Montreal 1997 and Peking 1999. Belarus was the first country at the territory of the Former Soviet Union that adopted the national Ozone Layer Protection Law (Law Nr.56-3 dated 12 November 2001). The country successfully fulfils its obligations undertaken under the said international agreements in due time and manner.

By the current moment, the country has developed and approved its National Strategy on HCFC Phase-Out by 2020. The present Project will contribute much to the achievements targeted by the Strategy Documents. Therefore, the Ministry of Nature fully support the project and appreciate the international efforts to assist the country.

“Capacity Strengthening  and HCFC Phase-Out in the Region”

Mr. Maksim Surkov, Programme Specialist, UNDPRegional Bureau in Bratislava

At present, the Regional Project is approved by GEF and its implementation has started in all the countries. Certain delays in project development were caused by the persistent institutional changes in the Ukraine. Incompliance justifications were provided to the Montreal Protocol Committee as well as adjusted phase-out schedule aimed at the compliance regimen reconstruction.

National project components are partially similar to such in other national projects that encourages the participating countries for experience and knowledge sharing. Regional Component of the project will be used as the platform for inter-government consultations and institutional building improvement.

“GEF/UNDP Project “Initial Implementation of Accelerated HCFCs Phase-Out in CEIT Region”

Ms. Liudmila Tratsevskaya, Project Manager

Its main goal is to implement activities aimed at the phase out of transaction ozone depleting substances (HCFCs) and their substitution by modern alternatives in accordance with the obligations of Belarus under the Montreal Protocol as well as improvement of the in-country HCFCs import and consumption management system. The purpose of this project is to ensure compliance of the country with the phase-out schedule approved by the Montreal Protocol as well as with the requirements of the European Union in relation to ODS use for providing access to the international markets for the local refrigeration and other equipment manufacturers and vehicles. The Project structure, budget and planned activities are designed for achieving the targeted goal.

Due to delay in project actual starting point significant changes were introduced into the Project Detailed Working Plan. Most activities planned for 2013 are shifted to the later period. The revised working plan is presented for consideration and further approval by the Ministry of Nature and the UNDP.

However, successful implementation of the project is conditioned significantly by active involvement of all the stakeholders, their competence and initiative. The project team encourages any proposals related to the project implementation to be addressed to the PIU and promises to treat them with due attention and care.

PART B: PROFESSIONAL TRAINING AND ADVANCED TRAINING IMPROVEMENT

“Improvement  of HCFC Import Control Measures System”

Mr. Oleg Fedotov, Head of Department, State Customs Committee

Crimes against the environment safety is multimillion business that is difficult to withstand. Borders of the Republic of Belarus are actually the only barrier line where an illegal traffic to the territory of the Customs Union (which is the area from the Atlantic to the Pacific Oceans) could be stopped.

The system of customs control at the borders consists of the following components:

- documents check;

- check against the list of forbidden ODS, list of licensed ODS;

- marking/labeling check;

- check of quota limits, licenses;

- technical control.

Volume of illegal import to Belarus is insignificant if compared with the Asian countries. However, in order to fulfil control over ODS import effectively it is necessary harmonize the legislations of three customs union member countries.

Besides, there is critical need in technical tools and equipment. Currently there is no possibility to conduct ODS search and chemical analysis at the border because of lack of specialized equipment. In this connection, the first priority demand is in purchasing of the advanced refrigerant identifiers and also, in case of budget availability, a modern gas chromatographymass spectrometer (GCS) for  the Customs  laboratory .The said equipment could provide for exact identification of ODS in short time and taking further actions by the customs entities as appropriate.

One more aspect is insignificant knowledge and skills of the customs inspectors and officers.

“Training in HCFC Consumption Control Methods On the Basis of National Training Center”

Mr. Vladimir Gerasimov, Director, National Training Center of Environment Staff

The National Training Center deals with advanced professional training in the field of environment protection and ecology, including the issues of HCFC phase-out. During the recent period over 300 specialist have been trained on this subject. Training was conducted at the premises of the National Center as well as at the working sites. Experience of the industrial enterprises and production works was also used as well as training materials.

In relation to the training component of the Project he highlighted that the trainees categories and sites should be clearly identified and considered.

National Training Center is constantly strengthening its technical basis. A new building will be soon built and put into operation. It will house not only study rooms but conference hall, library as well as hotel and café. Thus, the project contribution by providing equipment for one of the classes would be appreciated and used for the purposes of project implementation.

“APIMH Association Approaches to Compulsory Certification System Creation and Refrigerating Equipment Service Technicians Training”

Mr. Vasilij Volkov, Deputy Chairman, Association of Microclimate And Cold Industry Enterprises (APIMH)

APIMH is a non-governmental and non-commercial organization that unite professionals in the field of cold industry at the voluntary basis. The association exists since 2004 and target its activity at home cold industry development, protection of the national market from low quality products and promoting high quality products to the local and foreign markets.

One of the main issues of ozone layer protection is to prevent the environment from HCFC leakage during the whole life cycle of the equipment and after its end. In this regards it is very important (i) to create in-country training and certification system for professionals in the climate, cold and other industries; (ii) the create and introduce National Technicians Roster; (iii) to develop new training programmes and to update the existing ones; and (iv) to conduct training and certification of the technical specialists with entering the corresponding data into National Technicians Roster. Certification is considered to be a voluntary procedure. However, it is necessary to adopt the legislative document forbidding non-certified specialists to work with HCFC and other ODS. Certification is to be conducted basing on the national standard that is to be developed and introduced. It is considered to be reasonabe to harmonize the national standard with European one, viz. EN 13313:2010 “Cold Systems and Warm Pumps. Personnel Competence.”

APIMH uses journal “Microclimate and Cold” as information platform for wide distribution of HFCF phase out knowledge and popularizing these ideas. The journal could eagerly provide information platform for project use as well.

PART C: DEMONSTRATION PROJECTS IMPLEMENTATION

“Rational Use of HCFC Ozone Safe Alternatives. Implementation of Demonstration Projects Aimed at HCFC Phase-Out”

Mr. Aleksandr Bambiza, Project Scientific Coordinator, UNDP in Belarus

Currently the following four HCFC are used in Belarus: HFCF-21, HCFC-22, HCFC-141b and HCFC-142b. The Investment Programme supports the following activities aimed at timely HCFC phase-out: (1) Stop of use of HCFC in industrial sector for foam materials production and as solvents; (2) Demonstration of technologies of producing cold with low ozone depleting potential and high energy effectiveness; (3) Refrigerant Management  System Development.

The choice of enterprises for demonstration projects will be done basing on a number of factors, including the following: (i) technical specifications of the equipment (quantity of used refrigerants); (ii) direct impact of the chosen  equipment on the climate; (iii) benefit resulting from energy effectiveness; (iv) capital expenditures decrease; (v) operating costs decrease.

“Foam Agent Production Technology Update at “MAZ-Kupava” Works”

Mr. Viktor Vasilevskij, Deputy General Director, Chief Engineer, MAZ-Kupava, OOO

MAZ-Kupava produces 80-110 transport units per month depending on season. Currently equipment using HCFCis in operation. However, the plant has already started modernization process. The project is anticipated to assist in shifting technology to use of cyclopentane.  Such shift will result in (i) improving quality of panels used for manufacturing vans and trailers; (ii) termal conductivity could be decreased to 0,18 (current value is 0,4); (iii) sales volume will increase as a result of quality improvement; (iv) HCFC phase out will be completely finished at the plant as part of the obligations of the country under the Montreal Protocol.

“Conversion to New Solvents Composition”

Mr. Sergei Avdeichuk, Chief Engineer, David-Gorodok Electromechanical Plant

The plant implements the policy of environment protection and ecological safety. The solvents containing HCFC are used starting from 2007 as advanced at that time technology. They are used for washing the parts and details at the equipment manufactured and according to the technology developed in Japan in 90ies years. Average monthly consumption is 200 liters and more. The plant attempted to use alternative solvents at the existing equipment but failed in getting positive results. Ultrasound washing and regeneration technology which are considered to be ozone safe alternatives are too costly to be purchased by the plant’s funds. The plants hopes much for project’ financial assistance and is ready for their own contribution.

DISCUSSIONS

Mr. Nikolai Brushkov, Chief Engineer, “BelTorgProgress”, RPO: This Project has started in more organized and prepared manner if compared with the previous project. Lessons learned from implementation of the previous are as follow: (i) procurement of the equipment and tools shall be linked to the requirements of  Gosstandard of the Republic of Belarus, e.g. measuring tools and systems are to be certified in Belarus; (ii) when organizing training special attention shall be paid to the choice of trainees so that the targeted specialists undergo training but not those who are in no way related to the subject; (iii) the previous project failed to reach the technicians working at various enterprises (about 3 thousand people) since there’s no reester and no records on personnel engaged in cold industry sector; (iv) while purchasing equipment it is necessary to provide conditions for its post-warranty service and maintenance in order to prolong its total life cycle duration; (v) the targeted recycling indicators were not achieved because of low consumers’ activity in returning freon for recycling caused by certain reasons (time and costs burden); instead of planned 20 tons there were actually only 12 tons returned though the installed recycling equipment is in perfect operating conditions; thus, it is obvious that there’s need in specific law governing the behavior of HCFC consumers. The present project will be more successful if it accounts for the lessons learned from the previous one.

Mr. Vasililij  Pipik, Director, “Khladagent”, Private Enterprise: The enterprise deals with HCFC phase-out issues starting from 2007 and has reached perfect achievements. Most of them become real facts due to the interference and assistance of the Ministry of Nature. There are certain  problem with HCFC-12 phase-out task. The matter is that the main consumers of freon-12 are big state enterprises (Klen, Integral, Belarusian Railway, etc.), and they tend to be very reluctant in taking phase-out efforts because of their costs. Commercial enterprises have already transferred to ozone safe cold agent technologies while the state-owned enterprises would never do it unless they are obliged by certain compulsory measures.

Holodon recycling is not feasible now because of lack of quality analysis techniques and laboratories in the country. A special center is to be established and equipment for implementing this task.

Mr. Aleksand Borozdin, Director, «Laminar», Scientific and Production Private Unitary Enterprise: The enterprise is dealing with HFCF phase-out issues since 1995 including the refrigerated servicing sector. At the current moment there is no mechanism in the country that could encourage the consumers to collect and return refrigerants for recycling or disposal purposes. There are about 1000 HCFC single-use containers, containing remaining HCFC piled up at the enterprise now. There is risk of this total volume will be let go into atmosphere. It is necessary to convert to reusable containers instead of one-use ones.

Mr.Lukonin, General Director, “Kholodon», CJSC: Since Belarus does not produce but only consume HCFC the main purpose is import control. It is necessary to develop requirements common for the three countries of the Customs Union and to harmonise them with the European requirements. Besides, it is necessary to introduce production od reusable cylinders and to forbid non-reusable cylinders.

Mr. Leonid Turnyshev, Director, National Scientific Research Center Of Ozone Sphere Monitoring: Training is important project component. It will be reasonable to issue informational material on ozone, ozone layer role, etc. in order to present the problem in short and clear way. When people are sure in the importance of their actions they are more motivated to implement them in proper way and in proper time.

Mr. Boris Timofeev, Senior Staff Scientist, Professor, Doctor of Technical Sciences, International Cold Academy Member, Institute Of Power And Nuclear Research-Sosny, National Academy Of Sciences Of Belarus:  The sciences in Belarus possess enough capability in developing methods of HFCF quality analysis. Their involvement would be to benefit of the project and of the home science.

RESUME

- The participants evidenced their proper understanding of the Project goal, purposes and objectives as well as their interest in Project implementation. Project Implementation Unit will keep in close contact with all the stakeholders and pay due attention to any request and/or proposal. It is only by joined efforts that the project could reach actual achievements and positive impact on implementation of the national HCFC phase-out strategy.

- Due to delay with Project start it is necessary to adjust the time schedule for main activities. PIU has revised detailed work plan and budget for the period 2013 -2015. The revised detailed annual work plan for 2013 is presented in Annex IV. It is to be approved by the MNREP and the UNDP.

- Project staff will initiate procurement of seven (6) sets of audio and visual aids for the training institutions that will provide premises for training workshops and seminars to be conducted within the Project framework. Schedule of requirements need to be updated and agreed with the recipients.

- It is  requested by the State Customs Committee to include gas chromatographymass spectrometer for conducting analysis of ODS chemicals  into the list of the equipment to be procured under the project funds. Such is to be paid under the funds saved by totally deleting or partially decreasing the number of other tools and audio and visual aids. Customs Training Center is perfectly equipped with the educational equipment and materials and intends to provide its premises and the available equipment for project needs.

It is also requested by the State Customs Committee to include gas chromatographymass spectrometer  into the list of the equipment to be procured under the project funds. Such is to be paid under the funds saved by totally deleting or partially decreasing the number of other tools and audio and visual aids. The Training Center is perfectly equipped with the educational equipment and materials and intends to provide its premises and the available equipment for project needs.

- The proposed changes and/or updates have no significant impact on Project design as a whole. Therefore, during the inception workshop no necessity to revise project document was revealed.

- The workshop is considered starting platform for project launch.

## Annex IV.

## ANNUAL DETAILED WORK PLAN 2013

| Activity# and Description | Funds planned per quarter, USD |  |  | Total funds planned (USD) | Fund |  | Donor | Budget Account | Budget Account Description | Executing entity | Annual Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q2 | Q3 | Q4 |  |  |  |  |  |  |  |  |
| Component 1. Regional accelerated phase-out capacity building (to be implemented by UNDP Regional Center in Slovakia) |  |  |  |  |  |  |  |  |  |  |  |
| Component 2.HPMP, National Level Capacity Strengthening and HCFC Phase Out Investment |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.1: Formal HCFC Phase-out strategy and action plan developed and endorsed |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1. Organization of final HCFC phase-out strategy consultations and awareness raising workshop(s) | 0 | 0 | 2,500 | 2,500 | 62000 |  | GEF | 75700 | Training, Workshops and Confer | UNDP/ MNREP | HCFC Phase-out Strategy document is discussed with the main stakeholders. Recommendations for amendments (if any) are developped for approval. |
| 2.1.2. Publication of Russian language resource materials on various aspects related to HCFC phase-out | 0 | 0 | 500 | 500 | 62000 |  | GEF | 74200 | Printing & Publications | UNDP/ MNREP | Russian language resource materials on policy control options, enforcement and illegal trade, alternative technologies and energy-efficiency, ODS destruction, best refrigeration practices etc. (Component 1) are available. |
| TOTAL OUTPUT 2.1: | 0 | 0 | 3,000 | 3,000 |  |  |  |  |  |  |  |
| Output 2.2.: Trained and equipped working level Customs and enforcement officials, and refrigeration technicians using resources (trainers and training materials) from Component 1 |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2.1. Customs and environmental control officials training and equipment support to enhance Customs control capability |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.1.1. Procurement of office equipment for customs and MNR training institutes | 0 | 0 | 7,000 | 7,000 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | 2 Training centers are equipped with technical audio-visual aids (projector,screen and laptop) |
| 2.2.1.2.Procurement of HCFC monitoring equipment | 0 | 0 | 0 | 0 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | Scheduled for 2014 |
| 2.2.1.3.Provision of technical expertise to deliver trainings (development of training modules and study plans, monitoring of the equipment use ) | 0 | 0 | 0 | 0 | 62000 |  | GEF | 71200 | International Consultants | UNDP/ MNREP | Scheduled for 2014-2015 |
| 2.2.1.4.Conducting trainings on HCFC import and management control legislation and regulations | 0 | 0 | 0 | 0 | 62000 |  | GEF | 75700 | Training, Workshops and Confer | UNDP/ MNREP | Scheduled for 2014 |
| Sub -TOTAL OUTPUT 2.2.1: | 0 | 0 | 7,000 | 7,000 |  |  |  |  |  |  |  |
| Output 2.2.2. Refrigeration technicians training and equipment support to enhance refrigeration-servicing practices |  |  |  |  |  |  |  |  |  |  |  |
| 2.2.2.1.Procurement of office equipment for training institutions and Refrigeration Association | 0 | 0 | 17,000 | 17,000 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | 5 training centers for refrigeration technicians and Refrigeration Association are equipped with sets of office equipment (laptop with software, projector and screen) |
| 2.2.2.2.Procurement of tools and equipment kits for technicians | 0 | 0 | 0 | 0 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | Updated schedule of requirements and draft technical specifications are received from the recipient organisations. Procurement is scheduled for 2014-2015 |
| 2.2.2.3.Provision of technical expertise to deliver trainings (development of training modules and study plans, monitoring of the equipment use ) | 0 | 0 | 0 | 0 | 62000 |  | GEF | 71300 | Local Consultants | UNDP/ MNREP | Scheduled for 2014-2015 |
| 2.2.2.4.Conducting trainings for refrigeration technicians | 0 | 0 | 0 | 0 | 62000 |  | GEF | 71200 | Internation Consultants | UNDP/ MNREP | Scheduled for 2014-2015 |
|  | 0 | 0 | 0 | 0 | 62000 |  | GEF | 75700 | Training, Workshops and Confer |  |  |
|  | 0 | 0 | 0 | 0 | 62000 |  | GEF | 74200 | Printing & Publications | UNDP/ MNREP | Scheduled for 2014 |
| Sub-TOTAL OUTPUT 2.2.2: | 0 | 0 | 17,000 | 17,000 |  |  |  |  |  |  |  |
| TOTAL OUTPUT 2.2.: | 0 | 0 | 24,000 | 24,000 |  |  |  |  |  |  |  |
| Output 2.3: Targeted HCFC Phase-out Investment Program and Demonstration projects |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3.1. Implementation of a foam conversion project at MAZ Kupava |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.1. Procurement of equipment/ services to replace the current use of HCFC-141b with c-pentane technology with very low GWP characteristics | 0 | 0 | 0 | 0 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | Scheduled for 2014-2015 |
| 2.3.2. Provision of technical expertise (drafting of design and tender documentation, installation and tuning up of the equipment, training on new equipment operation) | 0 | 0 | 0 | 0 | 62000 |  | GEF | 71200 | International Consultants | UNDP/ MNREP | Terms of Reference for corresponding consultancy services are drafted. Selection process is conducted |
|  | 0 | 0 | 0 | 0 | 62000 |  |  | 71300 | Local Consultants |  |  |
| Sub-TOTAL OUTPUT 2.3.1: | 0 | 0 | 0 | 0 |  |  |  |  |  |  |  |
| Output 2.3.2. Implementation of a solvent conversion project at David Gorodok Electromechanical Plant |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.2.1. Procurement of closed-cycle vapour degreasing equipment/ services | 0 | 0 | 0 | 0 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | Scheduled for 2014 |
| 2.3.2.2.Provision of technical expertise (drafting of design and tender documentation, installation and tuning up of the equipment, training on new equipment operation etc) | 0 | 0 | 0 | 0 | 62000 |  | GEF | 71200 | International Consultants | UNDP/ MNREP | Terms of Reference for corresponding consultancy services are drafted. Selection process is conducted |
|  | 0 | 0 | 0 | 0 |  |  |  | 71300 | Local consultants |  |  |
| Sub-TOTAL OUTPUT 2.3.2: | 0 | 0 | 0 | 0 |  |  |  |  |  |  |  |
| Output 2.3.3. Demonstration of benefits of natural cooling in one or two sectors such as agricultural milk coolers |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.3.1.Procurement of equipment for natural cooling or non-ODS/low-GWP technologies | 0 | 0 | 0 | 0 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | Scheduled for 2015 |
| 2.3.3.2.Provision of technical expertise (collection of technology related data, support to IC, monitoring of equipment use and performance, trials, testing ,audit & reporting) | 0 | 0 | 0 | 0 | 62000 |  | GEF | 71200 | International Consultants | UNDP/ MNREP | Scheduled for 2014-2015 |
|  | 0 | 0 | 0 | 0 | 62000 |  |  | 71300 | Local Consultants |  |  |
| 2.3.3.3.Conducting a workshop to disseminate the results of the demonstration project | 0 | 0 | 0 | 0 | 62000 |  | GEF | 75700 | Training, Workshops and Confer | UNDP/ MNREP | Scheduled for 2014-2015 |
| Sub-TOTAL OUTPUT 2.3.3: | 0 | 0 | 0 | 0 |  |  |  |  |  |  |  |
| Output 2.3: Targeted HCFC Phase-out Investment Program and Demonstration projects |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3.4. Upgrades of HCFC re-use system |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.4.1.Provision of technical expertize (Preparation of design documentation and drafting tender documents for HCFC re-use system and procurement of specialized equipment) | 0 | 0 | 0 | 0 | 6200 |  | GEF | 71200 | International Consultants | UNDP/ MNREP | Scheduled for 2014-2015 |
| 2.3.4.2.Procurement of equpment for Recovery/Recycling (service centers) and Reclaim Center and HCFC-22 re-filling lines for for gas importers and distributors | 0 | 0 | 0 | 0 | 6200 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | Scheduled for 2014-2015 |
| 2.3.4.3.Monitoring the equipment distribution and use | 0 | 0 | 0 | 0 | 6200 |  | GEF | 71300 | Local Consultanats | UNDP/ MNREP | Scheduled for 2014-2015 |
| Sub-TOTAL OUTPUT 2.3.4: | 0 | 0 | 0 | 0 |  |  |  |  |  |  |  |
| Output 2.3.5. Unwanted ODS Pilot Destruction Project |  |  |  |  |  |  |  |  |  |  |  |
| 2.3.5.1.Provision of technical experize (consultations at the stages of design documentation preparation and installation) | 0 | 0 | 0 | 0 | 62000 |  | GEF | 71200 | International Consultants | UNDP/ MNREP | Scheduled for 2014-2015 |
|  | 0 | 0 | 0 | 0 |  |  |  | 71300 | Local Consultanats |  |  |
| 2.3.5.2.Procurement of a mobile ODS destruction unit and services on Installation of the equipment and monitoring the performance | 0 | 0 | 0 | 0 | 62000 |  | GEF | 72200 | Equipment and furniture | UNDP/ MNREP | Scheduled for 2015 |
| 2.3.5.3. Conducting regional workshop to report on the results of the pilot project | 0 | 0 | 0 | 0 | 62000 |  | GEF | 75700 | Training, Workshops and Confer | UNDP/ MNREP | Scheduled for 2015 |
| Sub-TOTAL OUTPUT 2.3.5: | 0 | 0 | 0 | 0 |  |  |  |  |  |  |  |
| TOTAL OUTPUT 2.3 | 0 | 0 | 0 | 0 |  |  |  |  |  |  |  |
| TOTAL OUTPUT 2. | 0 | 0 | 27,000 | 27,000 |  |  |  |  |  |  |  |
| Component 3.: Monitoring, learning, adaptive feedback, outreach and evaluation |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.M&E and adaptive |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.1.M&E and adaptive management applied to project in response to needs and extract lessons learnt. Lessons learned and best practices are replicated at the national level |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1.Conducting Mid-term Evaluation | 0 | 0 | 0 | 0 | 62000 | GEF |  | 71200 | International Consultants | UNDP/ MNREP | Scheduled for 2014 |
|  | 0 | 0 | 0 | 0 |  |  |  | 71300 | Local Consultants |  |  |
| 3.1.2.Conducting Final Evaluation | 0 | 0 | 0 | 0 | 62000 | GEF |  | 71200 | International Consultants | UNDP/ MNREP | Scheduled for 2015 |
|  | 0 | 0 | 0 | 0 |  |  |  | 71300 | Local Consultants |  |  |
| TOTAL OUTPUT 3: | 0 | 0 | 0 | 0 |  |  |  |  |  |  |  |
| Component 4.: Project Management Budget (PMB) |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1.Contracting project management group | 0 | 4400 | 18,100 | 22,500 | 62000 | GEF |  | 71400 | Contractual Services - Individ | UNDP/ MNREP | Project Manager, Fin/Admin assisstant and Scientific Coordinator are hired under SC |
| 4.1.2.Business trips | 0 | 0 | 6500 | 6,500 | 62000 | GEF |  | 71600 | Travel | UNDP/ MNREP | Monitoring visits to David Gorodok Electromechanical Plant and MAZ-Kupava Plant are conducted. Updated Demonstartion Projects' implementation plans are discussed. Participation in the Inception Workshop organized by BRC Slovakia (2 persons) |
| 4.1.3.Purchasing office furniture and equipment | 0 | 7400 | 1000 | 8,400 | 62000 | GEF |  | 72200 | Equipment | UNDP/ MNREP | Project offce operates effectively in accordance with the approved ADWP and Project Document |
| 4.1.4.Purchasing consumables, office supplies | 0 | 500 | 300 | 800 | 62000 | GEF |  | 72500 | Supplies | UNDP/ MNREP |  |
| 4.1.5.Translation, printing, IT maintanance and other services | 0 | 100 | 500 | 600 | 62000 | GEF |  | 71300 | Local consultants | UNDP/ MNREP |  |
| 4.1.6.Bank and postal charges, insurance of project assets, sundry expenses | 0 | 500 | 500 | 1,000 | 62000 | GEF |  | 72500 | Miscellaneous expenses | UNDP/ MNREP |  |
| 4.1.7.Connectivity charges (phones, internet) | 0 | 0 | 600 | 600 | 62000 | GEF |  | 72400 | Telecommunication services | UNDP/ MNREP |  |
| 4.1.8.Audit | 0 | 0 | 0 | 0 | 62000 | GEF |  | 74100 | Professional services | UNDP/ MNREP |  |
| 4.1.9.Project Visibility Activities | 0 | 0 | 2500 | 2,500 | 62000 | GEF |  | 75700 | Training, Workshops and Confer | UNDP/ MNREP | Manin stakeholders are informed on the Project start and the project goal, objectives, prospective activities and expected results. Project inception report with recommendations to adjust the proejct strategy based on the PSC. |
| TOTAL OUTPUT 4: | 0 | 12,900 | 30,000 | 42,900 |  |  |  |  |  |  |  |
| PROJECT TOTAL: | 0 | 12,900 | 57,000 | 69,900 |  |  |  |  |  |  |  |