Project PREPARATION GRANT (ppg)

Project Type:

type of Trust Fund:

Submission date:  06/07/2013

GEF Project ID: 5048

GEF Agency  Project ID: 4917

Country(ies): Belize

Project Title: Capacity-Building For The Strategic Planning And Management Of Natural Resources In Belize

GEF Agency(ies): , ,

GEF Focal Area(s):

a.   Project preparation Timeframe

| Start date of PPG | 07/01/2013 |
| --- | --- |
| Completion date of PPG | 02/01/2014 |

B.  proposed project preparation activities ($)

| Describe the PPG activities and justifications: The PPG will cover the following preparatory activities: 1. Baseline studies and strategy development: A) Data management and monitoring - Review current indicators of environment and development at national level, as used for existing national plans; - Review existing approach to data collection and to monitoring global environment; - Assess capacity to (i) select indicators, (ii) collect data (iii) design and run monitoring programmes; - Design project strategy to improve global environmental monitoring and reporting. B) EIA and SEA processes - Describe current approach to EIAs and to SEAs and identify entry points for incorporating global environment; - Review global and regional best practices in natural resource valuation; - Assess capacity to undertake natural resource valuation; - Design project strategy to improve global environmental impact of EIA and SEA processes. C) Coordination and financing - Prepare stakeholder analysis; - Review global and regional best practices in sustainable financing; - Design project strategy to improve coordination and sustainable financing of ensuring global environmental benefits. 2. Secure government commitment to project strategy: Make contact with key agencies. Negotiate with key government representatives to ensure full agreement on the project objectives, outcomes, outputs, and activities, including partnerships for support and government co-financing. 3. Secure government commitment to project implementation arrangements: Undertake consultations with key government representatives to secure agreement on project implemenetation arrangements, including roles, responsibilities, and accountabilities of lead and partner agencies. 4. Explore, and if feasible, secure bilateral and multilateral financing opportunities: Explore potential for partnerships with bilateral and multilateral donor agencies and organizations, including networking among other potential regional and international development organizations. Negotiate partnerships with on-going projects to re-align their activities to meet project objectives will be considered. If appropriate, finalize co-financing agreements. 5. Define Monitoring and Evaluation (M&E) Plan: A detailed M&E work plan and delivery strategy will be defined, including clear identification of responsibilities and accountabilities, as well as an appropriate budget allocation (based on best practices and UNDP guidelines). The Plan will reflect the requirements of the GEF M&E Policy and Capacity Building M&E framework. The Plan will also include provisions for an independent evaluation and provision to ensure the learning of lessons from implementation at both the mid-point and termination of the project. The Plan will most likely use the Capacity Development Scorecard (GEF Tracking Tool). 6. Define Sustainability Plan: The Sustainability Plan will outline an exit strategy, leading to the continuation of concerned activities without the need of long-term international financing. 7. Validation workshop Gathering representatives from all relevant stakeholders to present the final draft proposal. The final product of the proposed PPG phase will be a UNDP/GEF compliant medium-sized project document for submission to UNDP and GEF, including the following: • A detailed work plan with detailed roles and responsibilities for project implementation; • A targeted, in-depth analysis of the baseline situation and needs; • An updated report on the partnership and co-financing opportunities for the proposed project; • Explicit specification of all capacity building activities to be financed under the project and the rationale of their additionality to meeting Rio Convention objectives; • A detailed deconstruction of the project strategy using the Logical Framework Approach (log frame); • A detailed monitoring and evaluation plan for the project that builds upon the log frame; • A stakeholder participation plan; • Endorsement letters from the government and letters confirming co-financing commitments; • Medium-Size Project document per GEF and UNDP formatting and submission requirements; • Terms of Reference for key project staff, project management committee and key consultants. |
| --- |
| List of Proposed Project Preparation Activities | Output of the PPG Activities | Trust Fund | Grant Amount (a) | Co-financing (b) | Total c = a + b |
| Baseline study/strategy development - part 1A | Study report |  | 2,500 | 1,000 | 3,500 |
| Baseline study/strategy development - part 1B | Study report |  | 2,500 | 1,000 | 3,500 |
| Baseline study/strategy development - part 1C | Study report |  | 2,500 | 1,000 | 3,500 |
| Secure government committment | Endorsement letter |  | 0 | 1,500 | 1,500 |
| Finalise implementation arrangements | Project signature |  | 0 | 1,500 | 1,500 |
| Secure co-financing | Co-financing letters |  | 0 | 1,000 | 1,000 |
| Develop M&E strategy | M&E Plan |  | 2,000 | 1,500 | 3,500 |
| Determine sustainability arrangements | Sustainability Plan |  | 1,000 | 1,500 | 2,500 |
| Prepare MSP proposal, including sustainability plan, M&E plan, stakeholder plan | Project documens |  | 12,500 | 3,000 | 15,500 |
| Validation workshop | Project Validated |  | 2,000 | 1,500 | 3,500 |
| Total Project Preparation Financing |  | 25,000 | 14,500 | 39,500 |

C.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| Grant Amount | 25,000 | 2,375 |
| Co-financing | 14,500 |  |
| Total | 39,500 | 2,375 |

D.  PPG  Amount requested by agency(ies), focal area(s) and country(ies) 1

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |
| --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | Belize | 25,000 | 2,375 | 27,375 |
| Total PPG Amount | 25,000 | 2,375 | 27,375 |

1 No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

E.   PPG Budget

| Cost Items | Total Estimated Person Weeks for Grant (PW) | Grant Amount ($) | Co-financing ($) | Total($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 15.00 | 7,500 | 8,000 | 15,500 |
| International consultants* | 7.00 | 15,505 | 0 | 15,505 |
| Travel |  | 745 | 2,250 | 2,995 |
| Communication |  | 250 | 1,750 | 2,000 |
| Vaidation Workshop (Venue) |  | 1,000 | 1,750 | 2,750 |
| Material |  | 0 | 750 | 750 |
| Total PPG Budget |  | 25,000 | 14,500 | 39,500 |

* Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

F.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF LDCF/SCCF/NPIF Trust Fund criteria for project identification and preparation.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Deputy Executive Coordinator UNDP/GEF |  | June, 7, 2013 | Tom Twining-Ward UNDP Green-LECDRS | +421 2 59337 386 | tom.twining-ward@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Type of Consultant | Position / Titles | $/ Person Week1 | Estimated PWs2 | Tasks to be Performed |
| --- | --- | --- | --- | --- |
|  | Local Expert: Environmental Manager/ Natural Resource Planner | 500 | 3.00 | Baseline survey, data gathering, preparation of synthesis report on national data management/ Monitoring structure |
|  | Local Expert: Environmental Manager | 500 | 3.50 | Desk top survey, Synthesis Report: Analysis of national EIA process, identification of opportunities to improve national processes |
|  | Local Expert: Economist/ Sustainable Development | 500 | 3.50 | Prepare stakeholder ananlysis; determine transferable best practices for financing sustainable development |
|  | International Expert: Capacity Development/ Project Development | 2215 | 7.00 | Guide and support national team of consultans. Contribute technically to all outputs. Prepare MSP document and related sustainability and M& E plans. |
|  | Local Expert: Project Development | 500 | 5.00 | Support project preparation process; facilitate project validation sessions; Secure government commitment and cofinancing agreements. |

1 Provide dollar amount per person week.

2   Provide person weeks  needed to carry out the task