.

Project Group Execution Minutes #8					Date:  6 February 2015

Location: National Climate Change Office Conference Room			Time: 1:30 p.m

Attendees:

Adele Catzim - Sanchez –CEO- MFFSD-Chair		 	Ide Sosa Mckoy – Recording Secretary/PA, TNC

Earl Green- Project Manager, CCCCC				Collin Mattis- for UNFCCC Focal point, MFFSD

Safira Vasquez– Project Manager (PM), TNC			Ryan Cobb- Energy Unit, MESTPU

Dennis Gonguez-Chief Meteorologist, NMS			Vivian Belisle Ramnarace-  for GEF Focal Point,

Diane Wade Moore– Programme Analyst, UNDP		Fisheries Department

Edilberto Romero– Executive Director, Programme for Belize (PFB)

Andrew Harrison- Agriculture Officer, MNRA

Absent with apologies:

Emily Waight Aldana- Economist, MED 		Audrey Wallace–CEO- Office of the Prime Minister (OPM)

1.0 Meeting Called to Order

The meeting was called to order by the Chair at 1:56 p.m.

2.0 Review of Minutes from PEG Meeting #6

A motion was made by Programme for Belize and seconded by the Ministry of Energy, Science and Technology and Public Utilities for the approval of the PEG minutes.  The PEG minutes taken on 3rd July 2014 was approved with amendments by the PEG.

3.0 Review of Minutes from PEG Meeting #7

A motion was made by Ministry of Energy, Science and Technology and Public Utilities and seconded by the Ministry of Natural Resources and Agriculture for the approval of the PEG minutes.  The PEG minutes taken on 24 July 2014 was approved with amendments by the PEG.

4.0 Matters Arising from the Minutes

Since the last meeting was held in July 2014 and activities that occurred would be reported within the Project Manager's Report the PEG unanimously agreed that updates on activities be reported at that time.

5.0 Project Manager’s Report

5.1 Approval of End of Stage Report for Quarter 3, 2014.

The Project Manager presented the End of Stage Report for Q3 ,2014 to the PEG members.

A motion to approve the End of Stage Report for Q3, 2014 with amendments was made by Programme for Belize and seconded by National Meteorological Service. Approval was granted by the PEG.

5.2 Approval of Stage Plan and End of Stage Report Quarter 4, 2014

The Project Manager presented Quarter 4, 2014, Stage Report to the PEG members. A motion to approve the Stage Report for Q4, 2014 with amendments was made by Ministry of Energy, Science and Technology and Public Utilities and seconded by Programme for Belize. Approval was granted by the PEG.

Quarter 4 2014 End Report was presented to the PEG members. In reviewing the "Performance against stage tolerances" UNDP reported that in a meeting with the PMU, UNDP requested that activities be scaled back on TNC activities in order to dedicate and facilitate the closing of the EU-GCCA project.  Salaries for Q4, 2014 was paid under the EU-GCCA project in order to allow the bridging of salaries through the TNC project for 2015.

The PEG requested the circulation of the reports received under the training of primary school teachers and the climate change exchange programmes.

A motion to approve the Stage Report for Q4, 2014 with amendments was made by Programme for Belize and seconded by Ministry of Energy, Science and Technology and Public Utilities. Approval was granted by the PEG.

5.3 Approval of Stage Report Quarter 1, 2015

After a presentation made by the Project Manager regarding the "Plan Description," the Green House Gas Inventory was further discussed.

Green House Gas Inventory

CCCCC reported that they are unable to complete deliverables as originally stipulated within the Institutional Contract signed.  He indicated that hiring data collectors who have been trained would be more effective in completing the GHG data collection.   Initial contact being made to potential data collectors shows that the time allotted for completion is too short and the finance budgeted for payment of data collectors is small.  Although a few of the potential collectors can work within the limited budget the issue is the time allotted for interpretation and conversion of the data.  CCCCC enquired about the possibility for a three month extension.  UNDP stated that Belize is to commence its Fourth National Communication (FNC) and whereby financing for the FNC will not be available until the TNC is submitted.  It was also stated that according to UN salary rates Junior Professionals are paid approx. USD250.00 to 300.00 and therefore monies should be sufficient. CCCCC needs to reconcile their approach in order to stay within budget.

The GHG data collection discussion led to the following concerns:

1)Although the project is technically opened until June 2015 the UNFCCC Secretariat is expecting to receive the TNC by April 2015;

2) It is imperative that Ministerial staff collects data along with consultants in order to gain knowledge of the GHGI process;

3) Time is needed for the Ministerial staff assigned to collect data, lead in assessing the data collected;

Based on the concerns raised  UNDP will enquire if the UNFCCC Secretariat can grant an extension for submission of the TNC.  It was recommended by the CCCCC for future reference, that people selected from Government to complete the GHGI need to be able to analyze data.

The Project Manager will send the Biomass data collected by Dr. Percy Cho to CCCCC.

PEG approved that CCCCC contract be extended to 15 April 2015 until further arrangement is made with UNFCCC Secretariat. Meanwhile the process is being completed CCCCC will submit a draft of the GHGI summary report by 15th April 2015.

The Chair requested that a synopsis on the importance of GHGI be given to her in order to present it at the CEO Caucus to reflect the importance of the process and the need for all ministries to be involved.

National Climate Change Policy

The National Climate Change Policy, Strategy and Action Plan (NCCPSAP) has been sent to the BNCCC for review.  The draft Cabinet Paper currently being reviewed by CEO and the Minister.  It contains both NCCPSAP and the proposed Organizational Structure.  CEO to meet with Public Service and Financial Secretary to further discuss establishment of the office.

National Circumstance

The National Circumstance section of the National Communication will be completed within the NCCO.  UNDP stated that they are able to assist with technical backstopping once request is made.

Communication Strategy

The Communication Strategy received by the Communication Assistant did not meet expectations.  However, the Office has a volunteer assisting to finalize the document.  A timeline had not been finalized.

Project Manager to touch base with Tyronne Hall From CCCCC to assist in writing the communications portion of the TNC and review of the Communication Strategy. NCCO website to be presented to Tyronne to provide input.

Final Evaluation

UNDP  reported that the TNC project will not be audited, however verification if a Final Evaluation will be needed shall be confirmed by UNDP.

The PEG suggested that a rationalization exercise be done at the end of the project and where best practices, lessons learnt and risks be discussed and recorded.

The PEG requested that budget be allocated if necessary to complete GHGI and for Rationalization exercise.  UNDP stated that deviation of funds across budget lines should not be more than 15-20%.  Therefore confirmation on deviation will be done to determine  where funds can be allocated. UNDP and PMU to meet regarding deviation of funds.  Once UNDP verifies that a final evaluation is not needed monies can be then be used for the GHGI and rationalization session.

A motion to provisionally approve that monies be used for the GHGI and rationalization session once deviation of funds are within its limitations was made by Programme for Belize and seconded by Ministry of Energy, Science and Technology and Public Utilities. Approval was granted by the PEG.

EU-GCCA Project

The Project Manager reported on the outstanding activities under the EU-GCCA project:

1) Consultancy for the mainstreaming of climate change into sector plans - Consultant will be conducting his mission on the week of  February  23rd.

2) Consultancy for capacity building on Low Carbon Development Strategy (LCDS) and development of a Roadmap for LCDS - Capacity building to take place ont he 25-26 February 2015.

3) Negotiations Training to take place from the 4-6 March 2015.

The PEG realized that there was a planning oversight on the date selected for the negotiations workshop.  The 4th March is Municipal elections and several public servants would be called to work.  It was recommended that a discussion be held with the consultant in order to cut down the days to two or to change the date of the training.

A motion to approve the Stage Report for Q1, 2015 with amendments was made by Caribbean Climate Change Centre and seconded by Programme for Belize. Approval was granted by the PEG.

6.0 Any Other Matters

The Chair requested that all deliverables be placed on a CD or USB for circulation to CEO's of other line ministries.

7.0 Adjournment

A call to adjourn the meeting was motioned by the Caribbean Community Climate Change Centre and seconded by Programme for Belize.  The meeting was adjourned at 4:35 p.m.

Respectfully submitted by:

/                / 2015	  Ide Sosa Mckoy						              	Date

PEG Recording Secretary

Endorsed by:

_________________________                                                                              /                / 2015

Safira Vasquez								Date

Project Manager

/                / 2015

Adele Catzim						 			Date

Chairman of the PEG

# Text boxes

Enabling Activities for the Preparation of Belize’s Third National Communication to the UNFCCC- AND

Belize GCCA: Enhancing Belize’s Resilience to Adapt to the Effects of Climate Change” - (NCCO- Enhanced National Capacities to Plan for and to Coordinate a National Response to the Threats of Climate Change.)

00076372