United Nations Development Programme

Country: Barbados and the OECS

Project Document

| Project Title | TRAC II: Strengthening National Planning and Implementation Capacities in Caribbean SIDS with Access to an Integrated Data Framework for Governance, Social and Climate Risk Management |
| --- | --- |
| UNDAF Outcome(s): | Coherent, comprehensive and functional systems of poverty and MDG monitoring established regionally, supporting sound evidence, analyses, and policy making processes Regional and national capacities strengthened and integrated into planning and institutional frameworks, and countries better enabled to reduce sectoral risks and better manage multi-hazards and the environment |
| Expected SPD Outcome(s): | Democratic governance issues addressed in the context of national programmes, the OECS Development Charter and MDGs, via improved policy and institutional arrangements and policy/strategy work on the OECSEU |
| Expected Output(s): | SIDS-specific integrated data framework established |
| Executing Entity: | UNDP |
| Implementing Agencies: | OECS Member States – UNDP TRAC countries |

Agreed by (UNDP):

# Situation Analysis

Strengthening historically weak statistical databases, data collection and analysis are areas of continuing concern and assistance needed by the Caribbean Small Island States (SIDS). In the Caribbean, building evidenced-based policy and programming platforms has broad acceptance by donors and beneficiary countries. This need is particularly significant when viewed in the context of the vulnerabilities of the small island developing states (SIDS) in the region, as articulated in the United Nations Development Assistance Framework (UNDAF 2008-2011) and the Sub-regional Programme Document (SPD 2005-2009, extended until 2011):

- Small, open economies

- Limited human, institutional and resource capacities

- High levels of poverty and unemployment

- High prevalence of HIV/AIDS, especially amongst the adult working population

- Heavy reliance on a few sensitive economic sectors, especially tourism

- Fragile ecosystems

- Potential of these primary economic sectors to cause environmental degradation

- Vulnerability to natural disasters e.g. hurricanes, tsunamis, floods, earthquakes, volcanic eruption

- Concentration of human settlements and economic activities along coastlines exposed to hurricanes, storm surge and floods

- Impacts of climate change including sea level rise, changes in precipitation, increased frequency and intensity of tropical storms

It is also widely acknowledged that the processes supporting the collection and analysis of economic statistics are reasonably sound. However, continuing region-wide challenges related to the collection, analysis and dissemination of linked economic, social and environmental statistics, limit evidence-based policy formulation. A contributing factor to this paucity of credible and reliable data is the lack of structured data collection and analysis processes, i.e. a “systems approach”, linked to the Millennium Development Goals (MDGs) and other internationally agreed development goals. Other factors include limited data access, which prevents its broad-based use in programme development.

While it has been accepted that the MDGs offer a unique integrated framework for the effective measure of human development and progress towards the elimination of poverty, there remains a gap in the use of this framework as a primary tool for monitoring and achieving the region’s development goals. Bridging that gap requires the development of a mechanism by which economic, social and environmental data are collected and analysed within an integrated framework of evidence-based planning and governance as the region moves towards achievement of MDGs localised to the context of the region. The May 2010 UNDP MDG Breakthrough Strategy, which states that “[t]he financial and economic crisis, through economic slowdown, unemployment, reduced exports earnings and remittances, are yielding an alarming economic and human development impact. The governance implications of the crisis are also significant…” is of significant relevance to sustainable Caribbean SIDS development.

Recognising that the quality of data collected depends on reliable national data collection and reporting systems, which currently lack systematisation and standardisation, TRAC II funding will be used to support and develop standardised data platforms, starting in the four TRAC countries with replication to the remaining six UNDP programme countries. Linking economic, social and disaster management data through SPARC and climate risk methodologies will provide a SIDS- specific platform of indicators, with possible application of the UNDP/SIGOB Project. This capacity development initiative will also support adaptation of UNDP Global Management Information Systems (MIS) to Caribbean SIDS needs, and will link to UNDP’s support to the Caribbean Disaster Emergency Management Agency (CDEMA) and EDF European Development Fund Project.

# Strategy

The UNDP Strategic Plan 2008-2011 states that “[a] concerted and collective focus on human development and the internationally agreed development goals, including the MDGs, is crucial to long-term results...Improving the collection and quality of data will be essential, and UNDP will work closely with its partners, particularly DESA, United Nations regional commissions and the World Bank.” The mandate of UNDP includes the provision of “knowledge, policy advice, advocacy, and technical support in four focus areas on the basis of good practice and comparative advantage: poverty reduction, democratic governance, crisis prevention and recovery, and environment and sustainable development.” This project addresses data collection and analysis capacity needs within all of UNDP’s thematic areas, with UNDP supporting capacity building in policy development to strengthen national capacities and partnerships that ensure lasting results.

In alignment with the UNDP Strategic Plan, the UNDP Barbados Sub-Regional Office TRAC II funding is allocated to address critical gaps, building on existing data collection and analysis programmes, including SPARC, climate risk databases and impact modelling ,and governance indicators.

This TRAC ll funded project will start in the four TRAC-receiving countries (Dominica, Grenada, St. Lucia and St. Vincent and the Grenadines), with implementation replicated in the 6 non-TRAC programme countries supported by the UNDP Barbados Sub-regional Office (Antigua and Barbuda, Anguilla, Barbados, British Virgin Islands, Montserrat, and St Kitts and Nevis) based on funding availability and governments’ requests.

The project design is based on UNDP’s Capacity Development focus on organisational, systemic and individual level capacity building approaches. It also and fits within the following TRAC II Allocation Criteria:

- Criteria 1: Research and diagnostic capacities to support macroeconomic, governance and sector approaches that support MDGs/human development

- Criteria 2: National capacities for monitoring and accountability of development results

- Criteria 3: South-South cooperation initiatives and gender equality

Goals and objectives

This capacity development project will strengthen data capacities and gaps in SIDS with the provision of technical, expertise and equipment requirements to improve:

- weak policy formulation  and investment decision-making

- government planning and project management systems

- limited integration of data collection systems and statistical systems

- standardised data sharing and comparability

- monitoring and evaluation inputs to strengthen development policy, planning and programme results

- disaster data with the use of standardised collection methodologies and definitions

- advocacy on SIDS profiles

The overall goal of the project is to provide direct and strategic support to Eastern Caribbean SIDS by making available  integrated economic, social and climate risk data as effective tools for monitoring, mitigation and adaptation, linking data from sectoral management information systems (MIS) e.g. public sector investment programmes, social development and disaster management. The main objectives are to:

- Incorporate SPARC, governance indicators and climate risk methodologies to support the creation of a SIDS database and framework that supports strengthened policy formulation/analysis.

- Strengthen governance and reporting capacities through use of economic, social, demographic and disaster management indicators to support government policy formulation units.

- Develop climate change impact projections and costs to inform UNFCCC COP XVI negotations and assist policy makers in developing evidence-based adaptation solutions

- Establish advocacy platforms for evidence-based policy formulation.

Implementation plan

Implementation of these systems will be conducted in an incremental and participatory manner. The phased approach will be as follows:

- Phase 1 – Assessment and design of the data framework; definition of the parameters

- Phase 2 – Application: Adaptation of global methodologies e.g. DesInvestar adapted; high resolution climate impact models developed and background data collected and supported  with the provision of linked training  interventions

- Phase 3 – Implementation

  - Capacity building inputs to policy units, including use and application of data framework to support policy development and implementation

  - Enhanced climate scenario analysis and damage and loss assessments

  - Support for improved coordination between national emergency/disaster management organisations and meteorological services in communication and analysis of hydrometeorological data for improvement of regional multi-hazard early warning systems (MHEWS)

  - Programming and management of the agenda; monitoring the functioning of the system: management of requests, work agenda and the controls based specific administrative requirements

- Phase 4 – Revision of the practice: the process of implementation is evaluated and recommendations are elaborated for the institution in order to improve the functioning of the system.

Key components

- Assessment of pilot countries for linked SPARC, governance indicators and  climate risk modules

- In-country and sub-regional training in data collection methodologies and capacity building in statistical analysis

- Mapping and resources to update databases in four countries (undertake a detailed review and evaluation of databases/upgrade databases)

- Historical research of 30 year-period disaster data based on official government figures in 10 countries; data entry of new emergencies

- Capacity building and information management: sub-regional training workshops/creation of a cadre of technical resource personnel trained)

- Establishment of SPARC, governance and climate risk databases to facilitate linked analysis

- Dissemination and monitoring of the database

- Climate change impact modelling for at least five countries, with quantified damage and loss assessments

Expected impacts

It is anticipated that several tangible impacts will be realised on the ground in the implementing countries, including:

- Strengthened advocacy for regular use of data for evidence-based policy and decision making

- Enhanced data collection methodologies and analytical skills

- Improved capacity in data analysis and interpretation, addressing data gaps and enhanced database management

- Software and hardware procured and used by development stakeholders i.e.  civil society organisations (CSOs) and Ministries

- Improved monitoring of impacts and assessment of potential impacts from significant, proposed policy changes (Poverty and Social Impact Analyses - PSIAs)

- Delivery of quantitative data on predicted climate change impacts to inform policy decisions on adaptation and mitigation measures and Caribbean SIDS negotiations in international fora

- Informing the 2011 Global Assessment Report  process to highlight the SIDS Caribbean context and improve capacities for climate risk management

- Support the development of a substantive technical assistance initiative to improve MHEWS toward reducing loss of lives and disruption of livelihoods

- Strengthened in-country policy units using policy inputs, data  and frameworks to support sustainable human development in SIDS

- Strengthened public participation

Consequently, it is expected that the continued use and updating of these databases will yield faster formulation, approval and use of national level policy frameworks; development of risk profiles and trends as policy, planning, preparedness and mitigation indicators; evidence-based research and analysis to support policy reform and mitigation strategies; and more effective evidence-based advocacy of Caribbean SIDS vulnerability in global governance strategies.

# Results and Resources Framework

| Intended Outcome as stated in the Sub-regional Programme Document Results and Resource Framework: Capacity development for poverty and social development monitoring System of multi-stakeholder dialogue and participation in national and regional decision making processes that include the contribution of CSOs to attaining the MDGs institutionalised Sustainable management of the environment and natural resources incorporated into poverty reduction and national development frameworks Enhanced regional and national capacities for disaster risk reduction associated with natural, environmental and technological hazards, within the broader context of climate change Democratic governance issues addressed in the context of national programmes, the OECS Development Charter and MDGs |
| --- |
| Outcome indicators as stated in the Subregional Programme Document Results and Resources Framework, including baseline and targets: Enhanced capacity of social development institutions in data collection, analysis and monitoring of social phenomena Strengthened capacity of environment and natural resource management agencies to implement MEAs and supporting national policies Disaster management structures functioning as illustrated by integration of DRR strategies into Ministry activities and by effective forecasting and EWS Detailed national and regional plans, policies and strategies to support the implementation of the OECS Development Strategy (with the MDGs integrated) approved and developed |
| Applicable Key Result Area (from 2008-11 Strategic Plan): |
| Partnership Strategy |
| Project title and ID (ATLAS Award ID): TRAC II: Strengthening National Planning and Implementation Capacities in Caribbean SIDS with access to an Integrated Data Framework for Governance, Social and Climate Risk Management (ID 000) |
| INTENDED OUTPUTS | OUTPUT TARGETS FOR (YEARS) | INDICATIVE ACTIVITIES | RESPONSIBLE PARTIES | INPUTS |
| Output 1 Integrated governance, SPARC and climate risk data framework and management information systems (MIS) structured Baseline: Historically statistical databases, data collection and analysis capacities throughout the region are weak Indicators: Establishment of Integrated data framework and MIS | Targets (year 1) - Definition of Data Framework and MIS system: design methodology; required inputs; framework and institutional arrangements - Targets (year 2) - Establishment of Integrated MIS - Creation of Integrated Data Framework | In-country assessments conducted Assessment of country capacity, gaps and opportunities for integration of existing systems in pilot countries with links to the ECCB - Suggested Model: Policymaking Framework/Architecture Countries Support to a consultation to discuss proposed system System definition Delineation of parameters, codes, etc. Identification of users by function | UNDP | 95,500 |
| Output 2 Capacities improved in data collection, analysis and management for evidence-based policy design and planning Baseline: Insufficient technical knowledge/ capacity in new and existing research and data collection methodologies Indicators: Number of country officials trained in research methodology, statistical software, database management, PSIAs or their recommendations integrated into planning cycles Policy Units established to: Review policy proposals from line ministries ensuring standardised assessments in line with established guidelines for Cabinet submissions Conduct policy-oriented research in collaboration with key researchers in local, regional and international institutions, Formulate policy advice to ministries based on macroeconomic analysis and forecasting of social and economic policy issues and emerging concerns; Monitor economic performance and fiscal outcome for quarterly reporting in relation to pre-established annual fiscal targets; Develop the country strategic outlook, annual budgets and/or medium term economic strategy paper (MTESP). through collaboration with the planning, debt and budget units and through incorporation of social and environmental data and analysis to identify priority projects | Targets (year 1) - Regional capacity development initiative: training carried out by country in research methodologies, data analysis, database management and policy analysis Targets (year 2) - Capacity development for 4 OECS countries in ‘monitoring for development’ approaches including PSIA, MDGs | Training for identified users Orientation to new methodologies Training in statistical data analysis and interpretation Database management Procurement of software and hardware Strengthening of ongoing data collection Identification of data gaps Collection and collation of data Implementation of PSIA recommendations/further assessment with concurrent capacity development in PSIA methods | UNDP | 105,000 |
| Output 3 Linked governance, SPARC and climate risk databases developed to strengthen regular reporting on development targets and indicators. Baseline: Little integration of social/ environmental data in planning; weak frameworks for data sharing across sectors for integrated planning Indicators: Development of a coordinated national mechanism for use of integrated data in policy planning | Targets (year 1) - Development of national integrated data framework of governance, social and climate risk indicators in two OECS pilot countries Targets (year 2) - Development of institutional mechanism for use of integrated governance, social and environment data in policy planning | Population of databases Development of strategy for data and database maintenance Creation of monitoring systems to link trends and policy changes Development of data sharing policies Strengthening of national mechanisms for monitoring and data sharing, including on MDGs | UNDP, WMO | 85,000 |
| Output 4 Climate risk management priorities defined and a strategy for implementation well defined and resourced Baseline: Inadequate communication between meteorological services and NEMOs resulting in limited multi-hazard early warning systems (MHEWS) Indicators: Definition of a coordination strategy and improved application of hydrometeorological data for DRR and EWS | Targets (year 1) - Development of a regional initiative to address effective MHEWS Targets (year 2) - Capacity development for 4 OECS countries to address information to support MHEWS | Programme development for a Caribbean MHEWS Drafting of initiative Multi-stakeholder review meeting Ratification meeting Capacity development in climate risk data analysis and management Training in data management and analysis and strategy development for 4 OECS countries Database upgrading/expansion | UNDP, WMO | 50,000 |
| Output 5 Climate change projections for the Caribbean region developed under +2°C and +2.5°C global warming scenarios Baseline: Scenarios were developed in 2009 of likely impacts of climate change on Caribbean countries, showing the socioeconomic impacts on coral reefs, agriculture, and water resources that result from varying temperature and sea level rise, and projected cost to adapt to those changes generated. Ice sheet melt analysis not previously done Results were published, presented and disseminated at UNFCCC COP XV in Copenhagen in 2009, at the CARICOM Climate Change Task Force meeting in January 2010, and to various regional partners and stakeholders. Indicators: Model resolution Number of CC models generated and analysed Number of key sectors analysed in each country Total cost of damages and losses per country and per sector Incremental increase in SLR due to ice sheet melt modelled All material peer reviewed and published for distribution at COP XVI Summary document for policy makers prepared | Targets (year 1) - Spatial detail and resolution of models improved - Assessment of the vulnerability of coastal infrastructure completed - Damage and loss assessments and long term consequences completed and peer reviewed - Ice sheet melt analysis completed - All material peer reviewed and published for distribution at COP XVI - Summary document for policy makers prepared | Enhance CC model scenarios Data generation, model runs and analysis Assessment of temperature comparisons, daily rainfall distributions for climate, distribution of other variables such as wind speed Detailed examination of models; projections for each model developed independently SLR coastal model enhancement and impact analysis and ice sheet melt analysis Development of high resolution Digital Elevation Model Development of land use infrastructure geospatial data SLR coastal vulnerability analysis Impact cost assessment Collection, collation and analysis of secondary ice sheet melt data Impact cost assessment to define and analyse the losses and damages Detailed quantification of losses and damages Use of actuarial risk management tools Publishing of materials for COP XVI Design of full reports Design and printing of summary and key points documents and DVDs Shipping of materials | UNDP | 248,350 |
| Output 6 Mapping of poverty, resilience and vulnerability in Caribbean SIDS through review of poverty assessment methodologies and development of economic resilience indicators Baseline: Poverty line measures and vulnerability and resilience indices arguably do not capture the various dimensions and categories of poverty, vulnerability and resilience found in SIDS. Improved measures allow for more targeted macro/fiscal policy interventions and targeted poverty interventions especially in the area of women’s poverty Indicators: 3 CPAs and/or PRSs reviewed for their application of measurement methodologies SIDS/ Economic resilience indices developed Region-specific, gender-sensitive measures/methodologies developed and applied in 1 PRS in the OECS | Targets (year 1) - Development of SIDS poverty/vulnerability/resilience measures for use in CPAs, PRSs and in developing national policy as seen in strategic plans, MTESPs, national budgets Targets (year 2) - Use of SIDS poverty/vulnerability/resilience measures in CPAs, PRSs and in developing national policy as seen in strategic plans, MTESPs, national budgets - Integration of existing gender-sensitive CPA and PRS methodology into national-level assessments | Poverty assessment methodology review Consultancy to review current methods and make recommendations Meeting with development and national partners to consider output of consultancy Gender-sensitive CPA/PRS methodology review Meeting with development and national partners to consider integration of amended methodology into PRS 3 Mapping exercise to construct vulnerability and resilience indices for Caribbean SIDS | UNDP | 90,000 |
| Output 7 Regional advocacy campaigns by country to promote MDG monitoring as a SIDS development tool and address structural obstacles to MDG achievement Baseline: Reporting on MDGs carried out as add-on process whether than as tool in development interventions and planning; low levels of awareness at national administrative and public levels on usefulness and importance of data/information in using MDGs to achieve development targets Indicators: Campaign executed | Targets (year 1) - Regional advocacy campaign executed | Execution of campaigns Design of campaigns by country context Meetings with national partners to identify countries and country approach Design of campaign strategy by country and identification of national implementation teams Implementation of campaign strategy | UNDP | 124,500 |

# Annual Work Plan

Year: 2010

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 2 Capacities improved in data collection, analysis and management for evidence-based policy design and planning Baseline: Insufficient technical knowledge/capacity in new and existing research and data collection methodologies Indicators: Number of country officials trained in research methodology, statistical software, database management, PSIAs or their recommendations integrated into planning cycles Targets: Regional capacity development initiative: training carried out by country in research methodologies, data analysis, database management and policy analysis | Strengthening of ongoing data collection Identification of data gaps Collection and collation of data Implementation of PSIA recommendations/further assessment with concurrent capacity development in PSIA methods |  |  |  |  | UNDP | UNDP | Local consultants International consultants Equipment and supplies Travel Miscellaneous | 70,000 |
| Output 4 Climate risk management priorities defined and a strategy for implementation well defined and resourced Baseline: Inadequate communication between meteorological services and NEMOs resulting in Limited MHEWS Indicators: Definition of a coordination strategy and improved application of hydrometeorological data for DRR and EWS Targets: Development of a regional initiative to address effective MHEWS | Programme development for a Caribbean MHEWS Drafting of initiative Multi-stakeholder review meeting Ratification meeting |  |  |  |  | WMO | UNDP | Travel Local consultants | 30,000 |
| Output 5 Climate change projections for the Caribbean region developed under +2°C and +2.5°C global warming scenarios Baseline: Scenarios were developed in 2009 of likely impacts of climate change on Caribbean countries, showing the socioeconomic impacts on coral reefs, agriculture, and water resources that result from varying temperature and sea level rise, and projected cost to adapt to those changes generated. Ice sheet melt analysis not previously done Results were published, presented and disseminated at UNFCCC COP XV in Copenhagen in 2009, at the CARICOM Climate Change Task Force meeting in January 2010, and to various regional partners and stakeholders. Indicators: Model resolution Number of CC models generated and analysed Number of key sectors analysed in each country Total cost of damages and losses per country and per sector Incremental increase in SLR due to ice sheet melt modelled All material peer reviewed and published for distribution at COP XVI Summary document for policy makers prepared Targets: Spatial detail and resolution of models improved Assessment of the vulnerability of coastal infrastructure completed Damage and loss assessments and long term consequences completed and peer reviewed Ice sheet melt analysis completed All material peer reviewed and published for distribution at COP XVI Summary document for policy makers prepared | Enhance climate change model scenarios Data generation, model runs and analysis Assessment of temperature comparisons, daily rainfall distributions for climate, distribution of other variables such as wind speed Detailed examination of models; projections for each model developed independently SLR coastal model enhancement and impact analysis Development of high resolution Digital Elevation Model Development of land use infrastructure geospatial data SLR coastal vulnerability analysis Impact cost assessment Expanded assessment of coastal vulnerabilities and infrastructure Improved quantification of the extent of erosion risk Comprehensive SLR analysis for integration into investment, insurance, planning, policy and adaptation decisions Collection, collation and analysis of secondary ice sheet melt data Impact cost assessment to define and analyse the losses and damages Detailed quantification of losses and damages Use of actuarial risk management tools Publishing of materials for COP XVI Design of full reports Design and printing of summary documents key points documents and DVDs Shipping of materials |  |  |  |  | UNDP | UNDP | International consultants | 248,350 |
| TOTAL |  |  |  |  |  |  |  |  | 348,350 |

# Management Arrangements

This TRAC II project is executed under the DIM modality by UNDP Barbados and the OECS office. Its execution is the responsibility of the Programme Director. The UNDP Barbados and the OECS Programme Managers are assigned responsibility for project implementation and assurance.

A Project Monitoring Committee, formed by UNDP Barbados Programme Managers, will review the project as part of the Programme Management Meeting structure of UNDP Barbados and the OECS. A UNDP Project Coordinator will be responsible for day to day operations, supported by related UNDP Programme Managers, with oversight by the UNDP Barbados and the OECS SMT on implementation.

# Monitoring Framework And Evaluation

The project will be monitored in accordance with the programming policies and procedures outlined in the UNDP POPP, and will take account of CPAP implementation arrangements.

Quality Management for Project Activity Results

| OUTPUT 1: Integrated governance, SPARC and climate risk data and management information systems (MIS) structured |
| --- |
| Activity Result 1 (Atlas Activity ID) | SPARC Integrated MIS Development | Start Date: Jan 2011 End Date: Dec 2011 |
| Purpose | To assess the regional capacity for and thereafter design an integrated governance, SPARC and climate risk data and management information systems (MIS) |
| Description | Consultancy to assess country capacity, gaps and opportunities for integration of existing systems in pilot countries Support to a consultation to discuss proposed system System definition |
| Quality Criteria | Quality Method | Date of Assessment |
| Establishment of MIS | Consultancy reports | Nov 2011 |
| OUTPUT 2: Capacities improved in data collection, analysis and management |
| Activity Result 1 (Atlas Activity ID) | Capacity building in evidence-based planning for growth and poverty reduction | Start Date: Oct 2010 End Date: Oct 2011 |
| Purpose | To build national capacities in integrated data collection, analysis and use in policy planning |
| Description | Concurrent application of and training in data methods, PSIA and other ‘monitoring for development’ methodologies |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of country officials trained PSIAs or their recommendations integrated into planning cycles | Training reports | Sept 2011 |
| OUTPUT 3: Linked governance, SPARC and climate risk databases developed to strengthen regular survey and reporting capacities on governance, social, demographic and disaster management indicators |
| Activity Result 1 (Atlas Activity ID) | Development of national databases on governance, social and climate risk indicators | Start Date: Nov 2010 End Date: Nov 2011 |
| Purpose | To develop linked governance, SPARC and climate risk databases for strengthened survey, reporting and planning capacities |
| Description | Population of databases; development of strategy for data and database maintenance Creation of monitoring systems to link trends and policy changes Strengthening of national mechanisms for monitoring and data sharing, including on MDGs |
| Quality Criteria | Quality Method | Date of Assessment |
| Development of a coordinated national mechanism for use of integrated data in policy planning | Consultancy reports | Oct 2011 |
| OUTPUT 4: Climate risk management priorities defined and a strategy for implementation well defined and resourced |
| Activity Result 1 (Atlas Activity ID) | MHEWS programme development | Start Date: End Date: |
| Purpose | Identification and agreement of regional initiative to meet national requirements to improve EWS mainly for hydrometeorological hazards |
| Description | Support to a planning and development workshop Support to Project ratification meeting |
| Quality Criteria | Quality Method | Date of Assessment |
| Ratification by Directors of Meteorology and Disaster Management from at least 6 beneficiary countries | Meeting report Formal communication from countries | Q1 2011 |
| Activity Result 2 (Atlas Activity ID) | Capacity development in climate risk data analysis and management | Start Date: 15 Jan 2011 End Date: 31 Dec 2011 |
| Purpose | Capacity Development Support to Meteorological and Disaster Management offices for effective Development and application of climate related information |
| Description | Information for decision making workshop for 4 OECS countries |
| Quality Criteria | Quality Method | Date of Assessment |
| Improved communication on hydrometeorological hazards as indicated by specific strategies | Meeting report | Q4 2011 |
| OUTPUT 5: +2°C and +2.5°C global warming scenarios projections |
| Activity Result 1 (Atlas Activity ID) | Enhance CC model scenarios | Start Date: 15 Sept 2010 End Date: 15 Dec 2010 |
| Purpose | To compare various impacts on temperature, precipitation, etc under different climate change scenarios |
| Description | Run and analyse climate models |
| Quality Criteria | Quality Method | Date of Assessment |
| Spatial detail and resolution of models | Resolution | 1 Nov 2010 |
| Number of CC models generated and analysed | Number of CC models | 1 Nov 2010 |
| Activity Result 2 (Atlas Activity ID) | SLR coastal model enhancement and impact analysis | Start Date: 15 Sept 2010 End Date: 15 Dec 2010 |
| Purpose | To model the impact of SLR on the region |
| Description | Development of a high resolution Digital Elevation Model SLR coastal vulnerability analysis Impact cost assessment Expanded assessment of coastal vulnerabilities and infrastructure Collection, collation and analysis of secondary ice sheet melt data |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of key sectors analysed in each country | Number of key sectors | 1 Nov 2010 |
| Completed ice sheet melt analysis | Draft results | 1 Nov 2010 |
| Activity Result 3 (Atlas Activity ID) | Damages and loss assessment | Start Date: 15 Sept 2010 End Date: 15 Dec 2010 |
| Purpose | To quantify the projected losses to Caribbean countries as a result of climate change |
| Description | Detailed quantification of losses and damages Use of actuarial risk management tools |
| Quality Criteria | Quality Method | Date of Assessment |
| Total cost of damages and losses per country and per sector | Total cost | 1 Nov 2010 |
| Activity Result 4 (Atlas Activity ID) | Publishing | Start Date: 15 Sept 2010 End Date: 15 Dec 2010 |
| Purpose | To develop information and advocacy materials for COP XVI and beyond |
| Description | Printing of results documents, posters, DVDs |
| Quality Criteria | Quality Method | Date of Assessment |
| All material published for distribution at COP XVI | Quantities | 15 Dec 2010 |
| Summary document for policy makers prepared | Draft document | 1 Dec 2010 |
| OUTPUT 6: Review of poverty assessment methodologies/measures used by national and development partners |
| Activity Result 1 (Atlas Activity ID) | Poverty measure analysis | Start Date: Jan 2011 End Date: Dec 2011 |
| Purpose | To review current methods of poverty and vulnerability assessment for their usefulness in SIDS |
| Description | Methodology review, resilience mapping exercise and consultations with development partners to consider methods |
| Quality Criteria | Quality Method | Date of Assessment |
| 3 CPAs and/or PRSs reviewed for their application of measurement methodologies | Consultancy reports | Nov. 2011 |
| SIDS/Region-specific, gender-sensitive measures/methodologies developed and applied in 1 PRS or other national strategic document in the OECS | PRS or other pre-determined national strategic document | Dec 2011 |
| Construction of vulnerability/resilience indices | Consultancy report | Dec 2011 |
| OUTPUT 7: Regional advocacy campaign by country to promote MDG monitoring as SIDS development tool and address structural obstacles to achievement |
| Activity Result 1 (Atlas Activity ID) | Regional MDGs campaign | Start Date: Oct 2010 End Date: Sept. 2011 |
| Purpose |  |
| Description | Design of campaigns by country context Meetings with national partners to identify countries and country approach Design of campaign strategy by country and identification of national implementation teams |
| Quality Criteria | Quality Method | Date of Assessment |
| Campaign executed | Project reports | Aug 2011 |
| MDG Country reports produced | Quantities | Aug 2011 |

# Legal Context

Reference UNDP DIM executing arrangements

# ANNEXES

| Risk Analysis |
| --- |
| # | Description | Date Identified | Type | Probability and Impact 1 (low) - 5 (high) | Countermeasures/ Management response | Owner | Submitted, updated by | Last Update | Status |
| 1 | Weaknesses in current datasets | January 2010 | Operational | P = 5 I = 1 | Initial assessments in each of the targeted countries to address data gaps | Programme Team | Programme Team |  |  |
| 2 | Lack of technical capacity in varying degrees across programme countries, which can undermine the quality of project outputs | January 2010 | Operational | P = 5 I = 2 | Focus on targeted capacity development to meet project needs | Programme Team | Programme Team |  |  |
| 3 | Inadequate financial resources to support full implementation in all programme countries | January 2010 | Operational | P = 3 I = 4 | Adopt a pilot approach ensuring a spread of country involvement | Programme Team | Programme Team |  |  |
| 4 | Limited data access in programme countries, which can undermine the quality of project outputs | January 2010 | Operational | P = 4 I = 2 | Advocacy and national consultations to facilitate project ownership and implementation | Programme Team | Programme Team |  |  |
| 5 | High vulnerability of targeted programme countries, as SIDS, to external shocks may impact their capacity to participate in project | January 2010 | Environ-mental | P = 5 I = 5 | Adopt a flexible approach to project implementation on a case by case basis | Programme Team | Programme Team |  |  |
| 6 | Limited time frame for delivery of significant climate modelling outputs | October 2010 | Operational | P = 5 I = 3 | Adjust timeframe for delivery; Identify alternative dissemination strategies | Programme Team | Programme Team |  |  |

# Footnotes

UNDP’s MDG Breakthrough Strategy- Accelerate and Sustain MDG Progress, May 2010

SPARC - Support to Poverty Assessment and Reduction in the Caribbean - multi-donor capacity building programme to support the strengthening of poverty, MDG monitoring and social policy development systems in Caribbean countries. It has been designed to build on existing statistical support programmes developed and supported by CARICOM, Caribbean Development Bank (CDB), UN system and other development partners with the agreement to focus support on MDGs as well as strengthening national and regional capacities to systematically collect, analyse and disseminate social data through a Caribbean wide system of social data capture, poverty monitoring and policy development.

DesInventar - http://undp.desinventar.net collects disaggregated data geo-referenced through mapping tools up to three levels as State, District, and Villages.  The database performs analysis using variables such as effects, types of events, causes, sites, damage and losses, performing multiple level analyses and using the system in Disaster Risk Reduction process.

SIGOB - Strengthening Management Capacity for Good Governance - The Administrative Capacity for Democratic Governance (SIGOB) project is a UNDP regional project which supports strengthening administrative and institutional capacities of government policy-making structures. SIGOB’s methodology supports a unique technological application with modules:  Promote external transparency (based on citizens demand) and internal transparency (based on public administration demands; contribute to policy effectiveness, with early warning systems and scenarios for implementing public policy; promotes interaction with citizens through access to information and mechanisms to give voice and encourage participation to strategic programming and planning. SIGOB works across all government levels, but has focused on supporting the Centre of Government (Presidential and Prime Minister’s Offices). It has also contributed to strengthened local public administration by developing sub-national capacities in benchmarking, communications, citizens’ forums, bureaucratic processes and access to information.  More information is available in Spanish at: http://www. sigob.org/ sigob/

Project Institutional Support and Capacity Building for Disaster Management in the Caribbean (RCA/007/04), with reference to the sub-project of Information & Communications Technologies (ICTs), addressing broad limitations of information systems and its operating mechanisms at national levels.

Caribbean SIDS are experiencing impacts of multiple global crises, financial, food, fuel and climate, which are further highlighting the natural hazard and climate vulnerabilities of SIDS. UNDP, in partnership with the UN System, donors and other development partners, has long established assistance programmes supporting the creation and implementation of effective policy based programmes, such as social protection systems to mitigate increased poverty and vulnerability experienced by Caribbean SIDS populations. UNDP has presented evidence from many countries which suggests that social protection is a powerful tool for preventing and alleviating poverty, reducing inequalities and building a country’s resilience against exogenous shocks

Ref ECCB document: Policymaking Framework and Architecture in the Eastern Caribbean Currency Union

# Text boxes

Brief Description

This project addresses data collection and analysis capacity needs of Caribbean SIDS. The overall goal for the project is to provide direct and strategic support to Eastern Caribbean SIDS through the provision of integrated economic, social and climate risk data as effective tools for monitoring, mitigation and adaptation, linking data from sectoral databases and management information systems (MIS) e.g. public sector investment programmes, social development and disaster management. The main objectives are to:

- Integrate social, governance and climate risk data, indicators and methodologies to support the creation of a data framework that supports strengthened policy formulation/analysis in SIDS.

- Develop linked sectoral data modules to strengthen SIDS policy and strategy formulation.

- Strengthen governance and reporting capacities through use of economic, social, demographic and disaster management indicators.

- Develop climate change impact projections and costs to inform UNFCCC COP XVI negotiations and assist policy makers in developing evidence-based adaptation solutions.

- Establish advocacy platforms for evidence-based policy formulation.

Total resources required           	1,000,000

Total allocated resources:	1,000,000

- Regular (UNDP)	1,000,000

- Other:

  - Donor		_________

  - Donor		_________

  - Donor		_________

  - Government	_________

Unfunded budget:		_________

In-kind Contributions		_________

Programme Period:		                2005-2011

Key Result Area (Strategic Plan)	______________

Atlas Award ID:			______________

Start date:		     	28 Sept 2010

End Date			                31 Dec 2011

PAC Meeting Date		                ______________

Management Arrangements		DIM