## Undaf 4 (2009-10)
EXPECTED CP OUTPUTS and indicators including 18 months' targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs |  | TIMEFRAME | [5 empty] | RESPONSIBLE PARTY |  | PLANNED BUDGET
|  |  | 2011 |  |  |  | 2012 |  | Implementing Partner | UN | Source of Funds | Budget Description | Amount (US$)
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  |  |  |  | 2011 | 2012 | Total
I. Support to the Royal Court of Justice for its Capacity Development to ensure democratic governance and rule of law.
4.3.4 Enhanced institutional capacity of judiciary in ensuring democratic governance and rule of law Indicators: 1. No. of judicial personnel trained/sensitized on judicial process and system 2. Establishment of the Bhutan National Legal Institute (BNLI) Target (18 months): 1. 46 judicial personnel including both men and women+ 15 BNLI personnel trainned and sensitized 2. BNLI foundation established 3. Report on Juvenile Justice System | Result 1: Bhutan National Legal Institute established
| 1 | Development of strategy paper on the establishment and organisation of Bhutan National Legal Institute | X | [5 empty] | RCJ | UNDP | RR | Conference, Workshop | 10000 | 0 | 10000
| 2 | Conferences and workshops for judicial staff including judges and Registrars of all courts | X | [5 empty] | RCJ | UNDP | RR | Workshop | 3600 |  | 3600
| 3 | Procurement of legal materials | X | [5 empty] | RCJ | UNDP | RR | Procurement | 4630 | 0 | 4630
Result 2: Juvenile justice system intiated
| 4 | Conduct Needs Assessment on Juvenile Justice System | X |  | X |  |  |  | RCJ | UNICEF | RR | Int'l TA, | 30000 | 0 | 30000
Sub-Total Prg. UNDP | [12 empty] | 18230 | 0 | 18230
Sub-Total Prg. UNICEF | [12 empty] | 30000 | 0 | 30000
Assurance Activities
| 1 | Quarterly, mid year and annual review meetings | X | X | X | X | X | X | UNDP/NIM | UNDP | RR | travel, Misc. | 700 |  | 700
| 2 | On-site review | X | X | X | X | X | X | UNDP/NIM | UNDP | RR | travel, Misc. |  |  | 0
Sub-Total for Assurance | [12 empty] | 700 | 0 | 700
TOTAL | [12 empty] | 48930 | 0 | 48930
II. Institutional Strengthening and Capacity Development Support for the Parliament of Bhutan for effective legislative functioning
CT Output: 3.1a. Enhanced capacity of the parliament and its secretariats for its effective legislative functioning. Indicator: 1. % of legislations enacted of the tabled bills/policies inclusive of gender issues 2. % of Parliamentarians and officials with proportionate gender representation attached/trained at parliamentary functions 3. Parliamentary education resources inclusive of gender and participation of women in politics. 4. Parliamentary processes and systems Target: 1. 85% of legislations enacted of the tabled bills/policies inclusive of gender issues 2. 90% of Parliamentarians and officials with proportionate gender representation attached/trained at parliamentary functions 3. Parliamentary education resources inclusive of gender and participation of women in politics developed and circulated 4. Parliamentary processes and systems streamlined and strengthened | Result 1: Secretariats' capacity strengthened in providing parliamentary support services. | [13 empty] | 0
| 1.1 | Support capacity building of the National Council Secretariat
| 1.1.1 | Short term training on research techniques and methodologies | X |  | X |  |  |  | NC | UNDP | RR | training travel Misc. | 3000 |  | 3000
| 1.1.2 | Short term training on legislative drafting | X |  | X |  |  |  | NC | UNDP | RR | training travel Misc. | 6000 |  | 6000
| 1.1.3 | Short course on executive and leadership | X |  | X |  |  |  | NC | UNDP | RR | training travel Misc. | 3000 |  | 3000
| 1.2 | Support capacity building of the National Assembly Secretariat
| 1.2.1 | Short term training on research techniques and methodologies | x | x | x | x |  |  | NA | UNDP | RR | training travel Misc. | 3400 |  | 3400
|  |  | x | x |  |  |  |  | NA | UNDP | OR/DGTTF | training travel Misc. | 2600 |  | 2600
| 1.2.2 | Short term training on legislative drafting | x | x | x | x |  |  | NA | UNDP | RR | training travel Misc. | 6000 |  | 6000
| 1.3 | Support capacity development of project management unit (PMU) | x | x |  |  |  |  | NA & NC | UNDP | OR/DGTTF | training travel | 15000 |  | 15000
| Result 2: Observance of international days | [13 empty] | 0
| 2.1 | Int'l Democracy Day (15th September) observance |  |  | x |  |  |  | NA | UNDP | RR | workshop publication advocacy event | 1600 |  | 1600
| 2.2 | Observation of Human Rights Day (10th December) and related activities |  |  |  | X |  |  | NA | UNDP | RR | Advocacy, Travel, Event Misc. | 1000 |  | 1000
Result 3: Civic education for students
| 3.1 | Development and reproduction of documentary film for education and awareness programme on parliamentary functions | x | x |  |  |  |  | NA | UNDP | OR/DGTTF | Training audio visual documentation Misc | 4000 |  | 4000
| 3.2 | Mock parliament session with the students |  | X | X | X |  |  | NA | UNDP | OR/DGTTF |  | 2000 |  | 2000
Result 4: Orientation Handbook and Rules of Procedures developed/reviewed.
| 4.1 | Technical Assistance (TA) for development of Orientation Handbook and review of Rules of Procedures |  | x | x | x |  |  | NA | UNDP | RR | Int'l TA | 12000 |  | 12000
Result 5: Parliamentary committees, procedures and system strengthened
| 5.1 | Capacity development of Committees and members related to women and children of NC
| 5.1.1 | Attend meetings/seminars/workshops and conference on women and children for the NC parliamentarians | x | x | x | x |  |  | NC | UNICEF | RR | Training/Workshops | 5000 |  | 5000
| 5.1.2 | Attend meetings/seminars/workshops and conference on women and children for the NC officials | x |  | x |  |  |  | NC | UNICEF | RR | Training/Workshops | 5000 |  | 5000
| 5.2 | Capacity development of Committees and members related to women and children of NA
| 5.2.1 | Attend meetings/seminars/workshops and conference on women and children for the NA parliamentarians | [6 empty] | NA | UNICEF | RR | Training/Workshops | 5000 |  | 5000
| 5.2.2 | Attend meetings/seminars/workshops and conference on women and children for the NA officials | X | X | X | X |  |  | NA | UNICEF | RR | Training/Workshops | 5000 |  | 5000
| 5.3 | Parliamentary oversight functions strengthened
| 5.3.1 | Attend Public Accounts Committee (PAC) meetings within in the region for exposure/training |  |  | x |  |  |  | NA/NC | UNDP | RR | Training/Workshops | 8000 |  | 8000
| 5.3.2 | Short term training for PAC Secretariat staff to improve their skills to support PAC | x |  | x |  |  |  | NA/NC | UNDP | RR | Training/Workshops | 7000 |  | 7000
Result 6: Establish a parliamentary information resource centre.
| 6.1 | Support provision of essential books and relevant materials for the resource centre. | x |  | x |  |  |  | NA | UNICEF | RR | Books & materials | 5000 |  | 5000
Sub-Total Prg. UNDP | [12 empty] | 74600 | 0 | 74600
Sub-Total Prg. UNICEF | [12 empty] | 25000 | 0 | 25000
Assurance Activities
| 1 | Quarterly, mid year and annual review meetings | X | X | X | X | X | X | UNDP/NIM | UNDP | RR | travel, Misc. | 1000 |  | 1000
| 2 | Monitoring and evaluaiton |  |  |  | X |  |  | UNDP/NIM | UNDP | RR | travel, Misc. | 12500 |  | 12500
| 2 | Onsite reviews | X | X | X | X | X | X | UNDP/NIM | UNDP | RR | travel, Misc.
Sub-Total Assurance | [12 empty] | 13500 | 0 | 13500
TOTAL | [12 empty] | 113100 | 0 | 113100
III. Support for the Election Commission of Bhutan for its institutional and capacity development (Note: Specific fund and activity details will be agreed in due course)
4.3.2 Enhanced capacity of key organisations in conducting free & fair elections at national & local levels. Indicators: 1. % of electoral staff including both men and women at national and local levels trained in the conduct of the elections Target (18 months): 20% (0, 2009) 2. % of voters voting in LG elections Target (18 months): Above 60% registered voters (0, 2009) 3. % of voters including men and women covered by voter education programmes Target (18 months): Above 80% of registered voters (NA, 2009) | Result 1: Digitization process of delimitation maps initiated
| 1.1 | Preparation for digitization of delimitation maps |  |  | X | X |  |  | ECB | UNDP | RR | Travel | 20000 | 5000 | 25000
Result 2: Networks and exchanges established with election agencies
| 2.1 | Support participation in electoral seminars, conferences and visitor programmes |  |  | X | X |  |  | ECB | UNDP | RR | Travel | 15000 |  | 15000
Result 3: Civic education and voter awareness
| 3.1 | Conduct of inclusive voter and civic education programmes for the upcoming LG elections | X | X |  |  |  |  | ECB | UNDP | RR | Travel, Workshops | 10000 |  | 10000
Sub-total | [12 empty] | 45000 | 5000 | 50000
Assurance Activities
| 1 | Quarterly, mid year and annual review meetings |  | X | X | X | X | X | UNDP/NIM | UNDP | RR | travel, Misc. | 700 |  | 700
| 2 | Joint field monitoring visits and advocacy visits |  | X | X | X | X | X | UNDP/NIM | UNDP | RR | travel, Misc. | 5000 |  | 5000
| 3 | HACT Audit |  |  | X |  |  |  | UNDP/NIM | UNDP | RR | travel, Misc. | 500 |  | 500
| 4 | Onsite reviews |  | X |  | X |  | X | UNDP/NIM | UNDP | RR | travel, Misc.
Sub-total | [12 empty] | 6200 |  | 6200
TOTAL | [12 empty] | 51200 | 5000 | 56200
IV. Support for gender inclusive democratic governance and capacity development
4.3.2 Enhanced capacity of key organisations in conducting free & fair elections at national & local levels. Indicators: 1. % of local government officials trained on gender responsive governance Target (18 months): 100% (0%, 2008) 2. % of women elected in Local Governments Target (18 months): Above 15% registered voters (>1%, 2009) | Result 1: Increased participation of women in local governance
| 1.1 | Research on factors influencing women’s participation in elections | X | X | X |  |  |  | DLG/ NCWC | UNDP | OR/UN Women | Travel, workshops | 20000 |  | 20000
| 1.2 | Training of local government officials on gender responsive governance |  | X | X | X | X |  | DLG | UNDP | OR/UN Women | Travel, workshops | 30000 | 13770 | 43770
| 1.3 | Capacity building of UN officials on gender responsive governance |  | X | X | X |  |  | UNDP/NIM | UNDP | OR/UN Women | Travel, workshops | 25000 |  | 25000
CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. % of public officials sensitized on gender, inclusive democratict governance, rights and duties. Target: 60% (NA, 2008) 2. % general public sensitised on gender, inclusive democratic governance, rights and duties. Target: 30% (NA, 2008) | Result 1: Increased public awareness on gender, inclusive democratic governance, rights and duties | [14 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information | [9 empty] | CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information
| 1.1 | Production of 2 films on Gender and Governance in Bhutan |  | X | X | X | X |  | NCWC | UNDP | OR/UN Women | Procurement | 30841 | 22383 | 53224 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000 |  | 1.1 | Seminar/workshop on Online Media | X | X | BCMD | UNDP | OR/UNDEF | International consultant | 3000 | 3000
| 1.2 | Communication Strategy and IEC materials on gender inclusive democratic governance, rights and duties through civic education |  | X | X | X |  |  | NCWC | UNDP | OR/UN Women | Procurement | 19195 |  | 19195
|  | Facilities and Administraion GMS (7%) | [7 empty] | UNDP | OR/UN Women | F&A | 9159 | 2617 | 11776 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500 | [8 empty] | seminar/workshop | 3500 | 3500
Sub-total | [12 empty] | 134195 | 38770 | 172965
Assurance Activities
| 1 | Quarterly, mid year and annual review meetings |  | X | X | X | X | X | UNDP/NIM | UNDP | OR/UN Women | travel, Misc. | 700 |  | 700
| 2 | Joint field monitoring visits and advocacy visits |  |  | X | X | X | X | UNDP/NIM | UNDP | OR/UN Women | travel, Misc. | 800 |  | 800
| 3 | Onsite reviews |  | X |  | X |  | X | UNDP/NIM | UNDP | OR/UN Women | travel, Misc.
Sub-total | [12 empty] | 1500 |  | 1500
TOTAL | [12 empty] | 135695 | 38770 | 174465
V. Support to Bhutan Centre for Media & Democracy (BCMD)
CT Output 4.3.3 Enhanced public awareness on gender, inclusive democratic governance, rights and duties through civic education Indicator: 1. No. of community representatives, including women, sensitised on access to information and other democratic concepts. 2. No. of teachers trained on democracy and civic education 3. No. of journalists trained in reporting skills Baseline: 1.50% community representatives, including women, sensitised on access to information and other democratic concepts 2. 30% teachers trained on democracy and civic education 3. 50% journalists trained in reporting skills Target: 1. 40 male and 40 female community representatives sensitised on access to information and other democratic concepts. 2. 25 female and 20 male teachers trained on democracy and civic education 3.30 male and 30 female journalists trained on reporting skills | Result 1: Strengthened awareness on Acess to Information
| 1.1 | Seminar/workshop on Online Media |  | X | X |  |  |  | BCMD | UNDP | OR/UNDEF | International consultant | 3000 |  | 3000
[12 empty] | seminar/workshop | 3500 |  | 3500
| 1.2. | Media sensitization training for GAOs | X | X |  |  |  |  | BCMD | UNDP | OR/UNDEF | national consultant | 1000 |  | 1000
[12 empty] | seminar/workshop | 3500 |  | 3500
Result 2: Expanded public discourse
| 2.1 | Civic education training/workshop |  |  | X | X |  |  | BCMD | UNDP | OR/UNDEF | international consultant | 8000 |  | 8000
[12 empty] | seminar/workshop | 4000 |  | 4000
| 2.2 | Development of 2 resource books on Democracy | X | X | X | X |  |  | BCMD | UNDP | OR/UNDEF | international consultant | 5000 | 0 | 5000
[12 empty] | national consultant | 2000 |  | 2000
[12 empty] | seminar/workshop | 6000 |  | 6000
[12 empty] | printing and publications | 32500 |  | 32500
| 2.3 | Development of web portal | X | X | X | X |  |  | BCMD | UNDP | OR/UNDEF | national consultant | 4000 |  | 4000
[12 empty] | IT Equipments | 6000 |  | 6000
| 2.4 | Development of Media and Democracy Library | [9 empty] | Equipments | 2200 |  | 2200
|  |  | X | X | X | X |  |  | BCMD | UNDP | OR/UNDEF | printing and publications | 2200 |  | 2200
Result 3: Strengthened Media as the fourth Estate
| 3.1 | News reporting training |  | X | X |  |  |  | BCMD | UNDP | OR/UNDEF | international consultant | 4000 | 0 | 4000
[12 empty] | seminar/workshop | 3000 |  | 3000
| 3.2 | Annual Media conference |  |  | X | X |  |  | BCMD | UNDP | OR/UNDEF | international consultant | 4000 | 0 | 4000
[12 empty] | seminar/workshop | 3000 |  | 3000
| 3.3 | Annual Non-fiction writing workshop |  | X | X |  |  |  | BCMD | UNDP | OR/UNDEF | international consultant | 4000 | 0 | 4000
[12 empty] | seminar/workshop | 4000 |  | 4000
| 3.4 | Capacity building of BCMD | X | X | X | X |  |  | BCMD | UNDP | OR/UNDEF | international consultant | 5000 | 0 | 5000
[12 empty] | trainings/workshop | 7000 |  | 7000
Result 4: Commemoration of International Events
| 4.1 | World Democracy (Sept. 15) |  |  | X |  |  |  | BCMD | UNDP | OR/UNDEF | seminar/workshop | 3000 |  | 3000
| 4.2 | World Press Freedom Day Observance |  | X |  |  |  |  | BCMD | UNDP | OR/UNDEF | TA (collaborate with DoIM) | 2000 |  | 2000
| 4.3 | Youth Festival |  | X | X |  |  |  | BCMD | UNDP | OR/UNDEF | seminar/workshop | 4500 |  | 4500
| 5 | Prog. Support cost | X | X | X | X | X | X | BCMD | UNDP | OR/UNDEF |  | 8000 |  | 8000
| 6 | Sundry/Rent | X | X | X | X |  |  | BCMD | UNDP | OR/UNDEF |  | 2800 |  | 2800
| 7 | Contingency | X | X | X | X |  |  | BCMD | UNDP | OR/UNDEF |  | 1800 | 0 | 1800
Sub-Total | [12 empty] | 139000 |  | 139000
Assurance Activities
| 1 | Quarterly, mid year and annual review meetings | X | X | X | X |  |  | UNDP/NIM | UNDP | OR | travel, Misc. | 700 |  | 700
| 2 | Joint field monitoring visits and advocacy visits |  | X | X | X |  |  | UNDP/NIM | UNDP | OR | travel, Misc.
| 3 | Onsite reviews | X | X | X | X |  |  | UNDP/NIM | UNDP | OR | travel, Misc.
| 4 | Special Audit |  |  | X |  |  |  | UNDP/NIM | UNDP | OR | travel, Misc. | 500 |  | 500
| 5 | F & A | [6 empty] | UNDP/NIM | UNDP | OR |  | 9100 |  | 9100
Sub-Total | [12 empty] | 10300 |  | 10300
TOTAL | [12 empty] | 149300 |  | 149300
Total for UNDP | [12 empty] | 307530 | 5000 | 312530
Total for UNICEF | [12 empty] | 55000 |  | 55000
Total for UN Women | [12 empty] | 135695 | 38770 | 174465
AWP TOTAL | [12 empty] | 498225 | 43770 | 541995
Note on N67: kunzang.norbu: m/e for observation tour during LG elections