## AWP
Work Plan for Local Governance Support Programme-2011-12
LGSP Joint Programme Outcome: Democratic governance at local levels enhanced and services delivered effectively and efficiently as mechanism to reduce poverty and contribute to achieving the MDGs.
Expected Programme Outputs -and indicators and including targets |  | Planned Activities | Time frame | [8 empty] | Responsible Party | Budget Description | Amount (NU) |  |  | Source of Funds in Nu. | [8 empty] | UN funds in USD
|  |  | 2009-10 | 2011-12 | [5 empty] | 12
|  |  | J-M | J-M | A-J | J-S | O-D | J-M | A-J | Q1 | Q2 | Implementing Partners |  | 2010/11 | 2011/12 | Total | LoD | SDC | UNDP RR/OR | UNCDF | EU | ROD | SDC | UNDP RR/OR | UNCDF | UNDP/RR US$ | UNDP/OR US$ | UNCDF /RR US$
1.0. Effective and transparent financing mechanism for Local government service delivery LGSP Indicators; • % of Local governments receive and report capital budgets on time and schedule Target: 80 % Baseline: NA LGSP Indicator: • % of Local Governments submitting timely reports on the use of the Grants Target: 80 % Baseline: NA LGSP Indicator:: • % of LGs functionaries (elected/staff) men and woment trained on the use of the Annual Grants Target: 80 % Baseline: 0 LGSP Indicator:: • Performance based block grants piloted in 2 Dzongkhags & lessons learned documented Target: Pilots completed and lessons for upscaling completed by 2013 Baseline: 0 | 1 | Capital annual block grants for 205 Gewogs |  |  |  | X |  | X |  |  |  | LDD, GNHCS | Grants | 0 | 169714930 | 169714930 | 128835900 | 10842930 |  | 9000000 | 86800000 | 63072000 | 10842930 | 0 | 9000000 | 0 | 0 | 200000
| 2 | Support the pilot performance based grants CCA/LoCAL for LGs |  |  | X | X | X | X |  |  |  | MOF/DLG(MoHCA | Int'l TA | 2323651.5 | 1395000 | 3718651.5 |  |  |  | 3718651.5 | 0 | 0 | 0 | 0 | 3718651.5 | 0 | 0 | 82636.7
| 3 | Strengthen the utilization and understanding of Annual Grant system/guidelines (AGG) for the LGs(elected/staff) through training /sensitization of the AGG. |  |  | X | X | X |  |  |  |  | LDD, GNHCS | Training, travel and Misc. | 253525.5 | 225000 | 478525.5 |  |  | 478525.5 |  | 0 | 0 | 0 | 478525.5 | 0 | 10633.9 | 0 | 0
|  | Sub-total | [11 empty] | 2577177 | 171334930 | 173912107 | 128835900 | 10842930 | 478525.5 | 12718651.5 | 86800000 | 63072000 | 10842930 | 478525.5 | 12718651.5 | 10633.9 | 0 | 282636.7
2.0 Inclusive, efficient and accountable public expenditure management(PEM) & planning procedures/tools for LGs in place & well functioning LGSP Indicator; No of functional planning/budgeting tools for local governments developed Target: Local Development Planning Manual published and LGs trained on its use; Annual Capital Grant guidelines published and LGs sensitized Baseline: 0 LGSP Indicator:; RBM approach used as fucntional planning tool within the LDMP Target: LDMP training for 205 gewogs Baseline: RBM completed in 20 districts . LGSP Indicator: % of LGs by Dzo/Gewogs trained to use the community protocol and templates Target: 40% ( sex disaggregated data) Baseline: 0 | 1 | Training and sensitization on small scale infrastructure design and costing templates for the LGs(elected/staff) |  |  |  | X | X |  |  |  |  | LDD, GNHCS | TA local, meeting, workshop | 382815 | 225000 | 607815 |  |  | 225000 | 382815 | 0 | 0 | 0 | 225000 | 382815 | 5000 | 0 | 8507
| 2 | Training and sensitization of communtiy contract protocol to the LGs(elected/staff) |  |  |  | X | X |  |  |  |  | DLG, MoHCA | TA local, meeting workshop | 0 | 225000 | 225000 |  |  | 225000 |  | 0 | 0 | 0 | 225000 | 0 | 5000 | 0 | 0
| 3 | Training and awareness on local development planning manual for the LGs (elected/staff) and planning and prioritization |  |  |  | X | X |  |  |  |  | LDD, GNHCS | TA local, workshops/ meetings | 0 | 450000 | 450000 | 450000 |  | 450000 |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | A. Develop and introduce Best Practice Award/Recognition for LG's that demonstrate outstanding approach to local governance. B. Develop Awards/Recognition criterias for individual incentives to LGs( Gup, GAO's etc.) |  |  | X | X | X |  |  |  |  | DLG, MoHCA | LoCAl TA, workshop | 900000 | 0 | 900000 |  |  | 900000 |  | 0 | 0 | 0 | 900000 | 0 | 20000 | 0 | 0
|  | Sub-total | [11 empty] | 1282815 | 900000 | 2182815 | 450000 | 0 | 1800000 | 382815 | 0 | 450000 | 0 | 1350000 | 382815 | 30000 | 0 | 8507
3.0 Effective national support/training mechanism for local government personnel & elected members in place LGSP Indicator: • % of LG functionaries (elected&public -male/female) trained to apply RBM skills for local development planning, budgeting and results. Target: 70% ( sex disaggregated data) Baseline: 20 district sector officials trained in RBM LGSP Indicator: • % of LGs functionaries (elected/public -male/female) trained in NMES guidelines & PLaMS for monitoring Target: 70% ( sex disaggregated data) Baseline: 0 LGSP Indicator: • No of LG functionaries trained as skilled TOTs (men and women) by Dzo/Gewogs for providing ongoing training and coaching to LGs Target:100 % ( sex disaggregated data) Baseline: Existing 58% GAOs trained LGSP Indicator; Basic functional equipments supplied to LGs Target: 100% ( sex disaggregated data) Baseline: 70% districts supplied | 1 | Capacity development of LGs (elected/staff) to strengthen planning process and public expenditure managemt using RBM and NMES |  |  | X | X | X | X |  | X | X | DLG(MOHCA) LDD(GNHCS) | Travel, training, workshop, TA local Misc | 1142155.8 | 450000 | 1592155.8 | 225000 |  | 1367155.8 |  | 0 | 225000 | 0 | 1367155.8 | 0 | 30381.24 | 0 | 0
| 2 | Conduct Training of Trainers (ToT) for Gewog Administrative Officers (men and women) on planning & prioritization using new participatory tool (VIPP) | [5 empty] | X | X | X | X | LDD,GNHCS | Travel, training, workshop, TA local Misc | 0 | 1170000 | 1170000 | 225000 |  | 945000 |  | 0 | 225000 | 0 | 945000 | 0 | 21000 | 0 | 0
| 3 | Training for LGs (elcted/staff) on effective office management skills (Basic computer course/dzongkha unicode, writing standardized minutes, etc) including sensitization of LG Act, and rules and regulation. | [5 empty] | X | X |  |  | DLG, MoHCA | Travel,Training/ workshop | 0 | 1867500 | 1867500 | 900000 |  | 967500 |  | 0 | 900000 | 0 | 967500 | 0 | 21500 | 0 | 0
| 4 | Capacity Development for LGs(elected/staff) in conflict resolution and leadership, etc. | [5 empty] | X | X |  |  | DLG,MOHCA | TA(int & local), training, travel, misc | 0 | 450000 | 450000 | 450000 |  |  |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Peer learning visits for LGs (men & women) to exchange experience & learn from these experiences |  |  | X | X | X |  |  |  |  | DLG, MoHCA | Travel, training, workshop, TA(local, intl) Misc | 450000 | 445455 | 895455 |  |  | 895455 |  | 0 | 0 | 0 | 895455 | 0 | 19899 | 0 | 0
| 6 | Supply of Computers (6 Gewog Accountants, Lhuentse Dzongkhag) |  |  |  | X | [5 empty] | DLG, MoHCA | Equipments | 0 | 450000 | 450000 | 360000 |  |  |  | 0 | 450000 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Formulate inclusive service rules for elected local government officials (men & women) based on the LG Act 2009 |  |  |  | X | X | X | X |  |  | DLG, MoHCA | TA Local and Meetings | 0 | 360000 | 360000 | 135000 |  | 225000 |  | 0 | 135000 | 0 | 225000 | 0 | 5000 | 0 | 0
| 8 | Develop and formulate inclusive mechanisms and guidelines for the LG Capacity Development grant |  |  |  |  | X | X |  |  |  | DLG, MoHCA | TA ( int'l and local), workshop, Grants |  | 1800000 | 1800000 |  |  |  |  | 0 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Develop radio spots and advocacay materials on decentralisation and annual grants to sensitize LGs on these issues |  |  | X | X | X |  |  |  |  | DLG, MoHCA | TA Local | 225000 | 450000 | 675000 | 450000 |  | 225000 |  | 0 | 450000 |  | 225000 | 0 | 5000 | 0 | 0
| 10 | Sensitization on Gender Responsive Budgeting (GRB) and Training of Trainers |  |  | X | X | X |  |  |  |  | DLG, MoF, NCWC | Travel, training, workshop, TA(local, intl) Misc | 900000 | 1569105 | 2469105 |  |  | 1884105 |  | 0 | 0 | 0 | 2469105 | 0 | 0 | 54869 | 0
| 11 | Gender sensitization of local governments and Gender Capacity Assessment and Capacity Development Strategy (including TNA, Development of training materials and roll out of pilot triainings) |  |  | X | X | X |  |  |  |  | NCWC,DLG | Travel, training, workshop, TA(local, intl) Misc | 900000 | 1986660 | 2886660 |  |  | 2607255 |  | 0 | 0 | 0 | 2886660 | 0 | 0 | 64148 | 0
|  | Sub-total | [11 empty] | 3617155.8 | 10998720 | 14615875.8 | 2745000 | 0 | 9116470.8 | 0 | 0 | 4635000 | 0 | 9980875.8 | 0 | 102780.24 | 119017 | 0
4.0 Central government’s policy, regulatory, support and supervision functions strengthened LGSP Indicator; No. of official functional capacities in agencies strengthened | 1 | Support to LGs (elected/staff)to participate in relevant training in local governance and decentralization policy and programmes in the region. | [5 empty] | X | X |  |  | DLG, MoHCA | Ex- country travel, meeting/ workshops, | 233422.65 | 1102500 | 1335922.65 | 1102500 |  | 233422.65 |  | 0 | 1102500 | 0 | 233422.65 | 0 | 5187.17 | 0 | 0
| 2 | Exchange visit to Tanzania (MOF,DLG,GNHC,LGs) on best practices in national discretionary capital grant systems, fiscal reforms and resource allocation formulas. |  |  | X | [6 empty] | DLG, MoHCA | Ex- country travel, meeting/ workshops, | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
| 2 | Support for capacity development in fiscal decentralization |  |  |  | X | X |  |  |  |  | MoF | Ex- country travel, meeting/ workshops, | 0 | 900000 | 900000 | 225000 |  | 225000 |  | 0 | 675000 | 0 | 225000 | 0 | 5000 | 0 | 0
| 3 | Institutional support to DLG(website, ePABX system, LAN) |  |  |  | X | X |  |  |  |  | DLG, MoHCA | Equipments | 0 | 787500 | 787500 |  |  | 787500 |  | 0 | 0 | 0 | 787500 | 0 | 17500 | 0 | 0
|  | Sub-total | [11 empty] | 233422.65 | 2790000 | 3023422.65 | 1327500 |  | 1245922.65 |  | 0 | 1777500 | 0 | 1245922.65 | 0 | 27687.17 | 0 | 0
5.0 Effective models for integrated public service and information delivery at local levels LGSP Indicator: • no of models(integrated public service centres) tested and established and in operation -Newly elected(m/f) use new service rules -LGs make CD plans LGSP Indicator: • no of services availed online | 5.0.1 | Online system developed for atleast 10% of most commonly availed services developed and a server purchased |  |  |  | X | X | X | X |  |  | G2C | TA, equipments | 0 | 5113575 | 5113575 |  | 5113575 |  |  | 0 | 0 | 5113575 | 0 | 0 | 0 | 0 | 0
| 5.0.2 | Establish inter-operability framework (eGIF) |  |  |  | X | X | X | X |  |  | DIT/G2C | TA | 0 | 13365000 | 13365000 |  | 13365000 |  |  | 0 | 0 | 13365000 | 0 | 0 | 0 | 0 | 0
| 5.0.3 | Purchase of server and redundancy to host on-line services |  |  |  | X | [5 empty] | G2C | Equipmets | 0 | 3068100 | 3068100 |  | 3068100 |  |  | 0 | 0 | 3068100 | 0 | 0 |  | 0 | 0
| *5.0.4 | Study visit to Singapore | [9 empty] | DIT/G2C/DLG | Ex-country Travel | 0 | 1559250 | 1559250 |  | 1559250 |  |  | 0 | 0 | 1559250 | 0 | 0 | 0 | 0 | 0
| 5.0.5 | Equipment support for 25 OSS (computers, photocpier, fax, telephone, and other accessories) |  |  |  | X | X | X | X |  |  | DIT/DLG | Euipmets | 0 | 10453050 | 10453050 |  | 10453050 |  |  | 0 | 0 | 10453050 | 0 | 0 | 0 | 0 | 0
| 5.0.6 | Conduct awareness raising on set up of OSS and services availed from there |  |  |  | X | X | X | X |  |  | DIT/G2C/DLG | Training /workshop | 0 | 920250 | 920250 |  | 920250 |  |  | 0 | 0 | 920250 | 0 | 0 | 0 | 0 | 0
| 5.0.7 | Training/meetings for Local Government Officials on One-Stop Shops |  |  |  |  | X | X | X |  |  | DIT/G2C/DLG | Training/workshop/travel | 0 | 5727240 | 5727240 |  | 5727240 |  |  | 0 | 0 | 5727240 | 0 | 0 | 0 | 0 | 0
| 5.0.8 | Produce audio-visaul programmes for broadcast on OSS at the CCs and national media outlets | [9 empty] | DIT/G2C/DLG | TA | 0 | 2861640 | 2861640 |  | 2861640 |  |  | 0 | 0 | 2861640 | 0 | 0 | 0 | 0 | 0
Output 5.1 (DGTTF ) : Design and development of the integrated web portal Indicators 1.Development of common web portal 2.Development of assessment mechanism of customer needs Targets: 1. Integrated common gateway portal in place. 2. Voice of customer portal in place, with feedback mechanism. Baseline: No such portals exists | 5.1.1 | Development of an integrated citizen-oriented G2C Common web portal for all automated G2C services |  |  |  |  | X |  |  |  | DLG (MOHCA) | DLG/G2C | Local TA | 0 | 450000 | 450000 |  |  | 450000 |  | 0 | 0 | 0 | 450000 | 0 | 0 | 10000 | 0
| 5.1.2 | Development of a Voice-of-customer portal (grievance portal) to monitor citizens’ feedback and satisfaction |  |  |  |  | X |  |  |  |  | DLG/G2C | Local TA | 0 | 450000 | 450000 |  |  | 450000 |  | 0 | 0 | 0 | 450000 | 0 | 0 | 10000 | 0
| 5.1.3 | Approx 5 roadshows by G2C officials and vendor on the portal among communities | [5 empty] | X | X |  |  | DLG/G2C | Training/workshop | 0 | 540000 | 540000 |  |  |  |  | 0 | 0 | 0 | 540000 |  | 0 | 12000 | 0
| 5.1.4 | Publication of the user feedbacks(online and paper based surveys). | [5 empty] | X | X |  |  | DLG/G2C | Printing publication | 0 | 360000 | 360000 |  |  |  |  | 0 | 0 | 0 | 360000 | 0 | 0 | 8000 | 0
Output 5.2 (DGTTF ) : Improved technical capacity of service providers, implementers and citizens to implement and utilize e-Governance Indicators: i Technical skills of government service providers and district officials strengthened. ii . Project Management capacity of project officials strengthened. Targets: i. 250 service providers trained; 150 from central agencies (100m/50f) and 100 from districts (60m/40f). ii. 6 project officials (4m/2f) trained on Project management. Baseline: Necessary skills non-existent among the cadre of targetted officials | 5.2.1 | Training of Trainers (ToT) for service providers of various government agencies on the e-Service applications |  |  |  | X |  |  |  |  | DLG (MOHCA) | G2C/DLG | Training and workshop | 0 | 900000 | 900000 |  |  | 900000 |  | 0 | 0 | 0 | 900000 | 0 | 0 | 20000 | 0
| 5.2.2 | Train 100 district officials from 20 districts (groups of 25 - 30) as district and gewog level service providers |  |  |  |  | X |  |  |  |  | G2C/DLG | Training and workshop | 0 | 1035000 | 1035000 |  |  | 1035000 |  | 0 | 0 | 0 | 1035000 | 0 | 0 | 23000 | 0
| 5.2.3 | Project Management and service delivery course for Project officials (6 members) for effective management of the project. |  |  |  |  | X |  |  |  |  | G2C/DLG | Ex country Training and workshop | 0 | 1305000 | 1305000 |  |  | 1305000 |  | 0 | 0 | 0 | 1305000 | 0 | 0 | 29000 | 0
| 5.2.4 | Establishment of an online network for CC operators | [6 empty] | X |  |  | G2C/DLG | Consultant | 0 | 135000 | 135000 |  |  |  |  | 0 | 0 | 0 | 135000 |  | 0 | 3000 | 0
| 5.2.5 | Approx 10 advocacy meetings on the services for community representatives | [5 empty] | X | X |  |  | G2C/DLG | Training/workshop | 0 | 450000 | 450000 |  |  |  |  | 0 | 0 | 0 | 450000 |  | 0 | 10000 | 0
| 5.2.6 | Onsite reviews by G2C project officials | [5 empty] | X | X |  |  | G2C/DLG | In-country travel | 0 | 360000 | 360000 |  |  |  |  | 0 | 0 | 0 | 360000 |  | 0 | 8000 | 0
Output 5.3 (DGTTF ) : Development of outreach materials for advocacy and awareness Indicators :Citizen education materials developed Targets: Outreach materials distributed to all districts Baseline: G2C Awareness Brochure and introductory insertion developed. | 5.3.1 | Development of outreach materials | x |  | X | X | X |  |  |  | DLG (MOHCA) | G2C/DLG | Consultant | 225000 | 0 | 225000 |  |  | 225000 |  | 0 | 0 | 0 | 225000 | 0 | 0 | 5000 | 0
| 5.3.2 | Printing of materials in Dzongkha and English |  |  | X | X | X |  |  |  |  | G2C/DLG | Printing publication | 675000 | 0 | 675000 |  |  | 675000 |  | 0 | 0 | 0 | 675000 | 0 | 0 | 15000 | 0
| 5.3.3 | Development of audio visual clippings on SDS of the e-services | [5 empty] | X |  |  |  | G2C/DLG | Local consultant | 0 | 225000 | 225000 |  |  |  |  | 0 | 0 | 0 | 225000 | 0 | 0 | 5000 | 0
| 5.3.4 | Publication of audio-visual clippings on e-services | [6 empty] | X |  |  | G2C/DLG | Printing publication | 0 | 450000 | 450000 |  |  |  |  | 0 | 0 | 0 | 450000 | 0 | 0 | 10000 | 0
| 5.3.5 | Development of a 15-20 minutes audio-visual clippings on the overall G2C initiative | [6 empty] | X |  |  | G2C/DLG | Local consultant | 0 | 135000 | 135000 |  |  |  |  | 0 | 0 | 0 | 135000 | 0 | 0 | 3000 | 0
Output 5. 4 (DGTTF ) : Scale up strategy for MDGs | 5.4.1 | Development of scale up strategy for MDGs | x |  | X | X |  |  |  |  | UNDP/NEX | UNDP/NIM | Local TA | 225000 | 0 | 225000 |  |  | 225000 |  |  |  |  | 225000 | 0 | 0 | 5000
|  | Sub-total | [11 empty] | 1125000 | 49863105 | 50988105 | 0 | 43068105 | 5265000 | 0 | 0 | 0 | 43068105 | 7920000 | 0 | 0 | 176000 | 0
Project Assurance - Monitoring, Evaluation missions and participation in advocacy events | 1 | Support field visits for project staff to participate in-joint missions, evaluations, work plan meetings, monitoring &evaluation including advocacy initiatives |  |  | X | X | X | X | X | X | X | DLG , MoHCA | Travel, Misc. | 0 | 450000 | 450000 | 225000 |  | 225000 |  | 0 | 225000 | 0 | 225000 | 0 | 5000 | 0 | 0
| 2 | On site reviews |  |  |  |  | X |  | X |  |  | DLG, MoHCA |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Monitoring & Evaluation and Annual Technical Review mission support | X |  |  |  | X | X | X | X | X | UNDP/NIM | Travel, Misc. | 0 | 225000 | 225000 |  |  | 225000 |  | 0 | 0 | 0 | 225000 | 0 | 5000 | 0 | 0
| 4 | Monitoring & Evaluation and Annual Technical Review mission support | [9 empty] | UNCDF/NIM | Travel, Misc. | 0 | 900000 | 900000 |  |  |  | 900000 | 0 | 0 | 0 | 900000 | 0 | 0 | 0 | 20000
| 5 | Monitoring & Evaluation and participation during MTR, ARM, Quartely meeting |  | X | X | X | X | X | X |  |  | UNDP/NIM | Travel, Misc. | 31500 | 0 | 31500 |  |  | 31500 |  | 0 | 0 | 0 | 31500 | 0 | 0 | 700 | 0
| 6 | Joint Monitoring field visits UN Women project |  |  | X | X | X | X | X |  |  | UNDP/NIM | Travel, Misc. |  | 135000 | 135000 |  |  |  |  | 0 | 0 | 0 | 135000 |  |  | 3000 | 0
| 7 | Joint Monitoring flied visits G2C project | [5 empty] | X | X |  |  | UNDP/NIM | Travel, Misc. | 0 | 45000 | 45000 |  |  |  |  | 0 | 0 | 0 | 45000 | 0 | 0 | 1000 | 0
| 8 | Technical Assistance APRC G2C project (postpond to 2012) |  |  | X | X | X | X | X |  |  | UNDP/NIM | Travel, Misc. | 0 | 450000 | 450000 |  |  |  | 450000 | 0 | 0 | 0 | 450000 | 0 | 0 | 10000 | 0
| 9 | Facilities and Administration GMS (7%) | [9 empty] | UNDP/NIM |  | 0 | 397440 | 397440 |  |  | 309105 |  | 0 | 0 | 0 | 397440 | 0 | 0 | 8832 | 0
Project Management support | 10 | Contractual services of Assistant Project Manager(18th months) |  | X | X | X | X | X | X |  |  | DLG, MoHCA | Pay and Allowances | 0 | 517500 | 517500 | 517500 |  |  |  | 0 | 517500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total | [11 empty] | 31500 | 3119940 | 3151440 | 742500 | 0 | 790605 | 1350000 | 0 | 742500 | 0 | 2408940 | 0 | 10000 | 23532 | 20000
|  | GRAND TOTAL | [11 empty] | 8867070.45 | 239006695 | 247873765.45 | 134100900 | 53911035 | 18696523.95 | 14451466.5 | 86800000 | 70677000 | 53911035 | 23384263.95 | 13101466.5 | 181101.31 | 318549 | 311143.7
*Output 5, Actvity 5.0.4 “Singapore trip is only conditionally approved”,
Contribution from each donor in 2011-2012 |  |  |  | Contribution of each Developmental partner as per the AWP (total contribution 2008-2013)
ADA |  | Contibution till June, 2011 | [5 empty] | Euros 500,000(capacity bldg)
ROD |  | DKK 900,000 | [5 empty] | DKK 25,000,000( Grants and and Capacity Bldg)
DKK 7,500,000(Block grants)
|  | *DKK 18,750,000(Block Grants) | [5 empty] | DKK 40,000,000, (SESP contribution to Block Grants)
SDC |  | CHF 250,000(Block Grants) | [5 empty] | CHF 1,000,000.00 (Block Grants)
|  | CHF 1,500,000 | [5 empty] | CHF 829797.00(capacity Bldg)
UNDP |  | USD 181,101.3 | [5 empty] | USD 1,500,000
UNDP/OR |  | USD DGTTF 187,700
USD UN Women 130,849
UNCDF |  | USD 111,143.7 | [5 empty] | USD 750,000 (additional 50,000 formulation phase)
|  | USD 200,000 | [5 empty] | USD 100000 (Block grants) USD 100000 ( Performance grants CCA)
EU |  | Euros 1,400,000(Block Grants) | [5 empty] | Euros 2,800,000(block grants)
Curreny exchange rates udes US$ 1= Nu.45; DKK 1= Nu.8.1 ; CHF 1= Nu. 45;
Euros 1 = Nu.62
NOTE: Linked to Porject Document : UNDAF 2008 – 2012 Outcome 4: By 2012 institutional capacity and peoples' participation strengthened to ensure good governance (MDGs1, 3, 8). LGSP Output 1 linked to CT Output 4.4.3 LGSP Output 2 linked to CT Output 4.4.1 and 4.4.3 LGSP Output 3 linked to CT Output 4.4.2 LGSP Output 4 linked to CT Output 4.4.1 LGSP Output 5 linked to CT Output 4.4.1 and 4.4.2