STANDARD PROGRESS REPORT

FINANCIAL YEAR: 2013

REPORTING PERIOD: Q4 Report (November-December)

| Administrative Unit: Ministry of Labour and Human Resources | Department: Department of Employment |
| --- | --- |
| Division/Field Office/Regional Office: (if it is an independent budgeting entity) | Program & AWP Title: Support to MoLHR for strengthening labour market analysis and employment generation especially among youth and women (AWP Title: Labour Market Analysis and Employment Generation) |

- Contribution to UNDAF Outcomes & Other Goals

| Classification (e.g. UNDAF Outcome, MDGs) | Indicators | Baseline | Targets | Progress |
| --- | --- | --- | --- | --- |
| By 2012, opportunities for generation of income and employment increased in targeted poor areas (MDG 1,8) | Unemployment rate, by gender, age group, rural-urban Labour force participation rate – by gender, age group and rural, urban areas | 3.7%(BLSS 2007) 67.3%(BLSS 2007) | 2.5% | 2.1% |

2. 	Contribution to CT Outcomes

| Outcome | Indicators | Baseline | Targets | Progress |
| --- | --- | --- | --- | --- |
| 1. New Micro and SME and jobs created with emphasis on women and youth | Number of MSMEs availing Micro finance and business development |  |  | The tailoring training enabled most of the trainees in setting up their own businesses. |

3.	Output & Activity Progress Details

| Outputs & Activities | Indicators | Annual Target | Physical Progress | Budget (Nu.) (A) | Expenditure (Nu.) | Analysis of Variance (explain progress and the difference between Planned target and actual progress) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Current Quarter | Cumulative |  | Current Quarter | Cumula tive (B) | Balance (A)-(B) |  |
| Output 2: Community based MSMEs and cooperatives, particularly those of women and youth supported through improved access to micro-finance, business development services, marketing, group formation and post harvest management services | No. of prospective entrepreneurs trained in entrepreneurship and skills development (by gender, age) | 80 (50 female and 30 male) |  |  |  |  |  |  |  |
| Activity 1: Conduct tailoring training |  |  | 40 (34 female and 6 male) | 77 (68 Female and 9 Male) | 955,130.00 | 476,193.00 | 909,323.00 | 45,807.00 | No. of prospective entrepreneurs trained in entrepreneurship and skills development (by gender, age) |
| Activity 2: Develop audio-video on ‘Educating for positive attitude to job’ including messages to parents and award contract for regular broadcast/transmission. | Number of orientation programmes in schools and institutes on employment and career related issues |  | Developedaudio-video on ‘Educating for positive attitude to job’ |  | 543,700.00 | 241867.78 | 543700.00 | 0.00 | Audio-Video on ‘Educating for positive attitude to job’ developed. It will be transmitted in the next cycle. |
| Activity 3: Train MOLHR Staff in policy analysis and strategic planning with focus on strengthening functional capacities in reviewing, coordinating and implementing policies |  | Train at least 2 MOLHR staff |  |  | 650,000.00 | 650,000.00 | 650,000.00 | 0.00 | 7 MOLHR staff trained in policy analysis and strategic planning. The participants would be analyzing the labour force survey report as part of the learning outcome of the training. |
| Activity 3: Organize multi-sectoral advocacyand awareness (panel) programme in schools, colleges, TTIs & IZCs to encourage entrepreurship, vocational education and to instill positive attitude towards jobs, among youth. |  | At Least 20 TTIs, IZC and Schools covered | Conducted awareness in all TTIs and IZCs and also organized Job Fair at S/Jongkhar |  | 918,000.00 | 632,572.22 | 632,572.22 | 286,028.00 | Conducted awareness in all TTIs and IZCs and also organized Job Fair at S/Jongkhar |
| Total |  |  |  | 3,066,830.00 | 2,000,633.00 | 2,735,595.22 | 331,835.00 |  |

4.	Summary of Issues & Recommendations

| Key Achievements: (Highlight the main achievements in the current Quarter) | 40 people (34 female and 6 male) undergoing tailoring training. Developed audio-video on educating for positive attitude to job. |
| --- | --- |
| Constraints & Issues: (List the constraints/problems & issues faced) | The requirement for 80% financial delivery against fund releases for a particular quarter constraints activity implementation. |
| Recommendations: (Include your recommendations/remedial actions to improve implementation.) |  |
| Additional comments: |  |

| Prepared by | Name: | Gap Tshering | Designation: | Program officer | Agency: | PPD, MoLHR | Date: | January 9, 2014 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |