## Sheet1
ANNUAL WORK PLAN 2015:
Results Group: Environment and Climate Change
National Priorities & Goals | Vision 2016: A Prosperous, Productive and Innovative Nation
NDP10 MTR: Sustainable Management of Natural Resources; Pollution Prevention and Control; Climate Change/Global Warming
MDGs: Ensure Environment Sustainability: Eradicate Extreme poverty and hunger
UNDAF Outcome | By 2016, The rural poor, especially women, will derive greater benefit from the Environment and Natural Resources
COUNTRY PROGRAMME OUTCOME 4.1: Inceased uptake and utilisation of environmental information for decision making by key national institutions, civil society, private sector, individuals
Country Programme Output 4.1.1 Increased Access to Environmental Information
Activity output/result | Annual Indicators, baseline and targets | Activities | Implementing Partner | Q1 | Q2 | Q 3 | Q4 | Responsible UN Agency | Resources (US$)
[9 empty] | Funding Target UN | Funded UN | funded Gov | Total Funding
Strengthened Capacity in the implementation of the MEAs | Baseline: Basic EIS in place but not adequate. Other information systems exist (e.g. ODIS) (some stats for EIS exist, but baseline to be specified during strategy development) (State of Environment Reporting Framework exists; ESP PRODOC; EIS database under development; environmental indicators being developed) Indicator:______;Target: A fully-functional EIS | Engage an Environmental Assessment Expert to work with DEA in order to provide in-house training on Environmental Impact Assessment Reports and Strategic Environmental Assessment including monitoring. | DEA, EIA Sector |  | x |  |  | UNDP |  | 18 |  | 18
Sub total | [8 empty] | 0 | 18 | 0 | 18
Country Programme Output 4.1.2: Utilisation of Environmental information for deciosion making promoted
Activity outputs/result | Indicators, baseline and targets | Activities | Implementing Partner | Q1 | Q2 | Q3 | Q4 | Responsible UN Agency | Resources (US$)
[9 empty] | Funding Target UN | Funded UN | funded Gov | Total Funding
Building Transformative Frameworks Policy and Financing Frameworks to Increase Investment in Biodiversity Management | baseline: ________, indicators: ___, target: ________ | Policy & institutional Review (10 weeks over 6 months)workbooks 1a (Policies review) and 1b (Institutional review) completed an approved | MEWT, MFDP and other stakeholders | x |  |  |  | UNDP & German Government |  | 25 |  | 25
| baseline: ________, indicators: ___, target: ________ | Public expenditure Review (10 weeks over 6 months) workbook 1c (public expenditure review) completed an approved |  |  | x |  |  |  |  | 90 |  | 90
| baseline: ________, indicators: ___, target: ________ | Private Expenditure Review (14 weeks over 6 months) workbook 1c (private expenditure review) completed and approved |  |  |  | x |  |  |  | 35 |  | 35
| baseline: ________, indicators: ___, target: ________ | ap Assessment & Costing of NBSAP (20 weeks over 1 year) and resource mobilisation strategy. workbooks 3a (finance actors identified |  |  | x |  |  |  |  | 50 |  | 50
| baseline: ________, indicators: ___, target: ________ | Technical assistance towards NBSAP costing and resource mobilissation. Technical assistance towards completion/finalisation of workbooks & finance mechanisms developed) and 3b (operational plan for resource mobilisation) completed and approved |  |  |  |  | x |  |  | 20 |  | 20
| baseline: ________, indicators: ___, target: ________ | Project management (BIOFIN national team, meetings, workshops, missions and travel). planned NBDA steering committee meetings conducted, - progress workshops to update stakeholders, solicit input conducted |  |  |  |  | x |  |  | 41.8 |  | 41.8
Sub total | [8 empty] | 0 | 261.8 | 0 | 261.8
Country Programme Outcome No 4.2.: Sustainability principles integrated into National Development Planing and implementation
Country Programme Output 4. 2.1. NSSD developed
Activity outputs/result | Indicators, baseline and targets | Activities | Implementing Partner | Q1 | Q2 | Q3 | Q4 | Responsible UN Agency | Resources (US$)
[9 empty] | Funding Target UN | Funded UN | funded Gov | Total Funding
National Strategy for Sustainable Development (NSSD) developed and implemented | Baseline:_____; Indicators: _____ ; Target: _______ | Stakeholder consultations completed | MEWT-DEA, MFDP, Relevant Sector Ministries/Departments | x |  |  |  | UNDP |  | 80 |  | 80
|  | National framework for sustainable development formulated |  |  |  | x |  | UNDP |  | 50 |  | 50
|  | Sustainable Development oversight structures functional |  |  |  |  | x | UNDP |  | 20 |  | 20
|  | Capacity development and benchmarking carried out. |  |  | x |  |  | UNDP |  | 25 |  | 25
|  | Expert sector studies undertaken |  |  |  |  | x | UNDP |  | 35 |  | 35
|  | Communication material Developed |  |  |  | x |  | UNDP |  | 10 |  | 10
Gaborone Declaration for Sustainable Development | Baseline:_____; Indicators: Strategy in place; Target: Strategy in place | Technical support to Gaborone Declaration and Botswana’s contribution to other regional sustainable development initiatives | MEWT-DEA, MFDP, Relevant Sector Ministries/Departments |  |  | x |  | UNDP |  | 20 |  | 20
Sub total | [9 empty] | 240 | 0 | 240
CP output 4.2.2.: Sustaibabilty mainstreamed into NDP 11, Vision 2016 and District Development Plans
NDP11 Sustainable development integrated into NDP11 and Vision beyond 2016 | Baseline: Documents still being developed; Indicators: Sustainability criteria; Target: Sustainability criteria / approach met. | Sustainable Development integrated into district and urban plans (DDP8/UDP4) | MEWT-DEA, MFDP, Relevant Sector Ministries/Departments |  | x |  |  | UNDP |  | 70 |  | 70
|  | NDP11 framed on sustainable development |  |  | x |  |  | UNDP |  | 30 |  | 30
|  | NDP11 Thematic Chapters based on sustainable development |  |  | x |  |  | UNDP |  | 60 |  | 60
|  | M&E Framework of NDP11 integrates sustainable development |  |  |  | x |  | UNDP |  | 20 |  | 20
|  | Sustainability appraisals of key NDP11 programmes and projects |  |  |  |  | x | UNDP |  | 30 |  | 30
|  | Capacity of Planners and Thematic Working Groups on Sustainable Development enhanced |  |  |  | x |  | UNDP |  | 15 |  | 15
|  | Key decision makers exposed to best practices on sustainable development from other countries |  |  | x |  |  | UNDP |  | 25 |  | 25
|  | Sustainable Development facilitation structures functional |  |  |  |  | x | UNDP |  | 25 |  | 25
Sub total | [9 empty] | 275 | 0 | 755
National Policies and Institutuions promote and support the Particpation and Beneficiation of Communities in Natural Resources Management
Country Programme Outcome 4.2.1 Improved national capacity and community participation (especially women and youth) in management of water resources, including trans-boundary, management, sanitation and hygiene
Country Programme output4.2.1.1 Strengthened capacities for management of water resources, pollution and sanitation for increased increased awareness
Activity outputs/result | Indicators, baseline and targets | Activities | Implementing Partner | Q1 | Q2 | Q3 | Q4 | Responsible UN Agency | Resources (US$)
[9 empty] | Funding Target UN | Funded UN | funded Gov | Total Funding
Development of a Full Size Project UNDP/GEF project on Promoting Production and Utilization of Bio-Methane from Agro-Waste in South Eastern Botswana | baseline: ________, indicators: ___, target: ________ | Full Size PRODOC for submission to the GEF Council to facilitate approval by June 30, 2015 | MEWT-DFRR, MOA-DAP, BMC, NWDC,NGO's, UB-ORI |  | x |  |  | UNDP |  | 10 |  | 10
Sub total | [8 empty] | 0 | 10 | 0 | 10
Country Programme 4.2.2 The capacities of communities (especially women and youth) for ecosystem management and benefit acquisition
Activity outputs/result | Indicators, baseline and targets | Activities | Implementing Partner | Q1 | Q2 | Q3 | Q4 | Responsible UN Agency | Resources (US$)
[9 empty] | Funding Target UN | Funded UN | funded Gov | Total Funding
Mainstreaming SLM in Ngamiland Productive Landscapes | baseline: ________, indicators: ___, target: ________ | Improves range condition and flow of ecosystem services to support livelihoods of local communities in Ngamiland | MEWT-DFRR, MOA-DAP, BMC, NWDC,NGO's, UB-ORI |  |  |  | x | GEF |  | 920 |  | 920
| baseline: ________, indicators: ___, target: ________ | Effective resource governance frameworks and markets provide incentives for livestock off-take and compliance with SLM | MEWT-DFRR, MOA-DAP, BMC, NWDC,NGO's, UB-ORI |  |  | x |  |  |  | 360 |  | 360
|  | Project Management |  |  |  |  | x |  |  | 40 |  | 40
Sub total | [9 empty] | 1320 | 0 | 1320
Improved Management Effectiveness of the Chobe-Kwando-Linyanti Matrix of Protected Areas | baseline: ________, indicators: ___, target: ________ | Collaborative Governance framework in place in PA's and Buffer Zones resulting in reduced threats to Biodiversity and Economic Growth | MEWT-DWNP,DFRR, Chobe District Council, NGO's, CBO's, UB-ORI |  | x |  |  | UNDP/GEF |  | 390 |  | 390
| baseline: ________, indicators: ___, target: ________ | Management Effectiveness and financial Sustainability in Core Protected Areas strengthened to address existing and emerging threats to Biodiversity |  |  |  | x |  |  |  | 320 |  | 320
|  | Project Management |  |  |  |  | x |  |  | 100 |  | 100
Sub Total | [9 empty] | 810 | 0 | 810
SLM Makgadikgadi | baseline: _____, indicators: ___, target: ________ | SLM in Sua Pan | MEWT-DFRR, MOA-DAP, NWDC, NGO's | x |  |  |  | UNDP/GEF |  | 200 |  | 200
| baseline: ____, indicators: ___, target: ______ | Effective Resources Governance |  |  |  | x |  |  |  | 41 |  | 41
|  | Project Management |  |  |  |  | x |  |  | 137 |  | 137
Sub total | [9 empty] | 378 | 0 | 378
Securing environmental benefits through community based initiatives |  | Increased access to funds for CSOs to manage natural resources (still to be allocated) | CBO's, NGO's |  |  |  | x | GEF/SGP |  | 82 |  | 82
|  | Capacity development for NGOs and CBOs for effctive implementation projects (still to be allocated) | CBO's, NGO's |  | x |  |  |  |  | 50 |  | 50
|  | Regulation of Agro-Chemicals to Avert Killing of Non-Target Species: Vultures as Case Study (Otse, South East) | Cape Vulture Environmental Association, Birdlife Botswana, DWNP, MoA |  |  | x |  |  |  | 25 |  | 25
|  | Enhancing sustainble use of Bathoen Dam Nature Sanctuary through tourism (Kanye, Southern) | Bathoen Dam Nature Sanctuary Management Trust; DWNP, BTO, DWA, TA, SDC, DC, DoT |  | x |  |  |  |  | 24 |  | 24
|  | Enhancing environmental conservation and sustainable utilisation of natural resources in Jackalas 1 ( Jackalas 1, North East) | Mazibakufa Development Trust; DWNP, BTO, DWA, TA, NEDC, DC, DoT |  |  |  | x |  |  | 5 |  | 5
|  | Mural against destruction of water resources: Effective public participation in the management of water bodies (in Mabalane, Sikwane, Mmathubudukwane, Ramonaka,Malolwane & Olifants Drift, Kgatleng) | Botswana Gourds Association; DWA, TA, KDC, DC, |  |  | x |  |  |  | 5 |  | 5
|  | Maun Public Waste Drop - Off and Recycling Centre (Maun, Ngamiland) | Tlhare Segolo Foundation; DWMPC, TA, DC, NWDC, KBL, Collect A Can, Duma Tau, Dung Beetle Logistics |  |  |  | x |  |  | 25 |  | 25
|  | The Reclamation and Regeneration of Land Within Mokolodi Nature Reserve (Mokolodi) | Mokolodi Wildlife Foundation; DFRR, DWNP, Botswana College of Agriculture |  |  |  | x |  |  | 5 |  | 5
|  | Establishment of Mantenge Botanic Garden: An Enhancement of Carbon Stocks in Botswana (Kalakamati, North East) | Kalakamati Mantenge Conservation Trust; DWNP, BTO, DWA, TA, NEDC, DC, DoT |  |  | x |  |  |  | 25 |  | 25
|  | Empowering effective Civil Society participation in the implementation of the Makgadikgadi Framework Management Plan (Makgadikgadi ecosystem, Central Boteti) | BirdLife Botswana; DWNP, DEA, TA, DC,CDC |  |  | x |  |  |  | 57 |  | 57
|  | Enhancing waste management through glass recycling (Mochudi, Kgatleng) | Botswana Workcamps Association; DWMPC, TA, DC, KDC, KLB, Somarelang Tikologo, Recycle It Botswana, Dumatau, Collect A Can |  |  |  | x |  |  | 35 |  | 35
|  | Conservation of the African bees through bee-keeping and agro-forestry in Diabo (Diabo, Southern) | Climate Action Group Association; MoA (Bee keeping), SDC, DC, TA, DWNP |  |  |  | x |  |  | 25 |  | 25
|  | Environmental Conservation and Sustainable Utilisation of Natural Resources in Nlapkhwane ( Nlapkhwane, North East) | Nlapkhwane Lingilila Environmental Conservation Trust; DWNP, DFRR, NEDC, DC, TA | [6 empty] | 10 |  | 10
Sub total | [9 empty] | 373 | 0 | 373
Enhanced National Policy Frameworks and Institutional capacities for efefctive Climate Change Adapatation and Mitigation
Country Programme Outcome 4.3.1 National and Sub-National integrated Cliamte Change and Adapatation and Mitigation Policy, Stargety and Action Plan Developed
Country Programme output 4.3.1.1 National and sub-national integrated climate change adaptation and mitigation policy, strategy and action plan developed
| Indicators, baseline and targets | Activities | Implementing Partner | Q1 | Q2 | Q3 | Q4 | Responsible UN Agency | Resources (US$)
[9 empty] | Funding Target UN | Funded UN | funded Gov | Total Funding
National climate change policy formulated and mainstreamed into National Development Plans | baseline: ________, indicators: ___, target: ________ | Climate Change policy, strategy and action plan developed | MEWT - DMS, All Ministries and Departments; Ags Chambers, BOTEC, BOBS; BOCCIMCSIR, ICSO, IPCC, NGOs |  | x |  |  | UNDP |  | 6 |  | 6
| baseline: ________, indicators: ___, target: ________ | Monitoring and Evaluation Framework developed |  |  |  | x |  |  |  | 18 |  | 18
| baseline: ________, indicators: ___, target: ________ | Implementation Framework developed |  |  |  |  | x |  |  | 15 |  | 15
Sub total | [8 empty] | 0 | 39 | 0 | 39
Third National Communication | baseline: ________, indicators: ___, target: ________ | Preparation of INDCs to the 2015 UNFCCC agreement | MEWT - DMS, All Ministries and Departments; Ags Chambers, BOTEC, BOBS; BOCCIMCSIR, ICSO, IPCC, NGOs |  |  |  |  | UNDP |  | 90.91 |  | 90.91
| baseline: ________, indicators: ___, target: ________ | National Circumstances |  |  | x |  |  |  |  | 10 |  | 10
| baseline: ________, indicators: ___, target: ________ | GreenHouse Gas Inventory |  |  |  | x |  |  |  | 86.5 |  | 86.5
| baseline: ________, indicators: ___, target: ________ | Vulnerability and Adaptation |  |  |  | x |  |  |  | 114 |  | 114
|  | Mitigation |  |  | x |  |  |  |  | 21 |  | 21
|  | Compilation and Production of BUR and TNC |  |  |  | x |  |  |  | 19 |  | 19
|  | Monitoring & Evaluation |  |  |  | x |  |  |  | 10 |  | 10
| baseline: ________, indicators: ___, target: ________ | Other information considered relevant to the achievement of the Convention |  |  |  |  | x |  |  | 114 |  | 114
|  | Project Management | [7 empty] | 22 |  | 22
Sub total | [8 empty] | 0 | 487.41 | 0 | 487.41
[8 empty] | Grand Total | 4692.21