Basic Project Information

| Project Duration | From 15 September, 2015 to 14 September, 2020 |
| --- | --- |
| Reporting Period | January- March.2015 |
| Implementing Partners | Ministry of Environmental Protection/ Foreign Economic Cooperation Office (FECO) |
| Other UN/International Collaborating Agencies | UNDP |
| Cost-sharing Third Parties |  |
| UNDP PM/PA | Ma Chaode |

Executive Summary

This QPPR summarized the main project activities and outputs in the 1st quarter of 2017, evaluated the sufficiency of project management and oversight efforts, assessed project progress against 2017 YWP. In this quarter, the Inception Report and the 2017-2018 TYWP were submitted. The sub-contracts with Yunnan, Hunan, and Guangxi were drafted, and the kick-off meeting of Pilot demonstrations on ABS in Yunnan province and the detailed survey were  organized during the 25th to 28th March, which support an enhanced understanding of genetic resources and associated traditional knowledge, related ABS opportunities and associated barriers, which is essential in providing a pipeline of additional work and opportunities related to ABS work in Yunnan province, while highlighting the nature and extent of such opportunities. The corresponding meetings and surveys in Hunan and Guangxi are planned to be finished in April.

Total expenditure of this quarter is 72,786.09 USD.

The “Executive Summary” section should be a summary (max 250 words) of the outcome section of this report and should summarize the report, highlighting key outcomes and achievements. Please include the main quantitative results of the project (e.g. 10 Mu of rice planted, 4 men and 2 women trained) and other such measurable evidence related to the progress of the specific outcomes listed.

- Project Implementation Status and Progress Report (Report against AWP)

  - Outcome & Output Progress Report

UNDP China CPD Indicator(s)

| Indicator Description | Progress Report |
| --- | --- |
| Indicator 2.1.3: Extend to which adopted regulations, ordinances and standards bring about stronger biodiversity protection | In progress |

UNDP SP Indicator(s)

| Indicator Description | Progress Report |
| --- | --- |
| Indicator 3.2.1 Ratio of expenditure to budget allocation received at the sub-national level (recurrent and capital) | In progress |
| Indicator 7.6.2 Number of pilot and demonstration projects initiated or scaled up by national partners (e.g. expanded, replicated, adapted or sustained) | In progress |

Project Outcome/Output Indicator(s)

| Indicator Description | Progress Report |
| --- | --- |
| Nagoya Protocol accession enabled | Completed |
| Status of adoption and/or implementation of the National ABS Framework at national level | In progress The TOR for this activity is under preparing, which will be finished before the end of April. |
| Status of adoption and/or implementation of the National ABS Framework at sub-national levels | This activity will be started preparing after the sub-contracts with the three pilot provinces signed. |
| Incentives for biodiversity conservation | This activity will be started preparing after the sub-contracts with the three pilot provinces signed. |
| Elements (policy, legislation, guidance) of a national framework | In progress The related draft law has been released to the public for general discussion. |
| Incentive programs and codes of conduct for major commercial sectors | This activity will not be implemented this year as planned. |
| Guidance for adoption of relevant sub-national legislation | This activity will not be implemented this year as planned. |
| Instruments and mechanisms necessary to formally establish elements of the national framework | In progress National ABS clearinghouse has been maintaining as planned. |
| Guidance documents re. elements of the national framework | This activity will not be implemented this year as planned. |
| National-level institutional capacity for ABS implementation | In progress Case studies and training material on the basis of the pilot/demos and the legislation, procedures and contracts are under developing, which will be incorporated into staff training programs. |
| Provincial-level institutional capacity for ABS implementation in Yunnan Province, Guangxi Autonomous Region and Hunan Province | In progress This activity will be started preparing after the sub-contracts with the three pilot provinces signed. |
| Understanding of local ABS opportunities at the level of pilot provinces and jurisdictions | In progress PMO have been disseminating the information about GRs and ATK in three provinces. |
| Quantity and nature of ABS agreements in China | In progress This activity will be started preparing after the sub-contracts with the three pilot provinces signed. |
| Jurisdictions with ABS implementation experience | In progress This activity will be started preparing after the sub-contracts with the three pilot provinces signed. |
| Local communities benefit from GR and ATK utilization | In progress This activity will be started preparing after the sub-contracts with the three pilot provinces signed. |
| Availability of best practice information on ABS implementation in China | In progress This activity will be started preparing after the sub-contracts with the three pilot provinces signed. |

  - Activity Implementation Status Report

Activity 1.1 The project undertook PMO participating in the COP-MOP2 of the Nagoya Protocol, the conference was hold in the December of 2016, which the expense account was submitted in January, 2017.

Please list out all the other key activities delivered in this quarter not covered by above section. Please do not exceed 2 page. e.g. Activity 1.2 The project undertook three trainings/workshops on hand weaving involving 85 women and 12 men

- Finance Management

Please mark with red the ‘Accumulated Quarterly Delivery Rate’ box (Accumulated Expenditure/ Accumulated Budget) if the delivery rate is under 60%. For delivery rate ranging from 60% to 85%, please mark with yellow. For delivery rate in the range of 85% - 100%, please mark with green. Comments must be provided for delivery rates of outputs marked with red and yellow texts. The content of comment should cover reasons for low delivery rate and action plans for catching up.

The estimated expenditure rate of Q1 2017 accounted for approximately 5% of total budget 2017, and it was nearly half of the quarterly budget. According to the financial analyzing, the spending rates of outcome 1, 2, 3 respectively were 452.35%, 165.28% and 22.59%. It was meanly because that it is still going through the procedure for signing the sub-contracts with the three pilot provinces Yunnan, Hunan and Guangxi for outcome 3. It’s expected to cover the budget during Q2 2017. The project requires that all three provincial pilots to develop appropriate schemes after signing the agreements/contracts to meet the requirement of the year-work-plan.

(Detailed information see annex)

| Output | Annual Budget (USD) | Accumulated Expenditure (USD) | Quarterly Budget (USD) | Quarterly Expenditure (USD) | Accumulated Quarterly Delivery Rate% | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Output 1 | 381,640 | 34,152.66 | 7,550 | 34,152.66 | 452.35% |  |
| Output 2 | 328,300 | 34,795.98 | 21,052.5 | 34,795.98 | 165.28% |  |
| Output 3 | 717,550 | 3,837.45 | 16,987.5 | 3,837.45 | 22.59% | It’s going through the procedure for signing the sub-contracts with the three pilot provinces. Therefore, the payments of sub-grants have to be delayed to Q2 2017. |
| PM | 49,306 | 0 | 14,691.5 | 0 | 0% | It will be calculated together with the expenditure in Q2 |
| Total | 1,476,796 | 72,786.09 | 60282 | 72,786.09 | 120.74% |  |

- Project Management and Oversight

  - Risk Log Status Update

| Description | Status | Management Response |
| --- | --- | --- |
| Controversy or other factors might delay or prevent China’s accession to the NP, which could in turn delay legislative development. | Reducing | N/A |
| Ministries and government agencies potentially affected by/involved in ABS unable to agree on coordinate of relevant activities and mandates (key prerequisite to legislation) | Reducing | N/A |
| The Pilot/demos could be negatively impacted if targeted commercial users determine that they should not participate in the pilots. | Reducing | N/A |
| Commercial confidentiality restrictions may limit information sharing on development process | Reducing | N/A |
| Biopiracy risks increase as specific data (ATK, genetic code, etc) is transferred and committed to writing. | No Change | N/A |
| Delay in the complex, time-consuming Chinese legislative process may affect timely commencement or completion of other aspects of the project. | No Change | N/A |
| MEP and pilot province staff may not have the benefit of a policy and regulatory environment that gives them adequate opportunity and authority to engage productively in ABS framework development and oversight. Delay in the complex, time-consuming Chinese legislative process may affect timely commencement or completion of other aspects of the project. | No Change | N/A |
| MEP and pilot province staff may not have the benefit of a policy and regulatory environment that gives them adequate opportunity and authority to engage productively in ABS framework development and oversight. | No Change | N/A |
| Climate change is having a negative impact on genetic resources, with potential implications for ABS | No Change | N/A |
| Risk associated with effective involvement of local populations such as producers | Reducing | N/A |

| # | Description | Status | Management Response |
| --- | --- | --- | --- |
| 1 | Copy from your Risk Log in ProDoc Annex | Reducing, increasing, no change | N/A if the status is reducing or no change. |
| 2 | Copy from your Risk Log in ProDoc Annex | Reducing, increasing, no change | N/A if the status is reducing or no change. |

  - Communication and Advocacy

During the Yunnan kick-off meeting and the survey, PMO conducted extensive consultation and advocacy campaigns targeting commercial stakeholders in pilot areas to stimulate awareness and interest. The communication and advocacy strategy is being developed, which is planned to be finished in 2nd quarter.

- Briefly (<250 words) highlight significant communications and advocacy efforts undertaken during the reporting period. Does the project have a communication and advocacy strategy? If not, is one required?

  - Management Recommendations

1. Only full support by Recipient country government (GOC) and cooperation between relevant public and private stakeholders can lead to successful projects.

2. Productive engagement of the private sector at all phases, including project design, implementation, and evaluation can result in a multiplier effect for achieving related goals.

3. A simple project document with step-by-step guidance on implementation, clearly delineated roles and responsibilities, and defined financial resources is essential for guiding a smooth implementation process.

4. M&E incorporated into various project activities facilitates cross-referencing of achievements and results. However, the presence of a project-level M&E/tracking system is essential to guide the project’s reporting and activity coordination against planned outcomes and targets.

5. Selection of competitive organizations for sub-contracts and project delivery is crucial for overall project performance.

The “management recommendations” section should highlight any key lessons learned and list any other recommendations that towards how the project could increase its current level of success and that not covered in above sections. This section should review the key judgments made in the report, note lessons learned from all significant problems identified, and use these judgments and lessons to make appropriate recommendations of action required.

3.4	New opportunities/Initiatives

According to the communicating in COP-MOP2, there’re some foreign enterprises could be invited to participate the project to enrich practice, investigation, and analysis of ABS institution, and provide experiences for ABS in China. There are some enterprises using genetic resources going on in China, for example, the Louis Vuitton Moet Hennessy, which produces items from exceptional natural materials, such as the unique cashmere and baby cashmere found in Northern China. It launched a pilot project in China in 2009 aiming to protect the quality of its cashmere supplies and develop the entire sector on a sustainable basis. LV’s skincare range is manufactured in France using extracts from Pu’er Tea tree leaves from the ancient forests of Yunnan, China’s “green lung”. LV has also launched a pioneering initiative in China by having its 21 stores in Shanghai supplied by electric trucks. The teleconference with LV is planned on 2nd May.

New opportunities under the project and potential initiatives that could have positive impact to the project. No more than 150 words.

3.5	Engagement of target groups

During all the activities implementing period, PMO seek to enhance the understanding of ABS and the ability to participate appropriately in ABS transaction of target groups, which  including decision-makers and public, research institutions, pilot enterprises, NGOs, etc. The seminars and training courses for the above target groups are under developing. Strategic awareness raising and capacity building will be conducted for target groups.

Engagement of target groups during project implementation, no more than 150 words.

3.6 	Gender equality and gender activities

Based on the representatives participated in the kick-off meeting of Yunnan Pilot demonstration on 26th March, more than half of which are female. That is to say, more women participated in the pilot demonstration project.

Element of gender equality in this project and/or emphasis on gender disaggregated data for programme beneficiaries, no more than 150 words.

- Annex (Provided by UNDP programme staff before uploading onto the intranet)

  - Project Budget Balance (PBB) Report

| ABS Project Quarterly Progress Report Q1 2017 |
| --- |
| Project ID and Project Name:5533 Developing and Implementing the National Framework on Access to and Benefit Sharing of Genetic Resources and Associated Traditional Knowledge |
| EXPECTED OUTPUTS/OUTCOMES INDICATORS | PLANNED ACTIVITIE | TIMEFRAME 2017 | RESPO-NSIBLE PARTY | PLANNED BUDGET |
| Output/outcome indicators and annual indicator targets/ benchmarks (if applicable) | List all activities to be undertaken (including evaluations and publications etc.) | Jan | Feb | Mar |  | Source of Funds | COA | Description | Annual Budget(USD) | Expenditure of the current reporting period(USD) |
| Outcome 1 Establishment of a national regulatory and institutional framework on ABS |
| Output 1.1 State Council of China is provided with information needed to formally approve accession to the Nagoya Protocol and provide support to the National Implementation Program for Nagoya Protocol（Indicator: China accession to NP, and draft for National Implementation Program for Nagoya Protocol) |  |  |  |  |  |  |  |  |  |  |
| Output 1.1 State Council of China is provided with information needed to formally approve accession to the Nagoya Protocol and provide support to the National Implementation Program for Nagoya Protocol（Indicator: China accession to NP, and draft for National Implementation Program for Nagoya Protocol) | Activity 1.1.1: Organize the Inception meeting and the 1st meeting of Project Steering Committee (PSC) | 0% | 0% | 0% | MEP | GEF |  | inception workshops&PSC meeting $3,000*1 | 0 | 0.00 |
|  | Activity 1.1.2: Organize the 2nd meeting of Project Steering Committee (PSC) |  |  | 100% | MEP | GEF | 75700 | 2nd PSC meeting $3,000*1 | 3000 | 0.00 |
|  | Activity 1.1.3： Research on international ABS focuses and national experience of foreign countries and ABS case studies | 0% | 100% | 0% | UNDP | GEF | 7120000% | International Consultants for international experience introducing, 1 person, part time $3,000/mw | 72000 | 0.00 |
|  | Activity 1.1.4: Case studies on foreign bio-prospecting in China | 0% | 0% | 100% | MEP | GEF | 72100 | 2 local consultants, from ABS related sectors (eg. Medicine, Agriculture& forestry/) 2017: 2contract 15,000each. Q1: 700mw*9weeks=$6,300 | 84000 | 0.00 |
|  | Activity 1.1.5: National field survey, international study tour on ABS and participation in international workshop and conference on ABS （natioanal surveys only in Q1) | 0% | 0% | 100% | MEP | GEF | 71600 | Travel Q1: 4 persons, $600/person 2 times （3 PMO staff and 1 consultants) | 50000 | 33,978.49 |
|  | Activity 1.1.6： Organize Consulting and Reviewing meetings for all research activities under the outcome 1, and participation relevant workshops | 30% | 30% | 40% | MEP | GEF | 75700 | Q1: consulting meetings and recruitment meetings $600*6=$3,000, 5-15 persons each | 10000 | 174.17 |
|  | Activity 1.1.7: Communications between various stakeholders | 0% | 50% | 50% | MEP | GEF | 72400 | Communic & Audio Equip | 1000 | 0.00 |
|  | Activity 1.1.8 Report printing | 0% | 50% | 50% | MEP | GEF | 74200 | Audio Visual&Print Prod Costs | 3000 | 0.00 |
|  | Activity 1.1.9: Research on preparation for the Nagoya Protocol National Implementation Program | 0% | 0% | 0% | MEP | GEF | 71300 | local consultants | 12600 | 0.00 |
|  | Activity 1.1.10: Office facilities and equipment | 0% | 20% | 80% | MEP | GEF | 72800 | office facilities | 1000 | 0.00 |
| Output 1.2: National ABS framework—including, if and as appropriate, NP compliant PIC and community protocols, model contracts, codes of conduct and certificates of compliance/origin on ABS—developed with stakeholder participation and in compliance with Nagoya Protocol (indicators: draft codes of conduct) | activity 1.2.1: Research on technical guidelines, including a series of standers for survey, inventory, database, social and cultural impact assessment, PIC, MAT, etc. for GRs & TK, codes of conduct for TK & GR from LCs, model of internationally recognized certificates of compliance, and others | 0% | 0% | 0% | MEP | GEF | 72100 | Contractual Services-Companies | 47040 | 0.00 |
| Output 1.3: ABS framework implementation plans formulated and operational, including: (i) plan for access to and benefit sharing of genetic resources and derivatives for commercial purposes; (ii) plan for access to genetic resources, traditional knowledge associated with genetic resources used for commercial purposes including application of PIC and community protocol, and benefit-sharing with regard to their utilization; and (iii) plan for academic/non-commercial research protocol (Indicators:implemetation plan outlines) | Activity1.3.1: Research on implementation plan for ABS of genetic resources and derivatives | 0% | 0% | 0% | MEP | GEF | 72100 | local consultant | 80000 | 0.00 |
|  | Activity 1.3.2: Research on implementation plan for ABS of traditional knowledge, firstly with case studies | 0% | 0% | 0% | MEP | GEF |  | local consultant |  | 0.00 |
|  | Activity 1.3.3: Research on implementation plan for ABS of GRs and TK for non-commercial uses | 0% | 0% | 0% | MEP | GEF |  | local consultant |  | 0.00 |
| Output 1.4: Establish national-level institutional arrangements for ABS | Activity 1.4.1: Research on ABS clearing-house mechanism | 0% | 0% | 100% | MEP | GEF | 72100 | 2017：2 Contractual Services-Companies 1 contract for data base development,$30,000 Q1： $15,000 | 18000 | 0.00 |
| Subtotal |  |  |  |  |  |  | 71200 | International Consultants | 72,000.00 | 0.00 |
|  | 71300 | Local Consultants | 12,600.00 | 0.00 |
|  | 71600 | Travel | 50,000.00 | 33,978.49 |
|  | 72100 | Contractual services - Companies | 229,040.00 | 0.00 |
|  | 72400 | Communic & Audio Equip | 1,000.00 | 0.00 |
|  | 72800 | Equipment & Furniture | 1,000.00 | 0.00 |
|  | 74200 | Audio Visual&Print Prod Costs | 3,000.00 | 0.00 |
|  | 74500 | Miscellaneous Expenses | 0.00 | 0.00 |
|  | 75700 | Workshops | 13,000.00 | 174.17 |
| Outcome 1 subtotal | 381,640.00 | 34,152.66 |
| Outcome 2 ABS capacity building and awareness raising |
| Output 2.1: Enhanced capacity and awareness of implementation of China’s ABS regime at the national and provincial levels (Indicators: awareness raising, survey, increased) | Activity 2.1.1: Public awareness raising material preparation, and training organizing consultant | 0% | 0% | 0% | MEP | GEF | 72100 | Contractual services - Companies | 21000 | 0.00 |
|  | Activity 2.1.2: public awareness raising activities, and participation relevant workshops | 0% | 0% | 0% | MEP | GEF | 75700 | public awareness raising activity | 30000 | 0.00 |
|  | Activity 2.1.3: Recruit consultants providing financial, technical advisor | 25% | 25% | 50% | MEP | GEF | 71800 | long term consultants Q1: technical advisor (CTA) 1 person $1,000/mw,12 weeks ($12,000) financial consultant:1 person,$500mw,12weeks ($6,000) | 49950 | 32,851.92 |
|  | Activity 2.1.4：Equipement for project implementing | 0% | 0% | 0% | MEP | GEF | 72800 | Equipment & Furniture | 3000 | 1,013.21 |
|  | Activity 2.1.5：communication, internet fees and Audio Equipment for project implementing | 0% | 0% | 0% | MEP | GEF | 72400 | Communic & Audio Equip | 1000 | 0.00 |
|  | Activity 2.1.8: ABS education base establishment for awareness raising | 0% | 0% | 0% | MEP | GEF | 72100 | Contractual services - Companies | 36750 | 0.00 |
|  | Activity 2.1.9: Preparation on public awareness raising strategy | 0% | 0% | 0% | MEP | GEF | 72100 | local consultant | 52500 | 0.00 |
| Output 2.2: Training materials and programme for ABS （Indicators: draft training materials and programme plan) | Activity 2.2.1: Prepare training materials for ABS relevant sectors, the public, local communities | 0% | 0% | 100% | MEP | GEF | 72100 | 3 local consultants Q1:1 legal, institutional & training consultant (related sectors) 700 mw*4weeks=$2,800 1 legal, institutional & training consultant (public) 700 mw*4weeks=$2,800 1 legal, institutional & training consultant (local communities) 700 mw*4weeks=$2,800 | 48000 | 0.00 |
|  | Activity 2.2.2: prepare training materials for users (private sectors, research institutes) | 0% | 0% | 0% | MEP | GEF | 71300 | local consultants | 33600 | 0.00 |
|  | Activity 2.2.3: Travel to training and workshops | 0% | 0% | 0% | MEP | GEF | 71600 | Travel | 25000 | 0.00 |
|  | Activity 2.2.4: Print training and workshop materials | 0% | 0% | 0% | MEP | GEF | 72200 | Equipment related to project implementing, office use including equipment for checkpoints | 10000 | 306.27 |
|  |  | 0% | 0% | 0% | MEP | GEF | 74200 | Audio Visual & Print Prod Costs | 10000 | 0.00 |
| Output 2.3: A platform to enable the sharing of technology and knowledge resources with Chinese stakeholders, including through the ABS Clearing-House (Indicators: meeting martials and participants information provided, interim report on communications for knowledge sharing strategy) | Activity 2.3.1: Organize meetings and seminars for information sharing mechanism participated by all stakeholders | 0% | 0% | 0% | MEP | GEF | 75700 | Workshops | 5000 | 0.00 |
|  | Activity 2.3.2: communications for knowledge sharing plan preparation | 0% | 0% | 0% | MEP | GEF | 74500 | Contingency expenses and transportation for component 2 | 2500 | 624.58 |
| Output 2.4: Systems and guidelines for sharing information and knowledge related to ABS among ministries (Indicators: information sharing plan) | Activity 2.4.1: Recruit national consultants to draft information sharing strategy among ministries | 0% | 0% | 0% | MEP | GEF | 71300 | 2018：Evaluation specialist for mid-term evaluation of Component 2 –1.5week * 700 = 1050 | 0 | 0.00 |
|  |  | 0% | 0% | 0% | UNDP | GEF | 71200 | 2018：International Evaluation Expert for mid-term evaluation of Component 2 – 1.5 week * 3,000 =4500 | 0 | 0.00 |
| Subtotal |  | 71200 | International Consultants | 0.00 | 0.00 |
|  |  |  |  |  |  |  | 71300 | local consultants | 33,600.00 | 0.00 |
|  | 71600 | Travel | 25,000.00 | 0.00 |
|  | 71800 | Long term consultants | 49,950.00 | 32,851.92 |
|  | 72100 | Contractual services - Companies | 158,250.00 | 0.00 |
|  | 72200 | Equipment & Furniture | 10,000.00 | 306.27 |
|  | 72400 | Communic & Audio Equip | 1,000.00 | 0.00 |
|  | 72800 | Equipment & Furniture | 3,000.00 | 1,013.21 |
|  | 74200 | Audio Visual & Print Prod Costs | 10,000.00 | 0.00 |
|  | 74500 | Miscellaneous Expenses | 2,500.00 | 624.58 |
|  | 75700 | Workshops | 35,000.00 | 0.00 |
| Outcome 2 subtotal | 328,300.00 | 34,795.98 |
| Outcome 3 Pilot demonstrations on ABS |
| Output 3.1:Enhanced understanding of genetic resources and associated traditional knowledge, related ABS opportunities and associated barriers in Hunan and Yunnan Provinces and Guangxi Autonomous Region （Indicators: baseline survey information) | Activity 3.1.1: Pilots' field survey on the target and relevant species and ATK, for their distributions, populations, cultivations, bio-prospecting, commercial use and new usages, current and potential users, markets and exports, BS practice, etc. | 0% | 0% | 100% | MEP | GEF | 72100 | Contractual services - Companies 3 contract with 3 pilots (included in the overall contract ($500,000, 2016-2021) to 1 pilot, as a content of the overall contract, is to conduct field survey on pilot species in the pilot area, to be completed by end of 2017) 2017:$10,000 for each pilot Q1:$5,000 | 100000 | 0.00 |
|  | Activity 3.1.2: Investigation and surveys in key sectors and industries, and consultations with key sectors and industries on ABS national framework establishment (eg. development and utilization of GR and ATK, and awareness on ABS) | 0% | 0% | 100% | MEP | GEF | 71300 | 1 contract with ABS related industry association 2017:$70,000. Q1: 30% of contract price $2,1000 | 95000 | 0.00 |
|  | Activity 3.1.3: Travel for Filed surveys (national and international) | 0% | 0% | 100% | UNDP | GEF | 71600 | Travel Q1 : 5 persons, $600/person 1 times | 10000 | 3,837.45 |
|  |  | 0% | 0% | 100% | MEP | GEF | 71600 | Travel of UNDP for M&E needs and other ad hoc events | 5000 | 0.00 |
|  | Activity 3.1.4: Analysis on demand for pilots' regions ABS on HR, coordinating mechanism, policies, regulations, institutions, technologies and information. | 0% | 0% | 100% | MEP | GEF | 72100 | Sub-contracts for development of comprehensive ABS action plans to scale up pilot demonstrations into full ABS implementation with Yunnan, Guangxi and Hunan EPBs and other pilot provinces EPBs (if any newly added as the project implementing) under Output 3.1 | 100000 | 0.00 |
|  | Activity 3.1.5: Analysis on demand for local communities and users. | 0% | 0% | 100% | MEP | GEF |  |  |  |  |
|  | Activity 3.1.6: Recruit consultants providing M&E, communication services, | 40% | 30% | 30% | MEP | GEF | 71800 | long term consultants Q1：communication officer $650 mw, 12 weeks ($7,800) M&E consultant: 500mw*12weeks=$6,000 | 49950 | 0.00 |
|  | Activity 3.1.7 Audit cost for the project | 0% | 0% | 0% | UNDP | GEF | 74100 | Professional Services | 5000 | 0.00 |
|  | Activity 3.1.8:Communications and Audio equipment cost | 0% | 0% | 100% | MEP | GEF | 72400 | communic & Audio Equip | 1000 | 0.00 |
| Output 3.2: Create the legal foundation for institutional arrangements and procedures that will govern ABS in the pilot areas (Indicators: interim research report on institutional responsibilities, operational mechanism and procedures, stakeholder support mechanisms for each demo ) | Activity 3.2.1 Workshops for provincial ABS mechanisms, and participation relevant workshops | 0% | 50% | 50% | MEP | GEF | 75700 | consulting meetings and recruitment meetings 2017: $600 *15=$9,000, 5-15 persons each (Q1:5 meeigns) $800*6=$4,800, 12-20 person each 1 activity $5,000, 1 activity $5,000 | 10000 | 0.00 |
|  | Activity 3.2.2 Research on coordinating mechanism for each pilot with the stakeholders' responsibilities and meetings. | 0% | 0% | 100% | MEP | GEF | 72100 | Contractual services - Companies 3 contract with 3 pilots (included in the overall contract ($500,000, 2016-2021) to 1 pilot, as a content of the overall contract, is to research on coordinating mechanism for each pilot with the stakeholders' responsibilities, to be completed by the end of 2019.) 2017 Q1:$2,000 for each pilot | 66000 | 0.00 |
|  | Activity 3.2.3: Research on ABS regulation at provincial level or municipal level, including PIC, MAT, administrative arrangement and responsibilities, monitoring, etc. | 0% | 0% | 100% | MEP | GEF | 72100 | Contractual services - Companies 3 contract with 3 pilots (included in the overall contract ($500,000, 2016-2021) to 1 pilot, as a content of the overall contract, is to analysis on demand for pilots' regions ABS on HR, coordinating mechanism, policies, regulations, institutions, technologies and information, to be completed by the end of 2019) 2017 Q1:$3,000 for each pilot | 66000 | 0.00 |
|  |  | 0% | 0% | 100% | UNDP | GEF | 71200 | International legislative / legal consultant to advise on: (i) institutional arrangements and procedures in pilot areas, and (ii) analysis of legal implications of lessons learned under pilots under Component 3 - 8 weeks * 3,000 = 24,000; International Evaluation Expert for mid-term evaluation of Component 3 – 1.5week * 3,000 = 4500 | 0 | 0.00 |
|  | Activity: 3.2.4: Research on detailed implementation guidelines for ABS test regulations. | 0% | 0% | 0% | MEP | GEF | 72100 | Contractual services - Companies 3 contract with 3 pilots 2017:$10,000 for each pilot Q1: 0 (included in the overall contract to 1 pilot, as a content of the overall contract, is to prepare ABS implementation guidelines at provincial level.) | 66000 | 0.00 |
|  | Activity 3.2.5: materials printing | 0% | 0% | 0% | MEP | GEF | 74200 | Audio Visual & Print Prod Costs | 7000 | 0.00 |
| Output 3.3: ABS agreements negotiated and implemented across Hunan and Yunnan Provinces and Guangxi Autonomous Region (including examples from medicine, healthcare and others) in the pilot-demonstration jurisdictions (Indicator: ABS agreements negotiation records/reports) | Activity 3.3.1: ABS negotiations and records of negotiations | 0% | 0% | 100% | MEP | GEF | 72100 | Contractual services - Companies 3 contract with 3 pilots 2017:1 pilot: $6,000, Q1:$2,000 | 66000 | 0.00 |
|  | Activity 3.3.2 Application case procedures in pilots of Yunnan， Guangxi and Hunan Province, including the negotiation, agreements, contracts, governmental approval, contract implementation, compliance, monitoring, etc. | 0% | 0% | 0% | MEP | GEF | 72100 | Contractual services - Companies 3 contract with 3 pilots | 66000 | 0.00 |
| Output 3.4 Lessons and experiences in implementing local ABS regimes are documented and disseminated for replication, based on the project’s replication plan (Indicators:lessosns abstracts) | Activity 3.4.1: Summary and compilation of the project's achievements, experience and lessons for 2016-2017. | 0% | 0% | 0% | MEP | GEF | 71300 | local consultant | 2000 | 0.00 |
|  | Activity 3.4.2: Disseminate materials of experience of the pilots in international conferences, including organize side events in COP-14 (2018) and (COP-15,2020) for publicity of the project's experience on demonstration internationally. | 0% | 0% | 0% | MEP | GEF | 74200 | Audio Visual& Print Prod Cost | 1000 | 0.00 |
|  |  | 0% | 0% | 100% | MEP | GEF | 74500 | Contingency expenses and transportation for component 3. | 1600 | 0.00 |
| Subtotal |  | 71300 | Local consultants | 97,000.00 | 0.00 |
|  |  |  |  |  |  |  | 71200 | International Consultants | 0.00 | 0.00 |
|  | 71600 | Travel | 15,000.00 | 3,837.45 |
|  | 71800 | Long term consultants | 49,950.00 | 0.00 |
|  | 72100 | Contractual services - Companies | 530,000.00 | 0.00 |
|  | 72400 | Communic & Audio Equip | 1,000.00 | 0.00 |
|  | 74100 | Professional Services | 5,000.00 | 0.00 |
|  | 74200 | Audio Visual & Print Prod Costs | 8,000.00 | 0.00 |
|  | 74500 | Miscellaneous Expenses | 1,600.00 | 0.00 |
|  | 75700 | Workshops | 10,000.00 | 0.00 |
| Outcome 3 subtotal | 717,550.00 | 3,837.45 |
| Project Management |
| Project Management | for PMO office | 30% | 40% | 30% | MEP | GEF | 71800 | Contractual Services – Imp Partner 2017:Project Manager 12 weeks $650MW($7,800) Project Assistant 12 weeks 500mw ($6,000) | 47300 | 0.00 |
|  |  | 30% | 40% | 30% | UNDP | GEF | 74599 | Direct Project Cost | 2006 | 0.00 |
| Subtotal |  |  |  |  |  |  | 71800 | Contractual Services – Imp Partner | 47,300.00 | 0.00 |
|  |  |  |  |  |  |  | 74599 | Direct Project Cost | 2,006.00 | 0.00 |
| Project Management subtotal | 49,306.00 | 0.00 |
| Grand Total |  |  | Please list the total amount for each budget code per year |
|  | 71200 | International Consultants | 72,000.00 | 0.00 |
|  | 71300 | Local Consultants | 143,200.00 | 0.00 |
|  | 71600 | Travel | 90,000.00 | 37,815.94 |
|  | 71800 | Long term consultants | 147,200.00 | 32,851.92 |
|  | 72100 | Contractual services - Companies | 917,290.00 | 0.00 |
|  | 72200 | Equipment & Furniture | 10,000.00 | 306.27 |
|  | 72400 | Communic & Audio Equip | 3,000.00 | 0.00 |
|  | 72800 | Equipment & Furniture | 4,000.00 | 1,013.21 |
|  | 74100 | Professional Services | 5,000.00 | 0.00 |
|  | 74200 | Audiovisual& PrintProdCost | 21,000.00 | 0.00 |
|  | 74500 | Miscellaneous Expenses | 4,100.00 | 624.58 |
|  | 74599 | Direct Project Cost | 2,006.00 | 0.00 |
|  | 75700 | Workshops | 58,000.00 | 174.17 |
| GRAND TOTAL | ########## | 72,786.09 |

4.2 Funding Authorization and Certificate of Expenses (FACE) Table

# Text boxes

Quarterly Project Progress Report

[00094671 Developing and Implementing the National Framework on Access to and Benefit Sharing of Genetic Resources and Associated Traditional Knowledge

[April 17, 2017]