| Government | UNDP |
| --- | --- |
| Name: | Name: |
| Date: | Date: |

| Total resources required: | 89 682 938 100,00 XAF (equiv. $147 437 271,77) |
| --- | --- |
| Government Contribution | 8 900 000 000,00 XAF (equiv. $14 631 453,28) |
| Total resources allocated: |  |
| Unfunded: | 80 782 938 100,00 XAF (equiv. $132 801 028,13) |

Presidential Plan for Reconstruction and Development (PPRD) for the North-West and South-West regions of Cameroon

Yaoundé, Cameroon
24th April 2020

Table of Contents

PRESIDENTIAL PLAN FOR RECONSTRUCTION AND DEVELOPMENT	8

PART I: OVERVIEW	8

I.1 General Overview	8

I.2 Economic Overview	8

I.3 Political Overview	9

I.4 Need for Recovery, Reconstruction and Development Interventions	11

PART II: IMPACT OF THE CRISIS	12

II.1 Social Sector	12

II.1.1 Housing	13

II.1.2 Civil Society and Community Based Organizations	14

II.2 Essential Infrastructure	14

II.2.1 Education	14

II.2.2 Health	15

II.2.3 Transportation	16

II.3 Local Economy	17

II.3.1 Agriculture	17

II.3.2 Livestock	19

PART III: RECOVERY AND RECONSTRUCTION INTERVENTIONS	21

III.1 Social Sector	23

III.2 Essential Infrastructure	25

III.3 Local Economy	25

PART IV: OPERATING PRINCIPLES	27

IV.1 Guiding Principles	27

IV.2 Monitoring & Evaluation	28

IV.3 Planning and Coordination	29

IV.3.1 Governance Structure	29

IV.4 Principles of Engagement and Mitigation Measures	35

PART V: BUDGET	38

PART VI: LEGAL FRAMEWORK	43

PART VII: APPENDICES	44

VII.1 Monitoring and Evaluation Framework	44

VII.2 Mapping of the North West and South West regions	53

VII.3 Accountability Framework for the Human Rights Due Diligence Policy	54

PART VIII: REFERENCES	55

Tables Summary

Table 1: Map of the North-West region	9

Table 2: Map of the South-West region	10

Table 3: Villages destroyed in the NW region	13

Table 4: Villages destroyed in the SW region	13

Table 5: Schools destroyed in the NW region	14

Table 6: Schools destroyed in the SW region	15

Table 7: Health Facilities destroyed in the NW region	15

Table 8: Health Facilities destroyed in the SW region	16

Table 9: Roads damaged in the NW region	16

Table 10: Roads damaged in the SW region	17

Table 11: Agricultural production in the NW region	18

Table 12: Distribution of agricultural production in the NW region	18

Table 13: Distribution of main products per production area in the SW region	18

Table 14: Agricultural production in the SW region	19

Table 15: Livestock damages in the NW region	19

Table 16: Livestock damages in the SW region	19

Table 17: Fishery damages in the SW region	19

Table 18: Summary of interventions	20

Table 19: Theory of Change	22

Table 20: Social Sector Interventions	23

Table 21: Essential Infrastructure Interventions	24

Table 22: Local Economy Interventions	25

Table 23: Governance Structure	33

Table 24: Budget Allocation	37

Table 25: Monitoring & Evaluation Framework	45

Table 26: UNDAF Framework	50

List of Abbreviations

BBB : Build Back Better

BUCREP : Bureau Central des Recensements et des Etudes de la Population

CAR : Central African Republic

CBO : Community-based organization

CDC : Cameroon Development Company

CEMAC : Central African Economic and Monetary Community

CFAF : Central French African Francs

CHRDA : Centre for Human Rights and Democracy in Africa

CRM : Cameroon Renaissance Movement

DDR : Disarmament, Demobilization and Reintegration

GDP : Gross Domestic Product

GESP : Growth and Employment Strategy Paper

HF : Health Facilities

IDP : Internally Displaced Persons

MINADER : Ministry of Agriculture and Rural Development

MINEPAT : Ministry of Economy, Planning and Regional Development

NDP : National Development Plan

NGO : Non Governmental Organisation

NW : North West

OCHA : Office for the Coordination of Humanitarian Affairs

PAMOL : Palmoil Company

RDMINEPIA : Ministère de l’Élevage des Pêches et Industries Animales

SBAA : Standard Basic Agreement

PPRD : Presidential Plan for Reconstruction and Development

PPRDMU : Presidential Plan for Reconstruction and Development Management Unit

SW : South West

UNDAF : United Nations Development Assistance Framework

UNDP : United Nations Development Programme

UNICEF : United Nations Children's Fund

# PRESIDENTIAL PLAN FOR RECONSTRUCTION AND DEVELOPMENT

# PART I: OVERVIEW

## I.1 General Overview

Cameroon is a lower-middle-income country with a population of over 25 million (2018). Located along the Atlantic Ocean, it shares its borders with Chad, the Central African Republic (CAR), Equatorial Guinea, Gabon, Nigeria and the Republic of Congo. Two of its border regions with Nigeria (North-West and South-West) are Anglophone, while the rest of the country is Francophone. Cameroon is endowed with rich natural resources, including oil and gas, minerals, high-value species of timber, and agricultural products, such as coffee, cotton, cocoa, maize, and cassava.

## I.2 Economic Overview

Cameroon is the largest economy in the Central African Economic and Monetary Community (CEMAC), a region experiencing an economic crisis triggered by the steep fall in oil prices. Along with its CEMAC partners, Cameroon has therefore had to put fiscal adjustment measures in place to adjust to the terms of trade shock and restore macro-stability and confidence in the common currency.

Growth in Cameroon is expected to reach 4.3% this year. The rebound is driven by three factors: an increase in natural gas production, with a new liquefied natural gas (LNG) offshore terminal coming online; the slight downturn in the oil sector; and sustained momentum in the construction, industry, housing, and services sectors.

Because its poverty reduction rate is lagging behind its population growth rate, the overall number of poor in Cameroon increased by 12% to 8.1 million between 2007 and 2014, and poverty is increasingly concentrated, with 56% of poor living in the northern regions. If Cameroon is to become an upper-middle-income country by 2035, it will have to increase productivity and unleash the potential of its private sector.

Specifically, Cameroon’s real GDP will have to grow by roughly 8% (or 5.7% per capita) between 2015 to 2035, which in turn will require the investment share of GDP to increase from about 20% in 2015 to 30% in 2035, and productivity growth to reach 2% over the same period from its average zero growth rate over the past decade. These challenges can be met.

The new National Development Strategy (NDS) 2020-2030 which is fully aligned to the 2030 agenda and SDGs provides the corrective measures to address inequalities and promote inclusive growth. The NDS is articulated around four pillars, namely (i) Structural transformation (ii) Human development (iii) Employment policy and (iv) Improvement of good governance.

Key transformational measures include:

- Progressive disengagement of state on financing of infrastructures and investment in social sectors;

- Decentralization reforms to allocate 15 % of the Government budget to local municipalities;

- Creation of a special status for the North-West and South West regions;

- Reduction of power of state representatives in the management of local municipalities to foster local development and acceleration of structural transformation.

## I.3 Political Overview

Having enjoyed several decades of stability, Cameroon has been grappling with attacks by Boko Haram in the Far North and a secessionist insurgency in the North-West and South-West regions. Since September 2017, this situation has displaced more than 500,000 people internally and claimed the lives of close to 400 civilians and over 200 military, gendarmerie, and police officers. Figures from the UN Refugee Agency (HCR) show that Cameroon is currently hosting over 401,213 refugees, primarily from the Central African Republic (289,982) and Nigeria (108,164).

Table 1: Map of the North-West region

The conflict in North-West and South-West regions of Cameroon had been simmering for decades, but boiled over in 2016, when teachers and lawyers started to protest against the use of French in schools and courts. Insurgents declared independence for the region they call "Ambazonia". In an attempt to end the crisis, President Paul Biya called for talks by organizing the Major National Dialogue in October 2019. The Prime Minister held preliminary consultations with representatives of all socio-political stakeholders - including the diaspora – to spark dialogue and encourage the return of peace and stability. More than 600 people participated, with approximately two thirds from the NW and SW regions, and 5% representing the diaspora.

Subsequent to the Major National Dialogue the President decided the discontinuance of proceedings by the military tribunal against 333 separatists arrested and detained in the NW and SW and 102 officials and militants, 8 of political parties. These decisions were welcome by national and international stakeholders including the UN Secretary General as an encouragement to appease tensions.

Table 2: Map of the South-West region

Several key recommendations came out of the Major National Dialogue:

- Improve bilingual practices across Cameroon and strengthen national social cohesion;

- Include community violence reduction in the DDR program and fight against small arms circulation;

- Provide a special status for the NW and SW regions;

- Enhance decentralization and local development in addition to strengthening the financial autonomy of regions;

- Remove positions of “Government delegates” to city councils who are appointed by the Executive;

- Create a local government public service and increase transfer of power and resources to local authorities;

- Formulate a Plan for Reconstruction and Development for the North-West, South-West and Far North regions.

## I.4 Need for Recovery, Reconstruction and Development Interventions

The Government of Cameroon conducted a socio-economic assessment to estimate the impact of the crisis in the NW/SW. Conclusions of the study urged for the creation of a Reconstruction and Development plan for the two regions.

The United Nations Development Program (UNDP), and all international partners of Cameroon, have collectively agreed that it is necessary and urgent to set the population of the NW/SW on an upward trajectory towards lasting prosperity and wellbeing, creating an enabling environment for their enterprises and industries to flourish.

The Government of Cameroon called for action in close collaboration with UNDP and in consultation with other UN Agencies, international NGOs, civil society and the private sector. To this end, UNDP formulated a Presidential Plan for Reconstruction and Development (PPRD) for the NW/SW, which aims to tie short-term rehabilitation and humanitarian measures with longer-term reconstruction and development interventions. The PPRD takes into consideration the impact of the crisis on all aspects of life, and formulates responses designed to have a permanent beneficial impact – to ‘Build Back Better’.

Through a common understanding between the Government of Cameroon and UNDP, Recovery and Reconstruction interventions are defined as a comprehensive process of socio-economic interventions and physical reconstruction, through which households and communities rebuild their assets, restore their livelihoods and strengthen their capacities to manage the impacts of the ongoing crisis.

# PART II: IMPACT OF THE CRISIS

It is intended that the priority interventions outlined in this plan not only restore the NW/SW to its previous condition but form the nucleus of a concerted effort to fundamentally improve all aspects of life in both regions. With this in mind, UNDP in collaboration with the Government of Cameroon has estimated the scale of damages and the magnitude of needs in all sectors and set about defining the Cameroonian priorities for overcoming them. Immediate priority will be given to providing housing kits to the dispossessed, repairing water networks, repairing schools and hospitals, and providing the appropriate conditions to return to normal life.

Rapid assessments of damage and needs within the social sector utilized a variety of approaches, focus group consultations, desk reviews and interviews. The infrastructure assessment was undertaken through local authorities who assessed damages and needs at the household and community levels. Within the context of the economic sector, assessments were conducted of the major productive sectors and financial system. The Ministry of Economy, Planning and Regional Development (MINEPAT) used the following composite methodologies in conducting the damage and needs assessment: mapping and valuation of physical and human damage and loss suffered to public sector institutions and non-state resources; appraisal of the consequences of damages on the recovery of public institutions, service delivery mechanisms, social cohesion and public participation; identification of priority recovery interventions at the immediate level; and structured interviews with a number of NGOs, including women’s groups.

## II.1 Social Sector

The conflict in the NW/SW resulted in the severe deterioration of the already precarious living conditions of the communities in those regions. This section describes how the widespread crisis in the NW/SW has created a highly stressed social environment, severely compromising the physical, psychological, social and emotional wellbeing and development of children, young people and adults in the NW/SW. The findings presented here give a focused account of those aspects of the damage which can be accurately calculated and suggest measures that can be taken immediately to stabilize the social structure, an essential basis for all other investments in NW/SW’s recovery and development.

However, because of the complexity of factors that need to be considered in determining the overall social impacts and the extent to which its effects can be overcome are still being determined. In this ongoing crisis, characterized by social, economic and physical insecurity, individual and shared resilience have been systematically undermined. Yet, as this document describes, the impacts are felt in diverse ways. For example, men and women do not face exactly the same challenges; they have different capacities and access to support systems through which to manage their distress. The elderly, people with disabilities and people with chronic illnesses face additional obstacles to full recovery. Children and adolescents, who represent the majority of the population, are particularly affected because the protective environment usually provided by caregivers has been overwhelmed by the scale of the destruction. Children tend to be the most vulnerable group since they do not have access to, or control over, the limited resources within their communities. However, they bear the full brunt of disruption to services and schooling.

### II.1.1 Housing

Information collected to date indicates that the housing situation of over 116,000 persons has been affected by the NW/SW crisis. Over 23,273 housing units have been damaged, leaving more people without homes, resulting in displacements and the deterioration of already difficult living conditions.

In the NW region, approximately 107 villages were burnt (Centre for Human Rights and Democracy in Africa (CHRDA), May 2019). One village is composed of approximately 113 houses. Destructions therefore left 12 091 households without a home. Provided a household is composed of a minimum of 5 people, the crisis has resulted in 60 455 people in precarious living conditions.

Table 3: Villages destroyed in the NW region

Source: CHRDA 2019

In the SW region, approximately 99 villages were burnt (Centre for Human Rights and Democracy in Africa (CHRDA), May 2019). One village is composed of approximately 113 houses. Destructions therefore left 11 187 households without a home. Provided a household is composed of a minimum of 5 people, the crisis has resulted in 55 935 people in precious living conditions.

Table 4: Villages destroyed in the SW region

### II.1.2 Civil Society and Community Based Organizations

NGOs have the potential to be key stakeholders within the recovery and reconstruction process in the NW/SW, particularly in promoting active citizenship and local ownership, documentation and information gathering, oversight and implementation functions, and engaging in service delivery to the affected population. However, many NGOs were severely affected by the crisis. There appear to be some restrictions on local NGO participation in the process of recovery. Together with the Government of Cameroon, UNDP seeks to reactivate the NGO network to support local communities based upon a non-partisan needs-based approach.

## II.2 Essential Infrastructure

### II.2.1 Education

The separatist crisis has contributed to the sharp increase in reported incidents of children being stopped from accessing education, physically attacked for trying to go to school or having their school destroyed. In the NW, approximately 174 out of 555 schools were damaged (MINEPAT, 2018). Available data concerning 32 sub-divisions, show that, on average 93% of preschools were not functional. None of the preschool were functional in Menchum, Bui and Ngoketunjia divisions, and twenty four sub-divisions (i.e. Nwa, Ndu, Ako, Bafut, Bali, Batibo, Ngie, Widikum, Balikumbat, Babessim Ndop, Wum, Fungom, Menchum valley, Mbven, Nkum, Oku, Noni, Jakirim, Belo, Fonfuka, Njinikom, Mbengwi and Njikwa).

Only 7.5% of secondary schools were functional, based on available data for 26 sub-divisions. At the divisional level, 8.2%, 20% and 6.7% of the schools were respectively functional in Donga-Mantung, Mezam and Boyo respectively. None of the secondary school were functional in Menchum, Bui and Ngoketunjia divisions and 26 sub-divisions (i.e. Nwa, Ndu, Ako, Bafut, Bali, Batibo, Ngie, Widikum, Balikumbat, Babessim Ndop, Wum, Fungom, Furu-awa, Menchum valley, Mbven, Nkum, Oku, Noni, Jakirim, Belo, Fonfuka, Njinikom, Mbengwi and Njikwa subdivisions. (PAID WA for UNICEF, 2019).

Table 5: Schools destroyed in the NW region

Source: MINEPAT 2018

In the SW, approximately 119 out of 501 schools were damaged (MINEPAT, 2018). Available data concerning 27 sub-divisions, show that, on average 15.27% of preschools were not functional. None of the preschool were functional in Wabane, Menji, Alou, Konye, Kumba 3, Kumba 2, Mbonge, Dikome Balue, Idabato, Toko, Ekondo Titi, Mundemba, Bangem, Nguti and Muyuka. Furthermore, 78.9% of secondary schools were not functioning. None of the secondary schools were operational in two divisions (Lebialem and Kupe Muanenguba) and thirteen (13) subdivisions (i.e. Wabane, Menji, Alou, Eyumojock, Konye, Kumba 2, Dikome Balue, Toko, Bangem, Tombel, Mundemba, Nguti and Muyuka).

Table 6: Schools destroyed in the SW region

Source: MINEPAT 2018

### II.2.2 Health

The separatist crisis has diverted scarce resources away from the promotion and protection of health, medical care and other health and social services. Over the past three years, the conflict has disrupted the health-supporting infrastructure of society in the NW region. Damaged Health Facilities (HF) include hospitals, health centers and pharmacies. Approximately 13% of health facilities in the NW region are damaged (MINEPAT, 2018).

Table 7: Health Facilities destroyed in the NW region

Source: MINEPAT 2018

Approximately 10% of health facilities in the SW region are damaged (MINEPAT, 2018).

Table 8: Health Facilities destroyed in the SW region

Source: MINEPAT 2018

### II.2.3 Transportation

The movement of people and goods in NW/SW remains difficult as a result of the crisis, in particular in rural areas. In total, approximately 258 km of roads and 14 bridges were damaged throughout the NW. Many key roads were also shredded in the SW, with 315 km of damage and 26 dysfunctional bridges. The degradation of roads throughout the NW/SW, coupled with the fact that many basic utility services such as water, electricity, sewage and communication lines built under the roads are now damaged, have resulted in the loss of basic services by scores of thousands of people. With the destruction of sewage lines, many of the roads have become sewage ponds, causing environmental and health hazards to the population. Everyday travel is difficult and hazardous for residents, humanitarian and recovery work is impeded, and the commercial and industrial sectors have severe difficulty conducting business operations.

Table 9: Roads damaged in the NW region

Source: MINEPAT 2018

Table 10: Roads damaged in the SW region

Source: MINEPAT 2018

## II.3 Local Economy

The once-promising economy of the NW/SW has been devastated by the crisis. Repeated attacks and restrictions have led to the near strangulation of economic life. This has left the NW/SW almost completely dependent on the salaries and transfers paid by the Government and on humanitarian assistance.

The economy requires significant assistance for recovery. The following section describe in detail the impact of the crisis on key economic subsectors.

### II.3.1 Agriculture

The NW/SW crisis resulted in widespread destruction of cultivated lands, greenhouses, livestock and poultry farms, water wells, irrigation networks and other productive agricultural assets. Farmer’s abilities to produce food and secure income for their households have been reduced to an alarming level. Agricultural activities are strained, and access to both inputs and agricultural areas is restricted.

The recent damages to the agricultural sector, which accounts for over 50% of employment in both the NW/SW, have placed many people out of work. Households spend the majority of their income on food, and increased unemployment and poverty, coupled with reduced local production, will have a negative short and medium-term impact on food security.

In the NW, abandoned plantations increased by more than 200% between 2017 and 2018, going from 30 000 abandoned hectares to 100 000 abandoned hectares. In addition, 17 markets were destroyed. Overall agricultural production dropped by 51% between 2017 and 2019. The most important drop affected production of Arabic Coffee, with a 68% drop in production.

Table 11: Agricultural production in the NW region

Source: MINADER 2019

Table 12: Distribution of agricultural production in the NW region

Source: MINADER 2019

In the SW, abandoned plantations increased by 50% between 2016 and 2018, going from 8 abandoned hectares to 12 abandoned hectares. Agricultural production (ficheries and food crops) dropped by 39% between 2017 and 2018. The most important drop affected production of Cocoyam, with a 81% drop in production.

Table 13: Distribution of main products per production area in the SW region

Source: RD MINADER South West

Table 14: Agricultural production in the SW region

Source: RD MINADER South West

### II.3.2 Livestock

Similarly, as a result of the crisis, livestock damages have considerably increased between 2017 and 2018. The Table below illustrates that in the NW, destroyed livestock has gone from 25 800 in 2017 to 341 125 in 2018.

Table 15: Livestock damages in the NW region

Source: RDMINEPIA 2019

Pastureland was also degraded, compounded with unavailability of equipment for land preparation. In the SW, honey production fell by more than 72%.

Table 16: Livestock damages in the SW region

Source MINEPAT 2018

In the SW, Fako and Ndian divisions are key fishing locations. Between 2016 and 2018 fisheries dropped massively. Artisanal maritime fishing fell by 7 365% and fish farming went from 20 826 tons to 55,4 tons, registering a drop of 37 492%.

Table 17: Fishery damages in the SW region

Source: MINEPAT 2018

# PART III: RECOVERY, RECONSTRUCTION AND DEVELOPMENT INTERVENTIONS

Table 18: Summary of Interventions

The Presidential Plan for Reconstruction and Development (PPRD) is a component of the National Development Strategy (NDS) that was articulated to reduce the effects of the crisis on populations of the NW/SW and to catch up with the rest of country. On demand of the Government of Cameroon, the PPRD will address the immediate needs of the affected populations of the NW and SW regions. The goal of the PPRD is to:

- Strengthen social cohesion;

- Rehabilitate essential infrastructure;

- Revitalize the local economy.

In order to address the needs of people in NW/SW in an integrated and coordinated way, the PPRD’s priority interventions ensure that sectoral and sub-sectoral needs are considered in relation to each other. For example, housing is linked to the water and sanitation needs of affected families, which in turn is linked to issues of availability of parts and equipment. In the context of road infrastructure, the careful prioritization and sequencing of road rehabilitation in relation to the needs of essential services and the activities of utility companies will enable a more cost effective and sustainable recovery. The recovery, reconstruction and development activities are guided by national policy frameworks and priorities set out in the National Development Plan to ensure coherence and consistency of policy across the Cameroonian territory.

The Government’s vision of the PPRD in Cameroon arises from key considerations related to development, governance and resilience. It has three important strands: (1) help the communities recover from the impact of the conflict and rebuild their assets and livelihoods with a focus on women, youth and persons with disabilities; (2) rebuild public and community infrastructure to bounce back from the conflict; and (3) develop national capacities and systems through the PPRD. A decentralized and, when relevant, area-based approach and gender equality will underpin the recovery vision, as most of the programmes will be delivered at local level and target women and other vulnerable groups that were disproportionally affected by the conflict.

Confronted with today’s complex development challenges the Government of Cameroon calls for the seamless integration of democratic governance, economic recovery, conflict prevention and peace-building interventions. Such an integrated approach guarantees that investments in human rights, the rule of law and accountable institutions are geared towards building social cohesion and preventing conflict, and vice versa, as investments in social cohesion, national dialogue and mediation capacities lay the foundations for sustaining peace.

The Government of Cameroon stresses that sustaining peace is best accomplished through a systematic attention to effective and inclusive democratic governance, access to public basic services for the population, the integration of national and local capacities for conflict mediation and resolution, through formal and informal institutions. A more integrated approach that pays attention to effective and inclusive democratic governance, economic growth and conflict prevention is better suited to create the resilient institutions needed to handle the stresses on the social contract that occur today in Cameroon.

The ability to transition from humanitarian response to sustainable development is determined by the willingness and capacity of development and government partners to collaboratively create, fund and integrate successful recovery. With recovery adequately and timely integrated into the overall crisis response framework, affected communities will acquire the capacity to Build Back Better (BBB) their assets, avoiding dependency, increasing the resilience of affected communities, and looking to solve long standing problems that may have contributed to the crisis in the first place.

Table 19: Theory of Change

Finally, the PPRD is integrated in the Humanitarian-Development-Peace nexus. The Plan is aligned with strategic priorities, strategies and programmes in Cameroon, such as the National Development Plan, Government special plans, sector policies and strategies, UNSDCF, technical and financial partners partnership agreements, PBF projects, humanitarian response plan, plans and strategies of humanitarian-development-peace organisations.

## III.1 Social Sector

In response to the overwhelming housing needs of communities, UNDP will provide housing kits to at least 50% of the households that have lost their homes in the NW/SW. Housing kits will include materials to reconstruct individual home such as wood, concrete and roofing sheets. Each kit is worth 1.5 million FCFA. The provision of kits will be demand-driven and based on vulnerability criteria.

UNDP recognizes that the crisis has also harmed traditional community mechanisms, such as chiefdom gatherings, community-based associations and intercommunity and intergenerational dialogue platforms. The Social Sector therefore involves housing and civil society. Many of the interventions in these subsectors will be implemented under the philosophy of the Build Back Better principle. Priority interventions in this area include:

- Providing vulnerable households with housing kits;

- Conducting training courses and workshops in building renovations to involve the young people affected by the crisis in community-based recovery activities, emphasizing the healing power of culture and creativity;

- Building capacity of civil society and CBOs through local authorities.

Table 20: Social Sector Interventions

| Social Sector | Type of damage | Recovery, Reconstruction and Development intervention |
| --- | --- | --- |
| Housing | 23 278 households have lost their homes | - Provide housing kits to 6 046 households from the NW and 5 593 households from the SW - Support the issuance of documents for 90 000 individuals in the NW and 80 000 in the SW - Create community-led reconstruction groups |
| Civil Society and CBOs | Restrictions on local NGO participation | - Organize 35 and 31 capacity building workshops in the NW and SW respectively - Organize 35 and 31 socio-cultural events in the NW and SW respectively - Create 35 and 31 warning cells respectively in the NW and SW to reinforce community networks such as self-help groups, community networks and mediation groups - Create 35 and 31 caregiver support groups in the NW and SW respectively to reinforce community networks such as self-help groups, community networks, caregiver support groups and mediation groups - Create a civic engagement platform to identify youth-led projects for positive change |

## III.2 Essential Infrastructure

The primary focus of restoring infrastructure includes restoring and repairing essential utilities and infrastructure, such as schools, health facilities, water, transportation, and telecommunications. In particular, there is a need to restore and repair:

- Education facilities;

- Health facilities;

- Transportation networks. Road reconstruction will be prioritized in the following order: regional roads, roads serving public service sites (such as hospitals, schools, landfill sites, water processing stations) and roads serving neighborhoods;

- Restoring damaged and destroyed community infrastructure such as canton courtyards, community halls, women and youth centers.

Table 21: Essential Infrastructure Interventions

| Essential Infrastructure | Type of damage | Recovery, Reconstruction and Development intervention |
| --- | --- | --- |
| Schools | 293 schools destroyed | - Rehabilitate 174 schools in the NW and 119 schools in the SW |
| Health Facilities | 82 Health Facilities and water networks destroyed | - Rehabilitate 38 Health Facilities in the NW and 44 Health Facilities in the SW - Rehabilitate 100 water points in the NW and 225 in the SW |
| Transportation | Damage of roads | - Rehabilitate 14 small bridges and 258 km of earth roads in the NW and 26 small bridges and 315 km in the SW |
| Community infrastructure | Damage of community infrastructure | - Rehabilitate 50 community infrastructures (canton courtyards, community halls, women and youth centers) in the NW and 50 in the SW |

## III.3 Local Economy

With regard to interventions in the economic sector, large scale job creation is a priority. Interventions will be directed to sectors that can feed and house the NW/SW people and economic benefits should be passed on to the private sector. Priority interventions in this area include:

- Reviving the agricultural production;

- Rehabilitating productive infrastructure;

- Providing short-term work opportunities.

Table 22: Local Economy Interventions

| Local Economy | Type of damage | Recovery, Reconstruction and Development intervention |
| --- | --- | --- |
| Agricultural production | Decline in agricultural production | - Rehabilitate 13 000 ha of farmland to the benefit of 1 500 famers in the NW and 10 000 ha of farmland to the benefit of 1 300 famers in the SW - Supply 2000 farmers with equipment, tools and materials in the NW and 1700 farmers in the SW - Support 70 cooperatives in the NW and 60 in the SW - Recapitalize 350 livestock farmers in the NW and 300 livestock farmers and 200 fishermen in the SW - Support 70 startups in the NW and 60 in the SW |
| Productive infrastructure | Damage of productive infrastructure | - Rehabilitate 200 ovens for coffee and cocoa in the NW and 200 in the SW - Rehabilitate 17 cattle and food crops markets in the NW and 2 markets in the SW |
| Short-term work opportunities | High unemployment rates | - Provide small grants start-up packages - Support the provision of business development services |

# PART IV: OPERATING PRINCIPLES

## IV.1 Guiding Principles

The strategic response is designed to build on humanitarian relief efforts, develop exit strategies from dependency on humanitarian assistance, and address the recovery needs of communities in the NW/SW, while putting in place the foundations for longer-term reconstruction, sustainable development and equitable growth. The following principles guide the formulation and implementation of the PPRD:

- Building back better, to ensure that recovery and reconstruction interventions do not simply replicate the conditions prior to the crisis but that they result in improved and more sustainable standards of living, and opportunities for a better life than before. The plan therefore takes into consideration the deterioration of socio-economic conditions and seeks to address the accumulated economic and social challenges of poverty, unemployment and stagnation.

- Revitalizing the private sector, civil society and the local economy, by facilitating the conditions for local economic development, including employment creation, and building local capacities to ensure that communities of the NW/SW are not just beneficiaries but are actors in the recovery and reconstruction process. The plan relies on NW/SW communities and systems to own and lead the process to transform their social and economic situation. It is designed to promote recovery initiatives by the affected communities and equip them with the resources and tools to be at the forefront of this effort. The private sector and a wide range of civil society organizations will be mobilized as both recipients of assistance and ‘managers’ of recovery and reconstruction interventions. This will mean, in particular, that those interventions will make use, whenever possible, of local labor, products and services. Adherence to this principle will provide an immediate stimulus to the local economy by supporting job creation, income generation and demand.

- Promoting equity and broad-based participation from all segments of the NW/SW population, including and particularly from women and vulnerable groups. The plan is based on a commitment to ensuring that recovery and reconstruction efforts are as inclusive and participatory as possible, and that their results benefit everyone in the NW/SW, and the most vulnerable and needy in particular. Throughout the assessment process, particular attention has been given to the situation of those who have traditionally been the most vulnerable and disadvantaged. Within acute time constraints, the design of priority interventions is informed by accurate and disaggregated information on the needs of women, children and groups that are under-served, such as people with disabilities.

- Efficient coordination and information sharing with stakeholders in the early recovery process to avoid duplication, identify gaps and optimize the resources available for sustainable recovery and development. Success requires that each input, be it human, financial or technical, is carefully calibrated and targeted. It is therefore essential that all actors involved agree to share information, coordinate their interventions in a mutually reinforcing and transparent manner, and that their activities be undertaken within the priorities, principles and parameters of this Plan.

- Ensuring local ownership through the leadership of the Government of Cameroon and UNDP in the planning, execution, and monitoring of the Plan, in cooperation with international and local partners.

- Resource mobilization through joint efforts by the Government and UNDP to secure adequate resources for the implementation of the PPRD. This will include the establishment of a multi-partner fiduciary framework adapted to the needs and procedures for the Technical and Financial Partners likely to contribute to the financing of the Plan. UNDP, in its capacity as Implementing Partner, will have fiduciary responsibility for the funds allocated to the PPRD and will receive the contributions in accordance with the agreed modalities.

## IV.2 Monitoring & Evaluation

The suggested Monitoring and Evaluation (M&E) mechanism is one of the key measures to be used to achieve efficiency and effectiveness in the process of recovery, reconstruction and development of the NW/SW. The M&E mechanism is based on the following set of criteria and indicators, which will be used to assess progress of the work undertaken in the NW/SW:

- The percentage of the population with access to resources to rebuild their homes;

- The percentage of the population with access to water and sanitation services;

- The percentage of the population with access to transportation services;

- The number of businesses operating in different sectors;

- The percentage of employed persons and number of new jobs created;

- The percentage of the population with access to, and using, pre-existing basic;

- infrastructure and social services;

- The value of exports and imports.

The Plan includes four periodic reviews to monitor progress and identify outstanding needs. These reviews will focus on quantitative and qualitative data about the affected population and will be conducted according to UNDP reporting standards. In order to ensure that recovery needs are met, it will be identified which organizations (Who) are carrying out what activities (What) in which locations (Where) and how they are being implemented (How). “Who does What, Where and How” will be used as a coordination

tool, which seeks to identify duplication and/or gaps in activities and ensure a developmental approach. It will list activities that are ongoing, planned, completed, and funded. The detailed M&E framework can be found in Appendices VII.1.

## IV.3 Planning and Coordination

Overall coordination and oversight of the PPRD rests with the Government of Cameroon, which will ensure that initiatives are embedded in national priorities and the best use is made of available resources. Given the scale and scope of the crisis, the implementation of recovery and reconstruction efforts will involve all key ministries and bodies, working across all levels of government and in close cooperation with numerous partners, including national development agencies, local and international NGOs and the private sector.

The PPRD is under the overall supervision of the Prime Minister, Head of Government. At the request of the Government UNDP is designated as the Government's strategic partner in the implementation of the Plan. The project is implemented by UNDP on a direct implementation modality. It may also, in accordance with special dispensations, conclude special arrangements with other partners for the implementation of certain activities. UNDP ensures: (i) the production of deliverables and the achievement of results on time; (ii) capacity building of government partners, with a view to knowledge transfer, development of know-how at central and local levels, (iii) exit strategy and continuation of program implementation by national partners.

For better national and local ownership of the PPRD, the presence of all key technical ministerial departments is important during its implementation. To this end, firm instructions defining the procedures and modalities of action between the government and the line ministries will be issued.

### IV.3.1 Governance Structure

The PPRD has a four-level management structure: Steering Committee, National Coordination, Regional Follow-up Committees and the Implementing Partner.

The Steering Committee shall coordinate and evaluate all operations contributing to the implementation and monitoring of the PPRD. In this capacity, it shall:

- Define the strategic orientations to be followed up by the competent administrations and the Implementing Partner in the framework of the implementation of the PPRD;

- Coordinate the interventions and actions of all entities involved in the implementation of the PPRD;

- Ensure the effective implementation of the selected projects;

- Examine and approve the Annual Work Plans of the PPRD National Coordination, the subsequent budgets and the execution of reports;

- Adopt all administrative, legal, technical and financial facilitation measures necessary for the diligent implementation of the projects;

- Ensure the harmonious and equitable execution of the PPRD by all the administration, structures and partners involved;

- Define and adopt a plan for the mobilization of the resources necessary for the implementation of the PPRD;

- Approve the budget of organs of the PPRD;

- Propose other measures which could improve the execution of the PPRD;

- Execute all other directives from the Prime Minister, Head of Government in relation to the implementation of the PPRD.

The Steering Committee is composed of:

- President: The Director of Cabinet of the Prime Minister;

- Co-President: The Resident Representative of the United Nations Development Program in Cameroon;

- Members:  Minister of Economy, Planning and Regional Development; Minister of Finance;  Minister of Territorial Administration, Minister of Agriculture and rural development; Minister of Public Works; Minister in charge of Decentralization and Local Development; Minister of Basic Education; Minister of Secondary Education, Minister of Health; Minister of Water and Energy; Minister in charge of Women empowerment; Minister in charge of Livestock; Minister in charge of Youth Affairs; The Archbishop of the Bamenda Ecclesiastical Province; The Moderator of the Presbyterian Church in Cameroon; The President of the Cameroon Baptist Convention; a representative of the Muslim community; a representative of Women Associations;  a representative of Youth Associations; the representative of each donor contributing to the PPRD; The Coordinator of the United Nations System in Cameroon;   the Representative of the Implementing Partner.

The Steering Committee will meet at least once per semester and, if necessary, upon convocation by its President. The Chairman of the Steering Committee may, in advisory capacity, call upon any natural or legal person for his or her competences in relation to the issues of the agenda.

The National Coordination is the operational body in charge with monitoring the implantation of the PPRD. The National Coordinator acts as an interface between the PPRD and the specialized technical Ministries. The National Coordinator will facilitate the mobilization of resources and the relationship between actors from the State's technical services and manage all issues relating to administrative constraints. The National Coordination shall be headed by a National Coordinator assisted by a deputy. The National Coordinator and the Deputy National Coordinator are appointed by the Prime Minister, Head of the Government.

As such, it shall:

- Elaborate the action plan and the annual work plan to be submitted to the Steering Committee for approval;

- Organize and monitor the mobilization of resources for the implementation of the PPRD;

- Act as an interface with the relevant State Services as needed to facilitate the implementation of the PPRD;

- Ensure the transfer of resources to the Implementing Partner;

- Ensure compliance with the terms of the Memorandum of Understanding by the Implementing Partner;

- Ensure the implementation of the directives and recommendations of the Steering Committee;

- Assist the administration involved in the operational monitoring of projects under their competence in relation to the PPRD;

- Examine and validate the budget, financial statements, activity and management reports produced by the Implementing Partner of the PPRD;

- Prepare the meetings of the Steering Committee;

- Report regularly to the Chairman of the Steering Committee on the activities carried out and any difficulties encountered;

- Ensure adequate communication on the implementation of the PPRD;

- Monitor field operations and reporting to the Steering Committee.

The National Coordination is composed of:

- Two regional coordinators;

- One Administrative and Financial Manager;

- One Monitoring and Evaluation Officer;

- One Communications and Public Relations Officer;

- Three Experts (social sector, essential infrastructure and economic revitalization);

- Support Staff.

The Regional Follow-up Committees are under the authority of the National Coordinator. The Regional Follow-up Committees are responsible for the follow-up of actions at regional local level. The Regional Follow-up Committees are based both in Bamenda (North-West region) and Buea (South-West region). These Committees will oversee the implementation of the PPRD in the NW/SW at local level. To this effect, the Committee is responsible of the following:

- Suggest improvements in the implementation of the PPRD;

- Foster synergies between various stakeholders involved in the implementation of the projects;

- Ensure proper involvement of the decentralized services of the State and other entities, notably Local and Regional entities, the private sector and the beneficiary communities in the implementation of the PPRD.

The Regional Follow-up Committee is composed of:

- Chairperson: The Governor of the Region;

- Co-chair: A representative of the Executing Agency (UNDP);

- Members: Senior Divisional Officers of the Region; Mayors; Chiefs-towns; Regional Delegates; Parliamentary representatives; Traditional Authorities; representatives of the Catholic Church, Presbyterian Church, Cameroon Baptist Convention, Muslim community, representatives of the private sector, in addition to representatives of civil society organizations.

The Regional Coordinator is the rapporteur of the Regional Follow-up Committee.

The Implementing Partner is designated by the Government of Cameroon who called upon UNDP to be the Implementing Partner of the PPRD. The Implementing Partner the following roles and responsibilities:

- Implementation of all components of the PPRD in accordance with the rules and procedures of UNDP;

- Fiduciary responsibility for the management of the funds made available to the PPRD;

- Establishment of a PPRD Management Unit (PPRDMU);

- Quarterly reporting on the technical and financial execution of the PPRD;

- Preparation of resource mobilization documents;

- Carry out necessary studies aimed at optimizing the implementation of the PPRD.

The Implementing Partner deploys his activities in accordance with the strategic orientations of the Steering Committee. The Implementing Partner works in close collaboration with the South-West Development Authority (SOWEDA) and the North-West Development Authority (MIDENO), as well as deconcentrated services and regional and local authorities of the NW/SW.

Under the authority and supervision of the Implementing Partner, the Presidential Plan for Reconstruction and Development Management Unit (PPRDMU) is responsible for the execution of the PPRD. The PPRDMU is composed of a team recruited by UNDP.

Table 23: Governance Structure

## IV.4 Principles of Engagement and Mitigation Measures

The proposed Principles of Engagement and Mitigation Measures have practical operational relevance, especially in situations of open conflict and hostility that characterizes the context in the NW and SW regions of Cameroon. Consistent adherence to the PPRD Principles of Engagement and Mitigation Measures will enable UNDP and all stakeholders to:

- Gain and maintain unrestricted, unimpaired and unhindered access to affected populations;

- Prevent risks to local communities, staff, partners and assets;

- Promote and ensure the rights and dignity of affected populations;

- Establish a principled engagement with authorities and all stakeholders on the ground.

Equally important is UNDP’s commitment to rights-based and community-based approaches that include efforts to engage and empower persons of concern in decisions that affect their lives. The humanitarian, development and peace actors are committed to coordinate and synchronize their interventions in the NW/SW, based on specific criteria and crisis dynamics, and on a sequential approach taking into account the ability and potential to achieve collective results. Existing coordination mechanisms at national, departmental and local levels will facilitate the synchronization of humanitarian-development-peace interventions and thus enhance impact on targeted populations.

To ensure transparency in assisting the NW/SW regions, the Government designated UNDP as the implementing partner and Fund manager of the PPRD. UNDP will implement the PPRD under the strict respect of UNDP’s Principles of Engagement and Mitigation Measures.

UNDP strives to respond to the NW/SW crisis with impartiality. This means that actions are based solely on need of affected populations, with priority given to the most urgent and vulnerable cases irrespective of ethnicity, gender, religious beliefs or political opinion.

UNDP will adopt a comprehensive and integrated approach to risk mitigation in the context of the PPRD. Rigorous application of the proposed Principles of Engagement and Mitigation Measures will avoid that the PPRD becomes subject to control or subordination by political, economic, military or other objectives.

Key principles are as follows:

- Respect of International Human Rights standards: Given the complexity and the environment of the areas where this program will be conducting its activities, and based on standard practices of the United Nations in working in complex situations, UNDP will conduct a due diligence assessment in order to ensure that all activities undertaken within the PPRD respond to the Human Rights Due Diligence Policy on UN support to non-UN security forces (HRDDP). Due diligence means (1) doing a risk assessment before giving support, (2) being transparent with national partners about the legally binding nature and core principles governing provision of UN support and (3) ensuring an effective implementation framework. UNDP will ensure risks are assessed and managed at every stage of its programmatic engagement with the security services. Before engaging in the NW and SW regions, UNDP will go through the accountability framework (see Appendices VII.3). Within the HRDDP framework UNDP will   draft (1) a questionnaire on pre-requisites; (2) a questionnaire assessing the reputational risk for the UNDP when entering the intervention areas; and (3) measures aimed at mitigating the risks identified. Ultimately, application of HRDDP will ensure that all stakeholders of the PPRD are vetted and that resources are not allocated to former and potential Human Rights violators

- Set-up a robust targeting approach: Due to the ongoing conflict, certain areas of the NW/SW are difficult to access. To mitigate this risk and ensure a gradual intervention, the PPRD will use a step-by-step approach, first targeting accessible areas before moving to more sensitive areas. Initial programming will be done in areas of the NW/SW where accessibility and security for staff and communities is ensured. Second-phase programming will be conducted by replicating and scaling up success from the initial programming phase in areas that are harder to access. Additionally, beneficiary targeting will be undertaken based on a people-centred and vulnerability-based approach to select the most vulnerable communities.

- Ensure local ownership with traditional/religious chiefs, youth and women groups: Before the start of activities on the ground, validation workshops will be organized in both the NW and SW regions. The specific objectives of the validation workshop are to (i) review the present PPRD with a view to validating information, data and needs and (ii) reach consensus with all involved stakeholders (local authorities, communities, partners etc.). The PPRD will ensure collective ownership by key stakeholders. The accountability and business process for the PPRD ensures that partners participate and benefit from mutual accountability, that processes are streamlined and clarified, that specific roles and responsibilities are defined to strengthen efficiency, that silos and fragmentation in implementing components are avoided, and that clear processes are developed for building strategic partnerships and coordinating the development of knowledge and sharing of systems.

- Support the Inter Cluster Coordination Group: Maintain UNDP involvement with the intersectoral coordination and exercise leadership role on the Early Recovery cluster. Enhance the "One-UN" approach with particular focus on the ability of partners to collaborate and ensure triangulation of information and deconflicting of activities at the ground level.

- Mitigate political instrumentalization through managed visibility: UNDP will develop a multi-stakeholder communication plan based on collectively agreed key messages. Risk communication is recognised as the two-way and multi-directional communications and engagement with affected populations so that they can take informed decisions to protect themselves. UNDP is mindful of using the most appropriate and trusted of channels of communication and engagement. Accordingly, the PPRD’s risk communication will serve to:

- Raise awareness on the PPRD and its objectives amongst communities, local administrations and local leaders;

- Encourage protective behaviour of community members in areas of operation;

- Inform to build up knowledge on hazards and risks linked to operating in conflict areas;

- Inform to promote acceptance of risks and management measures;

- Inform on how to behave during activities and ceremonies;

- Warn of and trigger action to impending and current events;

- Reassure the audience (to reduce anxiety or ‘manage’ outrage);

- Improve relationships (build trust, cooperation, networks);

- Enable mutual dialogue and understanding around the PPRD;

- Involve actors in decision making.

# PART V: BUDGET

The implementation of this PPRD is estimated at 89 682 938 100,00 XAF, equivalent to $151 896 849,87.

Table 24: Budget Allocation

The financing of the PPRD is the responsibility of the Government of Cameroon and UNDP, with the participation of other donors. UNDP and the Government will combine their efforts to mobilize partnerships and resources, through the establishment of an Open Partnership Framework. The Government of Cameroon commits to contribute 15% of the funding requirements. The gap will be mobilized through a joint mobilization effort of the Government and UNDP. The private sector will also be solicited to participate in the funding of this Plan, particularly on aspects related to local economic revitalization and entrepreneurship initiatives.

The funding strategy for the implementation of the priorities will include:

- Increase in the budget allocation to both regions;

- Effective use of existing public investments (national and international) in the two regions in response to the pillars and priorities of the PPRD;

- Alignment of international support for government efforts to increase public spending in the two regions and accelerate disbursements.

The definition of the funding modalities within the framework of this PPRD requires:

- Identification of existing financing (national and international public finances) in the two regions;

- Identification of funding gaps based on the mapping of existing funding and estimated costs to implement the priorities of the PPRD.

See detailed budget below.

# PART VI: LEGAL FRAMEWORK

This PPRD derives its legitimacy from many legal documents and principles governing peace and security worldwide. First, there is the partnership between the Government of Cameroon and UNDP Cameroon embodied in the 1991 Standard Basic Agreement (SBAA) between the two entities. It is in line with the strategic priorities defined by the United Nations Development Assistance Framework (UNDAF) and adapts to Cameroon's national reality in order to protect, secure and empower the populations affected by the effects of the crisis.

Amendments to this PPRD are only possible after agreement with the Government and signature of the UNDP Resident Representative, provided that the latter is satisfied that the other signatories to the PPRD document have no objection to the changes proposed.

Cameroon’s Vision 2035 expresses the aspirations of Cameroonians to be a united nation enjoying peace and security; democracy; decentralized administration; prosperity; and universal access to quality social services.  Cameroon’s Vision 2035 expressed through its Growth and Employment Strategy Paper (GESP), constitutes the reference framework of government’s policy and actions up to 2035.

The overarching thrust of the GESP is driven by the policies and actions which include promoting job creation by acting on jobs offers and efficiency of the job market and rehabilitating of the road network.

Meanwhile, priorities of Cameroon’s Poverty Reduction Strategy include developing essential infrastructure and natural resources, while protecting the environment; strengthening human resources and the social services and integrating vulnerable groups into the economy and promotion of good governance, which are all rooted in agenda 2030 - Sustainable Development Goals (SDGs).

On 25 September 2015, Member States of the United Nations adopted the 2030 Agenda for Sustainable Development with the Sustainable Development Goals (SDGs) at its core. The 2030 Agenda commits all countries and stakeholders to working together to achieve sustained and inclusive economic growth, social development and environmental protection.

The United Nations Development Assistance Framework (UNDAF) is the plan for the United Nations Country Team’s (UNCT) contribution towards national development priorities in 2018-2021 and incorporates the ambitions of the 2030 Agenda. This plan outlines how the UNCT aims to collaborate with partners during the UNDAF period on the Sustainable Development Goals (SDGs).

# PART VII: APPENDICES

## VII.1 Monitoring and Evaluation Framework

During the implementation of the PPRD particular attention will be paid to effectiveness and efficiency in the conduct of activities, the achievement of results and their targets, and the use of resources. With this in mind, the plan intends to monitor the qualitative and quantitative indicators defined in the results matrix. This will facilitate its monitoring and evaluation to ensure that Plan activities are carried out in accordance with the approved work plan.

The PPRD will set up the following mechanisms to ensure appropriate monitoring of results:

- Coordination bodies (Steering Committee, PSC), technical monitoring bodies (Technical Monitoring Committee, TMC) and management bodies (Plan Management Unit, PMU) whose meeting reports are essentially reporting on plan monitoring actions.

- A joint PMU and Government official meeting to launch the activities of the Plan during the first quarter following its official approval.

- A biannual review of the Plan’s progress towards expected results, challenges and solution to accelerate and improve the implementation of the PPRD.

- An annual review of the Plan at the technical level, based on the results-based annual implementation report, prepared by the PPRD management team in collaboration with the sectoral and/or provincial teams.

- An annual meeting of the Steering Committee with an appropriate report and guidelines based on the Technical Committee annual report.

- Field visits will also be part of the monitoring activities.

A Plan Monitoring and Evaluation system will be set up and will be run on a quarterly, half-yearly and annual basis:

- Weekly follow-up: meetings of the PPRDMU;

- Monthly follow-up: meetings of the PPRDMU and UNDP management;

- Quarterly monitoring: meetings of the technical monitoring committee and submission of summary progress reports by pillar

- Half-yearly follow-up: meeting of the steering committee, preceded by the production of a summary progress report on the plan;

- Annual review: Steering Committee meeting with a presentation of detailed annual activity reports and the detailed work plan for the following year.

With regard to the evaluation of the PPRD, the following actions are planned:

- A mid-term review: considering the short duration of the Plan's implementation (2 years) due to its urgent nature, a mid-term review will be carried out 12 months after the start of the plan implementation. The ultimate objective of this mid-term review is, on the one hand, to assess the progress made and the challenges faced in the implementation of the PPRD, the achievement of expected results, the weaknesses, constraints and challenges encountered, the strengths and weaknesses in the partnership and the management of the PPRD; on the other hand, this mid-term review will propose corrective actions for further implementation of the PPRD. The mid-term review and evaluation will be organized in accordance with arrangements agreed between the Government and UNDP. The members of the independent external evaluation team will be appointed in accordance with the profile required by the mission's TORs, which will be managed by UNDP.

- A final evaluation of the PPRD, shortly before its closure: the final evaluation will focus on the expected results and impacts of the Plan, as well as the achievements and lessons to be learned for other future Plan in this area.

A timetable of these different review and evaluation will be developed in collaboration with the Plan Management Unit. The various evaluation reports, and in particular their findings and recommendations, are intended to support appropriate decision-making to improve the effectiveness and efficiency of the PPRD’s implementation.

The entire monitoring and evaluation system and mechanism of the Plan is based on results-based management (RBM) principles in accordance with UNDP norms and standards. The results performance framework (Integrated Monitoring and Evaluation Plan) is the basic tool of RBM, as it provides indications on expected outcomes and outputs, a clear definition of the baseline, targets, and measurable (when quantitative) and realistic indicators. The PPRD targets are defined as exact values on an indicative scale (for qualitative indicators). The targets will be broken down into quarterly milestones in the Annual Work Plans (AWPs), and further refined in the Integrated Monitoring and Evaluation Plan (IMEP) to be designed for the plan.

Table 25: Monitoring & Evaluation Framework

| Project title and Atlas Project Number: Presidential Plan for Reconstruction and Development (PPRD) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED OUTPUTS | OUTPUT INDICATORS | DATA SOURCE | BASELINE |  | TARGETS |  |  | DATA COLLECTION METHODS & RISKS |
|  |  |  | Value | Year | Year 1 | Year 2 | FINAL |  |
| Output 1.1: The most affected and vulnerable people located in South West and North West regions have their houses rehabilitated to BBB standards through the active involvement of affected population and local contractors and/or CSOs | 1.1.1: Number of essential infrastructures rehabilitated and constructed. | Activity report | Rehabilitated =TBD Constructed =TBD | 2019 | 290 | 290 | 580 | Direct observation and activity reports |
|  | 1.1.2: Percentage of homeowners with a repaired dwelling that are women, youth, elderly or persons with disabilities | Activity report Survey | TBD | 2019 | 50% | 100% | 100% | Questionnaire |
|  | 1.1.3: Number of vulnerable individuals who have obtained temporary livelihoods and training through a labour-intensive program for the rehabilitation of affected houses | Activity report | TBD | 2019 | 200 | 200 | 400 | Direct observation and activity reports |
| Output 1.2: Strengthened local communities’ systems and structures to cope with the aftermath and recover from crisis | 1.2.1 Number of new community development, risk reduction and recovery intervention(s) that are informed by risk assessments | Activity report | 0 | 2019 | 100 | 100 | 200 | Direct observation and activity reports |
|  | 1.2.2 Proportion of people in crisis affected communities that are covered by early warning information through local governments or through national dissemination mechanisms (disaggregated by sex) | Activity report | 0 | 2019 | 50% | 75% | 75% | Programme report, media reports |
|  | 1.2.3 No of gender-sensitive recovery framework/ plans with capacity building initiatives at community level | Activity report | 0 | 2019 |  | 13 | 13 | Programme/government reports report |
| Output 1.3 Mechanisms that consolidate peace, security and social cohesion strengthened | 3.1.1 Existence of plans and strategies under implementation for reintegration of displaced persons and/or former combatants | Activity report | 0 | 2019 |  | 1 | 1 | Direct observation and activity reports |
|  | 3.1.2 Number of engagement and dialogue platforms, targeting inclusion and participation of women and youth in decision making processes | Activity report | TBD | 2019 | 6 | 7 | 13 |  |
|  | 3.1.3 Number of institutions and communities in the SW and NW regions whose capacities are enabled to provide, lead and coordinate reconciliation and dispute resolution processes | Activity report | 0 | 2019 | 6 | 7 | 13 |  |
| Output 2.1 Key community infrastructure in affected areas rehabilitated to BBB standards to restore the provision of education, health and socio-economic services | 1.2.1: Number of people accessing basic services, as a result of UNDP-supported work, disaggregated by target groups: a) Poor; b) Women c) People with disabilities d) Youth e) Displaced populations | Activity report | 0 | 2019 | 1000000 | 1000000 | 2000000 | Administrative reports |
| Output 3.1 Livelihoods and early economy recovery and income generation opportunities created | 3.1.1 number of livelihood opportunities created for people in affected communities | Activity report | 0 | 2019 | 2500 | 2500 | 5000 | Direct observation and activity reports |
|  | 3.1.2: Number of affected people improved livelihood options disaggregated by sex | Activity report | 0 | 2019 | 2000 | 2000 | 4000 |  |
|  | 3.1.3 Number of entrepreneurs benefiting from the value chain development and improvement initiatives. | Activity report | 0 | 2019 | 2000 | 2000 | 4000 | Direct observation and activity reports |
| Output 3.2 Crisis-affected people benefiting from community-driven and gender-focused emergency employment interventions | 2.2.1Number of affected communities that have implemented recovery and response strategies and plans | Activity report | 0 | 2019 | 50 | 50 | 100 | Direct observation and activity reports |
|  | 2.2.2 No of new emergency Jobs created as a result of UNDPs intervention | Activity report | 0 | 2019 | 70 | 70 | 140 | Direct observation and activity reports |
|  | 2.2.3 No people benefiting from cash-for-work recovery initiatives | Activity report | 0 | 2019 | 1500 | 1500 | 3000 | Direct observation and activity reports |
| Output 3.3 Micro, small and medium enterprises and other income generation initiatives reactivated and/or strengthened | 2.3.1 Number of Small grants/start-up packages provided to affected populations to re-establish their enterprises | Activity report | 0 | 2019 | 65 | 65 | 130 | Direct observation and activity reports |
|  | 2.3.2 No and type of enterprises that transition beyond the stabilization stage to the growth stage as a result of BDS | Activity report | 0 | 2019 | 10 | 10 | 20 | Direct observation and activity reports |
| Output 3.4 Institutional capacities for livelihoods/ employment and enterprise recovery/development enhanced | 2.4.1 Number of government institutions at subnational levels implementing and monitoring their operational plans that incorporate, community recovery, employment and resilience to in targeted areas. | Activity report | 0 | 2019 | 5 | 5 | 10 | Direct observation and activity reports |
|  | 2.4.2 Number communities benefiting from value chain enabling strategies in Agriculture, fisheries and/or allied sectors | Activity report | 0 | 2019 | 50 | 50 | 100 | Direct observation and activity reports |
|  | 2.4.3 Number of entrepreneurs benefiting from the value chain development and improvement initiatives. | Activity report | 0 | 2019 | 65 | 65 | 130 | Direct observation and activity reports |

Table 26: UNDAF Framework

Intended Outcome as stated in the UNDAF/Country [or Global/Regional] Programme Results and Resource Framework: Outcome 4.1 (UNDAF)/ Outcome 2 (CPD): By 2020, population (especially vulnerable groups) in the intervention areas are more resilient to environmental, social and economic shocks.

Outcome indicators as stated in the Country Programme [or Global/Regional] Results and Resources Framework, including baseline and targets: Indicator 2.3: Number of local institutions and platforms applying techniques and strategies for conflict prevention/management and social cohesion 2.3a: Local institutions: Baseline (2016): 3, Target: 7 2.3b: Platforms: Baseline (2016): 3, Target: 7 Indicator 2.4: Number of critical benchmarks identified, and actions implemented for local economic revitalization (LER) 2.4a: Economic livelihoods: Affected household assets are replaced; Households incomes at least at break-even levels Baseline (2016): 20 000, Target (2020): 41 000 2.4b: Infrastructure: Infrastructure (specify) is rehabilitated and functional Baseline (2016): 10, Target (2020): 20

Applicable Output(s) from the UNDP Strategic Plan: SP output 3.1.1 Core government functions and inclusive basic services restored post-crisis for stabilisation, durable solutions to displacement and return to sustainable development pathways within the framework of national policies and priorities. SP output 3.2.1. National capacities strengthened for reintegration, reconciliation, peaceful management of conflict and prevention of violent extremism in response to national policies and priorities

## VII.2 Mapping of the North West and South West regions

## VII.3 Accountability Framework for the Human Rights Due Diligence Policy

# PART VIII: REFERENCES

Afdb.org. (2019). African Economic Outlook 2019. [online] Available at: https://www.afdb.org/fileadmin/uploads/afdb/Documents/Publications/2019AEO/AEO_2019-EN.pdf

African Development Bank (2018). Central Africa Economic Outlook 2018. [online] Afdb.org. Available at: https://www.afdb.org/fileadmin/uploads/afdb/Documents/Publications/2018AEO/African-Economic-Outlook-2018-Central-Africa.pdf

Africanews. (2019). HRW report says at least 170 civilians killed in Anglophone Cameroon since October | Africanews. [online] Available at: https://www.africanews.com/2019/03/29/hrw-reports-says-at-least-170-civilians-killed-in-anglophone-cameroon-since/

https://www.worldbank.org/. (2019). Overview of the World Bank In Cameroon. [online] Available at: https://www.worldbank.org/en/country/cameroon/overview#1

Human Rights Watch. (2019). Rapport mondial 2019 : Cameroun. [online] Available at: https://www.hrw.org/fr/world-report/2019/country-chapters/325496

Humanitarianresponse.info. (2019). Aperçu des besoins humanitaires. [online] Available at: https://www.humanitarianresponse.info/sites/www.humanitarianresponse.info/files/documents/files/cmr_hno_2019_vf_light.pdf

Ministry of Economy, Planning and Regional Development (2018). Cameroon Economic Development Report - South West Region. Permanent Secretariat.

PIAD WA For UNICEF (2019). Education Needs Assessment Report July 2019. [online] Available at: https://reliefweb.int/sites/reliefweb.int/files/resources/UNICEF%20Cameroon%20Humanitarian%20Situation%20Report.pdf [Accessed 14 Nov. 2019].

REGIONAL DELEGATION OF ECONOMY, PLANNING AND REGIONAL DEVELOPMENT (2019). The socio-economic impact of public investment projects in the North-West region from 2012 to 2016 and the socio-economic impact of the socio-political crisis from 2017 to 2018. Service of Economic Affairs and Programming.

Reliefweb.int. (2019). Cameroon Humanitarian Situation Report. [online] Available at: https://reliefweb.int/sites/reliefweb.int/files/resources/UNICEF%20Cameroon%20Humanitarian%20Situation%20Report%20-%20September%202019.pdf

Ricciardelli, A. (2018). Governance, Local Communities, and Citizens Participation. [online] Available at: https://link.springer.com/

Stanley, D. (2003). What Do We Know about Social Cohesion: The Research Perspective of the Federal Government's Social Cohesion Research Network. [online] https://www.jstor.org/. Available at: https://www.jstor.org/stable/3341872?seq=1#page_scan_tab_contents [

The Economist. (2019). English-speaking villages are burning in Cameroon. [online] Available at: https://www.economist.com/middle-east-and-africa/2019/11/07/english-speaking-villages-are-burning-in-cameroon

Worldpopulationreview.com. (2019). Cameroon Population 2019. [online] Available at: http://worldpopulationreview.com/countries/cameroon-population/

It is recommended that projects use output indicators from the Strategic Plan IRRF, as relevant, in addition to project-specific results indicators. Indicators should be disaggregated by sex or for other targeted groups where relevant.