## Sheet2 (hidden)
Outcome 1: Ground water recharge and irrigation technologies implemented for crop and forage production by developing sub-surface dam within the Anseba river |  |  |  |  | Quarterly dibursement of budget for year 2015
Out put 1.1 Ground water recharge and irrigation technologies implemented for crop and forage production by developing sub-surface dam within the Anseba river |  |  |  |  | 1st qaurater |  | 2nd quarter |  | 3rd quarter |  | 4th quarter |  | Total
| Unit | quantity | Budget |  | USD | ERN | USD | ERN | USD | ERN | USD | ERN | USD | ERN
|  |  | USD | ERN
Activity 1.1.1 Preparation Technical design of sub-surface dam and associated facilities | Doc. | 1 | 40000 | 600000 | 20000 | 300000 | 20000 | 300000 |  |  |  |  | 40000 | 600000
Activity 1.1.2 Construct the sub-surface dam and associted irrigation technology | No. | 1 | 972400 | 14586000 | 195000 | 2925000 | 486200 | 7293000 | 291200 | 4368000 |  | 0 | 972400 | 14586000
Sub Total |  |  | 1012400 | 15186000 | 215000 | 3225000 | 506200 | 7593000 | 291200 | 4368000 |  | 0 | 1012400 | 15186000
Out-put 1.2 Flood water harvested to enable irrigation of rainfed cereal production and rangelands |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Activity 1.2.3 Construct small scale diversion system (Continuation from last year) |  |  | 30000 | 450000 | 15000 | 225000 | 15000 | 225000 |  | 0 |  | 0 | 30000 | 450000
Sub Total |  |  | 30000 | 450000 | 15000 | 225000 | 15000 | 225000 | 0 | 0 |  | 0 | 30000 | 450000
output 1.3 Micro dam construction to reatin and store rainfall run-off and recharge groundwater |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Activity 1.3.4 Construction of microdam | No. | 1 | 200000 | 3000000 | 100000 | 1500000 | 100000 | 1500000 |  | 0 |  | 0 | 200000 | 3000000
Sub Total |  |  | 200000 | 3000000 | 100000 | 1500000 | 100000 | 1500000 | 0 | 0 |  | 0 | 200000 | 3000000
Output 1.4 Soil and water conservation measures implemented to improve runoff management and infiltration |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
1.4.2 Construct hillside terraces along contours in identified locations, using stone-faced hillside terrace | Km. | 200 | 100000 | 1500000 | 50000 | 750000 | 50000 | 750000 |  | 0 |  | 0 | 100000 | 1500000
1.4.3 Construct check dams to slow down the speed of stream flow ( through communities cash for work scheme) | M3 | 7500 | 40000 | 600000 | 20000 | 300000 | 20000 | 300000 |  | 0 |  | 0 | 40000 | 600000
1.4.4 Implement planned enclosures and afforestation activities | No. | 75000 | 15000 | 225000 |  | 0 | 15000 | 225000 |  | 0 |  | 0 | 15000 | 225000
1.4.5 Train farmers to construct physical soil conservation measures, terraces, waterways, and gully controll on crop lands | No. | 200 | 30000 | 450000 | 15000 | 225000 | 15000 | 225000 |  | 0 |  | 0 | 30000 | 450000
1.4.6 Support communities and indivisual households to establish woodlots |  |  | 25000 | 375000 |  | 0 | 25000 | 375000 |  | 0 |  | 0 | 25000 | 375000
1.4.7 Establish one new tree seedling and forage legumes nursery in Habero and rehablitate the existing one in Hamelmalo | No. | 2 | 50000 | 750000 | 25000 | 375000 | 25000 | 375000 |  | 0 |  | 0 | 50000 | 750000
1.4.8 over-sow catchment with improved native grass seeds and forage to enhance restoration of enclosure | Ha. |  | 25000 | 375000 |  | 0 | 12500 | 187500 | 12500 | 187500 |  | 0 | 25000 | 375000
Sub Total |  |  | 285000 | 4275000 | 110000 | 1650000 | 162500 | 2437500 | 12500 | 187500 |  | 0 | 285000 | 4275000
Outcome 2: Climate resilient agricultural and livestock production enhanced |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Output 2.1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
2.1.1 Strengthen agricultural extension agent through training and enhanced mobility and communication | No. | 100 | 20000 | 300000 |  | 0 | 20000 | 300000 |  | 0 |  | 0 | 20000 | 300000
2.1.2 Provide a range of options to farmers , specifically on women-headed households on climate resilient technology including agroforestry, conservation tillage, drought resistant etc |  |  | 100000 | 1500000 | 25000 | 375000 | 50000 | 750000 | 25000 | 375000 |  | 0 | 100000 | 1500000
2.1.3 provide a range of options to agro-pastoralists specifically targeting women-headed households on climate resilient technologies for enhanced livestock and rabgeland management |  |  | 100000 | 1500000 | 25000 | 375000 | 50000 | 750000 | 25000 | 375000 |  | 0 | 100000 | 1500000
Sub Total |  |  | 220000 | 3300000 | 50000 | 750000 | 120000 | 1800000 | 50000 | 750000 |  | 0 | 220000 | 3300000
Output 2 Seasonal forecast used in farmer-led collaborative action learning process to enhance adaptive capacity and climate proof production systems |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Activity 2.2.1 Identify programme sites for the collabration action learning process and hold introductory meeting at all levels |  |  | 25000 | 375000 | 12500 | 187500 | 12500 | 187500 |  | 0 |  | 0 | 25000 | 375000
Activity 2.2.2 Support farmers in an iterative process to use seasonal forecasts to guide production activities |  |  | 25000 | 375000 | 12500 | 187500 | 12500 | 187500 |  | 0 |  | 0 | 25000 | 375000
Activity 2.2.3 Monitor progress systematically and record lessons learned from the action learning seasonal forecast component |  |  | 25000 | 375000 | 12500 | 187500 | 12500 | 187500 |  | 0 |  | 0 | 25000 | 375000
Sub Total |  |  | 75000 | 1125000 | 37500 | 562500 | 37500 | 562500 | 0 | 0 |  | 0 | 75000 | 1125000
Outcome 3 Improved climate risks information and climate monitoring used to raise awareness and enhance community preparedness to climate change hazards |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Output 3.1 Improved climate risk information generated and capacity developed for climate monitoring and analysis |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Activity 3.1.4 Install meterological stations in Habero and Hamelmalo |  |  | 32000 | 480000 | 20000 | 300000 | 12000 | 180000 |  | 0 |  | 0 | 32000 | 480000
Activity 3.1.5 Staff trained on taking meterological readings, standardised recording and reporting at zoba and sub zoba level |  |  | 10000 | 150000 | 10000 | 150000 |  | 0 |  | 0 |  | 0 | 10000 | 150000
Sub Total |  |  | 42000 | 630000 | 30000 | 450000 | 12000 | 180000 | 0 | 0 |  | 0 | 42000 | 630000
Output 3.2 Awareness raised at different levels on climate change risks facing zoba Anseba |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Activity 3.2.1 Develop a detailed strategy for the climate change awareness raising campaign for the programme |  |  | 10000 | 150000 |  | 0 | 10000 | 150000 |  | 0 |  | 0 | 10000 | 150000
Activity 3.2.2 Plan and hold a well-publicised launch event fopr CC awareness raising campaign to capture public imagination and secure initialpolitical commitment |  |  | 15000 | 225000 | 7500 | 112500 | 7500 | 112500 |  | 0 |  | 0 | 15000 | 225000
Activity 3.2.3 Hold awareness raising events at policy (Zoba) level, sub-zoba, and community level |  |  | 41500 | 622500 |  | 0 |  | 0 | 20750 | 311250 | 20750 | 311250 | 41500 | 622500
Sub Total |  |  | 66500 | 997500 | 7500 | 112500 | 17500 | 262500 | 20750 | 311250 | 20750 | 311250 | 66500 | 997500
Output 3.3 Community preparedness enhanced through community-based early warning system in sub zobas Hamelmalo and Habero |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Activity 3.3.1 carry out stocktaking assessment of former and existing initiative and structures for community prepardness and early warning systems to climate risks |  |  | 30000 | 450000 | 10000 | 150000 | 20000 | 300000 |  | 0 |  | 0 | 30000 | 450000
Activity 3.3.2 Initiate community-based planning exercise to design community based early warning systems |  |  | 20000 | 300000 | 20000 | 300000 |  | 0 |  | 0 |  | 0 | 20000 | 300000
Activity 3.3.3 Train community memebers in data collection, carry out institutional stregtghening to establish community-based early warning |  |  | 35000 | 525000 | 15000 | 225000 | 20000 | 300000 |  | 0 |  | 0 | 35000 | 525000
Activity 3.3.4 Build disaster risk reduction and early warning capacity in the zoba Administration |  |  | 40000 | 600000 | 10000 | 150000 | 10000 | 150000 | 10000 | 150000 | 10000 | 150000 | 40000 | 600000
Sub Total |  |  | 125000 | 1875000 | 55000 | 825000 | 50000 | 750000 | 10000 | 150000 | 10000 | 150000 | 125000 | 1875000
Outcome 4: Lessons learned and shared and policy influenced through knowledge management system |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Output 4.1 Knoweledge management system established and knoweledge management activities implemented |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
Activity 4.1.1 Design and establish a knoweledge management system for the programme, based on existing processes in the Zoba Anseba |  |  | 20000 | 300000 |  | 0 |  | 0 |  | 0 |  | 0 | 20000 | 300000
Activity 4.1.2 Conduct a study tour to country in the region with similar climate risks and enviromental constraints |  |  | 45000 | 675000 |  | 0 |  | 0 |  | 0 |  | 0 | 45000 | 675000
Sub Total |  |  | 65000 | 975000 | [8 empty] | 65000 | 975000
Total |  |  | 2120900 | 31813500 | 620000 | 9300000 | 1020700 | 15310500 | 384450 | 5766750 | 30750 | 461250 | 2120900 | 31813500

## Sheet3
Outcome 1: Ground water recharge and irrigation technologies implemented for crop and forage production by developing sub-surface dam within the Anseba river |  |  |  | Quarterly dibursement of budget for year 2015
Out put 1.1 Ground water recharge and irrigation technologies implemented for crop and forage production by developing sub-surface dam within the Anseba river |  |  |  | 1st qaurater | 2nd quarter | 3rd quarter | 4th quarter | Total
| Unit | Qty | USD | USD | USD | USD | USD | USD
Activity 1.1.1 Preparation Technical design of sub-surface dam and associated facilities | Doc. | 1 | 40000 | 20000 | 20000 |  |  | 40000
Activity 1.1.2 Construct the sub-surface dam and associted irrigation technology | No. | 1 | 972400 | 195000 | 486200 | 291200 |  | 972400
Sub Total |  |  | 1012400 | 215000 | 506200 | 291200 | 0 | 1012400
Out-put 1.2 Flood water harvested to enable irrigation of rainfed cereal production and rangelands | [7 empty] | 0
Activity 1.2.3 Construct small scale diversion system (Continuation from last year) |  |  | 30000 | 15000 | 15000 |  |  | 30000
Sub Total |  |  | 30000 | 15000 | 15000 | 0 |  | 30000
output 1.3 Micro dam construction to reatin and store rainfall run-off and recharge groundwater | [7 empty] | 0
Activity 1.3.4 Construction of microdam | No. | 1 | 200000 | 100000 | 100000 |  |  | 200000
Sub Total |  |  | 200000 | 100000 | 100000 | 0 |  | 200000
Output 1.4 Soil and water conservation measures implemented to improve runoff management and infiltration | [7 empty] | 0
1.4.2 Construct hillside terraces along contours in identified locations, using stone-faced hillside terrace | Km. | 200 | 100000 | 50000 | 50000 |  |  | 100000
1.4.3 Construct check dams to slow down the speed of stream flow ( through communities cash for work scheme) | M3 | 7500 | 40000 | 20000 | 20000 |  |  | 40000
1.4.4 Implement planned enclosures and afforestation activities | No. | 75000 | 15000 |  | 15000 |  |  | 15000
1.4.5 Train farmers to construct physical soil conservation measures, terraces, waterways, and gully controll on crop lands | No. | 200 | 30000 | 15000 | 15000 |  |  | 30000
1.4.6 Support communities and indivisual households to establish woodlots |  |  | 25000 |  | 25000 |  |  | 25000
1.4.7 Establish one new tree seedling and forage legumes nursery in Habero and rehablitate the existing one in Hamelmalo | No. | 2 | 50000 | 25000 | 25000 |  |  | 50000
1.4.8 over-sow catchment with improved native grass seeds and forage to enhance restoration of enclosure | Ha. |  | 25000 |  | 12500 | 12500 |  | 25000
Sub Total |  |  | 285000 | 110000 | 162500 | 12500 |  | 285000
Outcome 2: Climate resilient agricultural and livestock production enhanced | [7 empty] | 0
Output 2.1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers | [7 empty] | 0
2.1.1 Strengthen agricultural extension agent through training and enhanced mobility and communication | No. | 100 | 20000 |  | 20000 |  |  | 20000
2.1.2 Provide a range of options to farmers , specifically on women-headed households on climate resilient technology including agroforestry, conservation tillage, drought resistant etc |  |  | 100000 | 25000 | 50000 | 25000 |  | 100000
2.1.3 provide a range of options to agro-pastoralists specifically targeting women-headed households on climate resilient technologies for enhanced livestock and rabgeland management |  |  | 100000 | 25000 | 50000 | 25000 |  | 100000
Sub Total |  |  | 220000 | 50000 | 120000 | 50000 |  | 220000
0
Output 2.2 Seasonal forecast used in farmer-led collaborative action learning process to enhance adaptive capacity and climate proof production systems | [7 empty] | 0
Activity 2.2.1 Identify programme sites for the collabration action learning process and hold introductory meeting at all levels |  |  | 25000 | 12500 | 12500 |  |  | 25000
Activity 2.2.2 Support farmers in an iterative process to use seasonal forecasts to guide production activities |  |  | 25000 | 12500 | 12500 |  |  | 25000
Activity 2.2.3 Monitor progress systematically and record lessons learned from the action learning seasonal forecast component |  |  | 25000 | 12500 | 12500 |  |  | 25000
Sub Total |  |  | 75000 | 37500 | 37500 | 0 |  | 75000
Outcome 3 Improved climate risks information and climate monitoring used to raise awareness and enhance community preparedness to climate change hazards
Output 3.1 Improved climate risk information generated and capacity developed for climate monitoring and analysis | [7 empty] | 0
Activity 3.1.4 Install meterological stations in Habero and Hamelmalo |  |  | 32000 | 20000 | 12000 |  |  | 32000
Activity 3.1.5 Staff trained on taking meterological readings, standardised recording and reporting at zoba and sub zoba level |  |  | 10000 | 10000 |  |  |  | 10000
Sub Total |  |  | 42000 | 30000 | 12000 | 0 |  | 42000
Output 3.2 Awareness raised at different levels on climate change risks facing zoba Anseba | [7 empty] | 0
Activity 3.2.1 Develop a detailed strategy for the climate change awareness raising campaign for the programme |  |  | 10000 |  | 10000 |  |  | 10000
Activity 3.2.2 Plan and hold a well-publicised launch event fopr CC awareness raising campaign to capture public imagination and secure initial political commitment |  |  | 15000 | 7500 | 7500 |  |  | 15000
Activity 3.2.3 Hold awareness raising events at policy (Zoba) level, sub-zoba, and community level |  |  | 41500 |  |  | 20750 | 20750 | 41500
Sub Total |  |  | 66500 | 7500 | 17500 | 20750 | 20750 | 66500
Output 3.3 Community preparedness enhanced through community-based early warning system in sub zobas Hamelmalo and Habero | [7 empty] | 0
Activity 3.3.1 carry out stocktaking assessment of former and existing initiative and structures for community prepardness and early warning systems to climate risks |  |  | 30000 | 10000 | 20000 |  |  | 30000
Activity 3.3.2 Initiate community-based planning exercise to design community based early warning systems |  |  | 20000 | 20000 |  |  |  | 20000
Activity 3.3.3 Train community memebers in data collection, carry out institutional stregtghening to establish community-based early warning |  |  | 35000 | 15000 | 20000 |  |  | 35000
Activity 3.3.4 Build disaster risk reduction and early warning capacity in the zoba Administration |  |  | 40000 | 10000 | 10000 | 10000 | 10000 | 40000
Sub Total |  |  | 125000 | 55000 | 50000 | 10000 | 10000 | 125000
Outcome 4: Lessons learned and shared and policy influenced through knowledge management system | [7 empty] | 0
Output 4.1 Knoweledge management system established and knoweledge management activities implemented | [7 empty] | 0
Activity 4.1.1 Design and establish a knoweledge management system for the programme, based on existing processes in the Zoba Anseba |  |  | 20000 |  |  |  |  | 20000
Activity 4.1.2 Conduct a study tour to country in the region with similar climate risks and enviromental constraints |  |  | 45000 |  |  |  |  | 45000
Sub Total |  |  | 65000 |  |  |  |  | 65000
Total |  |  | 2120900 | 620000 | 1020700 | 384450 | 30750 | 2120900
0