GEF-6 Project Identification Form (PIF)

Project Type: Full-sized Project

Type of Trust Fund: GEF Trust Fund

PART I: Project Information

| Project Title: | Community-based, sustainable and integrated natural resource management in Sub-Zoba Nakfa, Northern Red Sea Region. |
| --- | --- |
| Country(ies): | Eritrea | GEF Project ID: |  |
| GEF Agency(ies): | UNDP | GEF Agency Project ID: | 5519 |
| Other Executing Partner(s): | Ministry of Land, Water and Environment; Northern Red Sea Administration Regional Office – Department of Land and Agriculture Development | Submission Date: | 31 July 2015 |
| GEF Focal Area(s): | Climate Change Mitigation, Biodiversity, Land Degradation and Sustainable Forest Management | Project Duration (Months) | 60 |
| Integrated Approach Pilot | IAP-Cities IAP-Commodities IAP-Food Security | Corporate Program: SGP |
| Name of parent program: | [if applicable] | Agency Fee ($) | 892,866 |

A. indicative Focal Area  Strategy Framework and Other Program Strategies

| Objectives/Programs (Focal Areas, Integrated Approach Pilot, Corporate Programs) | Trust Fund | (in $) |
| --- | --- | --- |
|  |  | GEF Project Financing | Co-financing |
| BD 4 Program 9 – Managing the Human-Biodiversity Interface |  | 1,508,624 | 4,000,000 |
| CCM 2 Program 4 – Promote conservation and enhancement of carbon stocks in forest, and other land use, and support climate smart agriculture |  | 2,210,761 | 7,000,000 |
| LD 3 Program 4 – Scaling up sustainable land management through the Landscape Approach |  | 2,881,101 | 9,500,000 |
| SFM 3– Restored Forest Ecosystems: Reverse the loss of ecosystem services within degraded forest landscapes |  | 3,320,242 | 9,000,000 |
| Total Project Cost |  | 9,920,728 | 29,500,000 |

B. indicative Project description summary

| Project Objective: To mainstream sustainable land management, forestry and biodiversity conservation into land-use planning and agricultural production practices in Sub-Zoba Nafka of the Northern Red Sea Region of Eritrea |
| --- |
| Project Component | Financing Type | Project Outcomes | Project Outputs | Trust Fund | (in $) |
|  |  |  |  |  | GEF Project Financing | Co-financing |
| Component 1: Enabling framework for integrated landscape management in the Nakfa sub-zoba | TA | Outcome 1.1: Implementation of integrated landscape management practices in 324,000 hectares in the Nakfa sub-zoba Indicators: Number of hectares under integrated landscape management Number of land-use and restoration plans developed (Baseline: 0 Target: 10) | Output 1.1.1: Integrated landscape restoration plans developed (including for watershed rehabilitation, reforestation and rangeland management) for each of the 10 administrative kebabis. Output 1.1.2: Institutional and technical support provided for the: i) expansion and strengthening of forest enclosure areas for each administrative kebabi; ii) revision of existing community by-laws to integrate conservation and sustainable use of biodiversity into management of agricultural landscapes; and iii) implementation of strategies for conservation and sustainable use of the African Olive and Juniper species through off-farm conservation strategies. Output 1.1.3: Water User Associations, Farmers’ Associations and village committees established and existing ones strengthened. Output 1.1.4: Biodiversity mapping (flora and fauna) and surveys conducted; based on the data collected, a conservation strategy developed. |  | 1,506,174 | 4,275,000 |
|  |  | Outcome 1.2: Capacity of research institutions, agricultural extension agents and community members to provide knowledge-based climate-smart advice and extension services strengthened. Indicator: Increase in capacity of institutions to provide knowledge-based climate-smart advice and extension support (measured as per UNDP Capacity Scorecard) Baseline: to be determined at PPG Target: to be determined at PPG | Output 1.2.1: Capacity and resource needs assessment undertaken for research institutions and agricultural extension services, including for forestry, agro-forestry and veterinary services. Output 1.2.2: Technical support and training provided for the development and implementation of measurement, reporting and verification (MRV) of carbon sequestration arising from forest restoration activities. Output 1.2.3: Training programme developed and implemented for research institutions, extension agents and selected members of the local community (with a focus on women) on collecting, monitoring and recording data for undertaking: i) degradation assessments; ii) ground-based carbon measurements and iii) hydro-meteorological analysis. Output 1.2.4: Training of local communities in the transfer and adoption of ecosystem restoration and livelihoods techniques to be deployed in Component 2, with a particular focus on (i) sustainable water use, micro-irrigation and water harvesting; (ii) construction and maintenance of soil and water conservation interventions and infrastructure; (iii) sapling planting and tree management; and (iv) improved crop-livestock management practices, poultry farming and apiculture (bee-keeping). |  | 850,000 | 2,850,000 |
| Component 2: Implementation of on-the-ground interventions to reduce land degradation and pressure on forests and to increase agricultural productivity | INV | Outcome 2.1. Enhanced resilience of ecosystems and livelihoods through landscape regeneration and integrated watershed management for increased agricultural productivity. Indicators: Number of hectares of agricultural land benefiting from increased productivity - Baseline: to be determined at PPG Target: to be determined at PPG Number of hectares of watershed extent under integrated management Baseline: for forest enclosures this stands at 9,000 hectares but exact baseline including other resoration activities to be determined at PPG Target: 17,500 hectares for forest resotoration but does not include other landscape restoration activities (exact planned coverage to be determined at PPG) Improved status of endangered African Wild Olive (Olea europaea sub-species Africana) and East African juniper (Juniperus procera) Baseline: to be determined at PPG Target: to be determined at PPG (means of measurement also to be determined at PPG) | Output 2.1.1: Rehabilitation of priority degraded areas through the implementation of appropriate soil and water conservation measures, including, inter alia, terraces, gabions, micro-dams and micro-catchments. Output 2.1.2: Upgraded water storage and irrigation infrastructure, including: i) the construction of 3 micro-catchment dams or ponds; ii) diversion furrows; iii) separate water storage facilities for domestic and livestock use; iv) replacement of irrigation pipes with PVC piping; v) existing Nakfa hydrometeorological stations restored. Output 2.1.3: Three community nurseries to support rehabilitation and enrichment planting established in Endilal, Agraie and Marriet, and existing ones strengthened in the Nakfa Sub-Zoba. Output 2.1.4: Community-managed forest enclosures expanded through planting and assisted natural regeneration of drought-resistant and indigenous species, including the African Wild Olive (Olea europaea sub-species Africana), East African juniper (Juniperus procera) and Carissa edulis amongst others. Output 2.1.5: Diversified, climate-smart agricultural practices implemented and up-scaled, including: i) implementation of integrated crop, livestock and agro-forestry practices; ii) increased dissemination and use of locally-adaptive tree species for farmer-managed natural regeneration; iii) increased production of temperate fruit and fodder at farm-level (from 5 hectares to 13 hectares); and iv) improved management of rangelands through planting improved grass species identified by research institutions (including the National Agricultural Research Institute and Hamelmalo Agricultural College) in enclosure and grazing areas. Output 2.1.6: Alternative livelihoods and value-addition opportunities identified and implementation and market access supported (e.g. agro-processing technologies, bee-keeping and honey production, as well as fruit and vegetable production). |  | 5,678,435 | 17,100,000 |
| Component 3: Knowledge and awareness-raising to promote integrated natural resource management |  | Outcome 3.1: Increased monitoring, knowledge-sharing and awareness of: i) the status of biodiversity and ecosystems and the threats facing them; ii) the benefits of biodiversity conservation and ecosystem restoration; and their contribution to livelihoods iii) best practices and approaches to sustainable management of natural resources Indicator: Increase in awareness of communities and institutions for integration of landscape approaches into resource use and management practices (measured as per the UNDP Capacity Scorecard) Baseline: to be determined at PPG Target: to be determined at PPG | Output 3.1.1: Communication strategy developed to collect and disseminate knowledge and best practices on natural resource management and ecosystem restoration. Output 3.1.2: Awareness-raising campaigns developed and implemented on: i) the ecosystem services provided by watersheds and forest ecosystems; ii) the benefits of biodiversity conservation and landscape-based ecosystem restoration for sequestering carbon and increasing the resilience of ecosystems and livelihoods to climate change; iii) climate-smart agricultural and sustainable land management practices, including alternative livelihood options; iv) land degradation and rehabilitation techniques; and v) sustainable forest management. Output 3.1.3: Development and dissemination of awareness-raising materials to local communities, including local media and other participatory methods. Output 3.1.4: Strategy developed and implemented for scaling-up lessons learned to other zobas (regions) and informing policy-level decision-making. Output 3.1.5: Course module on INRM developed and piloted through NARI and Hemalmalo Agricultural College. |  | 1,413,703 | 4,275,000 |
| Subtotal |  | 9,448,312 | 28,500,000 |
| Project Management Cost (PMC) |  | 472,416 | 1,000,000 |
| Total Project Cost |  | 9,920,728 | 29,500,000 |

For multi-trust fund projects, provide the total amount of PMC in Table B, and indicate the split of PMC among the different trust funds here: (     )

C. Indicative sources of  Co-financing for the project by name and by type, if available

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Amount ($) |
| --- | --- | --- | --- |
| Recipient Government | Government of the State of Eritrea | Grant | 15,000,000 |
| Beneficiaries | Project beneficiary communities | In-kind | 12,000,000 |
| GEF Agency | UNDP | Grant | 2,500,000 |
| Total Co-financing |  |  | 29,500,000 |

D. Indicative Trust Fund  Resources Requested by Agency(ies), Country(ies) and the Programming of Funds a)

| GEF Agency | Trust Fund | Country/ Regional/ Global | Focal Area | Programming of Funds | (in $) |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | GEF Project Financing (a) | Agency Fee (b)b) | Total (c)=a+b |
| UNDP | GEFTF | Eritrea | CC |  | 2,210,761 | 198,968 | 2,409,729 |
| UNDP | GEFTF | Eritrea | BD |  | 1,508,624 | 135,776 | 1,644,400 |
| UNDP | GEFTF | Eritrea | LD |  | 2,881,101 | 259,299 | 3,140,400 |
| UNDP | GEFTF | Eritrea | Multi-Focal Areas | SFM | 3,320,242 | 298,823 | 3,619,065 |
| Total GEF Resources | 9,920,728 | 892,866 | 10,813,594 |

- Refer to the Fee Policy for GEF Partner Agencies.

E.  Project preparation grant (ppg)

Is Project Preparation Grant requested? Yes    No  If no, skip item E.

PPG  Amount requested by agency(ies), Trust Fund,  country(ies) and the Programming  of funds

| Project Preparation Grant amount requested: $160,000 PPG Agency Fee: 14,400 |
| --- |
| GEF Agency | Trust Fund | Country/ Regional/Global | Focal Area | Programming of Funds | (in $) |
|  |  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  | Eritrea |  |  | 40,000 | 3,600 | 43,600 |
|  |  | Eritrea |  |  | 40,000 | 3,600 | 43,600 |
|  |  | Eritrea |  |  | 40,000 | 3,600 | 43,600 |
|  |  | Eritrea |  |  | 40,000 | 3,600 | 43,600 |
| Total PPG Amount | 160,000 | 14,400 | 174,400 |

F.  Project’s Target Contributions to Global Environmental Benefits

Provide the expected project targets as appropriate.

| Corporate Results | Replenishment Targets | Project Targets |
| --- | --- | --- |
| Maintain globally significant biodiversity and the ecosystem goods and services that it provides to society | Improved management of landscapes and seascapes covering 300 million hectares | 17,500 Hectares |
| Sustainable land management in production systems (agriculture, rangelands, and forest landscapes) | 120 million hectares under sustainable land management | 324,000 Hectares |
| Promotion of collective management of transboundary water systems and implementation of the full range of policy, legal, and institutional reforms and investments contributing to sustainable use and maintenance of ecosystem services | Water-food-ecosystems security and conjunctive management of surface and groundwater in at least 10 freshwater basins; | Number of freshwater basins |
|  | 20% of globally over-exploited fisheries (by volume) moved to more sustainable levels | Percent of fisheries, by volume |
| 4. Support to transformational shifts towards a low-emission and resilient development path | 750 million tons of CO2e mitigated (include both direct and indirect) | 3,580,000 metric tons |
| Increase in phase-out, disposal and reduction of releases of POPs, ODS, mercury and other chemicals of global concern | Disposal of 80,000 tons of POPs (PCB, obsolete pesticides) | metric tons |
|  | Reduction of 1000 tons of Mercury | metric tons |
|  | Phase-out of 303.44 tons of ODP (HCFC) | ODP tons |
| Enhance capacity of countries to implement MEAs (multilateral environmental agreements) and mainstream into national and sub-national policy, planning financial and legal frameworks | Development and sectoral planning frameworks integrate measurable targets drawn from the MEAs in at least 10 countries | Number of Countries: |
|  | Functional environmental information systems are established to support decision-making in at least 10 countries | Number of Countries: |

part ii:  project JustiFication

A.1 Project Description.

Global environmental problem, root causes and barriers that need to be addressed

- Eritrea is endowed with a variety of natural resources that have been declining as a result of human and natural disasters, including drought, deforestation and a prolonged 30-year war that ended in 1991. Biodiversity is critical to the livelihoods of the majority of the Eritrean people. Both wild plant and animal products are sources of fodder, medicines and income-generating activites, as well as building materials for the majority of poor rural households. Conserving biodiversity and its sustainable use is therefore a major concern. The loss of biodiversity, coupled with climate change and desertification, have consequently been identified in a recent GEF Country Portfolio Evaluation as the greatest challenges to sustainable development in Eritrea.

- Eritrea is characterised as arid and semi-arid, with rainfall varying from 500-700 mm in the highlands to below 200 mm a year in the coastal areas. The highlands represent ~14% of the total land area and have a mean annual temperature of 21.5 (C. Eritrea faces harsh climatic conditions and has shallow, highly erodible soils. Despite these constraints, cultivation and pastoralism are the major economic activities. The population of Eritrea is estimated as 3.5 million, of whom 70-80% live in the rural areas and derive their livelihoods from agricultural activities – crop and livestock production. Crop cultivation is widespread; however, increasing human populations have led to restrictions within the highlands. The rapidly increasing population and demand for food production are placing pressure on the land through overgrazing, deforestation and land fragmentation as more land is cleared for agriculture. Clearing vegetation to make way for cultivation is exposing soil to wind and water erosion and is leading to the siltation of rivers, wells and dams. Poor agricultural practices and overgrazing by domestic livestock are further promoting soil erosion. Climate change, particularly growing climate variability and more frequent droughts, are exacerbating soil erosion. Crop yield per unit area of land, as well as livestock and wildlife populations, are declining.

- Though land degradation is pervasive across Eritrea, the Central and Northern Highlands are worst affected, with a degraded area covering ~2.4 million hectares, constituting 19% of the country. The National Capacity Self-Assessment for Global Environmental Management (NCSA, 2006) identifies high population densities, overgrazing, recurrent drought, steep gradients, torrential rainfall and long-term traditional agricultural practices as specific drivers in the highland areas. Poverty levels are high within the highland areas and households only cultivate ~0.9 hectare of land on average. These households have few options to diversify agricultural production and are thus more susceptible to economic shocks and vulnerability to weather patterns and to climate change. There is limited investment in erosion control measures and productivity declines after a few cropping cycles. Consequently, more land is cleared to compensate for the loss of productivity, leading to a cycle of clearing and abandoning land, further exposing it to wind and water erosion and driving ecosystem instability.

- The proposed GEF-financed project is located in Zoba Semienawi Keih Bahri in Sub-Zoba Nakfa, and encompasses the following administrative kebabis: i) Agrae la’elai; i) Agrae tahitai, iii) Bakla; iv) Beyan; v) 01 Nakfa; vi) 02 Nakfa vii) Mariet; viii) Laba; ix) Endlal; and x) MoO, and xi) Apolo measuring ~ 324,750 hectares in extent. There are ~10,200 households within the project area who will benefit directly from the implementation of the proposed project, with a total population of 55,650 (26,155 of whom are male and 29,495 are female).

- Agriculture is the main economic activity in the project area. There are three farming systems in the project site: (i) a rain-fed farming system supplemented with small-scale irrigation using traditional methods with low inputs and low outputs, (ii) an agro-pastoral farming system where farmers practice growing cereal crops mixed with rearing cattle, goats and camels, and (iii) semi-nomadism on a very limited scale. The main rain-fed crops are wheat, barley and maize. Varieties of fruits and vegetables are also grown in the rain-fed areas and in the areas where spate irrigation is practised.

- Due to the Nakfa region being a stronghold during Eritrea’s war for independence between 1961–1991, land degradation has been particularly extreme and there is also an elevated number of female-headed households. The project target areas are food-insecure and vulnerable to the impacts of land degradation, loss of biodiversity and climate change. These impacts are having, and will continue to have, an adverse effect on food security, vulnerability, poverty and sustainable economic development.

- The proposed GEF-financed project addresses a number of these environmental challenges, in particular ecosystem degradation, including land and soil degradation, foresty loss and watershed degradation. It also directly addresses a specific recommendation of the GEF Country Portfolio Evaluation – to address sustainable forest management-related concerns, including strengthening the capacity for forest tree restoration and reduction of forest deterioration.

Baseline scenario

- Eritrea has a long history of implementing soil and water conservation structures through widespread local community mobilisation for labour inputs. These include soil and rock bunds, check dams and terracing and tree planting, all of which have been extensively utilised throughout the country. However, these physical measures alone are insufficient to address the increasing rate of soil erosion and land degradation. Increasing land use intensity and the utilisation of land beyond its inherent capacity affects the long-term sustainability of ecosystems. If these measures are not sufficiently informed by up-to-date knowledge and science – for example, utilising fast-growing but water-intensive exotic species of tree (e.g. Eucalyptus) to rehabilitate degraded lands, or inappropriately locating check-dams – they will further exacerbate ecosystem fragmentation and degradation. For instance, the gross annual rate of soil loss from croplands, rangelands and marginal lands is estimated at 2.1, 2.5 and 35 tonnes per hectare, respectively. Additional appropriate measures, accompanied by knowledge-sharing and awareness-raising, are therefore required to arrest these rates of soil erosion and their associated effects, including land degradation and biodiversity loss. Such measures include, inter alia, land use planning, conservation agriculture, sustainable grazing/rangeland management, sustainable forest management, rangeland and cropland rehabilitation, as well  as watershed rehabilitation.

- A century ago, Eritrea’s forest cover was ~30%. Currently, forest cover represents less than 1% of the total land area and is at risk of further decline. Despite the lack of information and data to generate reliable trends  and changes on the status of species diversity, there are multiple indicators to suggest that there is an overall declining trend for a significant number of species. Habitat transformation arising from the expansion of agricultural areas, particularly irrigated horticultural land, is a direct driver of forest and woodland decline.

- There are three major forest/woodland types in Eritrea, namely Acacia woodlands, riverine forests and highland forests. Historical records suggest that the Rora Habab plateau in the Nakfa area was once characterised by dense natural forests, fertile soils and endowed with a variety of wildlife. The natural forest area was composed of a mixture of coniferous species (Juniperus procera), broad-leafed species (Olea africana) and other woody species such as Acacia origena. The Rora Haba plateau forest constitutes part of the highland forest ecosystem and falls within the Afromontane Archipelago-like Regional Centre of Endemism. The natural forest has been significantly degraded over time, predominantly due to anthropogenic factors including: i) excessive collection of fuelwood and timber for construction; ii) forest clearance for agriculture; iii) over-grazing; and iv) the prolonged war. Only remnants of the natural forest survive and the distribution of woody perennials is sporadic. The over-exploitation of economically valuable indigenous tree species has resulted in ecological disturbances and deterioration of ecosystem services, which are essential sources of livelihood support.

- There is an urgent need for community development processes to aid communities in ecosystem restoration. The implementation of such practices should, however, be informed by effective land and water use and overall natural resources planning and management. Without systematic land-use and water-use planning, the continuation of land and water use intensification will pose a range of sustainability problems in the Nakfa Sub-Zoba. Land may be used beyond its inherent capability. The cumulative impacts of conversion of rangeland to cropland, as well as land-use changes on biodiversity, will therefore not be taken into account or mitigated. In addition, groundwater and surface water resources may be exploited beyond sustainable yield levels and beyond the capacity of ecosystems to naturally renew and recover. Changes in land use and further degradation of land and water resources will consequently have important impacts on ecosystem integrity, as well as the livelihoods of agricultural and pastoral communities within the Nakfa sub-zoba.

- Reforestation and agricultural development will therefore not be sustainable in the long-term if the natural resource base is not utilised in a sustainable manner. This would have devastating future impacts on the ability of households to continue to feed themselves, and jeopardise the ambitious national goals for food security. With the current focus of the Government on poverty alleviation, agricultural production is continuing with little consideration for the sustainable use of natural resources and ecosystems. There is therefore a strong need for close coordination between agricultural development and resource use and management. To neglect to do so would fail to recognise and respond to the interconnectedness of natural resources and their influence upon ecosystem structure and function. This GEF-financed project is therefore integral to the long-term sustainability of ecosystems and the livelihoods of local communities in the Nakfa Sub Zoba.

Baseline programmes

- Over the last decade, large-scale public soil and water conservation works and reforestation programmes have been implemented involving farm forestry, community forestry, village woodlots and popular participation. These programmes have resulted in 305,232 hectares of enclosures – 214,133 hectares of temporary and 91,099 hectares of permanent enclosures – in Eritrea. There are indications that Eritrea’s highland forest cover may now be approaching 1% owing to recent Government actions to prohibit the cutting of live trees for energy purposes and through the designation of over 100,000 hectares of forest areas as enclosures.

National Tree Planting Campaign

- The Government is addressing environmental degradation through social mobilisation in reforestation and soil and water conservation. Unlike other parts of Eritrea, these community investments are well appreciated by the farmers in the Nakfa region due to changes in the land tenure system having improved security of tenure. In 2010, land was redistributed equitably to households (including widows) by the local government. Households therefore own their own land and the traditional tenure patterns – such as Diessa, or village ownership – are no longer practiced as it is in other parts of the country. Training has been provided to religious leaders, students and other community members on the need for tree planting and environmental conservation as a key strategy to achieve food security. School pupils, communities, individuals and various institutions are actively participating in this campaign. Since 1991, more than 98 million seedlings have been planted and ~40,000 hectares of degraded land rehabilitated. Between 2010 and 2014 alone, more than 18 million seedlings were planted and 7,230 hectares of plantation established. In addition, the Government has identified ~72,000 hectares for further reforestation.

Ministry of Agriculture Five Year (2014–2018) Strategic Plan

- The Five Year Strategic Plan emphasises the sustainable management of natural resources – particularly soil, water and forests – to ensure agricultural development. The Ministry of Agriculture therefore plays a vital role in soil and water conservation efforts, as well as reforestation campaigns, and has prepared guidelines on the use of arable lands, forestlands and grazing lands. Field observations and discussions with local authorities show that the level of community participation in soil and water conservation initiatives is high throughout Eritrea, and ecosystem restoration is recognised at community level as an important aspect of addressing land degradation and increasing the productivity of land for agriculture.

Community mobilisation in Nakfa Sub-Zoba

- The target population consists of agro-pastoralists and the project site was historically rich in Olea africana, Juniperus procera and other afro-alpine tree species, as well as home to a variety of wildlife species, including the threatened Nubian ibex (Capra nubiana). In general, however, the status of biodiversity is not well understood in Eritrea as data are limited or not available. The project area is highly degraded, with the result that recently the local communities within the project area were intending to migrate to other areas where they would be able to find food, shelter and grass for themselves and for their livestock. However, the local administration, the Village Development Committees and community elders – including women – in the project site have discussed the issues and set out work plans on how to remain in the area and restore the region rather than relocate.

- Community members have subsequently undertaken limited restoration activities that will serve as a platform for replication and scale-up under the GEF-financed project. Activities have included the construction of: i) hand-dug wells; ii) 3 micro-dams and 100 ponds; and iii) soil water conservation structures, including terraces along denuded hills, micro-basins and check dams. Gully rehabilitation is also taking place through the planting of multi-purpose tree species – which include fruit trees, trees for firewood and for bee-rearing. Trees are also being planted on farm boundaries and in other marginal areas, and enclosure areas have been delineated that will only be used for grazing during dry periods of the year. These enclosure areas will be administered and managed through by-laws that the communities have developed. The local adminstration, Village Development Committee, local NGOs – the National Union of Eritrean Women (NUEW) and the National Union of Eritrean Youth and Students (NUEY) – and community elders have coordinated and mobilised community members to carry out these interventions.

- There are, however, a number of barriers to scaling-up these actions to the extent that they can seriously address land degradation. The effectiveness of Government extension services is limited, a problem compounded by poorly-developed human and institutional capacities for research, land-use planning and governance amongst technical staff, communal authorities and village leaders. Although institutions, such as the National Agricultural Research Institute and Hamelmalo Agricultural College, have clear roles and mandates, they suffer from a shortage of technical staff and have limited funding for on-the-ground activities. Research by IFPRI and NARI concludes that, due to the fact that more than half of Eritrea’s agricultural researchers are under 41 years old and 60% of them only hold bachelor degrees, Eritrea has one of the youngest and least-qualified pools of agricultural professionals in Africa. Furthermore, there is no system for capturing and disseminating lessons-learned and best practices for sustainable natural resource use and land management. Inadequate data and information (in terms of quality, quantity and access) constrain decision-making and the knowledge needed for effective practice of integrated land and natural resources management.

Barriers to be addressed

Barrier 1: Inadequate knowledge, awareness and skills for implementing integrated landscape management.

- It is widely recognised that Eritrea faces an acute shortage of skilled and professional staff within the environmental sector, particularly those with the knowledge and skills for addressing local resource use and development. For example, biodiversity conservation has received limited support as the Government has focused instead on pressing human development issues. Intensive awareness-raising regarding the conservation, sustainable use and sharing of the benefits of biodiversity conservation has also not been effectively undertaken. Consequently, there is weak capacity for the assessment, identification and monitoring of biodiversity.

- While there is a significant level of community-level investment in soil and water conservation throughout Eritrea, facilitated by Government investments, these are not always informed by up-to-date knowledge and science. Where knowledge does exist, it does not always reach farmers – many of whom are illiterate – in a user-friendly and timely manner. For instance, the practice of tree-enclosures has been widely adopted by farmers but often exotic species (e.g. Eucalyptus) are preferred over indigenous species. Even where the impacts of exotic species are understood by  – some – officials and practitioners, the short-terms gains – e.g. Eucalyptus grows faster and provides better timber than most indigenous species – outweigh longer-term environmental impacts. Furthermore, the trade-offs between timber production and watershed rehabilitation are not well understood and cost-benefit analysis is not integrated into decision-making.

- The Ministry of Agriculture provides extension support through the Agricultural Extension Department, which places trained personnel – usually referred to as Frontline Extension Agents – at regional administrative levels to oversee a kebabi. The Extension Agents deployed in the kebabis are usually residents of one of the villages in the kebabi they oversee. This approach is followed out of necessity, specifically the lack of financial resources to cover the costs of deploying Extension Agents in localities other than their own. It also allows these agents to be farmers themselves and practice what they teach. The Extension Agents are usually young and have less experience than most farmers. Their knowledge and expertise is therefore sometimes questioned by farmers, especially in cases where the  Extension Agents can identify the problems but are unable to solve them – for example, when they are unable to provide inputs such as seeds, fertilisers or pesticides to farmers.

- The absence of  a well organised information and knowledge management system focusing on landscape-level resource use and management has restricted the documentation and dissemination of best practices that could be adopted by other Kebabis in Eritrea. The transfer and exchange of local technology and methods is inadequate. This is compounded by limited feedback from farmers to Extension Agents regarding the effectiveness of SLM and other agricultural practices that have been promoted by the National Agricultural Research Institute through the Extension Agents. Consequently, there is no database of best and proven practices, and lessons learned; the provision of knowledge-based advice from Extension Agents is therefore limited by the quantity and quality of information available to them.

- In addition, specialised training programmes that can equip practitioners, including Extension Agents, with up-to-date scientific knowledge and expertise are limited particularly by the lack of access to training and learning opportunities for local practitioners.

Barrier 2: Institutional constraints to environmental conservation.

- The NCSA  highlights the following capacity issues in the environmental management sector in Eritrea: i) weak inter-institutional coordination and communication among Government line ministries; ii) weak policy and legal framework; iii) inadequate technical capacity to implement Multilateral Environmental Agreements; iv) weak institutional capacity; v) inadequate funding and lack of budget; and vi) inadequate research and training.

- The decentralisation of Government functions, including environmental issues, has sought to integrate environmental issues into decision-making processes at a regional and sub-regional administrative level. However, capacity deficiencies – relating to planning, baseline data, logistics, institutional and legal frameworks – exacerbate rather than support environmental efforts. Furthermore, the linkages between various natural resource sub-sectors is relatively weak. Environmental protection and the mainstreaming of international obligations – in accordance with the UNCBD, UNFCCC and UNCCD – is therefore not taking place as required. Limited financial resources and weak institutional capacity, in particular, therefore hamper Government efforts to plan and effectively implement environmental conservation activities on a landscape level.

Proposed alternative scenario, GEF focal area strategies and expected outcomes and components of the project

- The objective of the proposed project is to mainstream sustainable land management, forestry and biodiversity conservation into land-use planning and agricultural production practices in the Nakfa Sub-Zoba. Enhanced social mobilisation towards addressing land degradation and the upgrade of institutional and human resources capacity will improve implementation of on-the-ground measures – such as reforestation, enrichment planting, establishment of enclosures and agroforestry – to address environmental deterioration. There are few alternatives to ensuring food security in Eritrea other than through intensifying agriculture and increasing agricultural productivity at household and farm level. Restoring degraded ecosystems so that they continue to provide the necessary ecosystem goods and services is therefore the only solution to guarantee that arable and pastoral production remains viable for the typical farmer.

- The GEF alternative will therefore address sustainable natural resource management issues that would otherwise be largely unaddressed within the baseline scenario. A range of constraints (discussed under the barriers section) limits the adoption of sustainable natural resource use, land management, and forest strategies and practices that yield local-level benefits. Some of these barriers also impede the generation of global benefits, such as those related to conservation of biodiversity and carbon sequestration. In order to address these barriers, the project will demonstrate how agricultural development, sustainable natural resource use and land management, and sustainable forest management can be simultaneously achieved.

Component 1: Enabling framework for integrated landscape management in the Nakfa sub-zoba (sub-region).

- Under Outcome 1.1, the project will assist in the development of landscape restoration plans for each of the administrative kebabis. Instutional and technical support will be provided for the expansion and rehabilitation of enclosure areas. This will entail reviewing and making recommendations for the revision of community by-laws to ensure that conservation and the sustainable use of natural resources is integrated into the management of forest and agricultural landscapes. In addition, the project will develop and implement strategies for the conservation and sustainable use of species – such as the African Olive and Juniper species – through on-farm and off-farm conservation.

- Biodiversity mapping and surveys and assessments of flora and fauna will be undertaken to better understand the following: i) biodiversity present within the Nakfa Sub-Zoba; ii) pressures on biodiversity; iii) the state of biodiversity; and iv) the responses in place or required to maintain or facilitate recovery. Based upon the findings of these surveys and assessments, management practices will be developed and implemented at a community level. The outcome of the surveys and assessments will also inform the landscape restoration plans for each Kebabi. These surveys, assessments and mapping exercises (e.g. maps and wildlife inventories) will also generate the much-needed data required to inform natural resources management and conservation and build national capacity and skills (e.g. GIS mapping and analysis) to conduct these activities in other parts of the country.

- Under Outcome 1.2, the proposed project will address the capacity needs of various institutions at national and sub-national levels to coordinate land-use planning and management through strengthening of the institutional linkages and coordination between stakeholders. These include research institutions, extension agents, veterinary services, meteorological departments, sub-zoba administration and civil society based organisations – NUEW, Water User Associations and farmers’ associations. A training programme on MRV of forest carbon will be developed and implemented, aimed at two sets stakeholders: (i) technical specialists (such as professionals from research institutions and extension services, as well as enclosure managers) will be provided with conceptual and practical training on sampling techniques, estimation of the sizes of different carbon pools, allometric equations, etc., as well as on integration of carbon data into the GIS mapping system to be developed under Output 1.2.2; and (ii) local communities will receive training on basic data collection methods (such as measuring trunk diameters and soil coring), commensurate with capacity (e.g. literacy) limitations. To ensure community interest and participation, the equivalence of carbon storage with forest health (and hence NTFPs and other livelihood benefits) will be emphasised throughout.

- Climate risk information will be used to inform decision-making on land-use planning and climate-smart agricultural practices. Assessments will be undertaken to determine the current degradation status of natural resources in kebabis – including communal rangeland and woodland resources that are used by households on a regular or seasonal basis. The outcome of the assessments will contribute to: i) improving the knowledge and understanding of farmers with regards to the direct and indirect causes of land degradation; and ii) defining community and institutional responses to mitigate and reverse the effects of land degradation. Based upon the findings, kebabi land-use plans will be updated where they exist and new ones developed where none exist. The information will also be utilised in the preparation of integrated landscape restoration plans to be developed under Outcome 1.1.

- The kebabi land-use plans will be used to strategically manage and address the identified crop and livestock production issues. Villages will be assisted in the identification of appropriate SLM practices that can be implemented with the communities’ own resources and technical support from zoba and sub-zoba administrations. Training will be provided to community members to use low-cost, user-friendly biophysical indicators and rural appraisal tools to measure changes in the biological, chemical, physical and hydrological properties of the soil, as well as the extent and severity of soil erosion. In addition, the status of the vegetative cover and habitat diversity will also be assessed. The renovation of an existing hydro-meteorological station will also enable communities to monitor climatic conditions, including, inter alia, temperature and rainfall. Investments in such community-based systems will support vulnerable communities to prepare for anticipated changes and, in so doing, incorporate this knowledge and information into their production strategies, as well as protect their livelihoods and assets. The information generated by local communities will be recorded and transmitted to technical staff, including the meteorological department and agricultural extension agents. This will enhance the extension agents’ ability to provide knowledge-based advice to farmers. Extension agents will therefore be in a better position to inform farmers on the implementation of innovative climate-smart agricultural and livelihood strategies, which vulnerable communities can use to safeguard development.

Component 2: Implementation of on-the-ground interventions to reduce land degradation and pressure on forests and to increase agricultural productivity

- The project will support ecosystem restoration efforts already underway to a limited extent at community level. Although people are highly dependent upon ecosystem services for their livehood productions practices, their actions greatly impact on such ecosystem services’ integrity and ability to function properly. The project will therefore support the development of land-use plans and strategies and put in place restoration measures to ensure these ecosystems can recover and function better. Furthermore, the project will facilitate the development and implementation of sustainable and equitable land-use practices to sustain ecosystem services in the face of climate change.

- Under Outcome 2.1 of the project, restoration and natural regeneration activities in forested areas, rangelands/grazing lands  and productive landscapes, including cultivated lands – particularly enrichment planting – will be informed by: i) the predicted effects of climate change; ii) the capacity of species to supply ecosystem services under the predicted effects of climate change, such as species that are drought-resistant or flood resistant; and iii) community needs and preferences. Examples include: i) species that produce non-wood forest products such as fruit, fibre, and fodder ; ii) species with high market-value wood; iii) fast-growing species for firewood; and iv) species that promote rather than hinder growth of other species – including nitrogen-fixers and species that produce large amounts of compostable matter. Species with multiple benefits will be prioritised in order to establish an ecosystem that is both resilient and provides additional livelihood benefits. The need for firewood has historically been a significant driver of deforestation and land degradation. Despite the Eritrean population’s overwhelming reliance upon biomass as a source of energy, the Government of Eritrea introduced legislation which prohibits the cutting of live trees for energy purposes (and charcoal making). This has been in effect since 1994 and has reduced the cutting of live trees. The project will alleviate this issue through the establishment of community-managed woodlots for fuelwood.

- Community-based, landscape-level measures and technologies will reduce soil erosion, increase soil fertility and storage of excess water during flash floods – for use in irrigation – thereby mitigating the effects of droughts and floods. The implementation of agroforestry and the use of trees and shrubs within agricultural production systems will assist in securing food security, reducing communities’ vulnerability and increasing the adaptability of agricultural systems to climate change. In addition, the inclusion of trees and shrubs will reduce the effects of extreme weather events such as heavy rains, droughts and wind storms, as well as improve the effectiveness of agricultural inputs – such as manure – by increasing soil moisture and soil organic matter. The incorporation of fodder trees within crop fields will also increase the availability of fodder for livestock, and help reduce dependence on grazing lands, which are themselves limited in extent and degraded. Under conservation agriculture, trees: i) stabilise soils; ii) raise infilitration rates; iii) reduce soil erosion; and iv) halt land degradation. Nitrogen-fixing leguminous trees and shrubs will be especially important for soil fertility where there is limited access to agricultural inputs. These measures will be even more effective when combined with physical water management infrastructure such as check dams, terraces and gabions that control floods and regulate water availability.

- The detailed SLM practices to be implemented will be identified during further project development – the PPG phase – but are likely to include, where appropriate, the adoption of soil conservation measures to improve soil fertility, water harvesting techniques such as accumulation and preservation, establishment of windbreaks, buffer strips and filter strips to reduce erosion. Specifically degraded patches will be restored through the following indicative activities:

- restoration of key indicator species through selective planting and seedling care, whilst seedling survival will be enhanced through micro-water catchments;

- unstable soil surfaces will be stabilised through contouring, mulching and vegetation strips;

- overgrazing will be curbed by timing of grazing, improved nutritional species of grasses and fencing;

- soil compaction will be reduced by ripping and sub-soiling;

- soil organic matter will be increased through mulching;

- soil fertility will be improved through the use of nitrogen-fixing plants; and

- harvesting of non-timber forest products and timber will be regulated.

- Other measures are likely to include: i) grazing management to stimulate grasses for vigorous growth and healthy root systems; ii) use of the grazing process to feed livestock and soil biota through maintaining soil cover – plants and litter – and managing plant species composition to maintain feed quality; and iii) providing adequate rest from grazing without over-resting the plants. The project will ensure that the implementation of these measures is supported by building the requisite capacities – including skills development, training and partnerships. Local communities will therefore be provided with the requisite training and extension services to support the adoption of SLM practices through Outcomes 1 and 3.

- Improved agricultural productivity is expected to increase household incomes and reduce dependency on natural resources. Agricultural practices will be adopted that are based on both traditional and scientific knowledge and use proven practical techniques – such as mulching, intercropping with drought and flood-tolerant crops, crop rotation and changing planting schedules. Farming communities in the Nakfa Sub-Zoba will be able to respond to support livelihoods using sustainable agricultural approaches and methods. The adoption of improved agricultural practices will also enhance carbon sequestration and stocks. In addition, these practices will reduce threats to biodiversity in the wider landscape and facilitate the recovery of key species such as the Nubian Ibex and the African Olive and Juniper.

- Outcome 2.1. of the project will support the identification and adoption of alternative, income-generating livelihood activities to reduce dependence on natural resources. These alternative livelihood options will be locally-appropriate and socially acceptable, technically viable and increase the resilience of local communities. In addition, they will improve communities’ livelihoods and build on investments already made by communities. Potential alternatives include social forestry, bee-keeping for honey production, planting of indigenous and economic trees in community woodlots, poultry and dairy farming. For example, community-managed woodlots will be established – away from patches of natural forest – to reduce deforestation. Investments in climate-resilient livelihoods support people to make a living in a way that they are able to cope with, and recover from, the effects of sudden or slow-onset changes in weather patterns. Once restored through the landscape-based interventions, forest ecosystems will enhance the resilience and improve the livelihoods of local communities.

- The total loss of native woodland on the Rora Habab plateau would be an economic loss as well as a biological loss to the local communities and to the country in general. Practical restoration activities in the Rora Habab–Nakfa region have demonstrated that it is possible to restore altered or damaged forest ecosystems. Despite the severe degradation of the natural forest ecosystem in the project area, woody and herbaceous plants have continued to thrive and regenerate in a number of protected microsites. The expansion of enclosure areas from 9,000 hectares to 17,500 hectares and the restoration of the remnant forest ecosystems would reverse the loss of ecosystem services derived from existing forest resources and thereby improve the livelihoods of the local communities. Community enclosures have proven to be an effective mechanism in Eritrea. With regard to the expansion of enclosures, this is community-driven. The local communities have already established temporary enclosures measuring 3,500 hectares in extent and are seeking assistance to expand these areas by ~3,500 hectares per annum. These areas are closed seasonally to allow natural regeneration. However, they are opened for grazing during the dry season. Community members wishing to graze their livestock within the enclosure areas are required to pay an access fee, which is dependent upon the number of livestock. The proceeds are used to pay the guards – who patrol and protect these areas – and are reinvested into the establishment and maintenance of infrastructure, such as micro-catchment dams. The forests play an important role in sustaining biodiversity, providing a range of important environmental services and contributing to people’s livelihoods. Furthermore, the restoration of the remnant forests through sustainable forest management would enhance the multiple environmental benefits from improved management of these forests.

- Forest restoration within the Nakfa Sub-Zoba is seen as a major means of; i) controlling and combating land degradation; ii) controlling soil erosion; iii) conserving habitats and consequently biodiversity; iv) restoring ecosystem and environmental sustainability; and v) improving the socio-economic well-being of local communities. Sustainable forest management is therefore integral to conserving biodiversity, both faunal and floral species. Rehabilitation and improvement of remnant forest and woodland areas through planting and assisted natural regeneration using site appropriate species is also a means of ensuring social and economic benefits accrue to the surrounding local communities. The native tree species are highly drought-resistant, which is a key attribute for their survival and an essential element for their restoration.

Component 3: Knowledge management and awareness-raising to promote integrated natural resource management

- At present, there is limited generation and systematic sharing of knowledge on sustainable environmental and natural resources management, and how this knowledge can be turned into skills that farmers and other land-users can adopt in their livelihood practices. For instance, the impacts of unsustainable land-use practices are not well understood by farmers, such that these unsustainable practices continue to be adopted within the wider landscape, further posing risks and threats to ecosystems and reducing the resilience of livelihoods to withstand the impacts of climate variability and change. In addition, there are no communication or outreach strategies providing key information to stakeholders such as extension workers and farmers. Insufficient information and public awareness are major challenges affecting the implementation and integration of natural resource management into planning processes. As a result, natural resource management is not adequately integrated into new and existing national policies and strategies, nor are the potential benefits of adopting sustainable measures appreciated by government and local stakeholders.

- Knowledge and awareness of natural resource management and the associated benefits in building resilience of communities and ecosystems and improving community livelihoods is likely to remain limited if measures are not put in place to address this deficit. Furthermore, the capacity of national and local authorities to facilitate the implementation of activities that increase the resilience of ecosystems and communities will remain low. This will continue to hinder the application of uptake of integrated natural resource management in wider landscapes within Eritrea.

- The project will disseminate knowledge of climate-smart land management to local communities in all regions through a versatile approach. Under Outcome 3.1, the project will support the packaging of knowledge and information and promote awareness-raising among stakeholders through the use of several, locally-appropriate and participatory approaches. Training and workshops will be conducted on key issues that are of importance to informing the adoption and use of sustainable approaches to land use and agricultural production. The PPG phase will identify the knowledge and information needs of key groups, in particular farmers and incorporate these into project design. A communication strategy to raise awareness on the benefits and opportunities offered by natural resource management will be developed for use by national and sub-national authorities as well as agricultural extension officers. This approach will be underpinned by the collation of: i) best practice information; and ii) lessons learned during project implementation in Component 1.

- Technical capacity for planning and implementing natural resource management will be strengthened. This will be achieved through information-sharing sessions and participatory workshops with community members. These sessions and workshops will be organised and guided by surveys on the perceived benefits of natural resource management. Support for the implementation of project interventions will be generated through a public awareness campaign on the benefits of natural resource management. This will include the use of media including print, radio and theatre/drama productions to disseminate information to the public. Conventional extension methodologies will be improved with the adoption of a facilitative, “learning by doing” approach that introduces participatory experiential learning methods. For example, exchange visits will be undertaken among target communities of different kebabis and demonstration sites (e.g. at agricultural colleges) to expose farmers to successful practices that have been implemented elsewhere. Land-use plans and practices will consequently be revised in accordance with the outcomes of the exchange visits.

- Participatory monitoring and evaluation of the implementation of kebabi land-use plans is integral to the success of the project and continued learning and uptake of best practices that the project will generate. Appropriate equipment, skills development, training and awarenss activities will allow local community members to measure the impacts and analyse the effectiveness of project interventions and the practices they adopt as a result of the project. These activities will improve the performance of interventions in: i) capturing the changes in the physical environmental, extent and severity of the different types of land and ecosystem degradation occuring within the project area; ii) assessing the impacts of the activities currently promoted; and iii) evaluating the benefits on agricultural and livestock productivity, as well as rural livelihoods and household incomes.

- Training will also be provided on sustainable land management techniques and climate-smart agricultural techniques – such as agroforestry and conservation agriculture – as well as efficient irrigation techniques, which will be implemented in targeted communities.

- The project will also develop a strategy for the upscaling of lessons learned during project implementation to other sub-zobas and zobas. In addition, the lessons learned will be used to inform policy- and decision-making on a national level.

Incremental/additional cost reasoning

- Without the GEF investment, unsustainable agricultural practices and deforestation will continue to threaten ecosystem integrity and function in the Nakfa area. Natural resource use and management will continue with the current level of poor policies, inadequate policy implementation, poverty and population pressure. Further reduction in productivity, loss of biodiversity – including agro-biodiversity – and loss of household income will continue to aggravate overall poverty and further diminish the livelihood base of local communities who depend on the natural resources for their survival. The risks of increased land degradation are therefore substantial if nothing is done. Furthermore, the cost of the physical restoration or replacement of the degraded/lost biodiversity would become even more prohibitive in the future. The project therefore provides a cost-effective means of protecting and restoring the unique biodiversity, as well as ensuring the community benefits from a better managed ecosystem. Investments made now into better natural resource management practices in Eritrea have the potential to halt the widespread degradation of land and ecosystems in the country, particularly in already-vulnerable landscapes – such as the Northern Red Sea region where the project will be located. Furthermore, the GEF investment will ensure global environmental benefits are generated by improving the ability of the soil and vegetation to: i) sequester carbon and reduce soil erosion; and ii) reduce potential pollution to water bodies and prevent further degradation and collapse of ecosystems such as forests and groundwater aquifers. This will complement the efforts by Government currently being directed at improving land management practices and improving agriculture as the basis of economic development.

- At the operational level, project implementation arrangements will minimise bureaucracy, administrative and managerial wastage, and follow UNDP standard rules and procedures for procurement and recruitment. A cost-effectiveness appraisal will be made prior to final approval by the executing agency. The project will build local capacity for replicating and adapting the new participatory management models.

Global environmental benefits

- The total number of households expected to be involved in the project activities is ~10,200 – the majority of which are female-headed households – with a population of approximately 55,650. Access to irrigation water, ecosystem rehabilitation and restoration, sustainable forest management, climate-smart agriculture and training on climate-smart land management practices will contribute to increasing land productivity per unit area, meeting household food security with surplus for markets.

- The Rora Habab plateau in the Nakfa area is part of the Afromontane Archipelago-like Regional Centre of Endemism and the restoration of the remnant forest/woodland ecosystem and support to its restoration and conservation would therefore contribute to both regional and global biological conservation benefits. The project will expand the enclosure areas from ~9 000 hectares to ~17,500 hectares during the project implementation period. In addition to the biodiversity benefits, the restoration of forests/woodlands will lead to increased carbon sequestration and storage.

- The carbon sequestration benefit of the expansion of the forest enclosure area is estimated by the FAO EX-ACT tool, using IPCC Tier 2 data, to be ~559,200 tCO2e over a period of 4 years (on the assumption that planting takes place in year 2 of the project). This is equivalent to a cost of GEF $17.7/tCO2e. Tropical dry forest can continue to maintain positive net primary production and act as a carbon sink for decades, partly because stem respiration rates decrease with increasing tree size, and partly because continual turnover of leaves, roots and woody material contribute to stabilisation of soil organic matter. Equilibrium between carbon assimilation and respiration may, therefore, not occur for several decades after planting. The literature on carbon equilibrium in dry forest will be reviewed in detail during the PPG phase to inform more detailed carbon sequestration calculations. For current purposes, a highly conservative 20-year equilibrium timeframe is assumed, in which case the carbon sequestration benefits of the forest enclosures supported by the GEF-financed project can be extrapolated, again using the EX-ACT tool, to be ~3.6 million tCO2, at a cost of GEF $2.8/tCO2.

- SLM will reduce current resource degradation – of water, land and forests – trends in the project area. This will result in more productive pastures and consequently improvements in local livelihoods, such as food security and increased incomes for men and women in the project areas. The sustainable management of forests and pastures for moderating runoff will reduce flooding that affects downstream populations.

- The promotion of the use of drought-resistant livestock varieties and appropriate livestock management techniques will enhance the economic benefits of soil and water conservation activities. Together with improved extension services, these practices will result in improved rangeland management in the project area, with associated economic and environmental benefits.

- Better land management will also lead to improved ecosystem integrity, and delivery of ecosystem goods and benefits. By incentivising sustainable forest management and ecosystem restoration, the project will create an enabling environment for greater investments in such activities generating global environmental benefits beyond the project’s lifetime. Moreover, the project covers the geographical region with a high number of female-headed households, the majority of which are poor. Bearing this in mind, women will also benefit from participation in the sustainable forest, woodland and pasture management practices that constitute a large portion of income of beneficiary households.

Innovation, sustainability and potential for scaling-up

- Efforts to address deforestation, biodiversity loss and land degradation should be undertaken in a manner which supports the broader objective of sustainable development. The majority of the Eritrean population are dependent upon ecosystems goods and services for their livelihoods. Healthy, functioning ecosystems are therefore crucial. Enhancing the resilience and protective capacity of ecosystems will also ensure the economic and social well being of local communities – especially the rural poor who are identified as being vulnerable to ecosystem degradation and climate change. Rehabilitation of watersheds and landscapes is critical to the success of the project. Yet it is unlikely to be effectively done without requisite technical capacity for mainstreaming sustainability considerations into rehabilitation and restoration programmes.

Social sustainability: will be achieved by building the capacity of communities to undertake their own landscape-level land-use and rehabilitation plans, with appropraite technical support and incorporating knowledge, information and best practices from elsewhere. Community-based interventions have proven to constitute an effective vehicle for building resilience, as well as addressing social drivers of vulnerability and other factors related to social exclusion. The organisational capacity of the local communities will also be developed through project activities and training programmes will be provided for both community members, as well as Government staff.

Economic sustainablity:  the project will promote sustainable income-generating activities, such as the harvesting of non-timber forest products, as well as the establishment and/or upscaling of nurseries. Improvements to agricultural and livestock production will also be sought through technological improvement. In addition, alternative income-generating activities will be identified and technical support provided for the implementation thereof. Capacity to make informed investment decisions will be enhanced through capacity building programmes. This will ensure both social and economic sustainability.

Financial sustainability: communities and households will be required to make cash and in-kind contributions as a prerequisite for investment funding from the project. This ensures a level of community ownership of project activities. The level of contributions will be contingent upon the type of activities being implemented and the financial circumstances and needs of the community or household. Eritreans already invest significant amounts of labour and effort in community-level projects, be they Government- or donor-funded.

Institutional sustainability: all project planning processes and activities will be aligned with existing Government institutions – including NARI and Hamelmalo Agricultural College – and planning frameworks. Project activities and outcomes include both technical and institutional capacity building, as well training and support.

- A multi-faceted approach will build stronger social capital, where initiatives also empower commmunities to consider addressing the underlying development issues. Furthermore, such an approach will support communities to adopt more resilient livelihood strategies. By strengthening the capacity of research institutions – which have a national mandate – to provide knowledge-based advice to the extension services, the project will increase the probability and potential for replication. Similarly, an empowered extension service will ensure a nation-wide use of knowledge products developed by the project.

- Project implementation will be through the current Government and village institutions and extension structures. This will ensure ownership of the project initatives as well as on-the-job skills development for all technical staff involved. This approach has great potential for up-scaling and replication across Eritrea, unlike more costly structural measures. Involving communities in “appropriate technology” types of landscape-based measures is highly innovative in the context of Eritrea and sustainable because measures that involve massive engineering solutions and extensive use of technologies are beyond the reach of many rural communities. The project’s focus on developing capacity and use of nature-based solutions in combination with some soft engineering processes provides practical and locally-appropriate “soft” adaptation measures, which are highly cost-effective. As mentioned previously, Eritrea is unique in that the majority of activities are community-driven. The project is innovative in that it will adopt a bottom-up approach, whereby the local communities are responsible for both identifying the problems and solutions, as well as implementing and monitoring the identified interventions.

A2. Stakeholders. Will project design include the participation of relevant stakeholders from civil society and indigenous people?  (yes  /no ) If yes, identify key stakeholders and briefly describe how they will be engaged in project design/preparation.

- The involvement of policy makers and multiple stakeholders with distinct roles and responsibilities is integral to the success of a multi-focal approach. Moreover, improving natural resource use and management requires multi-level stakeholder coordination and communication. Broad-based consultations have been (PIF stage) and will be (PPG stage) undertaken, including among communities, civil society and resource user groups (e.g. farmers’ associations) and a wide variety of Government departments, led by the Ministry of Land, Water and Environment. A detailed stakeholder analysis will therefore be presented in the CEO Endorsement Request. However, the table below presents the preliminary list of stakeholders and their expected roles and responsibilities.

| Group | Indicative roles and responsibilities |
| --- | --- |
| Society: Local communities, private sector, civil society in areas including NUEY and NUEW – to address gender issue. | Local communities will play a central role in project preparation, in particular in the context of identifying the specific on-the-ground investments to be made under Component 2. Communities will be the beneficiaries but will also have the responsibility of direct implementation of project activities. During implementation, they will provide support that the Government agencies are not mandated to provide, in particular training. Collectively, the two groups may be responsible for the following activities: define and implement landscape restoration, and inform policy-makers about local needs. |
| Policy makers: Ministry of National Development; Ministry of Agriculture; Ministry of Land, Water and Environment with special emphasis on Land, Environment and Water Departments; Ministry of Local Government; Ministry of Transport and Communication (Meteorological Services); Ministry of Finance | Policy-makers will support community engagement in the improved practices as well as ensure mainstreaming of biodiversity conservation and sustainable use into the development processes. They will be involved as follows: mainstreaming restoration and ecosystem services; develop innovative funding; influence international policies; dialogue with research institutions; understand scientific uncertainties; finance research and monitoring; recognise local diversity; and promote environmental education. All the listed ministries have been (PIF development) and will be (PPG stage) involved in project design. |
| Research Institutions: National Agricultural Research Institute (NARI), Hamelmalo Agricultural College | Research institutions will provide leadership on integrated landscape restoration and link it to ecosystems, management practices, resilience and vulnerability. Specifically, they may quantify and value ecosystem services, evaluate uncertainties, work at local scales, communicate results to non-scientists, involve society in research; engage in dialogue with policy-makers; and support policy design and negotiations. |

3. Gender Considerations. Are gender considerations taken into account? (yes  /no ).  If yes, briefly describe how gender considerations will be mainstreamed into project preparation, taken into account the differences, needs, roles and priorities of men and women.

- Although women have equal rights in terms of national law, they are still disadvantaged in terms of access to economic opportunities and decision-making. Gender equality is, however, enshrined in the country’s legal frameworks, including the National Policy on Gender (2004) and the National Gender Action Plan (2003-2008). In addition, legislation has been passed relating to gender-sensitive issues, including tenure of land. Women, children and men are all involved in agriculture, soil and water conservation, as well as restoration activities in different ways in Eritrea. However, women are recognised as being one of the most vulnerable groups due to underdevelopment, which is exacerbated by recurrent natural and human-made disasters, widening and deepening poverty, armed conflicts and deeply entrenched traditional practices which give rise to inequalities within, between and among men and women. In particular, female-headed households are characterised by low farm production and income, because they lack sufficient human power and own fewer assets than the average poor household.

- Resource use and access are differentiated by gender, which is aggravated by environmental change. Women in Eritrea carry the heaviest burden in providing their households with basic environmental services. For example, the scarcity of biomass fuel in Eritrea results in women having to walk longer distances and spend more time – up to a day at a time – to collect sufficient quantities of firewood of good quality to meet her families’ needs. Legislation prevents the cutting of live trees for biomass/fuelwood. Consequently, there is a shortage of biomass.  The project includes the planting of community-managed woodlots for biomass and individual tree tenure to alleviate this problem. Water use and access are also differentiated by gender, and women in Eritrea are traditionally responsible for locating, obtaining and transporting freshwater for household use. Inadequate freshwater supplies mean that women and girls can spend up to three hours a day fetching water. Consequently, women are most affected by environmental degradation.

- In alignment with the National Gender Action Plan, gender considerations will be mainstreamed into the project’s activities to ensure that women are included in the selection of activities to increase their resilience and income-generation abilities, as well as in the various training and capacity-building programs. For example, womens’ user groups and female-headed households will be targeted in the implementation of sustainable forest management practices, as well as particular alternative livelihoods – such as bee-keeping and the planting of fruit trees. In addition, technical support and advice will be sought from the NUEW during the project design and implementation phase to ensure that women’s needs in Nakfa Sub-Zoba are accurately identified and addressed.

- Detailed gender analysis will be conducted during the PPG to examine how gender relations influence access to natural resources, management of natural resources and how these relations are likely to influence the effectiveness of project implementation and achievement of results. In particular, the influence of gender relations on the equitable distribution of costs and benefits of the project implementation, as well as long-term benefits of the project will be explored in detail. Based upon the findings, a gender strategy will be formulated.

# A4 Risks. Indicate risks, including climate change, potential social and environmental risks that might prevent the project objectives from being achieved, and, if possible, propose measures that address these risks to be further developed during the project design (table format acceptable).

| Risk description | Degree | Mitigation/Comment |
| --- | --- | --- |
| Severe drought or other extreme weather events intensified by climate change | H | Severe drought, linked with a temperature increase of ~4(C across Eritrea will result in higher evapotranspiration levels, while greater rainfall variability could result in higher soil erosion rates and reduced ground water recharge. Higher wind speed could lead to dust storms (kamsin), especially in the dry season. While the project interventions are designed to address the effects of increasing climate variability, such extreme weather events could negate project benefits in some years. The project will have an ongoing learning-by-doing component (3) that will allow for iterative and adaptive management (e.g. improved water harvesting practices, adoption of SLM/SFM, etc). Lessons learned will be generated to inform sustainability and replicability of similar interventions elsewhere in the region and in the country. |
| Further drop in groundwater, possibly leading to conflict | H | While the risk of further lowering of ground water levels is high, based on observed trends, a number of project activities – such as watershed rehabilitation, construction of sub-surface dams, treatment of river banks and SWC technologies – have been designed specifically to recharge groundwater levels. Thus implementation of project activities will mitigate against this risk and reduce levels of competition for this scarce resource. |
| Low human and institutional capacity, especially at the zoba and sub-zoba levels | M | The project has a strong capacity building and training component, designed to promote effectiveness and sustainability at the community and the sub-zoba and zoba administrative levels. |
| Delay in project implementation and particularly in the development of infrastructure interventions | H | The PPG period will support the regional administration to design capacity building programmes. Delays in projects are often related to capacity issues, which will be mitigated against. Ownership by the Government has been extremely high during the PIF formulation and such ownership will reduce this risk. |
| Environmental variability may impose new priorities on the funding of Eritrean Government and other partners | L | Environmental variability is ever-present in Eritrea, imposing substantial limits on the effectiveness of most medium- to long-term plans. Key project participants will be enabled to actively collaborate to share impending funding changes brought about by environmental variability. |
| Potential negative impacts of agro-biodiversity activities |  | The use of exotic tree species (e.g. Eucalyptus) for replanting and reforestation purposes is common in Eritrea, and if not well considered (e.g. appropriate species to plant and their sitting) may lead to further degradation of some ecosystem services (e.g. reduced streamflow in rivers). This issue will therefore have to be carefully planned, based on scientific knowledge, evidence and detailed understanding of the hydro-ecological interactions and dynamics within the project area. |

# A5. Coordination. Outline the coordination with other relevant GEF-financed and other initiatives.

- The project will be closely coordinated with the baseline programmes and all other projects addressing similar issues. It will, in particular, be closely coordinated with the GEF SIP, ‘Sustainable Land Management Pilot Project’ (PMIS 2979), whose objective is “To create the enabling environment (policy, capacity, knowledge, alternatives) necessary for adoption of sustainable land management practices and alleviate environmental degradation while improving livelihoods of the farming communities of the Central Highland Zone (CHZ)”. The project will draw from the lessons learned and replicate the best practices for SLM.

- The project will also collaborate with the Adaptation Fund project entitled ‘Climate Change Adaptation Programme in Water and Agriculture in Anseba Region, Eritrea’ (PMIS 4540), which is addressing climate change adaptation issues within the Anseba region in Hamelmalo and Habero Sub-Zobas. The Adaptation Fund project is focused on increasing community resilience and adaptive capacity to climate change through integrated water management and agricultural development approach. The GEF-financed project will draw upon the lessons learned regarding enhanced climate-resilient agricultural and livestock production, as well as erosion control through floodwater harvesting and irrigation technologies.

- Similarly, the GEF-financed project will coordinate with the GEF ‘Integrated Semenawi and Debubawi Bahri-Buri-Irrori-Hawakil Protected Area System for Conservation of Biodiversity and Mitigation of Land Degradation’ project  (PMIS 4816), whose objective is “To establish a national system of protected areas to conserve biodiversity and mitigate land degradation pressures on habitats in key biodiversity areas, initially centred in the Semenawi-Debubawi Bahri-Buri-Irrori-Hawakil Protected Areas Cluster”. SLM technologies will be promoted to combat land and accompanying habitat degradation, and reduce the vulnerability of the communities to climate change and poverty, thereby containing the threats to biodiversity within the landscape.

- The project will draw upon lessons learned, as well as tools and methods developed under any of the projects to ensure that there is no duplication of investments in methodology development. During the PPG, further analysis will be undertaken to identify relevant projects that should be coordinated with the current GEF proposal and linkages will be established.

A.6. Consistency with National Priorities. Is the project consistent with the National strategies and plans or reports and assessements under relevant conventions? (yes  /no ).  If yes, which ones and how:  NAPAs, NAPs, ASGM NAPs, MIAs, NBSAPs, NCs, TNAs, NCSAs, NIPs, PRSPs, NPFE, BURs, etc.

- The project is consistent with Eritrea’s National Action Programme (NAP - UNCCD), which identifies priority actions to arrest land degradation, desertification and drought. In particular, the proposed project is in alignment with the following priorities: i) empowering people to take active measures to arrest land degradation; ii) address the concerns of vulnerable groups affected by land degradation, particularly female-headed households, pastoralists and small-scale farmers; iii) reduction of poverty through income-generating activities; and iv) activities related to arresting land degradation, particularly degradation of productive agricultural land. The project will also support the Aligned National Action Programme 2014–2018 in raising awareness of decision-makers to land degradation issues and SLM at key institutions and within relevant Government departments. Institutional and human resources capacity will therefore be a focus of the project, as well as the effective planning of land uses and the sustainable use of natural resources.

- The project is also consistent with the National Biodiversity Strategy Action Plan (NBSAP), which seeks to ensure the provision of environmental services and natural resources through the restoration, conservation and management of Eritrea’s biodiversity. Goals of the NBSAP which the proposed project is in alignment with include, amongst others: i) reducing the overall degradation of natural resources; and ii) increasing the benefits flowing from natural resources through environmental management. The project will support the enhancement of terrestrial biodiversity through the rehabilitation of degraded ecosystems and encouraging the sustainable use of natural resources. Furthermore, the project will promote reforestation through community participation, as well as promote public awareness in biodiversity conservation. In addition, the proposed project will enhance agricultural biodiversity through conserving agricultural resources and ensuring the equitable and sustainable use thereof.

- The project is in alignment with Eritrea’s First National Communication (FNC) and Second National Communication (SNC) to the United Nations Framework Convention on Climate Change (UNFCCC). These reports guide the development of Eritrea’s policy, legal and institutional framework for adaptation to, and mitigation of, climate change. The project in alignment with the objectives of the FNC and SNC and will: i) promote the efficient use of land resources by integrating climate risk considerations into land-use planning and decision-making; ii) empower rural communities with skills to maintain a balance between agricultural production and demands for non-agricultural land uses; iii) strengthen the community-based management of natural resources; and iv) address institutional and technical limitations.

- Similarly, the project is in alignment with the country’s National Action Programme for Adaptation (NAPA), which identifies priority adaptation projects in Eritrea. The following NAPA priorities will be addressed by the proposed project, including water resources, agriculture, forestry and livestock. Furthermore, the proposed project will empower groups identified in the NAPA as particularly vulnerable to reduce their vulnerability to the effects of land degradation, climate hazards, food insecurity and water scarcity.

- The project  strongly responds to the National Capacity Needs Self-Assessment for Global Environmental Management in Eritrea (NCSA, 2006). In particular, the proposed project will enable the establishment and strengthening of conservation areas, as well as demonstrate and develop sustainable use methods in forestry as part of integrated land management in agricultural and forest landscapes in the highlands. In addition, the project will focus on the conservation and sustainable use of natural resources where such resources are threatened by increasing pressure from intensified land use, drought and desertification, often leading to land degradation. In compliance with the NCSA, the project’s indicatives activities will emphasise the prevention and control of land degradation through the development of sustainable methods for biodiversity conservation within the Nakfa Sub-Zoba, which is affected by significant levels of land degradation.

A.7. Knowledge Management. Outline the knowledge management approach for the project, including, if any, plans for the project to learn from other relevant projects and initiatives, to assess and document in a user-friendly form, and share these experiences and expertise with relevant stakeholders.

- Learning and knowledge management are recognised as an important component of the project. Various outcomes will produce results that will be encapsulated into the materials developed for subsequent capacity building and awareness-raising. The component will support improved understanding of the ecological and hydrological processes through Outcome 1.2 and this information will be used to inform decision-making on the use of ecosystems and how to manage them (water-related infrastructure, species of trees planted, as well as soil and water conservation measures). Materials developed for public awareness will also take climate risk considerations into account. Under Outcome 3.1, selected locations in the project area will be involved in learning-by-doing activities in which farmers develop their own capacities for applying on-farm conservation and adaptation measures. These activities will promote the integration of scientific knowledge, climate information and local knowledge in a farmer-led approach.  Farmers will therefore be able to make informed land-use decisions based on an integrated interpretation of the data and on their own traditional knowledge. Increased collaboration with NARI and Hamelmalo Agricultural College and enhanced capacities of agricultural extension agents will provide further support for the development of appropriate agro-ecological technologies.

- Under Outcome 2.1, user-friendly knowledge dissemination products will be developed and disseminated using improved climate risk information. In addition, public awareness campaigns will be undertaken at the Sub-Zoba  and community levels. These campaigns will use innovative methods, including community theatre/drama groups and radio programmes, to address audiences and illiterate farmers. Farmer-to-farmer seasonal forecast workshops will also assist farmers in developing their own capacities to apply on-farm conservation and adaptation measures, through an action learning process. This will involve farmers, research institutions, and both extension and meteorological services in a collaborative learning process.

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A. Record of Endorsement of GEF Operational Focal Point (s) on Behalf of the Government(s):  
      (Please attach the Operational Focal Point endorsement letter(s) with this template. For SGP, use this SGP OFP 
      endorsement letter).

| Name | Position | Ministry | Date (MM/dd/yyyy) |
| --- | --- | --- | --- |
| Mogos Woldeyohannes | GEF Operational Focal Point | Ministry of Land, Water and Environment | 07/27/2015 |

B. GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation under GEF-6.

| Agency Coordinator, Agency name | Signature | Date (MM/dd/yyyy) | Project Contact Person | Telephone | Email |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu, Executive Coordinator, UNDP-GEF |  | 31 July 2015 | Phemo Kgomotso | +251912503309 | phemo.kgomotso@undp.org |

GEF_PIF_60

C. Additional GEF Project Agency Certification (Applicable Only to newly accredited GEF Project Agencies)

For newly accredited GEF Project Agencies, please download and fill up the required GEF Project Agency Certification of Ceiling Information Template to be attached as an annex to the PIF.

Annex: EX-ACT Results

The carbon sequestration estimates have been computed using the Ex-Ante Carbon-Balance Tool (EX-ACT) Tier Standard Edition, developed by FAO. The forest-type selected for the calculations is Tropical Dry Forest, building on a baseline of degraded land in a Dry Tropical climate. The soil-type generally consists of fertile High Activity Clay loams derived from a basaltic substrate, albeit highly degraded through prior deforestation activity and subsequent over-grazing/agriculture. The project involves the expansion of enclosure areas from 9,000 ha to 17,500 ha using native and introduced tree species selected for their adaptability to semi-arid conditions, and the restoration of approximately 9,000 ha built around forest remnants. Over a period of 4 years (on the assumption that planting takes place in year 2 of the project), approximately 559,200 tCO2e will be sequestered through the project’s intervention.

# Footnotes

Project ID number will be assigned by GEFSEC and to be entered by Agency in subsequent document submissions.

When completing Table A, refer to the excerpts on GEF 6 Results Frameworks for GETF, LDCF and SCCF.

Financing type can be either investment or technical assistance.

For GEF Project Financing up to $2 million, PMC could be up to10% of the subtotal;  above $2 million, PMC could be up to 5% of the subtotal. PMC should be charged proportionately to focal areas based on focal area project financing amount in Table D below.

Calculated on the basis of labour-days contributed to the project by local community members using the average Eritrean daily wage as a measure of this in-kind contribution.

PPG requested amount is determined by the size of the GEF Project Financing (PF) as follows: Up to $50k for PF up to$2m (for MSP); up to $100k for PF up to $3m; $150k for PF up to $6m; $200k for PF up to $10m; and $300k for PF above $10m. On an exceptional basis, PPG amount may differ upon detailed discussion and justification with the GEFSEC.

PPG fee percentage follows the percentage of the Agency fee over the GEF Project Financing amount requested.

Strictly based on the target area for restoration within forest enclosures, but this is expected to be more (exact amount to be determined during PPG) as the restoration of forests and rehabilitation of degraded forests will also occur in other areas outside enclosures.

Estimated over a 20-year time horizon using IPCC Tier 2 data in the FAO EX-ACT tool.

GEF, 2014. Country Portfolio Evaluation: Eritrea (1992–2012).

Government of Eritrea. 2000. National Biodiversity Strategy Action Plan.

Government of Eritrea. 2008. Action Plan for Integrated Water Resource Management (IWRM) in Eritrea.

Government of Eritrea. 2001. Eritrea’s Initial National Communication under the UNFCCC.

Government of Eritrea. 2012. Eritrea’s Second National Communication under the UNFCCC.

Government of Eritrea. 2014. The Fifth National Report on the Implementation of the UNCBD.

Government of Eritrea. 1995. National Environmental Management Plan for Eritrea.

Eritrea is divided into 6 regions or Zobas, which are further divided into districts or Sub-Zobas. The project area is the Nakfa Sub-Zoba.

A kebabi is the smallest administrative unit in Eritrea and  encompasses approximately 3-5 villages.

GEF. 2014. Country Portfolio Evaluation: Eritrea (1992–2012).

Government of Eritirea. 2002. National Action Plan to Combat Desertification and Mitigate the Effects of Drought.

Government of Eritrea. 1995. National Environmental Management Plan for Eritrea.

Government of Eritrea. 2014. The Fifth National Report on the Implementation of the UNCBD.

Government of Eritirea. 2002. National Action Plan to Combat Desertification and Mitigate the Effects of Drought.

Government of Eritrea. 2014. The Fifth National Report on the Implementation of the UNCBD.

Three major tree species are found in the remnant forests – Juniperus exclesa, Olea erupaea and Rhus Abyssinica.

Government of Eritrea. 2014. The Fifth National Report on the Implementation of the UNCBD.

Enclosures are areas that have been put under full or partial protection by restricting human activities and livestock grazing for a number of years until regrowth of natural vegetation is secured. There are two kinds of enclosures: i) permanent enclosures do not permit any livestock grazing, farming, settlements or tree-cutting for an unlimited period of time; and ii) temporary enclosures are only closed for a limited period of time – a few months or a few years depending upon the state of the natural vegetation.

Government of Eritirea. 2015. Alignment of NAP to the UNCCD 10-Year Strategic Objectives (2008-2018).

Government of Eritrea. 2014. The Fifth National Report on the Implementation of the UNCBD.

UNDP field visits to the Debub Zoba, south of Asmara, July 2015.

IFPRI and NARI. 2014. Agricultral R&D Factsheet.

Government of Eritrea. 2006. National Capacity Needs Self-Assessment for Global Environmental Management in Eritrea.

Government of Eritirea. 2006. National Capacity Needs Self-Assessment for Global Environmental Management in Eritrea.

The Food and Agriculture Organization of the United Nations defines non-wood forest products as being ‘goods of biological origin other than wood derived from forests, other wooded land and trees outside forests.’

http://www.fao.org/tc/exact/ex-act-home/en/

See, for example, Keith et al (2009), ‘Re-evaluation of forest biomass carbon stocks and lessons from the world's most carbon-dense forests’, Proceedings of the National Academy of Sciences, Vol 106 (28).

Comprehensive Africa Agriculture Development Programme. 2013. Nutrition Country Paper – Eritrea.

Government of Eritrea. 2001. Eritrea’s Initial National Communication under the UNFCCC.

Government of Eritrea. 2008. Integrated Water Management Action Plan.

For regional and/or global projects in which participating countries are identified, OFP endorsement letters from these countries are required 
  even though there may not be a STAR allocation associated with the project.

GEF policies encompass all managed trust funds, namely: GEFTF, LDCF, and SCCF