| Annual Work Plan: Strengthening National Capacities for Conflict Prevention and Peace Building 2005-6 (2012/2013) |
| --- |
|  | UNDAF Results Area: Good Governance |
|  | Program /Project: Conflict Prevention and Peace Building |
|  | Agency Name: UNDP Implementing Agency: Ministry of Federal Affairs |
| No | EXPECTED OUTPUTS AND INDICATORS INCLUDING TARGETS | PLANNED ACTIVITIES | TIME FRAME | Total | Responsible body | Contributing ExCOM |
|  |  |  | Q1 | Q2 | Q3 | Q4 | USD |  |  |
| 1 | Output 1: Institutional and Technical capacities for the development and implementation of conflict prevention initiatives acquired and sustained by key project partners |
|  | Baseline: 0 P,M and System assessment 1 training on P,M and E Indicator: Effective communication system for conflict information exchange and program coordination put in place Target: MoFA and all regions | 1.1. Ensure Peace-building National program Officer is placed and rendering services | 10,000 | 10,000 | 10,000 | 10,000 |  | UNDP | 40,000 |
|  |  | 1.2. Conduct an assessment that identifies the gaps in the System of P,M and E for CPR interventions |  |  | 5,400 |  |  | UNDP | 5,400 |
|  |  | 1.3. Conduct a follow up training for MoFA staff and regional resource persons on P,M and E |  |  |  | 5,000 |  | MoFA | 5,000 |
|  |  | 1.4. Provide backstopping support for the program by regional support units |  |  |  |  |  | UNDP | No funding required |
|  |  | 1.5. Conduct international bench marking tour to a country with best experience |  |  |  | 3,000 |  | UNDP | 3,000 |
| 2 | Output 2: National conflict prevention architecture (including data collection, conflict analysis, Conflict Early Warning, and response systems incorporating internal mediation capacities at the federal, regional, and local levels), established and sustained on the basis of consultations with relevant stake holder. |
|  | Baseline: 0 Trained Early Warning Field Monitors 0 Trained peace commitee Indicator: Number Pool of Conflict Early Warning field monitors Target 150 Indicator: Number of trained peace committee members. Target 270 | 2.1. Conduct 2 rounds of Trainings for 270 Peace committee members on Mediation and Rapid response coordination. |  | 7,560 |  | 7,560 |  | MoFA | 15,120 |
|  |  | 2.2. Prepare a systems guideline or handbook for the comprehensive design of the Conflict Early Warning Architecture |  |  | 3,300 |  |  | UNDP | 3,300 |
|  |  | 2.3 Training of 150 field monitors in two rounds from 30 conflict prone Weredas. |  | 5,700 | 5,300 |  |  | MoFA | 11,000 |
| No | EXPECTED OUTPUTS AND INDICATORS INCLUDING TARGETS | PLANNED ACTIVITIES | TIME FRAME | Total | Responsible body | Contributing ExCOM |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |
| 3 | Output 3: Elements of a national “culture of peace” identified through facilitated, consultative processes at national, regional and local levels, and subsequently implemented through mass-media, education institutions, and civic associations. |
|  | Baseline : 0 Indicators: Number of universities with Strong local peace clubs | 3.1 Conduct ToT trainings on Conflict Prevention and Resolution CPR for university peace club members 3x22=66 in number | 8,660 |  |  |  |  | MoFA | 8,660 |
|  | Target: 32 |  |  |  |  |  |  |  |  |
|  | Baseline: 0 national peace forum Indicators: Established university forum and women’s peace initiatives Target: 1 UPC and 2 local women’s peace initiatives | 3.2 Conduct CPR Trainings for 10 new universities 600 participants (students and university staff) in number |  |  | 6,660 |  |  | MoFA | 6,660 |
|  |  | 3.4 Launch one national workshop that facilitates the establishment of University Peace Forum | 5,100 |  |  |  |  | MoFA | 5,100 |
|  | Baseline: 0 Indicators: Enhanced participations of traditional leaders Target: 450 | 3.5 Launch 2 local workshops to establish women’s peace initiatives for 200 participants. |  |  |  | 9,100 |  | MoFA | 9,100 |
|  |  | 3.6 Mobilize and sensitize total of 450 traditional leaders and respective stakeholders in three clusters and 29 Weredas to take active roles in local peace processes. | 10,780 | 10,780 | 18,780 | 18,780 |  | MoFA | 59,120 |
| 4 | Output 4: Capacity gaps in implementing local-level peace building efforts, and in the work of local peace committees and councils, identified through rigorous assessments of current agreements, and concrete steps implemented to address gaps. |
|  | Baseline: 0 Mediation capacity at local levels Indicators: Steering consultations conducted National capacity for mediation created Target: 16 Consultations and 18 mediators trained | 4.1. Conduct national (4 rounds i.e. quarterly) and cluster based (12 consultation) total 16 multi stakeholder consultations to review and steer local conflict management initiatives. | 20,000 | 18,000 | 38,000 | 38,100 |  | MoFA | 114,100 |
|  |  | 4.2. Conduct one Training of Regional resource persons (Trainers) who shall cascade mediation knowhow to the local levels. |  |  | 11,900 |  |  | MoFA | 11,900 |
| No | EXPECTED OUTPUTS AND INDICATORS INCLUDING TARGETS | PLANNED ACTIVITIES | TIME FRAME | Total | Responsible body | Contributing ExCOM |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |
| 5 | Output 5: Adequate system of M and E that informed the program for better results put in place. |
|  | Baseline: 0 baseline and mid-term review conducted Indicator: Proper Monitoring and Evaluation mechanism for the program put in place Target: A base line and a mid-term review process | 5.1. Conduct a mid-term program review | 9,000 |  |  |  |  | MoFA | 9,000 |
|  |  | 5.2. Prepare and disseminate communication products through various media |  |  | 1,500 | 1,500 |  | MoFA | 3,000 |
|  |  | 5.3 Conduct baseline study that identify the conflict prevention and resolution gaps in the country, including gaps in structures and mechanisms for CPR |  |  |  | 4,500 |  | UNDP | 4,500 |
|  |  | 5.4 Miscellaneous expenses | 750 | 670 | 790 | 790 |  | MoFA | 3,000 |
|  | Total | 64,290 | 52,710 | 101,630 | 98,330 |  |  | 316,960 |

·

Bottom of Form