**REACH – ENTRY FOR CORPORATE PLANNING SYSTEM - UPDATED FOR END OF QUARTER 4 2017**

**(updated 9 Jan 18)**

Cumulative for 2017. Output 1:2. 3 mobile units in operation. Status: Fully Achieved.

Output 1:3. 50% of Districts reached in each Division for awareness raising by joint teams. Status: Partially Achieved. 47% of Districts reached overall. Comprised of 93 Districts (and involved 526 communities) from a total of 196 Districts in Fiji reached.

Output 1:4. At least 4,000 people each year participating in awareness raising sessions conducted by joint teams undertaking mobile outreach services. Status: Achieved. 11,282 participants (5,319 women, 5,213 men and 750 children). (Includes 100 women from Eastern Division provided awareness on 12 June 2017).

Output 1:5. At least 2,500 people each year provided with service delivery by joint teams undertaking mobile outreach services. Status: Achieved. 15,540 people (8,412 women and 7,128 men) provided with services by joint teams. ((Department of Social Welfare services to 4,848 people (2,606 women and 2,242 men); Department of Women services to 2,478 people (2,222 women and 256 men); Legal Aid Commission services to 1640 people (847 women and 793 men); Human Rights and Anti-Discrimination Commission 242 people (81 women and 161 men); and other Ministries and Government agencies 6,332 (2,656 women and 3,676 men).

Output 1:6. 100 participants in awareness and capacity building training in 2017. Status: Partly Achieved. 42 participants. 39 representatives (25 female and 14 male) from Ministry of Women, Children and Poverty Alleviation, the Legal Aid Commission, the Human Rights and Anti-Discrimination Commission and other key stakeholders provided awareness and capacity building training during Lessons Learned Workshop 5 to 7 July 2017. Three representatives (1 female and 2 male) from UNDP (1) and Ministry of Women, Children and Poverty Alleviation (2) attended awareness and capacity building training in Dhaka, India related to Innovative Technology and Methods for Service Delivery related to Output 2 Start to Finish Service Delivery Tracker, during the period 7 to 14 December 2017.

Output 1:7. Two communications products developed that are gender responsive and meet human rights standards developed or revised. Status: Achieved. 5 communication products developed including videos, awareness materials including on website and Toolkit.

Output 2:1. Data from mission reports produced. Status: Achieved.

Output 2:2. One Options Paper on Innovative Awareness Raising, Service Delivery and Data Collection Models. Status: Achieved. Options Paper developed and endorsed at Lessons Learned Workshop in July 2017.

Output 2:3. One Plan developed for conduct of Pilot of Innovative Awareness Raising, Service Delivery and Data Collection Model. Status: Achieved. Plan developed and implementation commenced in December 2017.

Output 3:1. 3 project staff trained and retained. Status: Fully Achieved.

Output 3.2. 2016 Annual Report Completed. Status: Achieved.

Output 3:3. 2 Project Board Meetings conducted. Status: Achieved. Project Board meeting conducted 28 March 2017, and due to scheduling arrangements Project Board meeting planned for Q1 2018. Regular stakeholder updates and meetings undertaken.

Output 3:4. Routine updates provided to stakeholders. Status: Achieved.

Output 3:5. Mid-term evaluation conducted. Status: Partly Achieved. Mid-term evaluation consultant recruited to undertake evaluation commencing 2 January 2018.