Agreed by UNDP Resident Representative / UNDP Director:

| (Enter Name, Position) | Signature | Date: (Month, day, year) |
| --- | --- | --- |

INITIATION   PLAN

for a GEF Project Preparation Grant (PPG) or
Programme Coordination Budget (PCB)

Brief Description of Initiation Plan

(one paragraph narrative)

GEF PPG/PCB approved grant document and TBWP

Project PREPARATION GRANT (ppg)

Project Type:

type of Trust Fund:

Submission date:  04/02/2013

GEF Project ID: 5166

GEF Agency  Project ID: 4727

Country(ies): Fiji

Project Title: Capacity Building For Mainstreaming Mea Objectives Into Inter-Ministerial Structures And Mechanisms

GEF Agency(ies): , ,

GEF Focal Area(s):

a.   Project preparation Timeframe

| Start date of PPG | 07/01/2013 |
| --- | --- |
| Completion date of PPG | 02/01/2014 |

B.  proposed project preparation activities ($)

| Describe the PPG activities and justifications: The PPG will cover the following preparatory activities: 1. Baseline studies and strategy development: A) Institutional framework - prepare updated compilation of agencies and mandates; - prepare compiliation of data and information management mechanisms; - identify priority weaknesses and targets; - undertake training needs analysis; - prepare a draft project strategy to strengthen institiutional framework. B) legislative framework - prepare updated compilation of legislation; - prepare compilation of potential financing mechanisms and initialy analysis; - identify priority weaknesses and targets; - undertake training needs analysis; - prepare a draft project strategy to to strengthen legislative framework. 2. Secure government commitment to project strategy: Make contact with key agencies. Negotiate with key government representatives to ensure full agreement on the project objectives, outcomes, outputs, and activities, including partnerships for support and government co-financing. 3. Secure government commitment to project implementation arrangements: Undertake consultations with key government representatives to secure agreement on project implemenetation arrangements, including roles, responsibilities, and accountabilities of lead and partner agencies. 4. Explore, and if feasible, secure bilateral and multilateral financing opportunities: Explore potential for partnerships with bilateral and multilateral donor agencies and organizations, including networking among other potential regional and international development organizations. Negotiate partnerships with on-going projects to re-align their activities to meet project objectives will be considered. If appropriate, finalize co-financing agreements. 5. Define Monitoring and Evaluation (M&E) Plan: A detailed M&E work plan and delivery strategy will be defined, including clear identification of responsibilities and accountabilities, as well as an appropriate budget allocation (based on best practices and UNDP guidelines). The Plan will reflect the requirements of the GEF M&E Policy and Capacity Building M&E framework. The Plan will also include provisions for an independent evaluation and provision to ensure the learning of lessons from implementation at both the mid-point and termination of the project. The Plan will use the Capacity Development Indicators developed by UNDP, and the Capacity Development Scorecard (GEF Tracking Tool) to monitor impact and progress and support adaptive management. 6. Define Sustainability Plan: The Sustainability Plan will outline an exit strategy, leading to the continuation of concerned activities without the need of long-term international financing. 7. Validation workshop Representatives from all relevant stakeholders will gather to discuss and validate the final draft proposal. The final product of the proposed PPG phase will be a UNDP/GEF compliant medium-sized project document for submission to UNDP and GEF, including the following: • A detailed work plan with detailed roles and responsibilities for project implementation; • A targeted, in-depth analysis of the baseline situation and needs; • An updated report on the partnership and co-financing opportunities for the proposed project; • Explicit specification of all capacity building activities to be financed under the project and the rationale of their additionality to meeting Rio Convention objectives; • A detailed deconstruction of the project strategy using the Logical Framework Approach (log frame); • A detailed monitoring and evaluation plan for the project that builds upon the log frame; • A stakeholder participation plan; • Endorsement letters from the government and letters confirming co-financing commitments; • Medium-Size Project document per GEF and UNDP formatting and submission requirements; • Terms of Reference for key project staff, project management committee and key consultants. |
| --- |
| List of Proposed Project Preparation Activities | Output of the PPG Activities | Trust Fund | Grant Amount (a) | Co-financing (b) | Total c = a + b |
| Baseline study/strategy analysis (1A) | In-depth analysis and draft strategy |  | 5,500 | 5,000 | 10,500 |
| Baseline study/strategy analysis (1B) | In-depth analysis and draft strategy |  | 5,500 | 5,000 | 10,500 |
| Secure government commitment | Endorsement letters |  | 0 | 1,000 | 1,000 |
| Secure co-financing | Co-financing letters |  | 0 | 1,000 | 1,000 |
| Define M&E system | M&E plan |  | 0 | 3,000 | 3,000 |
| Define sustainability plan | Sustainability plan |  | 0 | 3,000 | 3,000 |
| Validation workshop | Consensus and agreement |  | 5,000 | 0 | 5,000 |
| Prepare project documentation | Complete project documentation |  | 9,000 | 2,000 | 11,000 |
|  |  |  |  |  | 0 |
|  |  |  |  |  | 0 |
|  |  |  |  |  | 0 |
|  |  |  |  |  | 0 |
| Total Project Preparation Financing |  | 25,000 | 20,000 | 45,000 |

C.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| Grant Amount | 25,000 | 2,375 |
| Co-financing | 20,000 |  |
| Total | 45,000 | 2,375 |

D.  PPG  Amount requested by agency(ies), focal area(s) and country(ies) 1

| Trust Fund | GEF Agency | Focal Area | Country Name/ Global | (in $) |
| --- | --- | --- | --- | --- |
|  |  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
|  |  |  | Fiji | 25,000 | 2,375 | 27,375 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
|  |  |  |  |  |  | 0 |
| Total PPG Amount | 25,000 | 2,375 | 27,375 |

1 No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

E.   PPG Budget

| Cost Items | Total Estimated Person Weeks for Grant (PW) | Grant Amount ($) | Co-financing ($) | Total($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 24.00 | 12,000 | 0 | 12,000 |
| International consultants* | 3.00 | 7,500 | 0 | 7,500 |
| Travel |  | 2,000 |  | 2,000 |
| workshops |  | 3,500 | 5,000 | 8,500 |
| advocacy and support |  |  | 10,000 | 10,000 |
| Other |  |  | 5,000 | 5,000 |
| Total PPG Budget |  | 25,000 | 20,000 | 45,000 |

* Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

F.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF LDCF/SCCF/NPIF Trust Fund criteria for project identification and preparation.

| Agency Coordinator, Agency Name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Adriana Dinu Officer In Charge UNDP-GEF |  | April, 02,2013 | Tom Twining-Ward, UNDP Green-LECRDS | +421 2 59337 386 | tom.twining-ward@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Type of Consultant | Position / Titles | $/ Person Week1 | Estimated PWs2 | Tasks to be Performed |
| --- | --- | --- | --- | --- |
|  | Legal Expert | 500 | 12.00 | Undertake baseline studies and strategy development related to ‘legislative framework’: - prepare updated compilation of legislation; - prepare compilation of potential financing mechanisms and initialy analysis; - identify priority weaknesses and targets; - undertake training needs analysis; - prepare a draft project strategy to to strengthen legislative framework. - Contribute to drafting of project design and GEF submission document. |
|  | Institutional Expert | 500 | 12.00 | Undertake baseline studies and strategy development related to ‘institutional framework’: - prepare updated compilation of agencies and mandates; - prepare compiliation of data and information management mechanisms; - identify priority weaknesses and targets; - undertake training needs analysis; - prepare a draft project strategy to strengthen institiutional framework - Contribute to drafting of project design and GEF submission document. |
|  | Capacity Development And Project Design Expert | 2500 | 3.00 | - Work together with the local consultants (LC), UNDP and national counterparts on setting PPG implementation strategy; - Finalize PPG work plan, TOR for LCs, and design consultation and validation workshops. - Oversee completion of background studies, ensuring they are appropriate in scope and provide required analys; - Facilitate and guide consultations to determine project strategy, priorities, key partners, and key barriers to success; - Provide technical and professional support to the LC and national stakeholders. - Develop the project strategy; detailed budget, work plan and logical framework, develop a replication strategy. - Draft final project documents. |

1 Provide dollar amount per person week.

2   Provide person weeks  needed to carry out the task

Total Budget and Work Plan

| Award ID: |  |
| --- | --- |
| Award Title: |  |
| Business Unit: |  |
| Project Title: |  |
| Project ID: |  |
| PIMS No. |  |
| Implementing Partner (Executing Agency) |  |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 2013 (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Development of medium-size project document | UNDP | 62000 | GEFTF | 71200 | International Consultant | 7,500 |
|  |  |  |  | 71300 | Local Consultant | 12,000 |
|  |  |  |  | 71600 | Travel | 2,000 |
|  |  |  |  | 75700 | Training, Workshops & Conferences | 3,500 |
|  |  |  |  |  | Total Outcome 1 | 25,000 |
|  |  |  |  | TOTAL | 25,000 |

| Summary of Funds: |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | GEF | 25,000 |  | $ |
|  |  | Co-financing | 20,000 |  | $ |
|  |  | TOTAL | 45,000 |  | $ |

# Footnotes

Summary table should include all financing of all kinds: GEF financing, co-financing, cash, in-kind, etc.  etc

# Text boxes

Total budget:		 ____________

Allocated resources:	 ____________

- Government		 ____________

- Regular 		 ____________

- Other:

  - Donor	_________

  - Donor	_________

  - Donor	_________

- In kind contributions  _________

Programme Period:_____________

Programme Component:_________

PPG Title:__________________

ATLAS Award ID: _______________

ATLAS Project ID: _________________

PIMS Project ID: ___________________

Duration:	______________

Management Arrangement: ______

Country  __________________

Relevant UNDAF Outcome(s) and Indicator(s): List UNDAF outcome.   If no UNDAF, leave blank

Relevant CP/CPAP Outcome(s) and Indicator (s):

Relevant UNDP Strategic Plan 2008-2011 Key Result Area:

Expected Project Outcome (s) and Indicator (s):  In addition to CPAP outcomes

Project Output(s) and Indicator(s):