## Work Plan 2017
EXPECTED OUTPUTS (see results framework for baselines, indicators and targets) | ACTIVITY RESULTS | ACTIONS | BRIEF NARRATIVE | STATUS | TIMEFRAME (2017) |  |  |  | RESPONSIBLE PARTY | DESCRIPTION | 2017 BUDGET ($)
[5 empty] | Q1 | Q2 | Q3 | Q4
OUTPUT 1: Strengthened institutional and fiduciary capacity to enable entity to access the GCF | Activity 1.1: Mapping and assessment of Ghanaian national public or private entities that are eligible to access funds from the GCF | Action 1.1.1: Conduct review /analysis of climate-related investments by non-governmental & private sector actors in Ghana | This action is focusing on thorough analyses of the private sector investments in the sectors prioritized for the project proposals. Once the 1 or 2 projects have were identified to be developed these analysis began to support the full proposals | ONGOING |  |  |  |  | MOF | Consultants cost | 4575
| Activity 1.4: Facilitate NDA engagement with GCF | Action 1.4.1: Support participation of NDA in multilateral events, negotiations, lessons exchange, etc | The key role of the NDA is to serve as an interface between the Government of Ghana and the Fund. The Readiness Programme would support this important role of the NDA through participation in multilateral events, negotiations, etc. | ONGOING |  |  |  |  | MOF | Travel costs - Other events | 13800
[10 empty] | Travel costs- NDA/GCF events | 20000
[10 empty] | Subtotal Activity 1.1 & 1.4 | 38375
OUTPUT 2: Enhanced coordination among stakeholders and institutions of national and sub-national entities to manage and deliver climate finance | Activity 2.1: Strengthen Ghana’s climate change coordination across national and sub-national levels | Action 2.1.1: Support the NCCSC for its enhanced coordination on climate planning and budgeting process | This action will support meetings of the NCCSC. The purpose of establishing the steering committee for the national climate change policy is to demonstrate government commitment to addressing the climate change in Ghana, by providing strategic framework for the implementation of the policy by all relevant MDAs, CSOs and NGOs, private sector as well as all relevant stakeholders. The Committee, as per its TOR, is expected to meet at least twice a year. | YET TO COMMENCE |  |  |  |  | MESTI | Meeting cost – venue | 15000
|  | Action 2.1.2: Support a working group on climate finance at NCCSC | This activity will be used to support the gender working group of the NCCSC on accessing climate finance. There is a need for the working group to grasp the basic requirements on climate finance. The various sources of funding, the processes and the standards to be met. | YET TO COMMENCE |  |  |  |  | MESTI/MOF | Meetings (venue and Travel) | 11400
[10 empty] | Subtotal Activity 2.1 | 26400
| Activity 2.4: Increase stakeholder access to information and knowledge products on climate change and climate finance guidance | Action 2.4.1: Strengthen the Climate Change Data Hub for collecting baseline inventory data | EPA (with the help of UNDP) has already created a data hub for climate change projects which needs further work. This action will now focus on further work or upgrade, which goes beyond projects captured at the national level and possibly selecting sample projects to provide in-depth data in relation to flow of expenditure and actual impacts. The upgrade will cover a section on pipeline projects (including GCF), the INDCs as well as policies and regulations | ONGOING |  |  |  |  | MESTI | Consultant cost – IT development | 16850
|  | Action 2.4.2: Compile policies, regulations, other relevant documents and knowledge products for public posting and targeted audience | [6 empty] | MESTI
|  | Action 2.4.3: Upgrade online systems to support the creation and implementation of the pipeline of bankable projects | [6 empty] | MESTI
|  | Action 2.4.4: Development of relevant and robust MRV frameworks, templates, and guidance for climate finance | GCF Readiness Programme will focus on developing a Monitoring/ Measuring, Reporting and Verification (MRV) system for climate finance which will build on the climate finance tracking tool developed with the MoF. | ONGOING |  |  |  |  | MESTI | Consultant | 50590
Action 2.4.5: Testing of MRV templates/guidance on climate finance
|  | Action 2.4.6: Workshop/training(s) to apply MRV system developed and use data hub | Validation and training workshops for MRV and training workshop for data hub usage | YET TO COMMENCE |  |  |  |  | MESTI | Meeting cost – venue and travel | 18500
[10 empty] | Subtotal Activity 2.4 | 85940
OUTPUT 3: Development of a system for identifying, prioritizing, and developing bankable and measurable climate change programs/projects | Activity 3.1: Guidelines and procedures developed for prioritizing climate change needs and interventions | Action 3.1.1: Development of procedures, criteria and menus to evaluate and select national priority projects based on needs and based on lessons learned from prioritization process | After the initial development of the projects' prioritization tool and its use in the evaluation and selection of priority projects. The focus will now be on setting up a team (of about 6) to identify priority projects on key sectors | ONGOING |  |  |  |  | MESTI | Consultant | 12300
|  | Action 3.1.2: Decision-making workshop to define GCF pipeline | The NDA and its TAC have selected priority projects which are being developed into proposals for submission to the GCF. The NDA and the TAC will need to hold subsequent meetings to take key decisions on the project proposal development process. | ONGOING |  |  |  |  | MESTI | Meeting cost – venue and travel | 22000
[10 empty] | Subtotal Activity 3.1 | 34300
| Activity 3.2: Market based and value chain business model tools developed to assess, design and measure climate change interventions, including Cost-Benefit Analysis (CBA) and project checklists and safeguards | Action 3.2.1: Review of national adaptation and low carbon development strategies and identify gaps and incremental needs | Review existing national adaptation strategies that can be put together as a national adaptation plan for implementation. This is to initiate the process of helping GoG access GCF's Readiness and Preparatory Support Programme which has a cap of $3 million per country. Once Ghana decides on a delivery partner, the results from this work would be a good starting place to submit a proposal on NAPs implementation to the GCF. | YET TO COMMENCE |  |  |  |  | MESTI/MOF | Consultant | 12000
|  | Action 3.2.2: Development of project/programme checklist aligned with national development plan (GSGDA II) and safeguards | Development of programme checklist/ manual to help the NDPC incorporate INDC in their next cycle of planning | YET TO COMMENCE |  |  |  |  | MESTI | Consultant | 25500
|  | Action 3.2.3: Support the integration of decision making tools into legislation, processes and regulations | Support for the NDPC's with the integration of the checklist through workshops across the 10 regions | YET TO COMMENCE |  |  |  |  | MESTI | Meeting cost – venue and travel | 45000
[10 empty] | Subtotal Activity 3.2 | 82500
[10 empty] | Total | 267515
Output 5: Project Management Cost |  | GCF Readiness Programme National Coordinator | [6 empty] | UNDP |  | 40000
|  | Administrative/Finance Associate | [8 empty] | 20000
|  | Rent, Equipment, Utilities, Internet Charges, Telephone, HR cost - leave monitoring | [8 empty] | 21500
|  | Audit/ Evaluation | [6 empty] | UNDP |  | 20000
[10 empty] | Subtotal | 101500
[10 empty] | Grand total | 369015
|  | GMS Charges (UNDP) | [6 empty] | GMS Charges (UNDP) |  | 36901.5
[9 empty] | Total Funds (2017) |  | 405916.5

## Work Plan 2017 UNEP
EXPECTED OUTPUTS (see results framework for baselines, indicators and targets) | ACTIVITY RESULTS | ACTIONS | Time frame | [7 empty] | RESPONSIBLE PARTY | DESCRIPTION | Budget
|  |  | 2016 |  |  |  | 2017 | [5 empty] | AMOUNT (US$)
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | 2016 | 2017 | Total
OUTPUT 1: Strengthened institutional and fiduciary capacity to enable entity to access the GCF | Activity 1.2: Support on GCF fiduciary requirements
|  | Action 1.2.1: Develop workshop and communications materials on GCF | [8 empty] | UNEP ROA/ MESTI |  | 14000 | 0 | 14000 | bar: 2016 Q2
|  | Action 1.2.2: Engage and collaborate with key public, private and CSO to participate | [8 empty] | UNEP ROA/ MESTI |  | 3500 | 0 | 3500 | bar: 2016 Q2
|  | Action 1.2.3: Undertake workshop to develop a roadmap for alignment of fiduciary standards and safeguards with clear timeline | [8 empty] | UNEP ROA/ MESTI |  | 23500 | 0 | 23500 | bar: 2016 Q2
|  | Subtotal Actvity 1.2 | [10 empty] | 41000 | 0 | 41000
Activity 1.3: Support the development of an implementing entity and NDA application to the GCF
|  | Action 1.3.1: Capacity assessment, selection and government endorsement of preferred NIE to access GCF funds | [8 empty] | UNEP DEPI | ACTIVITY COMPLETE 2016 | 16145 | 0 | 16145 | bar: 2016 Q1 to 2016 Q2
|  | Action 1.3.2: Provide expertise to Ghana to develop/compile documentation for submission for accreditation under the GCF direct access modality; this includes training to strengthen the NIE's capacities in terms of fund management and fiduciary standards | [8 empty] | UNEP DEPI |  | 32000 | 15855 | 47855 | bar: 2016 Q3 to 2017 Q4
|  | Action 1.3.3: Develop guidebook to strengthen the capacity of the national entity for meeting international institutional fiduciary, technical, accountability, transparency and governance standards and requirements. | [8 empty] | UNEP DEPI | ACTIVITY COMPLETE 12/2015 | 24000 | 0 | 24000
|  | Subtotal Actvity 1.3 | [10 empty] | 72145 | 15855 | 88000
OUTPUT 2: Enhanced coordination among stakeholders and institutions of national and sub-national entities to manage and deliver climate finance | Activity 2.2: Consultations with government stakeholders on the design and establishment of a Ghana National Climate Fund
|  | Action 2.2.1: Conduct review of relevant existing and past environment and climate related funds’ documents (such as RE Fund, EPA National Environment Fund, Ghana Green Fund, Forestry Commission National Plantation Fund, national Communications, INDC documents) and identify opportunities for a Climate Fund (as a sub-component) under the umbrella of the EPA Environment Fund or Ghana Green Fund | [8 empty] | UNEP -UDP | ACTIVITY COMPLETE | 32512 | 0 | 32512 | bar: 2016 Q2
|  | Action 2.2.2: Prepare a document (based on 2.2.1) with key decisions to be possibly taken by the Ghana government regarding climate fund in a EPA Environment Fund or Ghana Green Fund. | [8 empty] | UNEP -UDP |  | 26834 | 7039 | 33873 | bar: 2016 Q2 to 2017 Q1
|  | Action 2.2.3: Depending on the evaluation of the potential to establish a Climate Fund component (of the EPA Environment Fund or Ghana Green Fund), provide direct technical support to develop oversight and modality for fund management and disbursement. (Action removed and subsumed in action 2.2.2) | [8 empty] | UNEP -UDP |  |  |  | 0
|  | Action 2.2.4: Depending on the evaluation of the potential to establish a Climate Fund component (of the EPA Environment Fund or Ghana Green Fund), provide direct technical support in the process of setting up such a Fund | [8 empty] | UNEP -UDP |  | 4061 | 10535 | 14596 | bar: 2016 Q2 to 2017 Q1
|  | Action 2.2.5: Provide advice and expertise to government as needed | [8 empty] | UNEP -UDP |  | 1964 | 647 | 2611 | bar: 2016 Q2 to 2017 Q2
|  | Subtotal Actvity 2.2 | [10 empty] | 65371 | 18221 | 83592
OUTPUT 4: Leveraging of private sector resources to scale up climate change solutions through market based and inclusive value chain business model | Activity 4.1: Mapping value chain actors, business service providers, trade associations, gaps, risks, monetization of environmental services
|  | Action 4.1.1: Conduct study to identify the barriers and business risks in mobilizing private sector participation (Actions 4.1.1 to 4.1.4 have been integrated into one study) | [8 empty] | UNEP-FS |  | 23000 | 0 | 23000 | bar: 2016 Q1 to 2016 Q3
|  | Action 4.1.2: Conduct study to map the characteristics of private sector engagement in climate relevant activities, highlighting gaps and opportunities | [8 empty] | UNEP-FS |  | 10000 | 0 | 10000 | bar: 2016 Q1 to 2016 Q3
|  | Action 4.1.3: Conduct study to review regulatory, technical and financial framework for private sector investments in climate change solutions | [8 empty] | UNEP-FS |  | 7000 | 0 | 7000 | bar: 2016 Q1 to 2016 Q3
|  | Action 4.1.4: Assess options for leveraging public and private sector resources and make recommendations based on assessment, including specific regulatory incentives for private sector investment. | [8 empty] | UNEP-FS |  | 5000 | 5500 | 10500 | bar: 2016 Q1 to 2017 Q1
|  | Action 4.1.5: Develop a set of environment and social safeguards and guidelines to facilitate private investment into national climate change activities; and work with national banks and investments funds to adopt these safeguards and guidelines | [8 empty] | UNEP-FS |  | 24000 | 0 | 24000 | bar: 2016 Q3 to 2016 Q4
|  | Subtotal Actvity 4.1 | [10 empty] | 69000 | 5500 | 74500
Activity 4.2: Facilitate private sector resource mobilization and engagement on climate change activities
|  | Action 4.2.1: Utilize public sector resources to develop policy and financial de-risking instruments to support private sector participation in climate change programme design and activities | [8 empty] | UNEP ROA |  | 31000 | 0 | 31000 | bar: 2016 Q2 to 2016 Q4
|  | Action 4.2.2: Support Government to host outreach with private sector actors across priority sectors (e.g. EE, RE, Food security/Clean energy/water access, climate friendly agriculture and ecosystem-based adaptation and land use management) to identify synergies and investment opportunities | [8 empty] | UNEP ROA |  | 11500 | 0 | 11500 | bar: 2016 Q3 to 2016 Q4
|  | Action 4.2.3: Support the identification, design and preparation of selected climate change projects, leading to the development of a pipeline of projects that have advanced through the early project development stage. This includes, among others, the identification of viable programme/project areas and the development of project design documents | [8 empty] | UNEP DTIE |  | 81461.15 | 38538.85 | 120000 | bar: 2016 Q2 to 2017 Q2
|  | Action 4.2.4: Conduct consultations to review the financial sector (e.g. banks, MFIs) activities with focus on finance for mitigation and adaptation measures, assess lessons learned in implementing initial sustainable energy finance, and identify the gap between investment potential and finance supply | [8 empty] | UNEP-FS |  |  |  | 0 | bar: 2016 Q2 to 2016 Q4
|  | Action 4.2.5: Engage the Ghanaian financial sector (including Agriculture Development Bank, Ecobank and ARB-APEX Bank, African Development Bank) in developing and implementing measures to address the gaps and build the sector’s capacity to increase climate relevant investment | [8 empty] | UNEP-FS |  |  |  | 0 | bar: 2016 Q2 to 2017 Q1
|  | Subtotal Actvity 4.2 | [10 empty] | 123961.15 | 38538.85 | 162500
Activity 4.3: Strengthen the technical and financial capacity of public, private and CSO stakeholders in business development and marketing of climate change solutions
|  | Action 4.3.1: Peer to peer training for social entrepreneur/business incubator/venture capitalist (targeting also women and youth) as inclusive value chain actors in mitigating supply and demand risks | [8 empty] | UNEP-FS |  | 5000 |  | 5000 | bar: 2016 Q2 to 2016 Q4
|  | Action 4.3.2: Assist private sector to develop business plan and financial structuring for access to competitive credit/loans | [8 empty] | UNEP-DTIE |  | 3036 | 24964 | 28000 | bar: 2017 Q3
|  | Action 4.3.3: Train financial institutions in project evaluation and risk/return profiling for the development of new financial products and services (e.g. leasing, hire purchase, Toyola saving box) | [8 empty] | UNEP-FS |  |  | 37032 | 37032 | bar: 2017 Q1
|  | Subtotal Actvity 4.3 | [10 empty] | 8036 | 61996 | 70032
[11 empty] | Sub-total UN Environment |  | 379513.15 | 140110.85 | 519624

## Itemised Expenditure
| Project Title: |  | GCF Readiness Program-Ghana
Income and expenditure report for the year ended 31st Dec. 2016
| GHA10_94845 |  |  | $ | $ | $
Income for the year 2016
1 | Balance as January 2016 |  |  |  |  | 240662
Add:
| 1st Tranche received (Jul. 2016) |  |  |  | 150188.84
| 2nd Tranche received (Nov. 2016) |  |  |  | 150188.88
| 3rd Tranche received (Nov. 2016) |  |  |  | 150188.88
450566.6
A | Total income/Receipts for the year |  |  |  |  | 691228.6
2 | Expenditure for the year
| Activity lines |  | Expenditure Items
Activity 1.1: Mapping and assessment of Ghanaian national public or private entities that are eligible to access funds from the GCF
|  | Mapping and assessment of Ghanaian entities to access funds from the GCF (Workshop) | Stationery for NIE evaluation workshop | 7834.32
|  | Sub-Total |  |  | 7834.32
|  | ction 1.1.2: Conduct /analysis of climate-related investments by non-governmental & private sector actors in Ghana | Consultancy on climate investment | 11055.12
|  |  | Advert for consultancy | 831.38
|  |  | Evaluation of CC investment report | 5208.29
|  | Sub-Total |  |  | 17094.79
| Activity 1.4. Facilitate NDA engagement with GCF | Action 1.4.1.: Draft and approve NDA operational manual | Final payment fo NDA operation manual | 11914.17
|  |  | Evaluation of NDA manual/priotisation tools | 3429.68
|  | Action 1.4.2: Sensitization workshops for key ministries on engagement procedures with GCF and role of NDA - | Printing of CC tools | 9799.85
|  |  | MMDA's Sensitisation | 5834.64
|  | Action 1.4.3. Support participation of NDA in multilateral events, negotiations, lessons exchange, etc | Cop22 participation | 7362.11
|  |  | GCF event-Korea | 13009.3
|  |  | Sub-Total |  | 51349.75
| Activity 2.1: Strengthen Ghana’s climate change coordination across national and sub-national levels | Action 2.1.1: Solidify roles and responsibilities across stakeholders, processes and systems for action on climate change | Post Cop21 Way forward workshop | 4309.05
|  |  | Training of Regional and District Adaptation Fund committees | 26985.2
|  |  | Sub-Total |  | 31294.25
| Activity 2.3: Support the strengthening of climate change regulations, policies, plans and budgeting | Action 2.3.1: Design and oversee a national tracking tool for climate change finance and develop economic and budget analysis tools for climate-related decision-making and budgetary allocation and conduct training on tools for District Planning Coordinating Units and Regional Planning Coordinating Units | Dev't of CC Budget tracking tools | 82840
|  |  | Training on CC budget tracking tools | 11502.65
|  | Action 2.3.2: Strengthen the climate change mainstreaming process into national and district planning | NAPs traning on CBA tools | 17659.52
|  |  | Sub-Total |  | 112002.17
| Activity 2.4: Increase stakeholder access to information and knowledge products on climate change and climate finance guidance | Action 2.4.1: Strengthen the Climate Change Data Hub for collecting baseline inventory data
|  |  | 2 Consultancy payments on Data hub dev't. | 41092.87
|  |  | Advert for Data Hub consultant | 774.33
|  |  | Sub-Total |  | 41867.2
Action 2.4.4: Development of relevant and robust MRV frameworks, templates, and guidance for climate finance
|  |  | 1st Consultancy payment for MRV tools dev't | 23508.13
|  |  | Advert | 774.33
|  |  | Sub-Total |  | 24282.46
Activity 3.1: Guidelines and procedures developed for prioritizing climate change needs and interventions
|  | Action 3.1.1: Development of procedures, criteria and menus to evaluate and select national priority projects based on needs and based on lessons learned from NAMA prioritization process | Last 2 payments for prioritisation tools | 18224.73
|  | Action 3.1.2: Decision-making workshop on project prioritization to define GCF pipeline | Decision-making workshop on project prioritization to define GCF pipeline & TAC meeting DSA | 17451.14
|  |  | Sub-Total |  | 35675.87
| Project Management Cost |  | PMU Salaries/working equipments/SC meeting etc | 44273.14
|  |  | Sub-Total |  | 44273.14
| GMS |  |  | 32279.06
| Sub-Total |  |  |  | 32279.06
B | Total Expenditure for the year |  |  |  |  | 397953.01
C | Cash Balance (A-B) |  |  |  |  | 293275.59
D
Notes (A)
1 | Project fund for operation |  |  |  | 853345
| GMS |  |  |  | 85334.5
| Total Project fund |  |  |  |  | 938679.5
2 | Project expenditure to date:
| 2015 Expenditure |  |  |  | 134809.67
| 2016 expenditure |  |  |  | 397953.01
| Total expenditure |  |  |  |  | 532762.68
3 | Total project fund left for operation (1-2) |  |  |  |  | 405916.82
(B) | Outstanding payments:
| 1. Consultancy on climate Change investment/Base line |  |  | 4573.95
| 2. Consultancy for data Hub |  |  | 16825.4
| 3. MRV Finance |  |  | 50540.65
| Total |  |  | 71940
(C) | Cash Balance as at Jan. 2017 |  |  | 293275.59
| Expected transfer |  |  | 112641.23
| Total Project funds for 2017 |  |  | 405916.82