## Work Plan 2015
| Output | Activities | Responsible Party | Estimated Budget (USD) | 2015 Quarter 1 2 3 4 |  |  |  | Equipment | Contractual Services /Companies | Miscellaneous Expenses | Travel | Communication/publication | Local Consultants | Salary Costs | Justification/Remarks
Outcome 1: Ghana has an enabling environment in place for the transfer, production and regulation of the use of Renewable Energy Technologies in Ghana.
| Output 1.1 | Activity Result 1.1.1.: Review Chinese and Ghanaian RE policies and strategies to identify capacity building gaps and solutions to address them
|  | Sub-activity 1: Conduct workshops in Ghana for Stakeholders on China and Ghana’s Renewable Energy policy | Ghana Energy Commission (GEC) | 9000 | X | X | [9 empty] | Preparatory phase to collect data. A consultant to collect data from China, distill documents and brief key Ghanaian stakeholders on Chinese policy.
|  | Local Consultants |  | 6000 | X | X | [7 empty] | 6000 |  | Local consultant (or team of consultant) to review Chinese policies: $300*20 man days
|  | Contractual Services /Companies |  | 2000 | X | X |  |  |  | 2000 | [5 empty] | Cost of venue for workshop to review Chinese policies for 20 key Ghanaian participants for 1 day
|  | Miscellaneous Expenses |  | 1000 | X | X |  |  |  |  | 1000 |  |  |  |  | Miscellaneous
|  | Sub-activity 2: Joint review Renewable Energy policies in Ghana | GEC | 10000 |  | X | [9 empty] | Chinese officials will travel to Ghana to provide clarifications on Chinese policies.
|  | Travel |  | 7000 |  | X | [5 empty] | 7000 |  |  |  | 2 return tickets Beijing-Accra-Beijing (2x$2,000) and 5 days DSA for 2 experts at $300
|  | Contractual Services /Companies |  | 3000 |  | X |  |  |  | 3000 | [5 empty] | One day workshop to clarify Chinese policies to 30 key Ghanaian stakeholders for 1 day
|  | Sub-activity 3: Conduct gaps analysis through stakeholder consultations and seminars | GEC | 24000 |  | X | [9 empty] | Consultant to review status of implementation of RE Policy, RE Act (with focus on non-grid connected RE) and other related documents. One workshop for one day for 50 participants to review results gathered by the consultant. Activity 1,2 and 3 combined into one workshop
|  | Local Consultants |  | 12000 |  | X | [7 empty] | 12000 |  | Local consultant to do gap analysis and review of implementation of Ghanaian policies: $300*40 man days
|  | Travel |  | 2000 |  | X | [5 empty] | 2000 |  |  |  | Travel for 5 Ghanaian experts to Accra: DSA ($300*5); transportation ($500)
|  | Contractual Services /Companies |  | 10000 |  | X |  |  |  | 10000 | [5 empty] | One main workshop to review gaps and results for 50 participants for 1 day; 3 smaller workshops for consultant to meet specific groups of stakeholders.
|  | Sub-activity 4: Organize workshop/seminars to identify solutions to address the identified gaps | GEC | 16000 |  | X | X
|  | Local Consultants |  | 3000 |  | X | X | [6 empty] | 3000 |  | Local consultant to identify solutions: $300*10 man days
|  | Travel |  | 1500 |  | X | X |  |  |  |  | 1500 |  |  |  | Travel for 5 Ghanaian experts to Accra: DSA ($300*5)
|  | Contractual Services /Companies |  | 10000 |  | X | X |  |  | 10000 | [5 empty] | One main workshop to review gaps and results for 50 participants for 1 day; 3 smaller workshops for consultant to meet specific groups of stakeholders. Conduct 3 day workshop
|  | Miscellaneous Expenses |  | 1500 |  | X | X |  |  |  | 1500 |  |  |  |  | Miscellaneous
|  | Subtotal 1.1.1. |  | 59000
Activity Results 1.1.2: Draft and submit to Parliament the Renewable Energy Master Plan (REMP)
|  | Sub-activity 1: Develop Renewable Energy Master Plan based on Ghana’s National RE Strategies |  | 140000 | [11 empty] | There will be an initial phase to evaluate the status of current renewable energy facilities wind, solar, biomass/cookstoves, and hydro. This will form the baseline for the REMP.
|  | Local Consultants |  | 100000 |  | X | X | X | [5 empty] | 100000 |  | Team of consultants with one lead consultant and 4 sectoral consultants. Lump sum contract. Consultancy fees: $75,000 ($300*250 working days); travel: $21,000 ($300 DSA and $300 fuel/car for 35 days in the field); $4,000 (miscellaneous costs).
|  | Travel |  | 21000 |  |  | X | X |  |  |  | 21000 |  |  |  | Cost of travel for two members of project team to go to the field with consultants: $21,000 ($300*2people*35 days in the field)
|  | Contractual Services /Companies |  | 15000 |  |  | X | X |  | 15000 | [5 empty] | Cost of 10 stakeholder consultations to gather data and discuss issues related to the REMP for 15 people each: $15,000 ($100*15*10).
|  | Miscellaneous Expenses |  | 4000 |  |  | X | X |  |  | 4000 |  |  |  |  | Miscellaneous
|  | Sub-activity 2: Conduct multi-stakeholder consultation to review the Plan | GEC | 37000 |  |  |  | X | [7 empty] | 4 working days to review the REMP (1 day per sector)
|  | Travel |  | 13000 |  |  |  | X |  |  |  | 13000 |  |  |  | Reduced DSA for 30 participants for 4 days: $7,000; cost of air ticket for two chinese experts: $4,000 ($2,000*2); DSA for 2 Chinese experts for 5 days ($200*5*2)
|  | Contractual Services /Companies |  | 24000 |  |  |  | X |  | 24000 | [5 empty] | Cost of conference package for 40 people for 4 days outside Accra ($150*40*4)
|  | Subtotal 1.1.2 |  | 177000
|  | Total Output 1.1 |  | 236000
| Output 1.2 | Activity Results 1.2.1: Conduct in depth analysis of regulatory, technical, social and other barriers in Ghana and China currently hindering effective and widespread absorption of RET.
|  | Sub-Activity 1: Conduct a desk review and surveys/interviews to identify barriers for RET Transfer | GEC | 27000 |  |  | X | X
|  | Local Consultants |  | 21000 |  |  | X | X | [5 empty] | 21000 |  | Hiring of a consultancy team (at least two consultants with survey assistants): $21,000 ($300*70 man days)
|  | Travel |  | 4500 |  |  |  | X |  |  |  | 4500 |  |  |  | Cost of travel of members of project team to conduct surveys with consultant: DSA: $3,000 ($300*5days*2 people); transportation: $1,500 ($300*5days)
|  | Miscellaneous Expenses |  | 1500 |  |  | X | X |  |  | 1500 |  |  |  |  | Miscellaneous
|  | Subtotal 1.2.1 |  | 27000
|  | Total Output 1.2 |  | 27000
|  | TOTAL OUTCOME 1 |  | 263000
Outcome 2: Access to and use of relevant Renewable Energy Technologies (RETs) increased in Ghana.
| Output 2.1 | Activity Result 2.1.1: Selection and adaptation of appropriate RETs to be transferred
|  | Sub-activity 1: Develop criteria and standards for the selection of appropriate Renewable Energy Technologies | GEC | 31000 |  |  |  | X | [7 empty] | This activity will be jointly done with the on-site investigation, because some criteria are specific to the location where the equipment will be.
|  | Local Consultants |  | 6000 |  |  |  | X | [5 empty] | 42000 |  | 4 Chinese consultants to support Ghanaian research institutions to develop standards and criteria, 20 days each (5 before Gh, 10 in Gh, 5 after Gh), lump-sum contract: $24,000 fees ($300*4*25); $8,000 air ticket ($2,000*4); $10,000 DSA ($250*4*10). This is related to the on-site investigation too.
|  | Contractual Services /Companies |  | 4000 |  |  |  | X |  | 7500 | [5 empty] | Cost of meetings led by Ghanaian research institutions to develop the criteria and standards.
|  | Equipment |  | 20000 |  |  |  | X | 30000 | [6 empty] | Cost of equipment for research institutions needed to develop the criteria (e.g. testing facility)
|  | Miscellaneous Expenses |  | 1000 |  |  |  | X |  |  | 1500 |  |  |  |  | Miscellaneous
|  | Subtotal 2.1.1 |  | 31000
Activity Result 2.1.2: Facilities to receive, test, demonstrate and exhibit equipment and publish performance results
|  | Sub-activity 1: On-site investigation and feasibility study to select facilities for demonstration | GEC | 33800 |  |  |  | X | [7 empty] | We can short-list 3 sites per technology and conduct feasibility study to do the final selection.
|  | Local Consultants |  | 20000 |  |  |  | X | [5 empty] | 40000 |  | Cost of consultants to conduct feasibility studies in 2-3 pre-shortlisted sites for each technology: $25,800 fees ($300*86 man days); $14,000 field trips (28 days, $200 per diem, $300 fuel/vehicle); $200 incidentals
|  | Travel |  | 5000 |  |  |  | X |  |  |  | 11200 |  |  |  | Travel of 2 Government or research representatives to go to the field with consultants: $11,200 oer diem ($200*28*2)
|  | Equipment |  | 7000 |  |  |  | X | 10000 | [6 empty] | Equipment to facilitate field work.
|  | Miscellaneous Expenses |  | 1800 |  |  |  | X |  |  | 3800 |  |  |  |  | Miscellaneous
|  | Subtotal 2.1.2 |  | 33800
|  | Total Output 2.1 |  | 64800
|  | TOTAL OUTCOME 2 |  | 64800
Outcome 4: Project management and coordination structures established
| Output 4.1 | Activity Result 4.1.1: Set up PMUs in both Ghana and China
|  | Sub-activity 1: Prepare stakeholder list and identify PMU members | ACCA 21 /GEC | 0 | X
|  | Sub-activity 2: Establish PMU with required documentation and terms of reference | ACCA 21 /GEC | 0 | X | X
|  | Sub-activity 3: Convene regular meetings for work plans, project monitoring, implementation and other discussions | ACCA 21 /GEC | 2000 |  | X | X | X
|  | Miscellaneous Expenses |  | 2000 |  | X | X | X |  |  | 5000 |  |  |  |  | Miscellaneous costs for project management and coordination.
|  | Subtotal 4.1.1 |  | 2000
Activity Result 4.1.2: Set up PSCs for Ghana -China project
|  | Sub-activity 1: Prepare stakeholder list and identify PSC members | ACCA 21 /GEC | 0 | X
|  | Sub-activity 2: Establish PSC with required documentation and terms of reference | ACCA 21 /GEC | 0 | X | X
|  | Sub-activity 3: Hold PSC meetings to review project plans and reports | ACCA 21 /GEC | 5518.5 | X
|  | Miscellaneous Expenses |  | 5518.5 | [6 empty] | 20518.5 |  |  |  |  | Miscellaneous expenses for PSC meetings
|  | Subtotal 4.1.2 |  | 5518.5
Activity Result 4.1.3: Support project implementation
|  | Human Resources | UNDP Ghana/GEC | 35000 | X | X | X | X | [7 empty] | Salary of project manager: $86,400 ($1,800*48 months); Salary of project assistant: $33,600 ($700*48 months); $20,000 (contribution to salary of UNDP staff)
|  | Salary Costs |  | 35000 | X | X | X | X | [6 empty] | 140000
|  | Communication | UNDP Ghana./GEC | 1250 | X |  | X
|  | Communication/publication |  | 1250 | X |  | X | [5 empty] | 5000 |  |  | Cost of project related communication material and publicity
|  | Equipment | UNDP Ghana/GEC | 7000 | X
|  | Equipment |  | 7000 | X |  |  |  | 10000 | [6 empty] | Cost of IT equipment (laptops, printer) and furniture for PMU in Ghana
|  | Miscellaneous | UNDP Ghana/GEC | 1250 | X | X | X | X
|  | Miscellaneous Expenses |  | 1250 | X | X | X | X |  |  | 5000 |  |  |  |  | Miscellaneous
|  | Subtotal 4.1.3 |  | 44500
|  | Total Output 4.1 |  | 52018.5
TOTAL OUTCOME 4 |  | TOTAL OUTCOME 4 |  | 52018.5
|  | TOTAL 2015 BUDGET |  | 379818.5

## Sheet1
PROJECT BUDGET |  | Ghana
Award ID | 00082764
Project ID | 00091534
Business Unit | GHA10
Project Title | CHINA-GHANA SOUTH-SOUTH COOPERATION ON RENEWABLE ENERGY TECHNOLOGY TRANSFER
Implementing Partner | GHANA ENERGY COMMISSION
Outcome/Atlas Activity | Fund ID | Donor Name | Account Code | Budget Description | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Total (USD)
Outcome 1 | 30000 | 11906 (Danish Government) | 71300 | Local Consultants | 142000 | 19200 | 0 | 0 | 161200
|  |  | 71600 | Travel | 49000 | 10300 | 6400 | 0 | 65700
|  |  | 72100 | Contractual Services /Companies | 64000 | 49000 | 3000 | 0 | 116000
|  |  | 74200 | Communication/ publication | 0 | 16000 | 6000 | 0 | 22000
|  |  | 74500 | Miscellaneous Expenses | 8000 | 4700 | 400 | 0 | 13100
|  |  | Total Outcome 1 |  | 263000 | 99200 | 15800 | 0 | 378000
Outcome 2 | 30000 | 11906 (Danish Government) | 71300 | Local Consultants | 26000 | 56000 | 29500 | 38400 | 149900
|  |  | 71600 | Travel | 5000 | 43700 | 68250 | 38500 | 155450
|  |  | 72100 | Contractual Services /Companies | 4000 | 303500 | 154000 | 36000 | 497500
|  |  | 72200 | Equipment | 27000 | 53000 | 10000 | 5000 | 95000
|  |  | 74200 | Communication/ publication | 0 | 200 | 3900 | 3400 | 7500
|  |  | 74500 | Miscellaneous Expenses | 2800 | 15000 | 7250 | 5600 | 30650
|  |  | Total Outcome 2 |  | 64800 | 471400 | 272900 | 126900 | 936000
Outcome 3 | 30000 | 11906 (Danish Government) | 71300 | Local Consultants | 0 | 0 | 0 | 0 | 0
|  |  | 71600 | Travel | 0 | 0 | 0 | 0 | 0
|  |  | 72100 | Contractual Services /Companies | 0 | 0 | 0 | 0 | 0
|  |  | 74200 | Communication/ publication | 0 | 0 | 0 | 0 | 0
|  |  | 74500 | Miscellaneous Expenses | 0 | 0 | 0 | 0 | 0
|  |  | Total Outcome 3 |  | 0 | 0 | 0 | 0 | 0
Outcome 4 | 30000 | 11906 (Danish Government) | 61100 | Salary Costs | 35000 | 35000 | 35000 | 35000 | 140000
|  |  | 71200 | International Consultant | 0 | 0 | 50000 | 0 | 50000
|  |  | 72100 | Contractual services – Companies | 0 | 0 | 13000 | 0 | 13000
|  |  | 72200 | Equipment | 7000 | 1000 | 1000 | 1000 | 10000
|  |  | 74200 | Communication/ publication | 1250 | 1250 | 1250 | 1250 | 5000
|  |  | 74500 | Miscellaneous Expenses | 8768.5 | 7250 | 7250 | 7250 | 30518.5
|  |  | Total Outcome 4 |  | 52018.5 | 44500 | 107500 | 44500 | 248518.5
GHANA PROJECT TOTAL |  |  |  |  | 379818.5 | 615100 | 396200 | 171400 | 1562518.5
GMS (8% OF TOTAL PROJECT BUDGET*) |  |  |  |  | 44105.52 | 78208 | 56296 | 22872 | 201481.52
GRAND TOTAL |  |  |  |  | 423924.02 | 693308 | 452496 | 194272 | 1764000.02
|  | * Total project budget (excluding GMS) |  |  | 551319 | 977600 | 703700 | 285900 | 2518519