| EXPECTED OUTPUTS | PLANNED ACTIVITIES | BUDGET | TIMEFRAME | RESPONSIBLE AGENCY | SUPPORT AGENCIES |
| --- | --- | --- | --- | --- | --- |
|  |  |  | 2015 | 2016 |  |  |
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  |
| OUTCOME 1: Assets, needs and priorities for enhancing local capacity for CCA and DRR are understood, including indigenous knowledge |
| Output 1.1 A report on the scientific and socioeconomic impacts of climate change and disaster risks in the three northern regions | 1.1.1: Collect and map existing efforts and information on scientific and socio-economic impacts of climate change and disaster risks in the three northern regions. |  |  |  |  |  |  |  | MoFA (PIU) | UNU-INRA FAO MEST NADMO |
| Output 1.2 A report of relevant projects, plans and policies with potential for mainstreaming CCA and DRR. | 1.2.1 Analyse existing and relevant plans and policies at the national, district and regional levels and in the food and agriculture sector to identify where CCA and DRR considerations would add value |  |  |  |  |  |  |  | MoFA (PIU) | UNDP FAO |
| Output 1.3 Profiles of selected pilot communities | 1.3.1 Collect baseline data and develop process and criteria for district and community selection |  |  |  |  |  |  |  | MoFA | UN Team |
|  | 1.3.2 Consult with national and regional stakeholders to select pilot districts, using criteria |  |  |  |  |  |  |  | MoFA | UN Team |
|  | 1.3.3 Consult with representatives in pilot districts to select pilot communities, documenting rationale |  |  |  |  |  |  |  | MoFA | UN Team |
|  | 1.3.4 Collect and map existing and relevant information regarding community capacities, needs, and priorities in order to conduct a rapid appraisal to prioritise pilot communities and develop a profile of each |  |  |  |  |  |  |  | MoFA | FAO UN Team |
| Output 1.4 Plans outlining preferred climate change adaptation measures at the community level | 1.4.1 Develop a methodology for participatory adaptation planning |  |  |  |  |  |  |  | MoFA | FAO/UNU-INRA |
|  | 1.4.2 Conduct focus groups and workshops with community members, district assemblies, and key stakeholders to identify climate change adaptation measures |  |  |  |  |  |  |  | MoFA | UN Team |
|  | 1.4.3 Support platforms for collaboration amongst key stakeholders on CCA/DRR/SLM |  |  |  |  |  |  |  | MoFA | FAO UN Team |
|  | 1.4.4 Develop an action plan in the pilot communities that outlines the list of potential CCA and DRR measures |  |  |  |  |  |  |  | MoFA | UN Team |
| OUTCOME 2: Enabling Environment for smallholders is transformed to promote CCA/DRR/SLM and gender-related principles and practices at community and district levels |
| Output 2.1 CCA and DRR mainstreamed into district development plans and related food and agriculture plans and policies. | 2.1.1 Implement mainstreaming and capacity building activities at the community level. | $10,000 |  |  |  |  |  |  | TBD | UNDP UN Team |
|  | 2.1.2 Implement mainstreaming and capacity building activities for government at the district level | $10,000 |  |  |  |  |  |  | TBD | UNDP UN Team |
| Output 2.2 Women are able to benefit optimally from all project activities | 2.2.1 Undertake gender analysis, include a Rapid Care Analysis (conduct with 1.4.2 and 2.4.1) | $15,000 |  |  |  |  |  |  | TBD | UNDP |
|  | 2.2.2 Use gender and care analysis to reduce barriers for women to engage with VSLAs and FFSs | $15,000 |  |  |  |  |  |  | TBD | UNDP / FAO |
| Output 2.3 Enabling environment for community smallholders is improved | 2.3.1 Commission consultant to create Market Maps, integrating gender and CCA/DRR/SLM principles. (conduct with 1.4.2 and 2.2.1) | $20,000 |  |  |  |  |  |  | TBD | UNDP |
|  | 2.3.2 Use Market Maps to improve the enabling environment for community smallholders | $20,000 |  |  |  |  |  |  | TBD | UNDP |
| Output 2.4 Community capacity for advocacy on CCA and DRR is improved | 2.4.1 Train target communities on advocating government on CCA/DRR/SLM issues | $10,000 |  |  |  |  |  |  | TBD | UNDP |
| OUTCOME 3: Smallholder households have the capacity to apply prevention and mitigation measures and have increased access to social economic services |
| Output 3.1 Smallholder households have enhanced adaptive capacity to climate change and disasters in terms of food security | 3.1.1 Participatory vulnerability assessment to identify 4 pilot communities and 25 FFS |  |  |  |  |  |  |  | MoFA | FAO / UNU |
|  | 3.1.2 Capacity building for the FFS facilitators on SLM, CCA and DRR/M practices |  |  |  |  |  |  |  | MoFA | FAO |
|  | 3.1.3 Establishment and implementation of FFS (including consolidation of existing FFS) |  |  |  |  |  |  |  | MoFA | FAO |
| Output 3.2 Climate change adaptation and disaster risk reduction assets developed, built or restored by 2 targeted communities. $150,000 ($75,000 per community) | 3.2.1 Conduct technical assessment of potential CCA asset (dam) sites and select feasible ones for rehabilitation/fish ponds construction/small scale irrigation. | Wa West fish ponds |  |  |  |  |  |  |  |  | MOFA | WFP |
|  |  | Sissala West rehabilitation/irrigation |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.2 Develop project proposal 3.2.3 Mobilize communities for actual dam rehabilitation works/fish ponds construction/small scale irrigation | Wa West fish ponds |  |  |  |  |  |  |  |  | MOFA | WFP |
|  |  | Sissala West rehabilitation/irrigation |  |  |  |  |  |  |  |  | MOFA | WFP |
|  | 3.2.4 Distribute cash incentive to project participants working on the dam/fish ponds/irrigation system | Wa West fish ponds |  |  |  |  |  |  |  |  |  |  |
|  |  | Sissala West rehabilitation/irrigation |  |  |  |  |  |  |  |  |  |  |
|  | 3.2.1.2 provide inputs for small irrigation systems to link dams to agriculture production | Sissala West |  |  |  |  |  |  |  |  | MOFA | WFP/FAO |
| Output 3.3 Vulnerable groups empowered with income generation and economic activities to diversify livelihood opportunities. | 3.3.1 Capacity building for the FFS facilitators on VSLA approach, financial and business management 3.3.2 Village Savings & Loans Associations (VSLA) approach introduced to FFS 3.3.3 Promote home-based food production - mainly vegetables, fruit and poultry from improved kitchen gardens and legume and dairy products from improved farming operations |  |  |  |  |  |  |  | MoFA | FAO |
| OUTCOME 4: Knowledge and institutional capacity for mainstreaming and implementing CCA and DRR plans, policies and measures are improved |
| Output 4.1 Knowledge product outlining processes and lessons for mainstreaming and implementing community-based CCA and DRR. | 4.1.1 Evaluate the process of mainstreaming CCA and DRR at the district level |  |  |  |  |  |  |  | MoFA | UN team |
|  | 4.1.2 Documentation of good practices, mistakes and lessons learned using the existing Technologies and practices for small agricultural producers |  |  |  |  |  |  |  | MoFA | FAO / UNU |
| Output 4.3 Effective communication of findings and outputs that lead to behavioral change | 4.3.1: Develop communication materials for multiple channels that ensure findings and outputs of the programme are communicated and utilized. |  |  |  |  |  |  |  | MoFA | FAO with support of UN team |
|  | 4.3.2: Key messages disseminated to stakeholders, development partners and government agencies using a variety of communication strategies. |  |  |  |  |  |  |  | MoFA | FAO with support of UN team |