|  | SAMPLE QUARTERLY/ANNUAL REPORTING FORMAT |  |
| --- | --- | --- |

- BACKGROUND AND INTRODUCTION:

Project Title: Consolidating Peace in Ghana

Though Ghana has long been lauded internationally, as a safe haven in an otherwise troubled sub region, the National Peace Council, which is mandated to facilitate and develop mechanisms to prevent, manage, resolve and build sustainable peace in the country, recognizes that the country’s peace cannot be taken for granted, and all efforts must be made to consolidate it. Civil rebellion and wars that have affected most countries in the sub-region tend to spill across borders, hence the need to protect what peace we have. Consolidating Peace in Ghana is based on the premise that change can be created through a simultaneous emphasis on building the capacities of rights-holders and duty-bearers to partner effectively, thus reducing conflict. Effective partnerships will in turn improve the performance of government at all levels, with consequent improvements in human development and security.

- PURPOSE & OBJECTIVES:

Key national institutions of democracy are effective, accountable, gender responsive and promote peace inclusive governance, human security with focus on vulnerable groups, by 2016

- EXPECTED OUTCOME(S):

National Peace Architecture and Conflict Prevention Mechanism Institutionalised and functional

- REPORTING PERIOD: January 2015 to June 2015

| OBJECTIVE |  |
| --- | --- |
| Expected Output | Planned | Actual (Achievements) | Variations (Outstanding) | Reasons | Recommendations |
|  | Activities | Budget ($) | Activities | Disbursed |  |  |  |
| Support to the NPC/RPC to enable them mediate in at least eight actual or potential conflicts | Organise training sessions in conflict prevention and mediation for the boards of the NPC/RPCs to enable them mediate in 8 actual potential interventions Support mediation interventions Create platform for launching of peace fund | 50,000 | Training of 3 RPCs (Volta, Central and Western) Summit on religious tolerance and freedoms Stakeholder consultation on the lunch of the peace fund | (20465) 9,576.00 (1,558) | 40,424 (18,401) | Most of the activities here will be done in the third and fourth quarters | There will the need to increase the budget allocation for this component |
| Strengthen the capacity of traditional/religious leaders in conflict prevention and resolution | Develop training materials and peace brochures/flyers for conflict transformation Fashion out a structure for the effective running of the modular course on conflict prevention and resolution for traditional/religious leaders Create a plateform for trad/religious leaders to share experiences in conflict prevention dn resolution | 85,000 | Consultation with Manyhia Stakeholders’ consultative meeting On developing training Modules Development of training modules underway (UCC) | 24,614.00 | 60,386 | Extensive consultation so as to give the training a national identity and acceptability | There has been suggestion there might be the need to organise separate training for tradition and religious leaders |
| Strengthen the capacity of actors in peace architecture for the prevention and management of electoral violence | Train actors of the peace architecture to enable them contribute to a peaceful 2016 general election | 40,000 |  |  | 40,000 | This activity has been slated for the last two quarters of the year |  |
| Conduct research and assessment to promote knowledge about conflict prevention modalities and create opportunities for conflict transformation | Develop and implement Small Arms and Light weapons baseline survey Research into new and emerging peace and security threats in the country | 50,000 | Mapping of small Arms and Light Weapons Proposal have been received and the Council is in the process of awarding a contract to an expert to carry out the research | 10,090 | 39,910 | The large of this budget will be allocated to the research which will initiated in the third quarter |  |
| Enhance women’s role in conflict prevention and resolution and management through support to the implementation of UNSCR/GHANAP 1325 | Advocate for increased women and youth participation in peace building and mediation in 7 potential or actual conflict zones by 2016 | 30,000 |  |  |  |  |  |

- EMERGING ISSUES AND LESSONS LEARNT (OPPORTUNITIES & CHALLENGES)

- There is the need to encourage the NPC Board to work with the RPCs to enable them learn from the experience and skills the Board members have acquired.

- RPCs need financial and logistical support in their mediation efforts

- PLANNED ACTIVITIES AND BUDGET FOR NEXT QUARTER

| Expected Output | Planned |
| --- | --- |
|  | Activities | Budget |
| Support to the NPC/RPC to enable them mediate in at least actual and potential conflicts | Training for RPCs (Upper East, Upper West, Northern, BA, Ashanti and Eastern Regions) Support to mediation intervention (Bawku Inter-Ethnic Peace Committee) | 46511 10500 |
| Strengthen capacity of trad/religious leaders in conflict prevention and mediation | Development of training manuals and course outline | 22000 |

7.0. FINANCIALS

| TOTAL AMOUNT RECIEVED THIS QUARTER | TOTAL AMOUNT RECIEVED TO DATE (CUMMULATIVE) |
| --- | --- |
| 9576 | 47988 |

8.0 PROGRESS TOWARDS ACHIEVING AWP OUTPUTS FOR THE YEAR

| Indicators | Baseline | Achievement as at 2014 | Achievement as at …….. | Remarks |
| --- | --- | --- | --- | --- |
|  |  |  | Target | Achievement as at end of reporting period |  |
| No. of conflicts that the NPC, and RPCs intervene directly on | The NPC has intervened in 6 conflicts (1n 2014) | Intervention in 6 conflicts | The NPC/RPC intervenes in at least 2 new conflicts in addition to the previous 6 conflict by the end of 2016 | 5 conflicts (Bawku, Dagbon, Bimbilla, Nkonya-Alavanyo, Hohoe ) | Most of these processes started last year and have continued into this year |
| No. of trad/religious leaders trained | Traditional authorities lack the requisite skills to mediate in conflict | No elaborate training targeted trad. leaders | Train 30 trad./religious leaders to intervene in at least 2 conflicts by end of 2016 | Consultation and planning stage | Actual training to begin by October 2015 |
| Lack of capacity to intervene in conflicts | Actors in the peace architecture lack the capacity to intervene in conflicts | Some limited training were organised for some peace actors | Capacity of at least 50 peace actors built | Training yet to be initiated | First two quarters were dedicated to the RPCs and traditional leaders |

# Footnotes

Revised - 27/07/10