GOVERNMENT OF THE REPUBLIC OF GUINEA

United Nations Development Programme

Other Partners: Global Environment Facility, World Bank, UNESCO/World Heritage Centre, German Techincal Co-operation (GTZ), European Union (PACV), French Development Agency, FAO/International Fund for Agricultural Development (IFAD),

Japan, Fauna & Flora International (FFI)

Conservation of the Biodiversity of the Nimba Mountains through Integrated and Participatory Management

# TABLE OF CONTENTS

TABLE OF CONTENTS	2

ACRONYMS	3

SECTION I:  PROGRAMME NARRATIVE	5

Part 1.  Situation Analysis	5

1.1	Biophysical setting	5

1.2  Economic context and anthropogenic pressures in the Upper Cavally Basin.	6

1.3  Policy and legal contexts and relevancy to national projects and programmes	7

1.4  Threats to and causes of biodiversity loss in the NMBR	8

1.5  Institutional framework for managing the Upper Cavally Basin	10

1.6   Programme beneficiaries	12

Part 2.   Strategy	13

2.1 National strategic framework	13

2.2 United Nations framework and objectives of UNDP support	13

2.3 Partnership	13

Part 3. Management Arrangements	14

3.1  Programme Preparation and Planning	14

3.2  Programme Implementation	14

Part 4. Monitoring and Evaluation.	16

4.1  Programme monitoring and evaluation provisions	16

4.2  First internal phase	16

4.3  Second internal phase	17

4.4  Third internal phase	18

Part 5.   Legal Context.	18

References Cited:	19

SECTION II.  TOTAL WORK PLAN AND BUDGET	20

Part 1.  Logical Framework, including Expected Outcomes, Indicators of Success, Objectively Verifiable Indicators and Associated Costs.	20

Part 2.  Schedule of Activities (9 years).	35

SECTION III.  OTHER AGREEMENTS	43

Part 1.  Additional Agreements.	43

Part 2.  Annual Work Plan.	44

SIGNATURE PAGE	77

ANNEXES	78

Annex 1 – Comments from GEF Council members to the project brief; responses to comments	79

Annex 2 - Monitoring and Evaluation Plan	83

Annex 3 – Nimba Mountains Stakeholder and Public participation plan	88

Annex 4 – Table Indicative Monitoring and Evaluation Work plan and corresponding Budget	100

Annex 5 – Programme Structure	102

Annex 6 – Summary of information for selected protected areas:  data sheet	103

Annex 7 – TOR of the project staff and consultants	113

Annex 8 – TOR of the steering committee	128

Annex 9 – Brief document approved in May 2003

Annex 10 – Co-financing letters

# ACRONYMS

AFD			: 		French Development Agency

AGADEME 		:		Guinean Society for Support to Integrated Development of

Small Animal Husbandry

AGIR			:		Support Programme for Integrated Resource Management

AHSP			: 		Animal Husbandry Support Programme

APR			:		Annual project report

CCA			:		Common Country Assessment

CIDA			: 		Canadian Agency for Development International

CEGEN 		: 		Centre for the Management of the Environment of the

Nimba Mountains

CI			: 		Conservation International

CITES			:		Convention on the International Trade in Endangered Species

CNE			:		National Environmental Council

CO			:		Country office (of UNDP)

CRBREIG		:		Cane Rat Breeding, Research and Extension Institute of

Guinea

EIA			:		Environmental Impact Assessment

ERIB 			: 		Environmental Research Institute of Bossou

FAO			:		Food and Agricultural Organisation of the United Nations

FFEM 			: 		French Global Environment Facility

FFI 			:		Fauna & Flora International

GEF 			: 		Global Environment Facility

GIS 			: 		Geographical Information System

GNP 			: 		Gross National Product

GTZ 			: 		German Technical Co-operation

IEC			:		Information-Education-Communications

IFAD			: 		International Fund for Agricultural Development

IFAN			:		French Institute for Black Africa

IR			:		Inception report

IUCN			:		World Conservation Union

KfW			:		German Financial Co-operation Agency

LADP			:		Letter of Agricultural Development Policy

M&E			:		Monitoring and Evaluation

MAB			: 		Man and the Biosphere

METT			:		Management Effectiveness Tracking Tool for protected areas

MIFERGUI		: 		the Guinean Iron Mining Company

MTE			:		Mid-term evaluation

NC			:		National Co-ordinator

NDA			:		National Directorate for Agriculture

NDE			:		National Directorate for Environment

NDH 			: 		National Directorate for Health

NDL			: 		National Directorate for Livestock

NDSTR		:		National Directorate for Scientific and Technical Research

NDWF 			: 		National Directorate for Water and Forests

NEAP 			: 		National Environmental Action Plan

NEX			:		National execution (a UNDP  implementing arrangement)

NGO 			: 		Non-Governmental Organisation

NMBR			:		Nimba Mountains Biosphere Reserve

NPA			:		National project administrator

NTFP			:		Non-timber forest product

PACV 			: 		Village Community Support Programme

PDF-B 			: 		Project Development Facility - Block B grant

PDPEF/GF	:	Project for the Development of Small-scale Forest Inhabitants in Forested Guinea

PDSFI 			:		Project for the Development of Small-scale Forest

Inhabitants in Forested Guinea

PIR			:		Project implementation review

PPNM			: 		Pilot Project for the Nimba Mountains

PROGEFOR		:		Forest Resources Management Project

PRSP			:		Poverty reduction strategy paper

RDC 			: 		Rural Development Commune

RRMP 			: 		Rural Resources Management Project

TOR			:		Terms of reference

TPR			:		Tripartite review

TTR			:		Terminal tripartite review

UNDAF		:		United Nations Development Assistance Framework

UNDP 			: 		United Nations Development Programme

UNESCO 		: 		United Nations Educational, Scientific and Cultural

Organisation

UNHCR		: 		United Nations High Commission for Refugees

UNV			:		United Nations Volunteer

USAID 		: 		United States Agency for International Development

UVIDoZ	: 	Union of Volunteers for the Integrated Development of Zantompiézo

WFP 			: 		World Food Program

WWF			:		World-Wide Fund for Nature

ZOPP	: 	Ziel Orienttierte Project Planung (German abbreviation for Planning of Interventions by Objective)

# SECTION I:  PROGRAMME NARRATIVE

## Part 1.  Situation Analysis

### Biophysical setting

- The Nimba Mountains Biosphere Reserve (NMBR) extends over 145,200 ha and corresponds to the Guinean portion of the Cavally River Basin (Upper Cavally River Basin). Following the classic biosphere reserve model, whose objective is to integrate conservation of globally significant biological resources with human activity using an integrated, participatory approach, the NMBR is zoned into three land-use categories, namely a transition area (88,280 ha) where land uses are monitored, a buffer zone where land-uses are strictly controlled (35,140 ha) and a cluster of three strictly protected core areas:  the Bossou Chimpanzee Hills ecosystem (320 ha), the Déré Forest (8,920 ha) and the Guinean section of the Nimba mountain range that is a World Heritage Site (12,540 ha). This last area is contiguous with Côte d’Ivoire and Liberia (see Annex 12 – Project brief approved by the GEF Council – the map of the region (Annex 15 to the brief) as well as Annex 8 to the brief for details description of the programme site).

- The ecosystems of the NMBR are home to about 85% of the species that comprise the biological diversity of Guinea, which boasts 2,835 animal species including 107 mammals, 72 bird species, 58 reptile species, 45 amphibious species, 38 fish species, 38 mollusc species, 2408 insect species, 31 myriapod species, 17 scorpion species, 18 acarid species, 17 species of daddy long-legs and 46 species of annelids (Bangoura, 2001). Among these are high-altitude species living in areas characterized by average temperatures at least 6°C below those of surrounding lowlands, and a rigorous dry season followed by a rainy season with constant high humidity. The Déré Forest contains climax vegetation types of great botanical diversity that have been relatively well preserved for a long time (Von Droste et al., 1993). In the NMBR one finds many rare plant and animal species that are endemic or have almost vanished from the Upper Guinean Forest Ecosystem due to forest clearance and hunting, and which have been conserved in the Reserve because of its mountainous nature and, in places, lateritic soils. This is the case for the Nimba otter-shrew (Micropotamogale lamottei), the western chimpanzee (Pan troglodytes verus) and the viviparous toad (Nectophrynoides occidentalis), which are all on the IUCN Red List.  This last species, which lives tucked away in clay openings in the rock during the dry season, is a rare case of adaptation to the convex summit of the Nimba Massif, which lacks any year-round sources of water. The chimpanzees use stone tools and, according to oral tradition, live in harmony with the indigenous people of Bossou (the Manons), who consider them as sacred. Despite forest clearance and human population growth, the population of chimpanzees has increased to 27 individuals, as of November 2001.

- The Nimba Mountain Range is also unique for its beauty and unusual landscapes.  It has  a highly contrasting set of climatic influences due to a confluence of factors including geographic location, altitude and orientation, which are critical elements shaping climatic conditions. All of these factors and many others explain the successive classification of the Nimba range as a Strict Nature Reserve in 1944, a Biosphere Reserve in 1980 and a World Heritage Site in 1981.  Annex 8 of the Project brief (Annex 12 of this ProDoc) gives full details on the environmental context of the Nimba Mountains Biosphere Reserve.

- In addition, the biological diversity of the Nimba region in the plains, hillsides and forests, provides local populations with food, energy, water, medicine, shelter, agricultural land, oxygen, etc.  It is considered the resource that can stimulate economic growth and guarantee the welfare of local people.

### 1.2  Economic context and anthropogenic pressures in the Upper Cavally Basin.

- In 1984, at the end of the First Republic, Guinea opted for a development model based upon liberal economic policy. As a result of this policy, several economic trends took shape, including the formation of farmer co-operatives/groupings, reforms specifying land rights, readjustment of prices, those of agricultural products in particular, a revival of agricultural research, an increase in agricultural yields, collaborative management of biodiversity resources, improvement of sanitary conditions and poverty reduction (Letter of Agricultural Development Policy, 1997; Strategy for Poverty Reduction, 2000; Guinea, Vision 2010). In 1998, the Guinea’s debt represented 102% of GNP and its debt-servicing ratio was 19.5% of exports of goods and services (UNDP, 2000).  Thus a large portion of the country’s budgetary resources and foreign exchange goes directly to servicing the debt.  In order to maintain, diversify and increase its sources of hard currency, the Guinean government envisages extraction of the rich iron deposits of the Nimba and Simandou Mountains.

- Iron mining in the Nimba Mountains could bring social benefits at the national level as well as at the local level by providing direct and indirect employment, bringing improvements in infrastructure and social services, and having a positive effect on local and regional governance (see paragraph 9 of Annex 12 – GEF project brief).

- Poverty persists in the Basin, where inhabitants live dispersed in nearly 100 villages. In 1992 the estimated population was 59,000 inhabitants; the average density being s approximately 97 inhabitants/km2 in the zone. This is in the context of areas of habitable land versus areas unsuited to cultivation such as the lateritic savannahs and the Reserve’s core areas (Pascual, 1993; Dore, 2001). High infant mortality plagues the region, due to malnutrition and insufficient caloric intake as well as to kwashiorkor, measles, tetanus, yellow fever, malaria, whooping cough, diarrhoea, and meningitis. Safe water supply sources are inadequate and prophylactic and hygiene services are insufficient, underscoring the need to maintain healthy vegetative cover in the upper watersheds of rivers supplying the area, especially of the World Heritage Site. Access to education is inadequate and discriminatory, favouring boys over girls.

- In spite of the preceding, population growth in the Basin is high, about 4.1% per year, a rate higher than the national average of 3.1%, due mainly to in-migration. The significant agricultural potential of the area, with more than 50,000 ha of arable land, high average rainfall (>2000 mm per year), along with commercial forestry activities and the prospect of iron mining, have sparked the influx of large numbers of immigrants from sahelo-sudanese regions, most of whom are settled. Between 1990 and 1997, the wars in Liberia and Sierra Leone displaced approximately 40,000 refugees into the Upper Cavally Basin, some of whom still reside there.

- The indigenous peoples of the NMBR are the Manons and Konons, living mostly in the west and south of the Reserve along the Liberian border, and in the north and east of the Reserve along the Ivorian border, respectively (see paragraph 12 of Annex 12 – GEF project brief).

- Generally speaking, three principal internal variables characterize the evolution of the Upper Cavally Basin’s economy.  First is an increasing informal sector, particularly subsistence activities which directly impact natural resources. 80% of the resident population depends on agricultural production (see paragraph 13 of Annex 12 – GEF project brief).

- The second and third variables are trade with Côte d’Ivoire, and socio-economic networks within Guinea based on kinship, ethnicity or religion.  Commercial exchanges are significant in commodities/items such as coffee, cola nut, palm oil and various small industry products, etc.

- A closer look at local production systems shows that traditional food crop cultivation is practised on plains and hillsides by clearing forest lands, cultivating fertility declines and then letting the land lie fallow for the fertility to regenerate.  Over 52% of the surface area of the Upper Cavally Basin is cultivated. The predominant land use is upland, rained rice. Savannah patches are mostly used for livestock production, hunting, fuel wood, and non-timber and wildlife, harvesting. As stated above, 80% of the population practice agriculture, and land shortages have led to dramatically reduced fallow times (see Annex 12 for further details).

- At the local level, traditional hunting provides local animal protein.  It is practised year-round with snares, shotguns and flushing animals from hiding places.  The cane rat (Thryonomus swinderianus) is the most prized prey.  Game is destined for both household consumption and for sale (see paragraph 16 of Annex 12 – GEF project brief).

- Today, natural dense forests outside the Biosphere Reserve’s core areas have nearly disappeared, with the exceptions of a few isolated sacred groves and gallery forests along waterways.

- Eco-tourism, at the World Heritage Site and the Bossou Hills in particular, could eventually play a significant role in raising local incomes and providing a long-term, non-consumptive industry for the Reserve.

### 1.3  Policy and legal contexts and relevancy to national projects and programmes

- The Republic of Guinea is party to conventions and/or international agreements concerning biological diversity, in particular the Convention on Biological Diversity (ratified May 7th, 1993), the World Heritage Convention (1979), the Washington Convention on the International Trade in Endangered Species (CITES), the Ramsar Convention, the Convention to Combat Desertification and the United Nations Framework Convention on Climate Change.

- The National Environmental Action Plan (NEAP) was adopted by the Government in 1994. It includes a long-range vision, an implementation strategy and an action plan. The basic principle underlying the NEAP is the integration of the environmental dimension in the country’s economic and social development policies. Two major objectives are being pursued, namely sound and sustainable resource management and the definition or strengthening of sectoral policies.

- The Guinean National Biodiversity Conservation Strategy offers the following vision of biological diversity in the year 2015:  “A population, including all its socio-economic components, sufficiently informed of the values of biological diversity and the risks involved with it, and responsible and committed to the conservation and sustainable utilisation of its resources in the national and sub-regional interest, and for the satisfaction of present and future generations.”  The specific objectives of this programme (see logical framework, Section II part 1) aim to realize this vision in the NMBR.

- The programme follows also the priorities of the Guinean Government’s NEAP (1994), the 2010 Vision for Guinea (2000), the Poverty Reduction Strategy (2000) and the National Development Plan (2001), all of which cite combating poverty and promoting good governance for sustainable human development as overarching goals.  All of these are major concerns of the current programme and of the financial partners of Guinea, such as the World Bank, USAID, the French Development Agency (AFD) and the Canadian Agency for International Development (CIDA). The programme also follows the logic of the Letter on Agricultural Development Policy (LADP, 1997) whose principal objectives are an “increase in animal and crop production (specifically rice which is the basis of national food security), the rational utilisation of natural resources (land, forests and water) and protection of biodiversity”.

- From 1958 to 1984, the State was the sole owner of land and of biodiversity resources.  Since 1984, land ownership policy has aimed to return land to those who cultivate it, consequently reintroducing the notion of private property into the agricultural economy (Condé, 2001). In the Upper Cavally Basin access to land is generally governed by customary rights.  This system is incompatible with the provisions of the private land and property ownership code instituted in 1992, and individual acquisition of land is a source of conflict.  This conflict is intensified by arable land becoming scarce.

- The legal bases for community participation in Guinean law are found in the Forestry Act, the Wildlife and Hunting Act and the Land Tenure and State Property Act (Code foncier et domanial).  However these acts are not adequately implemented because the corresponding specific laws and regulations for their execution have never been published (see Annex 12 – Project brief, Annex 9 – for lessons learnt on this issue).

### 1.4  Threats to and causes of biodiversity loss in the NMBR

- Guinea had an annual deforestation rate of 5% between 1990 and 1995 (World Bank, 1999).  Although the numbers are unavailable specifically for the Upper Cavally Basin, local stakeholders agree that it is rapid there (ZOPP,  2001).  Species such as the pygmy hippopotamus, the buffalo (Syncerus caffer nanus), the leopard (Panthera pardus), the bushpig (Potamochoerus porcus) and many duikers (Cephalophus niger, C. dorsalis, C. manticola maxwelli, C. zebra, etc.), are threatened with extinction (Lamotte et Roy, 1998; Hamel, 2000).

- There are numerous, mutually reinforcing causes for the loss of biological diversity. Agricultural expansion is considered the primary cause of forest ecosystem degradation, with population growth as its root cause (Condé, 2001; Camara, 2001; ZOPP, 2001). Considering the annual population growth rate of 4.1%, in theory the population of the Upper Cavally Basin should increase from 59,000 in 2001 to over 83,000 in 2011 (end-date of this programme).

- Other factors influencing the Nimba Mountains Biosphere Reserve include the limited quantity of arable land, increasingly degraded soils, impoverishment of vegetative cover along the mountain gradient (forests, savannahs, bush), differential impoverishment of forests in the uplands, low agricultural yields, inappropriate agricultural techniques, low incomes, abusive logging, institutional weaknesses, poverty and a strong dependence on natural resources and low technology levels.  For more details, see the problem tree, Annex 1 of the GEF project brief (Annex 12 of this document).

- The proximate threats to the biodiversity in the Guinea Upper Cavally Basin, which is what defines the limits of the NMBR, are:

- Rapid expansion and degradation of arable land. Agricultural production per farm is insufficient. This results from relatively modest l farm sizes and from low yields.  The surface area cultivated per farmer remains small since it is limited by labour intensive techniques. Low-lying zones under irrigated cultivation are exposed to violent floods when watersheds are cleared of forest cover.

- The decline in soil fertility and topsoil loss resulting from deforestation and reduced fallow periods are aggravated by the absence of alternative agricultural practices. Yields are further reduced by crop damage from straying free-ranging livestock, bush fires (degrading forests and savannah alike) and several agricultural pests and organisms like stink bugs and invasive plants. Fires are more intense in degraded forest cover, and the ecological changes resulting from deforestation (forest fragmentation, discontinuity of forest patches) favour the propagation of the above-mentioned pests and organisms.

- Over-utilisation of fauna and game. The local population is malnourished in part because its income and crop production are low, and in part because of low outputs from domestic animal husbandry.  The resulting protein deficiency, for which farmers are unable to compensate by buying domestic animal protein on local markets, is exacerbated by the decreasing quantity and quality of traditional sources of animal protein, namely game, fish and small animals collected in the wild.  This spurs hunters to poach in the core areas, where game is more abundant but biological diversity is further threatened. The increasing scarcity of these wildlife resources results from a loss of habitat, and from excessive hunting pressure, due to both low incomes and high population growth, which increases malnutrition.

- Potential abusive forestry. Abusive and excessive tree-cutting is due mainly to industrial timber harvesting, which directly opens up and degrades the forest and facilitates agricultural encroachment into forested areas.  Tree-cutting for local purposes, essentially for fuel wood, is thought to have a negligible impact because wood collection occurs principally in fallow land and in areas being cleared expressly for agriculture.

- Potential threat from mining activities. Mining constitutes a real threat although it could constitute potential opportunities to the Reserve.  Prospecting which took place in the 1970s introduced exotic plant species to the site (Melinis multiflora and Dissotis grandiflora) which are already colonising the northern portion of the massif (Lamotte 1998, cited in Bangoura, 2001). Any further mining will certainly degrade the areas set aside for extraction and mining infrastructure, as well as potentially speed up alien invasive species expansion, and erode fragile slopes and watersheds.

- The root causes of the above threats include:

- Low incomes. Farmers’ incomes remain minimal due to low agricultural production, and because local production is sold at low prices. Low sales prices are the consequence of inter-linked factors including farmer isolation due to mediocre road infrastructure, weak management capacity of farmers who must deal with marketing channels organized against their interests, and difficulties in accessing credit leading to farmers becoming over-indebted to loan sharks who compel them to sell their crops prematurely. Non-agricultural sources of revenue are insufficient due to the isolation of the region, and the lack of any major economic motor. There are also difficulties encountered by women’s associations to develop income-generating processing activities due to these factors.

- Rapid population growth.  Population growth results primarily from immigration from other parts of Guinea and from Liberia and now Ivory Coast (refugees).  Sahelian populations thus represent a secondary wave of immigrants. Migration  effects on land scarcity are reinforced by the high dependency of this population on the land and by damaging, land-intensive production methods, while agricultural methods remain unchanged.

- Poor health conditions. The insufficient and poorly diversified diet contributes to high infant mortality rates in villages.  Other direct causes of poor health are inappropriate hygiene practices and degradation of water supplies due to watershed degradation, resulting in poor access to clean drinking water. Furthermore, traditional medicinal plants and traditional medical knowledge are fast disappearing.

- Unmet educational needs. Access to education was identified along with health as a major social problem in the NMBR.  The illiteracy rate is high and results from the low rate of children going to school and weak efforts to teach literacy, in particular among girls.  The reasons identified for the low school enrolment rate are the scarcity of schools and the predominance of low incomes, which also cause high drop-out rates.

- Land tenure conflicts. In a situation of scarcity of arable land, tenure conflicts are inevitable. Land competition pits farmers against one another, inciting them to cultivate even if only minimally in fallow land for fear that it could be taken away from them.  Fear of losing land rights thus contributes to rapid agricultural expansion in remaining forests since farmers are in effect engaged in a race for unclaimed land.

- Decline in traditional conservation knowledge and techniques. There is evidence of a decline in traditional systems of forest and wildlife conservation, such as sacred groves, regulation of access or use through taboos, and crop rotation strategies. This is due to the increasing competition for resources, and poverty of local communities, and the inability of traditional learning systems to sustain themselves under present circumstances.

- Institutional factors.  Weak management capacities of organisations such as the Centre for the Management of the Environment of the Nimba Mountains (known by its French acronym ‘CEGEN’), the inadequate legal framework and the lack of synergy among diverse stakeholders and local institutions are all contributing to a lack of capacity to address the threats and root causes mentioned above.  For example, institutional weaknesses are causing difficulty in achieving harmonious co-management among local residents of the Bossou Hills regarding their chimpanzee community, with evidence of threats to the latter.

- CEGEN suffers in particular from insufficient management capacities and from the fact that not only do institutional roles remain poorly or inappropriately defined in law, but in practice they are either unknown or not respected, CEGEN and other agencies operating in the NMBR have inadequate information on the state of the environment and biodiversity, as well as a good understanding of the links between healthy biodiversity, human welfare and directed interventions for change.  CEGEN suffers chronically from limited and insecure financial resources. Without financial security it cannot fulfil its mandate at the Reserve.

### 1.5  Institutional framework for managing the Upper Cavally Basin

- There exist several institutions established more or less recently that are responsible for the management of natural resources in the Upper Cavally Basin.  The comparative advantages of these potential stakeholders in the participatory management of these resources and the eventual benefits they can bring have been assessed for the proposed programme.

- First and foremost, CEGEN is the agency with statutory responsibility for managing the NMBR and for co-ordinating the different activities led by specialized sectoral agencies. Its official responsibilities and limited present capacity are summarized in Annex 12 – GEF project brief, paragraph 27 and Annex 13.

- Managing forestry is the responsibility of the Directorate of Water and Forests, which is part of the Ministry of Agriculture. Guinea has a Tropical Forestry Action Plan which was under implementation in Forested Guinea or “Guinée Forestière” at the time this programme was elaborated.  However, it had no significant impact in the region. While the Forestry Act is sound, enforcement of its provisions and of the technical specifications of concession agreements by the Directorate of Water & Forests has been seriously undermined by the lack of logistical means, the low motivation of numerous civil servants and loopholes allowing loggers to operate outside of normal concession agreements.

- Rural Development Communes (RDCs) prepare and implement local development plans, for example installing social and economic infrastructure at the community level.  Decentralized national services are responsible for implementing sectoral and national government policies and programmes at the local level. Of importance for the management of the NMBR are the National Directorates for Water and Forests (NDWF), for Scientific and Technical Research (NDSTR), for Livestock (NDL), for Agriculture (NDA), for Environment (NDE) and for Health (NDH).  In addition, organisations and institutes under the administrative authority of the above Directorates, such as the Environmental Research Institute of Bossou (ERIB – Institut de recherche environnementale de Bossou), the Forestry Centre of N’Zérékoré, the Environmental Documentation Centre (N’Zérékoré) and the Cane Rat Breeding Research and Extension Institute of Guinea (IRVAG - Institut de Recherche et de Vulgarisation de l’Aulacodiculture en Guinée), as well as other development partners (IFAD, UNHCR, GTZ and various other projects, etc.), also pursue development activities with the RDCs in the Reserve.

- Tri-national meetings were held (Sept. 2001 and Feb. 2002) between CEGEN and its partners in Côte d’Ivoire and Liberia, and were promising:  they have extended awareness of and opened dialogue on integrated environmental management in the three countries - Guinea, Liberia, Côte d’Ivoire - sharing the Nimba Mountains (Annex 12, GEF project brief, see paragraph 30 and Annex 12).

- The private sector is pursuing intensive activities in the Upper Cavally Basin, exerting strong pressure on elements of the Nimba Mountains’ biodiversity.  Due to the size of their potential investment, the mining partners will heavily influence the future of the region. A draft Agreement (known as the “Nimba Convention”) was formulated in 2001 and signed in May 2003 by the Minister of Environment. Part of the terms of this convention are that the Mining Consortium will undertake to contribute at least $500,000 per year to a Foundation or Fund, and that these resources will be used for both strengthening the protected area system in Nimba as well as for undertaking sustainable development activities. Furthermore, the Convention calls upon the Mining Consortium to provide an advance as soon as signature of the Convention is signed (see Annex 12, GEF project brief Annexes 10 and 11).

- Civil society organisations, in particular the Union of Volunteers for the Integrated Development of Zantompiéz (UVODIZ - Union des Volontaires pour le Développement Intégré de Zantompiéz), the Guinean Society for Support to Integrated Development of Small Animal Husbandry (AGADEME - Association Guinéenne d’Appui au Développement du Mini-élevage Intégré) and the Regional Federation of Livestock Breeders of Forested Guinea (Fédération Régionale des Éleveurs de Guinée Forestière) are also active in the greater Nimba Mountains ecosystems.

- Since the mid-twentieth century, the Nimba Mountains Biosphere Reserve has been the object of many scientific studies, carried out principally by the French Institute for Black Africa (Institut Français d’Afrique Noire), and today by the Primate Research Institute of Kyoto (Japan) and by Guinean and international researchers.  Amongst these studies, seventeen projects were conducted on the chimpanzees of Bossou under the direction of Professors Y. Sugiyama and T. Matsuzawa, who contributed to the creation of ERIB.

- In order to strengthen Guinean capacity to manage biodiversity, 32 Guinean students were trained under the Pilot Programme for the Nimba Mountains (PPNM) in the fields of biology, sociology and geography.  But the public and parastatal sectors have strict limits to the numbers of staff they can hire and many technically trained people have sought employment unsuccessfully for years, even when there is so much to be done.  In terms of skills available in the region, extension agents from the Directorate of Water and Forests received training through seminars, workshops and symposia organized by projects active in the region:  the Forest Resources Management Project (PROGERFOR - Projet de gestion des ressources forestières), the Rural Resources Management Project (RRMP - Projet de gestion des ressources rurales), the Project for the Development of Small-scale Forest Inhabitants in Forested Guinea (PDPEF/GF - Projet de développement des petits exploitants forestiers en Guinée forestière), the AGIR Programme (Appui à la gestion intégrée des ressources) that contributed to training guards at the Dalaba Centre, etc.

- At the national level, the National Directorate of Environment, under the Ministry of Environment, is responsible for the management of the environment and the implementation of activities conducted within the framework of the international conventions ratified by the Government of the Republic of Guinea, including in particular the United Nations Framework Convention on Climate Change and the Convention on Biological Diversity. This Ministry is legally responsible for implementing these legally binding conventions. For specific aspects, the Ministry of Environment shares responsibilities with the Ministries of Agriculture and Livestock, Fishing and Aquaculture, and the Ministry of Planning and the Ministry of Cooperation. A National Environment Council (CNE - Conseil National de l’Environnement), an intersectoral coordination entity, had been designed to ensure the sustainability of the development path but was not operationalized due to a lack of information and awareness of the designated members and, mainly, a lack of financial resources.

### 1.6   Programme beneficiaries

- According to the programme support document, the major beneficiaries of the activities planned include:

- the population of the NMBR, in particular those around the three core areas and especially youth, poor women and other targeted groups,

- relevant departments of the Ministries responsible for Environment, Health, Water, Agriculture and Livestock,

- the programme’s Steering Committee and CEGEN,

- the NGOs and organisations strongly involved in the fight against poverty and environmental protection, and

- micro-finance institutions.

## Part 2.   Strategy

### 2.1 National strategic framework

- The National Biodiversity Strategy and Action Plan approved by the Government in 2001 offers a global vision over 15 years. It defines a framework for action at all levels which should create the necessary conditions to improve the national capacity to ensure the productivity, the diversity and the integrity of the natural ecosystems. Its objective is conservation, the sustainable use of biological diversity and the strengthening of international cooperation for the equitable sharing in the benefits for such use. The National Biodiversity Strategy and Action Plan incorporate the specific guidelines contained in the PRSP (Poverty Reduction Strategy Paper – PRSP, 1999).

### 2.2 United Nations framework and objectives of UNDP support

- In close consultation with the PRSP Inter-ministerial Committee, the UN System elaborated the Common Country Assessment (CCA) and the UN Development Assistance Framework (UNDAF) for Guinea.  The priority strategic orientations of the UNDAF are: supporting pacification and security initiatives in the sub-region; promoting a favourable environment for sustainable human development, and ensuring access to basic social services.  The objectives of UNDP support for the 2002-2006 period are essentially in line with the latter two UNDAF orientations.

- More specifically, and according to the general orientations of the Cooperation Framework, the support provided by UNDP to implement the National Biodiversity Strategy and Action Plan will focus on one hand on biological diversity conservation in the Nimba Mountains, and on the other, in connection with the PRSP, on local development and micro finance.

### 2.3 Partnership

- At the national level, UNDP is working in close collaboration with all national institutions concerned, i.e. the Ministry of Environment, the Ministry of Agriculture and Livestock, the Ministry of Higher Education and Scientific Research, the Ministry of Land Administration and Decentralization, the Ministry of Economy and Finance and Civil society organizations.  At the international level, strategic partnerships will be developed, in particular with UNESCO/World Heritage Centre (WHC), the French Development Agency (Agence Française de Développement – AFD), the World Bank, the German Technical Co-operation (GTZ), the European Union, Japan, FFI, IFAD and NGOs.

## Part 3. Management Arrangements

### 3.1  Programme Preparation and Planning

- During preparation and planning of the programme, UNDP-Conakry hired a national administrator and administrative support, which were housed in CEGEN, with PDF-B, UNDP and UNESCO resources.  Local consultants were then hired to carry out the background and feasibility studies.  UNDP and UNESCO hired international consultants.

- Stakeholders’ participation was actively sought through consultations, a workshop for local population awareness-raising, village meetings, consultations with the donors (AFD, FFEM, USAID, European Union, UNESCO World Heritage Centre, GTZ/KfW, Japan, Canada, World Bank), the mining partners (MIFERGUI, BHP-Billeton, Rio Tinto), the RDCs, NDWF, NDE, NDSTR, NDA, NDH, the natural resource management projects (RRMP), the local NGOs (UVODIZ, AGADEME, etc.) and international NGOs (FFI and Conservation International -CI).  In all, over 500 people participated in the preparation within the PDF-B project.

- First, thematic reports were prepared, based in particular on a literature review, consultations with the populations groups around the Reserve and the local authorities, prior work (in particular those of the PPNM), and consultations with the governmental entities and development agencies concerned.  The consultations conducted in the Nimba region included numerous informational meetings with the population and the local authorities of the Reserve and the district capital of Lola, close to the project site.  Those thematic reports were examined and approved by a steering committee consisting of representatives of the various entities concerned.

- Then, in October 2001, some 50 representatives of the RDCs, local women organizations, decentralized sectoral services of the national directorates (NDWF, NDSTR, NDL, NDA, NDE and NDH), development programmes active in the region and the PDF-B project’s national and international consultants participated in a ZOPP workshop in the Nimba Mountains to plan the programme in detail, to reinforce consensus, mutual understanding, trust and cohesion, to train and inform all stakeholders of the complexity and inter-relatedness of developmental and environmental considerations, and to construct the logical framework of the full programme.

- Additional local information meetings were held to disseminate the results of the planning process to the communities concerned. This led to written commitments from local communities via the RDCs to provide  in-kind contributions worth approximately $100,000.

### 3.2  Programme Implementation

- The programme will be nationally executed through UNDP’s standard NEX arrangements.  The GEF contribution will be handled by the UNDP country office, and executed by the Ministry of Environment via CEGEN, which will be responsible for day-to-day execution of the programme.  UNDP, as the primary implementing agency, will provide administrative and technical assistance to CEGEN. In partnership with CEGEN, it will take part in the selection and recruiting of support staff for the programme and in the procurement of equipment required to carry out the activities and obtain the outputs. It will provide advice on the elaboration of thematic reports. UNDP will be responsible for opening the programme’s bank account and for supervising the administrative and financial management of all programme activities. In addition, it is expected that the funds from the Mining Consortium will also be managed through the UNDP in a separate account until such time as the Foundation is established and an appropriate administrative procedure put in place. UNESCO, FFI and CI are expected to provide advice on research, training needs and management of the programme. Furthermore, NGOs such as FFI may be called upon in the first few years, to provide technical support to CEGEN.

- UNDP will hire a National Project Administrator according to current UNDP/GEF procedures to work alongside CEGEN Director. (S)he will work with all due autonomy and without interference by the Ministry or CEGEN’s management, although (s)he will work in close cooperation with CEGEN.  UNDP expenditures will be certified by a National Co-ordinator (NC), a senior civil servant named by Ministry of Environment from the Minister’s Cabinet and with UNDP’s approval, to oversee the programme on behalf of government. The coordinator will not receive any compensation or salary. CEGEN (for matters relevant to this programme) will report to the NC and receive instructions through the NC on behalf of Government.

- A Programme Steering Committee will provide general supervision to the initiative, acting as the overall decision-making body and approving reports, annual work plans and evaluations.  Its terms of reference (TOR) appear in Annex 8.  It will be composed of representatives of national directorates and/or decentralized sectoral services (NDWF, NDSTR, NDL, NDA, NDE and NDH) and the national GEF focal point. It will also include representatives of mining companies, ERIB, the RDCs of Bossou and N’Zoo and local NGOs (especially those involved in protecting the Nimba Mountains). The Steering Committee will also include representatives of the donors, including GEF, UNDP and UNESCO. It will meet once a year and the National Administrator (execution agent) will ensure its secretariat.

- As CEGEN does not currently have all the requisite skills needed to carry out its mandate, staff with needed skills will be recruited from elsewhere, within as well as outside the public sector.  Staff thus brought into CEGEN will be integral members of the programme execution team, and will gradually be made official members of CEGEN as the programme is implemented, until there is full integration with government structures at the end of the programme. Until such time as they are made official members of CEGEN, they will be hired by an NGO and seconded to CEGEN.  CEGEN will be supported as needed by national and international consultants, as well as UN Volunteers (UNV). The Government will take all necessary steps to make available functional premises and offices for  the programme team. In addition, it commits to provide a budget, at programme completion, covering all of the operating expenses in connection with the continuation of the activities (maintenance costs of equipment procured under the project, consumables, etc.). The financing of such activities, after project completion, will therefore be ensured via the National Budget (internal resources or national counterpart). The Government will also take the required steps to capitalize on the best practices and lessons developed by the Programme.

- In order to accord proper acknowledgement to GEF for providing funding, all projects documents should include a paragraph to explicitly require that a GEF logo appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF. The UNDP logo should be more prominent -- and separated a bit from the GEF logo if possible as, with non-UN logos, there can be security issues for staff.

- The programme will be highly participatory, not limiting itself to merely consulting relevant stakeholders.  Rather it will engage, collaborate with and empower them to carry out defined management roles in the NMBR.  Annex 3 outlines the activities and groups.

## Part 4. Monitoring and Evaluation.

### 4.1  Programme monitoring and evaluation provisions

- Programme monitoring and evaluation will be both internal and external.  Internal monitoring and evaluation will be conducted for each programme component under the supervision of the National Administrator. Each component will be monitored by the appropriate programme personnel and will include information on staff, budget and technical and administrative matters (see Annexes 5 and 7 for more details).  This system will involve regular meetings to review progress.  Monitoring and evaluation indicators appear in the logical framework (Section II, Part 1).  An institutional monitoring & evaluation system will also be put into place for CEGEN and for the technical support team which will seek to strengthen CEGEN’s capacity throughout the programme (see Annexes 2 and 4).

- During programme implementation, the results for indicators will be transmitted monthly by the managers of programme components to the National Administrator, who will then consolidate them in a summary table for the programme.  Every semester, the summary table produced will be circulated to programme partners.  In addition, once per year a monitoring and evaluation report on the past year’s activities will be produced.  Measures will be taken during the Steering Committee meetings to resolve problems encountered.

- Three external independent evaluations (two “mid-term” evaluations, one at the end of the first two internal phases, and one final evaluation) are planned in addition to annual audits. These will be conducted in line with GEF and UNDP procedures.  They will focus on five main objectives:

- Measuring impact on globally significant resources and livelihoods,

- Measuring the performance differences between what was planned and what was achieved,

- Identifying problems related to executing the planned activities,

- Proposing corrective measures and solutions and recommending (or not) that the programme progress form one internal phase to the next, and

- Extracting and documenting any more general lessons for this and other programmes.

- The project strategy, work plan, and activities may be revised to match expected goals and impacts as a result of the recommendations of the first two independent evaluations. As the programme ends, the final evaluation will result in an exhaustive report on its achievements (programme performance, impact and lessons learnt) six months prior to programme completion. The costs of monitoring and evaluation will be taken into account in the programme budget, and will be detailed during the Appraisal phase.

- Results and lessons learned from the programme will be disseminated both within the Reserve as well as through the national protected area system, the CHM of the CBD, and other relevant national and international networks. Funds will be made available for programme staff and local community leaders to participate in relevant international and regional events to share experiences and analyse impacts and results.

- The project will be implemented in three internal phases of three years each. Benchmarks are proposed, that will be evaluated during the mid-term evaluations, to trigger the programme’s transition from one phase to the next.

### 4.2 First internal phase

- The key indicators of success for this phase, and thus for the programme to progress into its second phase, relate mostly to operational accomplishments and inputs.  Indicators include:

- demarcation of the reserve’s boundaries and approval of established limits by all RDC (see Output 1.1 of the logical framework, Section II, Part 1),

- preparation of initial versions of management plans for the three core areas of the biosphere reserve (see Output 1.5),

- land-use plans focusing on agriculture as well as hunting, animal husbandry, refugee contingency plans, and non-timber forest product (NTFP) use including medicinal plants prepared for all RDCs (or relevant grouping) for the NMBR buffer zone and 50% of the transition zone (see Output 2.1),

- installation of CEGEN’s and the programme’s basic infrastructure, acquisition of technical, managerial, and monitoring skills (see Output 5.2), and

- establishment of an ecological monitoring system based on vegetation/forest cover and indicator species (see Output 5.3).

### 4.3  Second internal phase

- The key achievements of this phase will include a mix of both operational achievements and higher-level impact indicators.  It is proposed that for the programme to pass to the subsequent and final phase, the World Bank/WWF Management Effectiveness Tracking Tool (METT – see Annex 6) score increases from 39 (baseline) to at least 55, and not more than one indicator per component remains unmet and at least 10 out of the 14 indicators are met.  These indicators should be refined during the first mid-term evaluation.  Preliminary indicators include:

- populations of key ecological integrity indicator species increased by at least 10% above baseline levels within the core areas (see Output 1.2),

- at least four years of data available from the ecological monitoring system (see Outputs 1.2/5.3),

- frequency of infractions per patrol-day decreased by 50% from the baseline level of Y1 (see Output 1.3),

- the detailed environmental study of all possible impacts and eventualities from the proposed mining project is prepared (see Output 1.4),

- corrective actions taken for 100% of infractions of land-use plans by end-year 6 (see Output 2.1),

- plans to improve cultivation methods and inputs are under implementation in at least 12 villages (see Output 2.2),

- incomes from non-agricultural sources increased in beneficiary villages by at least 10% (see Output 2.4),

- 12 villages benefiting from animal husbandry support (see Output 3.1),

- abundance of target harvested wildlife species increased by 20% above year 1 baseline (see Output 3.3),

- no inhabitant further than a 2-hour walk from a functioning health centre (see Output 4.2),

- at least 60% of health centres offering traditional treatments as standard treatments (see Output 4.2),

- the development master-plan for the NMBR is approved (see Output 5.1),

- 95% of higher and middle level CEGEN staff have received at least 4 months of training according to the detailed capacity-building training plan (see Output 5.2), and

- favourable attitudes towards the Reserve and its objectives understood by at least 60% of the population older than 10 years (see Output 5.5).

### 4.4  Third internal phase

- The third and final internal phase will concentrate on continuing the activities launched during the preceding phases, on launching activities that will not yet have begun, on expanding activities to the transition area, and on consolidating the sustainability of all activities so they may continue after the programme closes.  One element of this will be the formal establishment of the proposed ‘Nimba Foundation’ or similar institution and a related sustainable financing mechanism, to be supported by contributions from the mining company when extractive activities begin, and from other sources.  It will also share lessons learned on participatory management of the Nimba Mountains’ biodiversity resources at national, sub-regional and international levels, and act as an international presence in the zone.

The logical framework (Section II, Part 2) and Annex 2 on the programme’s M&E Plan provide more detailed indicators for all three internal phases.

## Part 5.   Legal Context.

- This support document shall be the instrument referred to as such in Article 1, Paragraph 1 of the Standard Basic Assistance Agreement concluded between the Government of Guinea and the United Nations Development Programme and signed by the Parties on 13 February 1975. The host country implementing agency shall, for the purpose of Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement.

- The following types of revisions may be made to this project document with the signature of the UNDP Resident Representative only provided he or she is assured that the other signatories of the project document have no objections to the proposed changes:

Revisions in, or addition of, any of the programme annexes;

Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of inputs already agreed to or by cost increases due to inflation; and

Compulsory annual budget revisions which alter the delivery of agreed project inputs, or reflect increased expert or other costs due to inflation, or take into account agency expenditure flexibility.

## References Cited:

- Bangoura A. M., 2001.- Conservation de la biodiversité des Monts Nimba. Faune sauvage des Monts Nimba. CEGEN and UNDP, Conakry, PDF-B Project.

- Camara L., 2001.- Conservation de la biodiversité des Monts Nimba. Aspects légal et institutionnel. CEGEN and UNDP, Conakry, PDF-B Project.

- Condé B., 2001.- Conservation de la biodiversité des Monts Nimba. Etude agricole et forestière. CEGEN and UNDP, Conakry, PDF-B Project.

- Dore K., 2001.- Conservation de la biodiversité des Monts Nimba. Sociologie rurale. CEGEN and UNDP, Conakry, PDF-B Project.

- Hamel, 2000.- Biodiversité et gestion durable des ressources. CERE-7180, Gamal Abdel Nasser University, Conakry.

- Lamotte  and Roy, 1998.  Cited in Bangoura, 2001.

- Pascual J.F., 1993.- La Pauvreté : contrainte majeure de la gestion rationnelle des ressources naturelles des monts Nimba, Final report for the Nimba Mountains Pilot Project (1st part), UNESCO-UNDP, 234 pp.

- Republic of Guinea, 2001.- National Development Plan, Conakry.

- Republic of Guinea , 1994.- National Environmental Action Plan, Conakry.

- Republic of Guinea, 2000.- Interim Strategy for Poverty Reduction, October 2000, Conakry.

- Republic of Guinea, 2000.- Guinea Vision 2010. Socio-economic Development Strategy for the Horizon 2010, Conakry.

- Republic of Guinea, 1997. LADP (Lettre de Politique de Développement Agricole), Conakry.

- UNDP, 2000.- Human Development Report, De Boeck University, Paris, Brussels, New York.

- Von Droste, Lamotte M., Pascual J.F., Koechlin J., Vernet E., Mankoto S., Taal B.-M., Touré S., Koné S., Dore G., Dore C., Traoré I.-S., Cissé A. Diallo M-B. and Sylla M.  Mont Nimba (Guinée). Site du Patrimoine mondial. World Heritage Centre, UNESCO, July 1993.

- World Bank, 1999.- Human Development Report - 1998 .

- ZOPP, 2001.- Activities Planning Workshop for the Full GEF Project. Nimba Mountains. 23-24 October, 2001.  Report prepared by FFI.

# SECTION II.  TOTAL WORK PLAN AND BUDGET

## Part 1.  Logical Framework, including Expected Outcomes, Indicators of Success, Objectively Verifiable Indicators and Associated Costs.

| Intervention logic | Indicators | Source of Verification | Indicative Cost to collect Verification Data and Project Budgetary Line |
| --- | --- | --- | --- |
| Overall Programme Objective: Core areas of the Nimba Mountains Biosphere Reserve protected in a manner compatible with local sustainable development needs | Removal of the Nimba Mountains from the List of World Heritage Sites in Danger by programme end. METT score increased from 39 to at least 65 by programme end. Average income in the buffer zone increased by 10% and in the transition zone by 5% by end of programme. | UNESCO publications Ministry of Planning or intl development agency (UNDP, UNHCR, AFD, EC, other) statistics |  |
| Specific Objective 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | Forest cover restored or actively recovering (viz. Déré Forest) in 100% of degraded parts of core areas by Y9. Populations of key indicator species: Stabilised by Y4, Increased by 10% over baseline by Y7, Increased by 20% by project end. | CEGEN’s ecological monitoring system |  |
| Output 1.1. Boundaries of the core areas recognized, legalized and demarcated | Officially approved legal gazettement documents by Y3 Beacons and signposts in place along core area boundaries by Y3 All relevant RDCs (4) state their acceptance of the boundaries by end Y3 | Legal documents Reports with photos Co-management contracts and signed statements from RDCs |  |
| Activity 1.1.1. Complete the process of legalizing the Core Areas | Drafted legal gazettement documents Introduction of these documents into the approval process | Letters and documents (physical copies) | 62000 International consultant 38 000 62000 Local Consultant 15 000 62000 Contractual services - indiv. 22 000 |
| Activity 1.1.2. Demarcate the boundaries of the core areas | Fielding of demarcation teams | Mission orders, mission reports | 62000 Contractual services - indiv. 30 000 62000 Equipments (Pictograms) 20 000 |
| S/Total |  |  | Sub total 125 000 |
| Output 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages | Ecological monitoring system based on vegetation/forest cover and indicator species: Established by year 3 4 years of data by year 7 7 years of data by end of project | Data base Reports analysing the data |  |
| Activity 1.2.1. Study the impact of fires, evaluate human impacts on fire dynamics and identify appropriate management responses | Plan of research topics prepared Contracts signed with and TOR prepared for researchers Final reports prepared on study topics | Plan for research (document) Contracts and TOR (documents) Research reports (documents) | 62000 Equipments Supplies 30 000 62000 Contractual services - comp. 65 000 62000 UNV (national) 20 000 |
| Activity 1.2.2. Develop a deeper understanding of the impacts of mining activities, including those related to introduced species | Research plan prepared Contracts signed with and TOR prepared for researchers Final reports prepared on study topics | Plan for research (document) Contracts and TOR (documents) Research reports (documents) | 62000 Equipments 20 000 62000 Professional Services 60 000 62000 Miscellaneous Expenses 5 000 |
| Activity 1.2.3. Develop a deeper understanding of conservation priorities, and identify solutions with participation of local communities | Research plan prepared Contracts signed with and TOR prepared for researchers as necessary Final reports prepared on study topics | Plan for research (document) Contracts and TOR (documents) Research reports (documents) | 62000 International consultant 30 000 04000 Equipments 20 000 62000 Equipment and furniture 10 000 |
| S/Total |  |  | Sub total 260 000 |
| Output 1.3. Decrease in incursions and illegal activities in the core areas | Frequency of infractions per patrol-day decreased by: 20% by end year 3, 50% by end year 6, and 70% by end of project | Reports on the law enforcement system |  |
| Activity 1.3.1. Design, equip and organize a patrol-and -protection system | Costed, phased plan for the protection-and-patrol system | Plan (document) | 62000 Contractual services - comp. 100 000 62000 Equipment 665 500 62000 Contractual services - indiv. 15 000 62000 Support Services 60 000 00123 Support services 62000 International consultants 500 000 30 000 |
| Activity 1.3.2. Involve local populations in the protection-and patrol system | Locally agreed participation strategy and plan Contract or other formal agreement framing/permitting local participation in the protection system | Strategy/plan (document) Formal agreement (document) signed by management authority and local population representatives | 00005 Contractual services - comp. 50 000 04000 Contractual services - indiv. 10 000 62000 Local Consultant 15 000 62000 Professional services 47 800 04000 Miscellaneous expenses 20 000 00311 Equipment 486 500 |
| Activity 1.3.3. Organize cooperation with public law enforcement agents | Agreed cooperation strategy and plan Contract or other formal agreement framing/permitting local participation in the protection system | Strategy/plan (document) Formal agreement (document) signed by management authority and local population representatives | 62000 Contractual services - indiv. 10 000 62000 Travel 20 000 04000 Professional services 20 000 62000 Miscellaneous expenses 00123 Equipment 00311 Miscellaneous 20 000 40 000 50 000 |
| S/Total |  |  | Sub total 2 159 800 |
| Output 1.4. Improved compatibility of planned mining activities, and strengthened cooperation. | Detailed environmental study of all possible developments Mining Consortium contributing as expected to Foundation/Fund by end of project | CEGEN reports and EIA |  |
| Activity 1.4.1. Monitor developments in the mining project and prepare precise environmental guidelines | Functional, capable, independent monitoring system in place Environmental guidelines agreed | Contracts/TOR with those responsible for monitoring Written guidelines (document) | 04000 Local Consultant 7 000 04000 Professional services 10 000 |
| Activity 1.4.2 Monitor compliance of mining consortium to Convention and program objectives – report to Ministry as necessary | Infractions identified by monitoring system and addressed proactively (rather than reactively in response to outside criticism) | Reports prepared by monitoring system and/or CEGEN | 62000 Contractual services - comp 120 000 00311 Contractual services-comp 100 000 |
| S/Total |  |  | Sub total 237 000 |
| Output 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities | Core areas' management plan focusing on the three areas: preliminary versions by year 3, final versions by year 4. | Management plans (documents) |  |
| Activity 1.5.1. Prepare and implement a management plan for the World Heritage Site, after consultations on relevant matters with the mining project, local populations and relevant authorities in the neighboring countries, and based on data collected above | World Heritage Site management plan: preliminary version by year 3, final version by year 4, and formal approval by affected local communities. | Management plans (documents) Formal local community communiqué | 04000 Local Consultant 6 000 62000 Support Services 50 000 62000 Contractual services - comp. 100 000 |
| Activity 1.5.2. Prepare and implement a management plan for the Bossou ecosystem after consultations on relevant matters with local populations and ERIB | Bossou HillsHillH management plan: preliminary version by year 3, final version by year 4, formal approval by affected local communities. | Management plans (documents) Formal local community communiqué | 05000 Local Consultants 13 300 04000 Travel 25 000 00311 Contractual services- Comp. 300 000 |
| Activity 1.5.3. Prepare and implement a management plan for the Déré ecosystem after consultations on relevant matters with the National Directorate for Water & Forests, Côte d'Ivoire and local populations | Déré Forest management plan: preliminary version by year 3, final versions by year 4, formal approval by affected local communities. | Management plans (documents) Formal local community communiqué | 62000 Travel 10 000 62000 Miscellaneous expenses 20 000 62000 Professional Services 30 000 |
| S/Total |  |  | Sub total 554 300 |
| Output 1.6. Impacts of refugees do not affect the core areas | Refugee camps located far from core areas by year 3 Reported infractions in Core Areas not committed by refugees. Refugee contingency plan developed by year 3 | Reports of humanitarian agencies active in the area (UNHCR, WFP, etc.) and of CEGEN; refugee contingency plan (document) |  |
| Activity 1.6.1 Liaise with humanitarian agencies to ensure incorporation of environmental concerns in relief work, including siting & sizing of camps and providing appropriate employment & income-generating activities | Agreement reached with humanitarian agencies on managing environmental issues related to refugees in the NMBR | Written record of agreement | 62000 Contractual services - comp. 20 000 62000 Miscellaneous expenses 30 000 |
| Activity 1.6.2 Develop with humanitarian agencies a refugees’ contingency plan in case of future refugee movements | Contingency plan Humanitarian and CEGEN staff trained in implementing the contingency plan | Contingency plan (document) Training materials for humanitarian agency and CEGEN staff | 04000 Local Consultant 15 000 00005 Contractual services - comp. 15 000 |
| S/Total |  |  | Sub total 80 000 Sub Total Out come 1 3 416 100 |
| Specific Objective 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practises | Average revenues of farmers increased in real terms by 20% in at least 15 target villages by end of project Stabilisation of the area cultivated by the same villages by end of project. | Revenue surveys/reports of decentralised sectoral services from the region CEGEN’s ecological monitoring system |  |
| Output 2.1 Sustainable land use systems | Local communities and local government have established land use plans in year 4 across the full NMBR. Refugee contingency plans (see 1.6) take into account land use plans. | Written plans and reports of partner agencies working in the area of improving agricultural production (IFAD, AFD/PDSFI, etc.) |  |
| Activity 2.1.1. Develop a deeper understanding of the social and land-tenure constraints linked to agricultural intensification | Report on social and land tenure constraints | Reports (document) | 62000 International consultant 30 000 04000 Equipments 10 000 |
| Activity 2.1.2 Develop capacity for land use planning with local government and local communities | Land use planning training plan established and implemented. | Written training materials Reports from training | 04000 Contractual services - comp. 30 000 04000 International consultant 8 000 |
| Activity 2.1.3. Develop land use plans, either for each community, or by commune, that take into account Refugee Contingency Plans | Specific references in land use plans to refugee contingency plans | Written references (in documents) | 04000 Local Consultant 5 000 04000 Equipment Supplies 5 000 |
| Activity 2.1.4 Disseminate and enforce land use system | Land use plans distributed to all villages in the NMBR Corrective actions taken in 100% of infractions of land-use code by Y7 | Report of CEGEN and the project team | 04000 Miscellaneous expenses 40 000 04000 Equipment and Furniture 10 000 |
| S/Total |  |  | Sub total 138 000 |
| Output 2.2. Increased agricultural yields | Annual rice production per hectare sown increased by 10% on upland sites without increasing soil depletion beginning in the 4th year in beneficiary villages. Proportion of rice production from irrigated sites increased in beneficiary villages by 5% by end-year 3, 20% by end-Y6, and 40% by end of project. Sales of products other than rice increase by 25% every three years in target beneficiary villages. | Agricultural statistical reports for the prefecture and for Guinée forestière Reports of partner agencies working in the area of improving agricultural production (IFAD, AFD/PDSFI, etc.) |  |
| Activity 2.2.1. Support improvements in cultivation methods (soil improvements like soil conservation methods, fertilizers, manures and other inputs, development of low-lying areas for irrigation, introduction of improved seed varieties, etc.) | Plan agreed to introduce improved cultivation methods and inputs. Site-specific inputs provided to 5 villages by end Y3, to 12 villages by end-Y6, and to 20 villages by end-Y9. | Plan (written document) Project reports, reports of agricultural development partners | 04000 International Consult. 30 000 04000 contractual services- indiv 23 000 04000 Local Consultant 5 000 04000 Contractual services - comp 230 000 00311 Contractual services- comp. 1 093 500 00123 Contractual services- comp 110 000 |
| S/Total |  |  | Sub total 1 491 500 |
| Output 2.3 Improved incomes from agricultural produce sold for higher prices | Net sales price per kilo of rice for farmers in the NMBR, with all charges/fees deducted, increased by 15% by year 6 and 30% by end of project | Local market surveys and surveys at Lola |  |
| Activity 2.3.1. Improve understanding of marketing channels | Study completed on marketing channels for key agricultural products | Study report (document) | 04000 Local consultant 23 000 |
| Activity 2.3.2. Improve storage techniques and how produce is marketed | Local commodity storage capacity increased by 10% by year 6 and 30% by the end of project | Local surveys of agricultural production and marketing | 04000 Contractual services-comp 60 000 |
| Activity 2.3.3. Strengthen the negotiating skills of farmers’ co-ops/communes/other groupings | Prices received by local farmers of the NMBR increased by 15% by Y6 and 30% by end of project in beneficiary villages | Local market surveys and surveys at Lola | 04000 Travel 15 000 04000 Miscellaneous expenses 65 000 |
| Activity 2.3.4. Facilitate access to credit | Number of credit accounts provided increased by 30% over Y0 by year 6 and by 50% by the end of project | Data base | 04000 Grant 130 000 62000 Grant 195 000 00311 Contractual services- Comp. 100 000 00123 Contractual services-Comp 46 500 |
| S/Total |  |  | Sub total 634 500 |
| Output 2.4. Diversified income sources | Income from non-agricultural sources increase in beneficiary villages by 10% by end- year 6 and 20% by end of project | Statistical reports from the Lola Prefecture and from the decentralised sectoral services of the Ministry of Economic Planning |  |
| Activity 241. Promote local micro-industry | Representatives from all RDCs and major villages in the NMBR aware of non-agricultural options for income-generation | Workshop report and distributions materials | 04000 Miscellaneous expenses 35 000 |
| Activity 242. Encourage the introduction of simple processing technologies of agricultural produce | Non-primary economic activities piloted in 5 villages by end Y3, 12 villages by end-Y6, and 20 villages by end-Y9. | Statistical reports from the Lola Prefecture and from the decentralized sectoral services of the Ministry of Economic Planning | 04000 UNV (national) 24 000 04000 Equipment/ Procurement MFP 45 000 04000 Professionals Services 10 000 |
| S/Total |  |  | Sub total 114 000 Sub Total Out come 2 2 378 000 |

| Intervention logic | Indicators | Source of Verification | Indicative Cost to collect Verification Data and Project Budgetary Line |
| --- | --- | --- | --- |
| Specific Objective 3. Local needs for animal protein more fully met using practices that do not damage wildlife | Reduced incidence of kwashiorkor by 30% in 15 beneficiary villages by end of project. Species indicating over-hunting increasing in their natural habitats (monkeys, antelopes, large birds) by end of project | Prefectural surveys of health and nutrition CEGEN’s ecological monitoring system |  |
| Output 3.1. More productive animal husbandry, integrated with agriculture | Villages benefiting from animal husbandry support: 5 villages by year 3, 12 villages by year 6, and 20 villages by end of project. Animal protein production in beneficiary villages increased by 5% by end-Y3, 20% by end-Y6, and by 35% by end of project without any associated decrease in agricultural production | Programme activity reports Reports on animal husbandry by technical sectoral services and relevant development agencies (National Directorate for Livestock, CRBREIG, AFD/AHSP, GTZ/RRMP) |  |
| Activity 3.1.1. Develop the management skills of animal husbandry co-ops/communes/ groupings | Training/extension workshops held for at least 60 co-ops/communes/groupings made up of at least 1000 individuals | Programme activity reports | 62000 Miscellaneous expenses 55 000 4000(NGO)Contractual services-Comp 110 000 4000 Miscellaneous expenses 60 000 |
| Activity 312. Facilitate access of individuals or groups raising animals to extension services and inputs | At least 30 co-ops/communes/groups having received services and inputs for improved animal husbandry | Reports from program team and development partners | 62000 Contract services-Comp 200 000 |
| S/Total |  |  | Sub total 425 000 |
| Output 3.2. Domestication and breeding of wild animals tested and disseminated | >50% of villages in the buffer zone with technically and commercially successful wildlife husbandry initiatives underway. 10% of animal protein consumed in the NMBR, outside of wild-hunted meat, will be from local residents raising domesticated wildlife by end of project | Programme activity reports Reports on animal husbandry by technical sectoral services and relevant development agencies (Natl. Directorate of Livestock, CRBREIG, AHSP, RRMP) |  |
| Activity 3.2.1. Develop a deeper understanding of past and current efforts to raise wild animals in captivity | Report on past and current efforts to raise wildlife species in captivity | Report (document) | 04000 UNV Veterinian 38 000 |
| Activity 3.2.2. Establish animal husbandry trials for wild animals | 10 experimental trials underway to raise two wild species by end-Y3. 10 experimental trials underway to raise two different wild species by end-Y6. 15 wildlife-raising micro-enterprises launched by year 6. | Program activity reports Reports on animal husbandry by technical sectoral services and relevant development agencies (Natl. Directorate of Livestock, CRBREIG, AHSP, RRMP | 00005 Contractual services-indv 86 000 62000 Miscellaneous Expenses 27 000 62000 Professional services 20 000 |
| Activity 3.2.3. Study the technical, economic and social feasibility of these trials | 3 conclusive trials achieved for 4 species by year 6 | Program activity reports | 62000 Contractual services-indv 26 000 00005 Contractual services-indv 24 000 |
| Activity 3.2.4. Progressively replicate breeding schemes for the most promising wild animals | Workshops presenting possibilities presented to >80% of all villages in the NMBR Extension services/inputs provided to at least 50% of villages in the buffer zone and 20% in the transition area | Program activity reports Reports on animal husbandry by technical sectoral services and relevant development agencies (Natl. Directorate of Livestock, CRBREIG, AHSP, RRMP | 00005 Miscellaneous Expenses 43 700 62000 Contractuel services-comp. 112 000 |
| S/Total |  |  | Sub total 376 700 |
| Output 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner | Abundance of target wildlife species: stabilised at baseline level established by year 3, increased by 20% above baseline by year 6, and increased by 40% by end of project. Off-take of target wildlife species: stabilised by year 6, and increased by 20% by end of project. | Ecological monitoring system (see Output 5.3) Studies of hunting and consumption of bushmeat |  |
| Activity 3.3.1. Raise awareness of those who hunt or collect wildlife of the principles of sustainable management and of enforcement of relevant laws | Sustainable management principles officially adopted by at least 50% of buffer zone villages | Written guidelines for sustainable off-take and formal commitments to follow them (documents) from communities | 62000 Miscellaneous expenses 101 000 |
| Activity 3.3.2. Promote simple management practices for the most widely consumed wildlife species | Hunters and gatherers report following these management practices in at least 50% of buffer zone villages. | Surveys of buffer zone villages | 62000 Miscellaneous expenses 65 000 62000 Equipment/Supplies wild species 103 200 04000 Local Consultant 11 000 |
| S/Total |  |  | Sub total Sub Total Out come 3 280 200 1 081 900 |
| Specific Objective 4. . Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | Mortality rate for children under 5 years reduced by 20% in at least 15 NMBR villages (measured at the level of the population and not at health centers) by end of project | Reports from the National Directorate of Health |  |
| Output 4.1. Improved medical and para-medical health care | Post-treatment recovery rate in beneficiary villages increased by 15% by end-year 3, 60% by end-Y6, and 90% by end of project. Satisfaction rating by patients increased by 40% by year 3, increased by 80%by year 6, and attains a level of at least 50% by end of project in NMBR clinics | Health studies of target villages Results of satisfaction surveys |  |
| Activity 4.1.1. Support organization of focused training for medical and para-medical staff | At least 100 health workers trained, coming from 100% of all villages of 100 persons or more | Training reports | 04000 Contractual services-comp. 60 000 |
| Activity 4.1.2. Facilitate on-going access to basic medicines | At least 50% of NMBR clinics report ‘significantly improved’ supplies of key medicines/drugs | Surveys of NMBR health clinics and patients | 04000 Equipment (drugs) 50 000 04000 Equipment 20 000 04000 Local consultant 10 000 00311 Contractual services-Comp. 100 000 04000 Miscellaneous Expenses 00311 Equipment (Supplies drugs) RDC Local communities 5 000 100 000 50 000 |
| S/Total |  |  | Sub total 395 000 |
| Output 4.2. Increased access to health care | No inhabitant further than a 2-hour walk from a functioning health centre (by year 7) The cost of basic services decreased by 20% by year 6. 60% percent of health centres offering traditional treatments by year 6; 90% offering traditional treatments by Y9 | Studies on the provision of local health services |  |
| Activity 4.2.1. Contribute to the geographic coverage of health dispensaries and clinics | At least 8 health centers constructed and equipped | Project reports | 04000 Miscellaneous expenses 25 000 |
| Activity 4.2.2. Promote better complimentarity between “modern” and traditional medicines | Patients report being offered traditional cures in at least 50% of all medical cases by end-project | Surveys of NMBR health clinics and patients | 04000 Contractual services-comp. 50 000 00311 Contractua lservices-Comp. 100 000 RDC Local community 20 000 00123 Contractual services – comp 80 000 |
| S/Total |  |  | 275 000 |
| Output 4.3. Increased access to potable water | Percentage of persons living more than 500 meters from a safe water source decreased by 40% by end-year 6, and drops to <10% by end of project | Studies on local water supply (access and quality) |  |
| Activity 4.3.1. Monitor water quality in context of changes to the environment | Monitoring stations and systems operational | Reports on water quality | 62000 Contractual services-comp. 42 500 00311 Contractual services –Comp. 250 000 |
| Activity 4.3.2. Identify sources and causes of pollution and execute the needed corrective measures | Report prepared on sources and causes of water pollution, as well as remedial action, Workshop on water pollution prevention. | Report (document) Workshop report and materials to be distributed | 04000 Contractual services-comp. 10 000 04000 Professionals services 40 000 00311 Miscellaneous expenses 90 000 |
| Activity 4.3.3. Contribute to the existing network of wells, pumps and water supply systems | Installation of >20 water sources/systems of different sizes | Project reports | 04000 Contractual services-comp. 137 000 62000 Travel 15 000 00311 Contractual services-Comp. 170 000 00311 Miscellaneous expenses 80 000 |
| S/Total |  |  | Sub total 834 500 |
| Output 4.4. Improved hygiene practices | Occurrence of illnesses directly related to poor hygiene (diarrhea, tetanus, meningitis) decreased by 20% by end-year 6 and 40% by end of project Absence of cholera by end of project | Local health studies/statistics |  |
| Activity 441. Support initiatives targeting public health and waste treatment | Half of all villages without waste treatment programmes in Y0 have them underway by end-Y6; 80% of all NMBR villages have them underway by end-project | Project reports; local health studies/statistics | 00005 Contractual services-comp 30 000 RDC Contractual services-Comp 30 000 |
| Activity 442. Support education in schools and public awareness initiatives on matters of hygiene | Health awareness & educational materials distributed in at least 90% of all schools and villages in the NMBR | Project reports | 00311 Contractual services-Comp. 150 000 00123 Miscellaneous expenses 54 000 |
| S/Total |  |  | Sub total Sub Total Out come 4 264 000 1 768 500 |
| Specific Objective 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | Independent evaluations (2 mid-term evaluations and 1 final evaluation) find that CEGEN is effectively managing the programme. No activity is undertaken that works against the objectives of the NMBR and the NMBR development master-plan by end of project. | Programme evaluation reports |  |
| Output 5.1. Synergy ensured between institutions and between interventions | Development master-plan (or other planning documents) approved before year 6 CEGEN is effectively consulted on all projects in the NMBR beginning in Y3 | Master-plan (document) Minutes of inter-institutional meetings |  |
| Activity 5.1.1. Amend and complete the legal texts related to CEGEN | CEGEN’s co-ordinating role for the NMBR formally recognised in approved legal texts by Y3 | Legal texts (document) | 00005 International consultant 60 000 00005 Local consultant 10 000 00311 Equipment 250 000 4000 International consultant 30 000 |
| Activity 512. Establish and run a consultation and planning mechanism with local populations | Local consultation/planning mechanisms effectively running for every RDC or other relevant community-level division | Minutes of meetings with the target community groups | 62000 UNV (national) 30 000 |
| Activity 513. Ensure complimentarity between relevant institutions | Operational inter-agency consultative mechanism for the NMBR | Minutes of inter-institutional meetings | 62000 Contractual services-comp 135 000 |
| Activity 5.1.4. Prepare a development master-plan for the Nimba Mountains Biosphere Reserve in collaboration with all stakeholders | The NMBR’s development master-plan (or other planning documents) is approved by year 6 | Master-plan (document) | 62000 Miscellaneous Expenses 65 000 |
| S/Total |  |  | Sub total 580 000 |
| Output 5.2. CEGEN’s human and material resources strengthened and well managed | CEGEN operating effectively at Nimba (judged by independent evaluators). CEGEN staff have the skills and are deployed in accordance with agreed capacity needs (see capacity assessments from PDF B and follow-on updates). External technical assistance needs decreased by 90% (end of programme). | Independent mid-terms reports and final evaluation Activity reports |  |
| Activity 5.2.1. Implement a staff training programme | Infrastructure installed CEGEN’s staff in place at Nimba CEGEN’s documentation center is equipped & stocked by end-year 3 95% of higher and middle level CEGEN staff have received at least 2 months of training by every three years according to the detailed capacity-building plan | Project reports | 62000 Contractual services-indiv. 108 000 62000 Contractual services-indiv. 72 000 62000 Support Services 152 000 62000 Miscellaneous expenses 5 000 04000 Support Services 79 400 |
| Activity 5.2.2. Establish a monitoring and evaluation system for CEGEN | M&E system operational M&E system producing recommendations to improve CEGEN’s operations | M&E system (document) Reports from M&E system | 04000 Contractual services-comp 15 000 04000 Miscellaneous expenses 15 000 00311 Miscellaneous expenses 180 000 00311 Contractual services-comp 400 000 |
| S/Total |  |  | Sub total 1 026 400 |
| Output 5.3. An operational ecological monitoring system | Trends for the principal bio-indicators are determined and fed into programmed management | Program reports (demonstrating how recommendations from the system are fed into management decisions) |  |
| Activity 5.3.1. Establish and manage a geo-referenced database on land-use, botanical and faunal inventories and the overall ecosystem | Database structure created and tested | Print-out of data base structure and manual for the database | 62000 Contractual services - indiv. 72 000 00005 Miscellaneous expenses 55 000 00005 International Consultant 30 000 |
| Activity 5.3.2. Ensure data collection necessary for the ecological monitoring system | Baseline data at t=0 for the principal bio-indicators are established by end-year 2 Data on the status of the principal bio-indicators available for every subsequent year of the program | Reports from the monitoring system | 62000 UNV/GIS 32 000 62000 Contractual services-comp 230 000 |
| S/Total |  |  | Sub total 419 000 |
| Output 5.4. Guaranteed long-term funding for conservation | Sustainable financing mechanism capitalised with at least $1,000,000 by end of project with donor commitments of further funding. Locally distributed ecotourism revenues of US$ 5000 per year by year 6, and US$ 10,000 per year by end of project. | Articles of the mechanism Bank statement of deposits Written commitments from donors Project reports |  |
| Activity 5.4.1. Establish a sustainable financing mechanism and Foundation (or analogue agency) for the Guinean Nimba Mountains | Sustainable financing mechanism designed by end-year 8 Sustainable financing mechanism in place by end of project | Draft articles and operational manual Legal statutes of the mechanism | 62000 Miscellaneous Expenses 10 000 62000 Travel 15 000 00005 International Consultant 30 000 00005 Local Consultant 6 000 |
| Activity 5.4.2. Explore alternative income-generating activities (especially eco-tourism, etc.) | At least 3 pilot eco-tourism or other ecologically based income-generating activities launched by end-year 7 | Project reports | 04000 Professional services 5 000 00005 Travel 30 000 00311 Miscellaneous expenses 500 000 |
| S/Total |  |  | Sub total 596 000 |
| Output 5.5. Stakeholders better informed and aware of the issues and of resource conservation | Favourable attitude towards and objectives understood for the NMBR by at least: 25% of the population older than 10 years by end-year 3 60% of the population older than 10 years by end-Y6 90% of the population older than 10 by end of project | Attitudinal surveys of the population of the NMBR |  |
| Activity 5.5.1. Design relevant messages for stakeholders and prepare materials to distribute | Printed, verbal and radio messages drafted and tested Materials for print printed | Written drafts of messages for different media Printed materials | 04000 Local Consultant /IEC 20 000 62000 Contractual services-comp 10 000 |
| Activity 5.5.2. Identify appropriate communication channels | Strategy/plan agreed | Written strategy/plan | 62000 Miscellaneous expenses 56 000 |
| 553. Organise environmental awareness meetings | At least 20 consultations and 20 hours of radio campaigns conducted | Project reports Radio annals | 04000 Miscellaneous expenses 10 000 62000 Travel 20 000 |
| S/Total |  |  | Sub total 116 000 |
| Output 5.6 Contribution to a national protected area system | National coordination system for parks established by end of project | Written plan (and legal document?) |  |
| Activity 5.6.1. Contribute to establishment of a national coordinating committee for Parks | Design of a national coordination system for parks established by year 8 | Draft system plan (document) | 04000 Local consultant 5 000 04000 Miscellaneous Expenses 5 000 |
| Activity 5.6.2. Evaluate CEGEN performance and consider expanding mandate to Simandou Mountain, with accompanying revision in legal texts | Evaluation report Revised statutes for CEGEN | Report (document) Statutes (document) | 00005 Equipment 25 000 |
| Activity 5.6.3. Contribute to review of policy and regulatory frameworks at national level for Protected Areas management | Study reviewing policy and regulatory frameworks for national-level protected areas management | Report (document) | 04000 Professional services 20 000 |
| S/Total |  |  | Sub total Sub Total Out come 5 55 000 2 792 400 |
| Total overall budget |  |  | 11 436 900 |

## Part 2.  Schedule of Activities (9 years).

| Objectives / Outputs / Activities | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd |
| Specific Objective 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve. |
| Output 1.1. Boundaries of the core areas recognized, legalized and demarcated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1.1. Complete the process of legalizing the Core Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1.2. Demarcate the boundaries of the core areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2.1. Study the impact of fires, evaluate human impacts on fire dynamics and identify appropriate management responses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2.2. Develop a deeper understanding of the impacts of mining activities, including their possible impact on to introduced species |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2.3. Develop a deeper understanding of conservation priorities, and identify solutions with participation of local communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.3. Decrease in incursions and illegal activities in the core areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3.1. Design, equip and organize a patrol-cum-protection system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3.2. Involve local populations in the protection-cum-patrol system. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3.3. Organize cooperation with public law enforcement agents. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.4. Improved compatibility of planned mining activities, and strengthened cooperation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4.1. Monitor developments in the mining project and prepare precise environmental guidelines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4.2 Monitor compliance of mining consortium to Convention and program objectives – report to Ministry as necessary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.5.1. Prepare and implement a management plan for the World Heritage Site, after consultations on relevant matters with the mining project, local populations and relevant authorities in the neighboring countries, and based on data collected above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.5.2. Prepare and implement a management plan for the Bossou ecosystem after consultations on relevant matters with local populations and ERIB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.5.3. Prepare and implement a management plan for the Déré ecosystem after consultations on relevant matters with the National Directorate for Water & Forests, Côte d’Ivoire and local populations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 1.6. -Impacts of refugees do not affect the core areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.6.1 Liaise with humanitarian agencies to ensure incorporation of environmental concerns in relief work, including establishment & sizing of camps and providing appropriate employment & income-generating activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.6.2 Develop with humanitarian agencies a refugees contingency plan in case of future refugee movements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Objectives / Outputs / Activities | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd |
| Specific Objective 2. Sustainable land use and Agricultural revenues of local people increased on the basis of more productive practices. |
| Output 2.1 Sustainable land use systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1.1. Develop a deeper understanding of the social and land-tenure constraints linked to agricultural intensification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1.2 Develop capacity for land use planning with local government and local communities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1.3. Develop land use plans, either for each community, or by commune, that take into account Refugee Contingency Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1.4 Disseminate and enforce land use system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2. Increased agricultural yields |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2.1. Support improvements in cultivation methods (soil improvements like soil conservation methods, fertilizers, manures and other inputs, development of low-lying areas for irrigation, introduction of improved seed varieties, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.3 Improved incomes from agricultural produce sold for higher prices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3.1. Improve understanding of marketing channels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3.2. Improve storage techniques and how produce is marketed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3.3. Strengthen the negotiating skills of farmers’ co-ops/communes/other groupings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3.4. Facilitate access to credit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.4. Diversified income sources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 241. Promote local micro-industry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 242. Encourage the introduction of simple processing technologies of agricultural produce |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Objectives / Outputs / Activities | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd |
| Specific Objective 3. Local needs for animal protein more fully met using practices that do not damage wildlife. |
| Output 3.1. More productive animal husbandry, integrated with agriculture |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 311. Develop the management skills of animal husbandry co-ops/communes/ groupings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 312. Facilitate access of individuals or groups raising animals to extension services and inputs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2. Domestication and breeding of wild animals tested and disseminated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 321. Develop a deeper understanding of past and current trials to raise wild animals in captivity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 322. Establish animal husbandry trials for wild animals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 323. Study the technical, economic and social feasibility of these trials |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 324. Progressively replicate breeding schemes for the most promising wild animals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 331. Raise awareness of those who hunt or collect wildlife of the principles of sustainable management and of enforcement of relevant laws |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 332. Promote simple management practices for the most widely consumed wildlife species |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Objectives / Outputs / Activities | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd |
| Specific Objective 4. . Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve. |
| Output 4.1. Improved medical and para-medical health care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 411. Support the organization of focused training for medical and para-medical staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 412. Facilitate on-going access to basic medicines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.2. Increased access to health care |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 421. Contribute to the geographic coverage of health dispensaries and clinics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 422. Promote better complementarities between “modern” and traditional medicines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.3. Increased access to potable water |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 431. Monitor water quality in light of changes to the environment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 432. Identify sources and causes of pollution and execute the needed corrective measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 433. Contribute to the existing network of wells, pumps and water supply systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.4. Improved hygiene practises |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 441. Support initiatives targeting public health and waste treatment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 442. Support education in schools and public awareness initiatives on matters of hygiene |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Objectives / Outputs / Activities | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd | 1st | 2nd |
| Specific Objective 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system. |
| Output 5.1. Synergy ensured between institutions and between interventions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 511. Amend and complete the legal texts related to CEGEN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 512. Establish and run a consultation and planning mechanism with local populations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 513. Ensure complementarity between relevant institutions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 514. Prepare a development master-plan for the Nimba Mountains Biosphere Reserve in collaboration with all stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.2. CEGEN’s human and material resources strengthened and well managed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 521. Implement a staff training programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 522. Establish a monitoring and evaluation system for CEGEN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.3. An operational ecological monitoring system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 531. Establish and manage a geo-referenced database on land-use, botanical and faunal inventories and the overall ecosystem |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 532. Ensure data collection necessary for the ecological monitoring system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.4. Guaranteed long-term funding for conservation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 541. Establish a sustainable financing mechanism and Foundation (or analogue agency) for the Guinean Nimba Mountains |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 542. Explore alternative income-generating activities (especially eco-tourism, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.5. Stakeholders better informed and aware of the issues and of resource conservation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 551. Design relevant messages for stakeholders and prepare materials to distribute |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 552. Identify appropriate communication channels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 553. Organise environmental awareness meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.6 Contribution to a national protected area system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 561. Contribute to establishment of a national coordinating committee for Parks |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 562. Evaluate CEGEN performance and consider expanding mandate to Simandou Mountain, with accompanying revision in legal texts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 563. Contribute to review of policy and regulatory frameworks at national level for Protected Areas management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# SECTION III.  OTHER AGREEMENTS

## Part 1.  Additional Agreements.

No additional agreements are available to be appended to this project document.  As any are signed, they will be kept in UNDP-Guinea’s project files.

The approved GEF project proposal and annexes, containing additional information on the initiative, can be accessed via http://www.gefonline.org/projectDetails.cfm?projID=1139 .

## Part 2. Annual Work Plan.

ATLAS budget and work plan.

1.   Budget and Work Plan (GEF, UNESCO and UNDP)

|  |  |  |  |  | Total Budget and Workplan |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | (GEF, UNESCO and UNDP) |  |  |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Yr6 | Yr7 | Yr8 | Yr9 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.1. Boundaries of the core areas recognized, legalized and demarcated | X | X | X |  |  |  |  |  |  | UNDP | 62000 | 71200 International consultant | 38 000 |
|  |  | X | X | X |  |  |  |  |  |  | UNDP | 62000 | 71400 Contractual services - indiv. | 22 000 |
|  |  | X | X | X |  |  |  |  |  |  | UNDP | 62000 | 71400 Contractual services - indiv. | 30 000 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 62000 | 71300 Local Consultant | 15 000 |
|  |  | X | X | X |  |  |  |  |  |  | NEX | 62000 | 72200 Equipments (Pictograms) | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 125 000 |
|  | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. |  |  | X | X |  |  | X |  |  | NEX | 62000 | 72200 Equipments Supplies | 30 000 |
|  |  |  |  | X | X |  |  |  |  |  | UNDP | 62000 | 71200 International consultant | 30 000 |
|  |  |  |  |  | X |  | X |  |  |  | UNDP | 62000 | 72200 Equipments | 20 000 |
|  |  |  |  | X |  |  |  |  |  |  | NEX | 04000 | 72200 Equipments | 20 000 |
|  |  |  |  |  |  | X |  |  |  |  | NEX | 62000 | 72200 Equipment and furniture | 10 000 |
|  |  |  |  | X | X | X | X |  |  |  | UNDP | 62000 | 72100 Contractual services - comp. | 65 000 |
|  |  |  |  | X |  |  | X |  | X | X | NEX | 62000 | 74100 Professional Services | 60 000 |
|  |  |  |  | X | X | X | X |  |  |  | UNDP | 62000 | 71500 UNV (national) | 20 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 62000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 260 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. | X | X | X | X |  |  |  |  |  | UNDP | 62000 | 72100 Contractual services - comp. | 100 000 |
|  |  |  |  |  |  |  |  |  |  |  | UNDP | 05000 | 72100 Contractual services - comp. | 50 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 62000 | 71400 Contractual services - indiv. | 15 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | 71400 Contractual services - indiv. | 10 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 62000 | 71400 Contractual services - indiv. | 10 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 62000 | 72200 Equipment | 665 500 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 62000 | 73520 Support Services | 60 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 62000 | 71600 Travel | 20 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 62000 | 71300 Local Consultant | 15 000 |
|  |  |  |  |  | X | X | X |  |  |  | UNDP | 62000 | 74100 Professional services | 47 800 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | 74100 Professional services | 20 000 |
|  |  |  |  |  |  | X |  |  |  |  | NEX | 04000 | 74500 Miscellaneous expenses | 20 000 |
|  |  |  |  | X | X |  |  |  |  |  | NEX | 62000 | 74500 Miscellaneous expenses | 20 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 62000 | 71200 International consultants | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 1 083 300 |
|  | 1.4. Improved compatibility of planned mining activities, and strengthened cooperation | X |  | X |  |  |  |  |  |  | UNDP | 62000 | 72100 Contractual services - comp | 120 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | 71300 Local Consultant | 7 000 |
|  |  |  |  |  | X |  |  |  |  |  | NEX | 04000 | 74100 Professional services | 10 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 137 000 |
|  | 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities | X |  |  |  |  |  |  |  |  | UNDP | 62000 | 73520 Support Services | 50 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 04000 | 71300 Local Consultant | 6 000 |
|  |  |  | X |  | X |  |  |  |  |  | UNDP | 05000 | 71300 Local Consultant | 13 300 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 62000 | 72100 Contractual services - comp. | 100 000 |
|  |  | X | X |  |  |  |  |  |  |  | NEX | 04000 | 71600 Travel | 25 000 |
|  |  |  |  | X |  |  |  |  |  |  | NEX | 62000 | 71600 Travel | 10 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 62000 | 74500 Miscellaneous expenses | 20 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 62000 | 74100 Professional Services | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 254 300 |
|  | 1.6. Impacts of refugees do not affect the core areas. | X |  | X |  |  |  |  |  |  | NEX | 62000 | 74500 Miscellaneous expenses | 30 000 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 04000 | 71300 Local Consultant | 15 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 62000 | 72100 Contractual services - comp. | 20 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 05000 | 72100 Contractual services - comp. | 15 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 80 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  |  |  |  |  | 1 939 600 |
| 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practices. | 2.1. Sustainable land use systems | X | X |  |  |  |  |  |  |  | UNDP | 62000 | 71200 International consultant | 30 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | 71200 International consultant | 8 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 04000 | 71300 Local Consultant | 5 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | 72100 Contractual services - comp. | 30 000 |
|  |  |  | X | X | X |  |  |  |  |  | NEX | 04000 | 74500 Miscellaneous expenses | 40 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | 72200 Equipments | 10 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | 72200 Equipment Supplies | 5 000 |
|  |  |  |  | X |  |  |  |  |  |  | NEX | 04000 | 72200 Equipment and Furnitures | 10 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 138 000 |
|  | 2.2. Increased agricultural yields |  | X | X |  |  |  |  |  |  | UNDP | 04000 | 71200 International Consult. | 30 000 |
|  |  |  | X |  | X | X |  |  |  |  | UNDP | 04000 | 71400 contractuel services- indiv | 23 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | 71300 Local Consultant | 5 000 |
|  |  |  | X | X | X | X |  |  |  |  | UNDP | 04000 | 72100 Contractuel services -compag | 230 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 288 000 |
|  | 2.3. Improved incomes from agricultural produce sold for higher prices |  |  | X | X |  |  |  |  |  | NEX | 04000 | 74500 Miscellaneous expenses | 65 000 |
|  |  |  | X | X |  | X |  |  |  |  | UNDP | 04000 | 72100 Contractual services-comp | 60 000 |
|  |  |  |  |  |  |  |  |  |  |  | NEX | 04000 | 74500 Miscellaneous expenses | 0 |
|  |  |  | X | X |  | X |  |  | X |  | UNDP | 04000 | 71300 Local consultant | 23 000 |
|  |  |  |  | X | X |  | X |  |  |  | UNDP | 04000 | 72600 Grant | 130 000 |
|  |  |  |  | X | X |  | X |  |  |  | UNDP | 62000 | 72600 Grant | 195 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | 71600 Travel | 15 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 488 000 |
|  | 2.4. Diversified income sources |  |  |  | X | X |  |  |  |  | NEX | 04000 | 74500 Miscellaneous expenses | 35 000 |
|  |  |  |  |  | X | X | X |  |  |  | UNDP | 04000 | 71500 UNV (national) | 24 000 |
|  |  |  |  |  | X | X |  |  |  |  | UNDP | 04000 | 72200 Equipment/ Procurement MFP | 45 000 |
|  |  |  |  |  |  |  |  | X |  |  | NEX | 04000 | 74100 Professionnel Services | 10 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 114 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 028 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.1. More productive animal husbandry, integrated with agriculture |  | X | X | X | X |  |  |  |  | NEX | 62000 | 74500 Miscellaneous expenses | 55 000 |
|  |  |  | X | X | X | X | X |  |  |  | UNDP | 62000 | 72100 Contract services-Comp | 200 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 255 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated |  | X | X | X | X | X | X |  |  | UNDP | 04000 | 71500 UNV Veterinian | 38 000 |
|  |  |  | X | X | X | X | X |  |  |  | UNDP | 00005 | 71400 Contractual services-indv | 86 000 |
|  |  |  | X | X | X | X |  |  |  |  | UNDP | 62000 | 71400 Contractual services-indv | 26 000 |
|  |  |  | X | X | X | X | X |  |  |  | UNDP | 00005 | 71400 Contractual services-indv | 24 000 |
|  |  |  |  |  |  |  | X |  | X |  | UNDP | 62000 | 74500 Miscellaneous Expenses | 27 000 |
|  |  |  | X | X | X | X |  |  |  |  | UNDP | 00005 | 74500 Miscellaneous Expenses | 43 700 |
|  |  |  | X |  | X |  |  |  |  |  | UNDP | 62000 | 72100 Contractuel services-comp. | 112 000 |
|  |  |  |  |  |  |  |  |  |  | X | NEX | 62000 | 74100 Professional services | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 376 700 |
|  | 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner | X | X | X | X | X |  |  |  |  | NEX | 62000 | 74500 Miscellaneous expenses | 101 000 |
|  |  |  | X |  | X |  |  |  |  |  | NEX | 62000 | 74500 Miscellaneous expenses | 65 000 |
|  |  |  | X |  | X |  |  |  |  |  | UNDP | 62000 | 72200 Equipment/Supplies wild species | 103 200 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 04000 | 71300 Local Consultant | 11 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 280 200 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  |  |  |  |  | 911 900 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care |  |  | X | X |  |  |  |  |  | UNDP | 04000 | 72200 Equipment (drugs) | 50 000 |
|  |  |  | X |  | X | X |  |  |  |  | UNDP | 04000 | 72100 Contractuel services-comp. | 60 000 |
|  |  |  |  |  |  |  | X |  | X |  | UNDP | 04000 | 72200 Equipment | 20 000 |
|  |  |  |  |  |  |  |  | X |  |  | NEX | 04000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | 71300 Local consultant | 10 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 145 000 |
|  | 4.2. Increased access to health care |  |  |  | X | X |  |  |  |  | UNDP | 04000 | 74500 Miscellaneous expenses | 25 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | 72100 Contractual services-comp. | 50 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 75 000 |
|  | 4.3. Increased access to potable water | X |  | X | X | X | X | X |  |  | UNDP | 62000 | 72100 Contractual services-comp. | 42 500 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | 72100 Contractual services-comp. | 10 000 |
|  |  |  |  | X |  |  | X |  |  |  | UNDP | 04000 | 74100 Profesional services | 40 000 |
|  |  |  |  |  | X |  |  |  |  |  | UNDP | 62000 | 71600 Travel | 15 000 |
|  |  | X | X | X | X | X |  | X |  |  | NEX | 04000 | 72100 Contractuel services-comp. | 137 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 244 500 |
|  | 4.4. Improved hygiene practices |  |  |  | X |  | X |  |  |  | NEX | 00005 | 72100 Contractuel services-comp | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 30 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  |  |  |  |  | 494 500 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.1. Synergy ensured between institutions and between interventions. | X | X | X |  |  |  |  |  |  | UNDP | 62000 | 72100 Contractual services-comp | 135 000 |
|  |  | X | X | X | X | X |  |  |  |  | UNDP | 62000 | 71500 UNV (national) | 30 000 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 00005 | 71200 International consultant | 60 000 |
|  |  | X |  |  | X |  |  |  |  |  | NEX | 62000 | 74500 Miscellaneous Expenses | 65 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 00005 | 71300 Local consultant | 10 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 300 000 |
|  | 5.2. CEGEN’s human and material resources strengthened and well managed. | X | X | X | X | X | X | X | X | X | UNDP | 62000 | 72100 Contractual services-indiv. | 108 000 |
|  |  | X | X | X | X | X | X | X | X | X | UNDP | 62000 | 72100 Contractual services-indiv. | 72 000 |
|  |  |  |  | X |  |  | X | X | X | X | UNDP | 62000 | 73520 Support Services | 152 000 |
|  |  |  |  |  | X | X |  |  |  |  | UNDP | 04000 | 73520 Support Services | 79 400 |
|  |  |  |  |  |  |  | X |  |  |  | UNDP | 04000 | 72100 Contractual services-comp | 15 000 |
|  |  |  | X |  |  |  |  |  |  |  |  | 04000 | 74500 Miscellaneous expenses | 15 000 |
|  |  |  |  |  |  |  |  |  |  | X | NEX | 62000 | 74500 Miscellaneous expenses | 5 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 446 400 |
|  | 5.3. An operational ecological monitoring system | X | X | X |  |  |  |  |  |  | UNDP | 62000 | 71400 Contractual services - indiv. | 72 000 |
|  |  | X | X |  |  |  |  |  |  |  | NEX | 00005 | 74500 Miscellaneous expenses | 55 000 |
|  |  | X | X | X | X | X | X |  |  |  | UNDP | 62000 | 71500 UNV/GIS | 32 000 |
|  |  | X | X | X | X | X |  |  |  |  | UNDP | 62000 | 72100 Contractual services-comp | 230 000 |
|  |  |  |  |  |  |  |  | X |  |  | NEX | 00005 | 71200 International Consultant | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 419 000 |
|  | 5.4. Guaranteed long-term funding for conservation |  |  |  |  |  |  | X |  |  | UNDP | 00005 | 713000 Local Consultant | 6 000 |
|  |  |  |  |  |  |  |  |  | X |  | UNDP | 62000 | 74500 Miscellaneous Expenses | 10 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 04000 | 74100 Professional services | 5 000 |
|  |  |  |  |  |  |  |  | X |  |  | UNDP | 62000 | 74600 Travel | 15 000 |
|  |  |  |  |  |  |  |  |  | X |  | UNDP | 00005 | 74600 Travel | 30 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 00005 | 71200 International Consultant | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 96 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | X | X | X |  |  |  |  |  |  | UNDP | 04000 | 71300 Local Consultant /IEC | 20 000 |
|  |  | X | X |  | X | X | X | X | X |  | NEX | 62000 | 74500 Miscelaneous expenses | 56 000 |
|  |  |  |  | X |  |  |  |  |  | X | NEX | 04000 | 74500 Miscelaneous expenses | 10 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 62000 | 72100 Contractual services-comp | 10 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 62000 | 71600 Travel | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 116 000 |
|  | 5.6. Contribution to a national protected area system |  |  |  |  |  |  | X |  |  | UNDP | 04000 | 71300 Local consultant | 5 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 04000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  |  | X |  | UNDP | 00005 | 72200 Equipment | 25 000 |
|  |  |  |  |  |  |  |  |  |  | X | NEX | 04000 | 74100 Professional services | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 55 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  |  |  |  |  | 1 432 400 |
| Total Budget (GEF, UNESCO & UNDP) |  |  |  |  |  |  |  |  |  |  |  |  | 5 806 400 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET UNDP | 1 646 400 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET GEF | 3 660 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET UNESCO | 500 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Total 1 | 5 806 400 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | BUDGET MINING | 4 500 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Total 2 | 10 306 400 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | FFI | 200 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | GVT | 830 500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | CL | 100 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | TOTAL GLOBAL | 11 436 900 |

| Year 1 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.1. Boundaries of the core areas recognized, legalized and demarcated |  | x |  |  | UNDP | 62000 | 71200 International consultant | 15 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 9 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 10 000 |
|  |  |  |  | x |  | UNDP | 62000 | 71300 Local Consultant | 5 000 |
|  |  |  |  | x | x | NEX | 62000 | 72200 Equipments (Pictograms) | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 49 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. |  | x | x | x | UNDP | 62000 | 72100 Contractual services - comp. | 30 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 15 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72200 Equipment | 665 500 |
|  |  |  |  |  |  |  |  | Sub total | 710 500 |
|  | 1.4. Improved compatibility of planned mining activities, and strengthened cooperation |  | x | x | x | UNDP | 62000 | 72100 Contractual services - comp | 50 000 |
|  |  |  |  |  |  |  |  | Sub total | 50 000 |
|  | 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities | x | x | x | x | UNDP | 62000 | 73520 Support Services | 50 000 |
|  |  |  | x | x |  | UNDP | 04000 | 71300 Local Consultant | 6 000 |
|  |  |  |  | x | x | UNDP | 62000 | 72100 Contractual services - comp. | 70 000 |
|  |  | x | x | x | x | NEX | 04000 | 71600 Travel | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 141 000 |
|  | 1.6. Impacts of refugees do not affect the core areas | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 20 000 |
|  |  |  | x | x |  | UNDP | 04000 | 71300 Local Consultant | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 30 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 980 500 |
| 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practices. | 2.1. Sustainable land use systems. |  | x |  |  | UNDP | 62000 | 71200 International consultant | 15 000 |
|  |  |  | x | x |  | UNDP | 04000 | 71300 Local Consultant | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  | 20 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner. | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 16 000 |
|  |  |  |  | x | x | UNDP | 04000 | 71300 Local Consultant | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 21 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 21 000 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.3. Increased access to potable water | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 8 000 |
|  |  |  | x | x | x | NEX | 04000 | 72100 Contractual services - comp | 30 000 |
|  |  |  |  |  |  |  |  | Sub total | 38 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  | 38 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.1. Synergy ensured between institutions and between interventions |  | x | x | x | UNDP | 62000 | 72100 Contractual services - comp | 35 000 |
|  |  |  | x | x | x | UNDP | 62000 | 71500 UNV (national) | 6 000 |
|  |  |  | x |  |  | UNDP | 00005 | 71200 Internat. consultant | 30 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 45 000 |
|  |  |  |  |  |  |  |  | Sub total | 116 000 |
|  | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractuel servies-indiv. | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
|  | 5.3. An operational ecological monitoring system | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 10 000 |
|  |  | x | x | x | x | NEX | 00005 | 74500 Miscellaneous Expenses | 25 000 |
|  |  |  | x | x | x | UNDP | 62000 | 72100 Contractual services - comp. | 50 000 |
|  |  |  | x | x | x | UNDP | 62000 | 71500 UNV/GIS | 6 000 |
|  |  |  | x | x | x | UNDP | 62000 | 72100 Contractual services - comp. | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 111 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | UNDP | 62000 | 71600 Travel | 20 000 |
|  |  | x | x |  |  | UNDP | 04000 | 71300 Local Consultant/IEC | 5 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 6 000 |
|  |  |  |  |  |  |  |  | Sub total | 31 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 278 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 1 | 1 337 500 |

| Year 2 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.1. Boundaries of the core areas recognized, legalized and demarcated |  |  | X |  | UNDP | 62000 | 71200 International consultant | 15 000 |
|  |  | X | X | X | X | UNDP | 62000 | 71400 Contractual services - indiv. | 9 000 |
|  |  | X | X | X | X | UNDP | 62000 | 71400 Contractual services - indiv. | 10 000 |
|  |  | X | X |  |  | UNDP | 62000 | 71300 Local Consultant | 10 000 |
|  |  | X |  |  |  | NEX | 62000 | 72200 Equipments (Pictograms) | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 49 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. | x | x | x | x | UNDP | 04000 | 71400 Contractual services - indiv. | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 73520 Support Services | 60 000 |
|  |  | x | x | x | x | NEX | 62000 | 71600 Travel | 20 000 |
|  |  | x | x | x | x | UNDP | 05000 | 72100 Contractual services - comp. | 50 000 |
|  |  | x | x |  |  | UNDP | 62000 | 71300 Local Consultant | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 165 000 |
|  | 1.4. Improved compatibility of planned mining activities, and strengthened cooperation |  | x | x |  | UNDP | 04000 | 71300 Local Consultant | 7 000 |
|  |  |  |  |  |  |  |  | Sub total | 7 000 |
|  | 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities |  | x | x |  | UNDP | 05000 | 71300 Local Consultant | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 74100 Professional Services | 30 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractual services - comp. | 30 000 |
|  |  | x | x | x | x | NEX | 04000 | 71600 Travel | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 76 000 |
|  | 1.6. Impacts of refugees do not affect the core areas | x | x | x |  | NEX | 05000 | 72100 Contractual services - comp. | 15 000 |
|  |  | x | x | x |  | NEX | 62000 | 72100 Contractual services - comp. | 20 000 |
|  |  |  | x | x |  | UNDP | 04000 | 71300 Local Consultant | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 40 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 337 000 |
| 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practices. | 2.1. Sustainable land use systems |  |  |  | x | UNDP | 62000 | 71200 International consultant | 15 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractual services - comp. | 30 000 |
|  |  | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 20 000 |
|  |  | x | x | x | x | NEX | 04000 | 72200 Equipments | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 75 000 |
|  | 2.2. Increased agricultural yields |  | x |  |  | UNDP | 04000 | 71200 International Consult. | 15 000 |
|  |  | x | x | x | x | UNDP | 04000 | 71400 contractuel services- indiv | 8 000 |
|  |  |  | x | x |  | NEX | 04000 | 71300 Local Consultant | 5 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractuel services -compag | 80 000 |
|  |  |  |  |  |  |  |  | Sub total | 108 000 |
|  | 2.3. Improved incomes from agricultural produce sold for higher prices | x | x | x | x | NEX | 04000 | 72100 contractuel services- comp | 20 000 |
|  |  | x | x | x | x | NEX | 04000 | 71600 Travel | 15 000 |
|  |  |  |  | x | x | UNDP | 04000 | 71300 Local Consultant | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 40 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  | 223 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.1. More productive animal husbandry, integrated with agriculture | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 5 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contract services-Comp | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 25 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated | x | x | x | x | UNDP | 04000 | 71500 UNV Veterinian | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp. | 30 000 |
|  |  | x | x | x | x | UNDP | 00005 | 71400 Contractuel services-indv | 10 000 |
|  |  | x | x | x | x | UNDP | 00005 | 74500 Miscellaneous Expenses | 13 700 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual services-indiv | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp. | 50 000 |
|  |  | x | x | x | x | UNDP | 00005 | 71400 Contractual Services - indiv | 4 000 |
|  |  |  |  |  |  |  |  | Sub total | 123 700 |
|  | 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 74500 Miscellaneous Expenses | 20 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72500 Supplies wild species | 30 000 |
|  |  | x | x |  |  | UNDP | 04000 | 71300 Local consultant | 6 000 |
|  |  |  |  |  |  |  |  | Sub total | 66 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 214 700 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-comp. | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 15 000 |
|  | 4.3. Increased access to potable water | x | x | x | x | UNDP | 04000 | 71400 Contractuel services-indv | 10 000 |
|  |  | x | x | x | x | NEX | 04000 | 72100 Contractuel services-comp. | 20 000 |
|  |  | x | x | x | x | NEX | 04000 | 72100 Contractuel services-comp. | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 45 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  | 60 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.1. Synergy ensured between institutions and between interventions. | x | x | x | x | UNDP | 62000 | 72100 Contractual services-comp | 50 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 6 000 |
|  |  |  |  | x |  | UNDP | 00005 | 71200 Internat. Consultant | 30 000 |
|  |  |  | x | x |  | UNDP | 00005 | 71300 Local consultant | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 96 000 |
|  | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractuel servies-indiv. | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 35 000 |
|  | 5.3. An operational ecological monitoring system | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 10 000 |
|  |  | x | x | x | x | NEX | 00005 | 74500 Miscellaneous expenses | 30 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV/GIS | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractual services-comp | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 66 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation |  |  | x | x | UNDP | 04000 | 71300 Local Consultant /IEC | 10 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscelaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 217 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 2 | 1 051 700 |

| Year 3 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.1. Boundaries of the core areas recognized, legalized and demarcated |  |  |  | X | UNDP | 62000 | 71200 International consultant | 8 000 |
|  |  | X | X | X | X | UNDP | 62000 | 71400 Contractual services - indiv. | 4 000 |
|  |  | X | X | X | X | UNDP | 62000 | 71400 Contractual services - indiv. | 10 000 |
|  |  | X | X | X | X | NEX | 62000 | 72200 Equipments (Pictograms) | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 27 000 |
|  | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. | x | x | x | x | NEX | 62000 | 72200 Equipments Supplies | 10 000 |
|  |  |  | x |  |  | UNDP | 62000 | 71200 International consultant | 15 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72200 Equipments | 20 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractual services - comp. | 25 000 |
|  |  | x | x | x | x | UNDP | 62000 | 74100 Professional Services | 30 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 108 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-compagnie | 50 000 |
|  |  | x | x | x | x | UNDP | 04000 | 74100 Profesional services | 20 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10 000 |
|  |  | x |  |  |  | UNDP | 62000 | 71200 International consultants | 30 000 |
|  |  |  |  |  |  |  |  | Sub total | 110 000 |
|  | 1.4. Improved compatibility of planned mining activities, and strengthened cooperation | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-compagnie | 70 000 |
|  |  |  |  |  |  |  |  | Sub total | 70 000 |
|  | 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities | x | x | x | x | UNDP | 62000 | 74500 Miscellaneous expenses | 20 000 |
|  |  | x | x | x | x | NEX | 62000 | 71600 Travel | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 30 000 |
|  | 1.6. Impacts of refugees do not affect the core areas | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 355 000 |
| 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practices. | 2.1. Sustainable land use systems |  |  | x |  | UNDP | 04000 | 71200 International consultants | 8 000 |
|  |  | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 10 000 |
|  |  | x | x | x | x | NEX | 04000 | 72200 Equipment and Furnitures | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 28 000 |
|  | 2.2. Increased agricultural yields |  |  | x |  | UNDP | 04000 | 71200 International consultants | 15 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-compagnie | 30 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractual services-compagnie | 70 000 |
|  |  |  |  |  |  |  |  | Sub total | 115 000 |
|  | 2.3. Improved incomes from agricultural produce sold for higher prices | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 15 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractual services-compagnie | 10 000 |
|  |  | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 30 000 |
|  |  | x | x |  |  | UNDP | 04000 | 71300 Local consultant | 5 000 |
|  |  | x |  |  |  | UNDP | 04000 | 72600 Grant | 50 000 |
|  |  | x |  |  |  | UNDP | 62000 | 72600 Grant | 50 000 |
|  |  |  |  |  |  |  |  | Sub total | 160 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  | 303 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.1. More productive animal husbandry, integrated with agriculture | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 30 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contract services-Comp | 100 000 |
|  |  |  |  |  |  |  |  | Sub total | 130 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated | x | x | x | x | UNDP | 04000 | 71500 UNV Veterinian | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  | x | x | x | x | UNDP | 00005 | 71400 Contractuel services-indv | 8 000 |
|  |  |  |  |  |  | UNDP | 00005 | 74500 Miscellaneous Expenses | 10 000 |
|  |  | x | x |  |  | UNDP | 62000 | 71400 Contractual services-indiv | 2 000 |
|  |  |  |  |  |  |  |  | Sub total | 34 000 |
|  | 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 184 000 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care | x | x | x | x | UNDP | 04000 | 72200 Equipment (drugs) | 30 000 |
|  |  | x | x | x | x | UNDP | 04000 | 71300 Local consultant | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 40 000 |
|  | 4.2. Increased access to health care | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-comp. | 50 000 |
|  |  |  |  |  |  |  |  | Sub total | 50 000 |
|  | 4.3. Increased access to potable water | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  | x | x | x | x | UNDP | 04000 | 74100 Profesional services | 20 000 |
|  |  | x | x | x | x | NEX | 4000 | 72100 Contractuel services-comp. | 30000 |
|  |  |  |  |  |  |  |  | Sub total | 58 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 148 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.1. Synergy ensured between institutions and between interventions. | x | x | x | x | UNDP | 62000 | 72100 Contractual services-comp | 50 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 6 000 |
|  |  |  |  |  |  |  |  | Sub total | 56 000 |
|  | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractuel servies-indiv. | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  | x | x | x | x | UNDP | 62000 | 73520 Support Services | 72 000 |
|  |  |  |  |  |  |  |  | Sub total | 92 000 |
|  | 5.3. An operational ecological monitoring system | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 52 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV/GIS | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractual services-comp | 50 000 |
|  |  |  |  |  |  |  |  | Sub total | 108 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | UNDP | 62000 | 72100 Contractual services-comp | 10000 |
|  |  |  | x | x |  | UNDP | 04000 | 71300 Local Consultant /IEC | 5 000 |
|  |  | x | x | x | x | UNDP | 04000 | 74500 Miscelaneous expenses | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 276 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 3 | 1 266 000 |

| Year 4 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. | x | x | x | x | NEX | 62000 | 72200 Equipment Supplies | 10 000 |
|  |  |  | x |  |  | UNDP | 62000 | 71200 International Consultant | 15 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72200 Equipment | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 4 000 |
|  |  |  |  |  |  |  |  | Sub total | 49 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 20 000 |
|  |  | x | x | x | x | UNDP | 62000 | 74100 Professional services | 18 900 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 48 900 |
|  | 1.4. Improved compatibility of planned mining activities, and strengthened cooperation | x | x | x | x | NEX | 04000 | 74100 Professional services | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
|  | 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities | x | x |  |  | UNDP | 00005 | 71300 Local consultant | 7 300 |
|  |  |  |  |  |  |  |  | Sub total | 7 300 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 115 200 |
| 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practices. | 2.1. Sustainable land use systems | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 10 000 |
|  |  | x | x | x | x | NEX | 04000 | 72200 Equipment Supplies | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 15 000 |
|  | 2.2. Increased agricultural yields | x | x | x | x | UNDP | 04000 | 74100 Contractuel services-comp | 20 000 |
|  |  | x | x | x | x | NEX | 04000 | 72100 Contractual services - indiv. | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 28 000 |
|  | 2.3. Improved incomes from agricultural produce sold for higher prices | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 20 000 |
|  |  |  | x |  |  | UNDP | 04000 | 72600 Grant | 50 000 |
|  |  |  | x |  |  | UNDP | 62000 | 72600 Grant | 70 000 |
|  |  |  |  |  |  |  |  | Sub total | 140 000 |
|  | 2.4. Diversified income sources | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 15 000 |
|  |  | x | x | x | x | UNDP | 04000 | 71500 UNV (national) | 12 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72200 Equipment/ Procurement MFP | 20 000 |
|  |  | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 57 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  | 240 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.1. More productive animal husbandry, integrated with agriculture | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 30 000 |
|  |  |  |  |  |  |  |  | Sub total | 40 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated | x | x | x | x | UNDP | 04000 | 71500 UNV Veterinian | 12 000 |
|  |  |  |  |  |  | UNDP | 62000 | 72100 Contractuel services-comp | 32 000 |
|  |  | x | x | x | x | UNDP | 00005 | 71400 Contractuel services-indiv | 52 000 |
|  |  |  |  |  |  | UNDP | 00005 | 74500 Miscellaneous expenses | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indiv | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 114 000 |
|  | 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner | x | x | x | x | UNDP | 62000 | 74500 Miscellaneous expenses | 30 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 45 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72200 Equipment/Supplies wild species | 73 200 |
|  |  |  |  |  |  |  |  | Sub total | 148 200 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 302 200 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-comp | 20 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72200 Equipment/ Supplies drugs | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 40 000 |
|  | 4.2. Increased access to health care | x | x | x | x | UNDP | 04000 | 74500 Miscellaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
|  | 4.3. Increased access to potable water | x | x | x | x | UNDP | 62000 | 71600 Travel | 15 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  | x | x | x | x | NEX | 04000 | 72100 Contractuel services-comp | 16 000 |
|  |  |  |  |  |  |  |  | Sub total | 39 000 |
|  | 4.4. Improved hygiene practices | x | x | x | x | NEX | 00005 | 72100 Contractuel services-comp | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 15 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  | 104 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.1. Synergy ensured between institutions and between interventions. | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 6 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 26 000 |
|  | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indiv | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indiv | 8 000 |
|  |  | x | x | x | x | NEX | 04000 | 73520 Support Services | 50 000 |
|  |  |  |  |  |  |  |  | Sub total | 70 000 |
|  | 5.3. An operational ecological monitoring system | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 50 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV/GIS | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 76 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10000 |
|  |  |  |  |  |  |  |  | Sub total | 10000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 182 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 4 | $ 943 400 |

| Year 5 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. | x | x | x | x | NEX | 62000 | 72200 Equipment and furniture | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72200 Contractuel services-comp | 15 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 4 000 |
|  |  |  |  |  |  |  |  | Sub total | 29 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. | x | x | x | x | UNDP | 62000 | 74100 Professional services | 10 000 |
|  |  | x | x | x | x | NEX | 04000 | 74500 Miscellaneous | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 30 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  | 59 000 |
|  | 2.2. Increased agricultural yields |  |  |  |  | UNDP | 04000 | 71200 International Consultant |  |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-comp | 30 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-indiv. | 7 000 |
|  |  |  |  |  |  |  |  | Sub total | 37 000 |
|  | 2.3. Improved incomes from agricultural produce sold for higher prices |  | x | x |  | UNDP | 04000 | 71300 Local Consultant | 8 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-comp | 30 000 |
|  |  |  |  |  |  |  |  | Sub total | 38 000 |
|  | 2.4. Diversified income sources | x | x | x | x | UNDP | 04000 | 71300 UNV (national) | 6 000 |
|  |  | x | x | x | x | UNDP | 04000 | Procurement/ Equipment MFP | 25 000 |
|  |  | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 41 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  | 116 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.1. More productive animal husbandry, integrated with agriculture | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 30 000 |
|  |  |  |  |  |  |  |  | Sub total | 40 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated | x | x | x | x | UNDP | 04000 | 71500 UNV Veterinian | 6 000 |
|  |  | x | x | x | x | UNDP | 00005 | 71400 Contractue services- indiv | 8 000 |
|  |  |  |  |  |  | UNDP | 00005 | 74500 Miscellaneous expenses | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractue services- indiv | 6 000 |
|  |  | x | x | x | x | UNDP | 62001 | 71400 Contractue services- indiv | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 38 000 |
|  | 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 25 000 |
|  |  |  |  |  |  |  |  | Sub total | 25 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 103 000 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-comp | 25 000 |
|  |  |  |  |  |  |  |  | Sub total | 25 000 |
|  | 4.2. Increased access to health care | x | x | x | x | NEX | 04000 | 74500 Miscellaneous expenses | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 15 000 |
|  | 4.3. Increased access to potable water | x | x | x | x | NEX | 04000 | 72100 Contractuel services-comp | 16 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 16 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  | 56 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.1. Synergy ensured between institutions and between interventions. | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 6 000 |
|  |  |  |  |  |  |  |  | Sub total | 6 000 |
|  | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractue services- indiv | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractue services- indiv | 8 000 |
|  |  | x | x | x | x | NEX | 04000 | 73520 Support Services | 29 400 |
|  |  |  |  |  |  |  |  | Sub total | 49 400 |
|  | 5.3. An operational ecological monitoring system | x | x | x | x | UNDP | 62000 | 71500 UNV/GIS | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 26 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  | 91 400 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 5 | $ 425 400 |

| Year 6 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. | x | x | x | x | NEX | 62000 | 72200 Equipment | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 74100 Professional services | 10 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71500 UNV (national) | 4 000 |
|  |  | x | x | x | x | UNDP | 62000 | 72100 Contractuel services-comp | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 39 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. | x | x | x | x | UNDP | 62000 | 74100 Professional services | 18 900 |
|  |  |  |  |  |  |  |  | Sub total | 18 900 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 57 900 |
|  | 2.3. Improved incomes from agricultural produce sold for higher prices |  |  | x |  | UNDP | 04000 | 72600 Micro credit | 30 000 |
|  |  |  |  | x |  | UNDP | 62000 | 72600 Micro Grant | 75 000 |
|  |  |  |  |  |  |  |  | Sub total | 105 000 |
|  | 2.4. Diversified income sources | x | x | x | x | UNDP | 04000 | 71500 UNV (national) | 6 000 |
|  |  |  |  |  |  |  |  | Sub total | 6 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  | 111 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.1. More productive animal husbandry, integrated with agriculture | x | x | x | x | NEX | 62000 | 72100 Contractual Services - Comp | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated | x | x | x | x | UNDP | 04000 | 71500 UNV Veterinian | 6 000 |
|  |  | x | x | x | x | UNDP | 00005 | 71400 Contractuel services-indiv | 8 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 7 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indiv | 4 000 |
|  |  |  |  |  |  |  |  | Sub total | 25 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 45 000 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care | x | x | x | x | UNDP | 04000 | 7220 Equipment | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
|  | 4.3. Increased access to potable water | x | x | x | x | UNDP | 04000 | 74100 Professional services | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractuel services-indv | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
|  | 4.4. Improved hygiene practices | x | x | x | x | NEX | 00005 | 72100 Contractuel services-comp | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 15 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  | 45 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contratuel sevices -indiv | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contratuel sevices -indiv | 8 000 |
|  |  | x | x | x | x | NEX | 04000 | 73520 Support Services | 20 000 |
|  |  | x | x | x | x | UNDP | 04000 | 72100 Contractuel services-comp | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 55 000 |
|  | 5.3. An operational ecological monitoring system | x | x | x | x | UNDP | 62000 | 71500 UNV/GIS | 2 000 |
|  |  |  |  |  |  |  |  | Sub total | 2 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | NEX | 62000 | 74500 Miscellaneous expenses | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 67 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 6 | $ 325 900 |

| Year 7 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. | x | x | x | x | NEX | 62000 | 72200 Equipment Supplies | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 10 000 |
|  | 2.4. Diversified income sources | x | x | x | x | NEX | 04000 | 74100 Professionnel Services | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  | 10 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated | x | x | x | x | UNDP | 04000 | 71500 UNV Veterinian | 2 000 |
|  |  | x | x | x | x | UNDP | 00005 | 71400 Contractual services - indiv. | 8 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 10 000 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care | x | x | x | x | NEX | 04000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 5 000 |
|  | 4.3. Increased access to potable water | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 2 500 |
|  |  | x | x | x | x | NEX | 04000 | 72100 Contractual Services -comp. | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 12 500 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  | 17 500 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual services - indiv. | 8 000 |
|  |  | x | x | x | x | NEX | 62000 | 73520 Support Services | 30 000 |
|  |  |  |  |  |  |  |  | Sub total | 50 000 |
|  | 5.3. An operational ecological monitoring system |  |  |  |  | NEX | 00005 | 71200 International Consultant | 30 000 |
|  |  |  |  |  |  |  |  | Sub total | 30 000 |
|  | 5.4. Guaranteed long-term funding for conservation | x | x |  |  | UNDP | 00005 | 713000 Local Consultant | 6 000 |
|  |  | x | x | x | x | UNDP | 62000 | 74600 Travel | 15 000 |
|  |  |  |  |  |  |  |  | Sub total | 21 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 5 000 |
|  | 5.6. Contribution to a national protected area system | x | x |  |  | UNDP | 04000 | 71300 Local consultant | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 5 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 111 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 7 | $ 158 500 |

| Year 8 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. | x | x | x | x | UNDP | 62000 | 74100 Professional services | 10 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 15 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 15 000 |
| 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practices | 2.3. Improved incomes from agricultural produce sold for higher prices |  |  | x | x | UNDP | 04000 | 71300 Local Consultant | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 5 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  | 5 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.2. Domestication and breeding of wild animals tested and disseminated |  |  |  |  | UNDP | 00005 | 71400 Contractual Services - indiv | 4 000 |
|  |  |  |  |  |  | NEX | 62000 | 74500 Miscellaneous Expenses | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 24 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 24 000 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care | x | x | x | x | UNDP | 04000 | 72200 Equipment | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  | 10 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractual Services - indiv | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual Services - indiv | 8 000 |
|  |  | x | x | x | x | NEX | 62000 | 735200 Support Services | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 40 000 |
|  | 5.4. Guaranteed long-term funding for conservation | x | x | x | x | UNDP | 00005 | 71600 Travel | 30 000 |
|  |  |  | x |  |  | UNDP | 00005 | 71200 International Consultant | 30 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 10 000 |
|  |  | x | x | x | x | NEX | 04000 | 74100 Professional services | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 75 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | UNDP | 62000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 5 000 |
|  | 5.6. Contribution to a national protected area system | x | x | x | x | NEX | 04000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  | x | x | x | x | UNDP | 00005 | 72200 Equipment | 25 000 |
|  |  |  |  |  |  |  |  | Sub total | 30 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 150 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 8 | 204 000 |

| Year 9 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. | x | x | x | x | NEX | 62000 | 74100 Professional services | 10 000 |
|  |  |  |  |  |  |  |  | Sub total | 10 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  | 10 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.2. Domestication and breeding of wild animals tested and disseminated | x | x | x | x | NEX | 62000 | 74100 Professional services | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  | 20 000 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.2. CEGEN’s human and material resources strengthened and well managed. | x | x | x | x | UNDP | 62000 | 71400 Contractual Services - indiv | 12 000 |
|  |  | x | x | x | x | UNDP | 62000 | 71400 Contractual Services - indiv | 8 000 |
|  |  | x | x | x | x | UNDP | 62000 | 735200 Support Services | 10 000 |
|  |  | x | x | x | x | NEX | 62000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 35 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | x | x | x | x | NEX | 04000 | 74500 Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  | Sub total | 5 000 |
|  | 5.6. Contribution to a national protected area system | x | x | x | x | NEX | 04000 | 74100 Professional services | 20 000 |
|  |  |  |  |  |  |  |  | Sub total | 20 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  | 60 000 |
|  |  |  |  |  |  |  |  | TOTAL YEAR 9 | 90 000 |

2.  Budget and Work Plan         (GEF, UNESCO, UNDP, Gvt, FFI, RDC and MINING)

Summary

|  |  |  |  |  | Total Budget and Workplan |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | (GEF, UNESCO, UNDP, Gvt, FFI, RDC and MINING) |  |  |
| EXPECTED Outcomes | Outputs. See Logical Framework Anlaysis for corresponding indicators and means of verification | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Yr1 | Yr2 | Yr3 | Yr4 | Yr5 | Yr6 | Yr7 | Yr8 | Yr9 |  | Source of Funds | Budget Description | Amount |
| 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | 1.1. Boundaries of the core areas recognized, legalized and demarcated | X | X | X |  |  |  |  |  |  | UNDP | 62000 | International consultant | 38 000 |
|  |  | X | X | X |  |  |  |  |  |  | UNDP | 62000 | Contractual services - indiv. | 22 000 |
|  |  | X | X | X |  |  |  |  |  |  | UNDP | 62000 | Contractual services - indiv. | 30 000 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 62000 | Local Consultant | 15 000 |
|  |  | X | X | X |  |  |  |  |  |  | NEX | 62000 | Equipments (Pictograms) | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 125 000 |
|  | 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages. |  |  | X | X |  |  | X |  |  | NEX | 62000 | Equipments Supplies | 30 000 |
|  |  |  |  | X | X |  |  |  |  |  | UNDP | 62000 | International consultant | 30 000 |
|  |  |  |  |  | X |  | X |  |  |  | UNDP | 62000 | Equipments | 20 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | Equipments | 20 000 |
|  |  |  |  |  |  | X |  |  |  |  | NEX | 62000 | Equipment and furniture | 10 000 |
|  |  |  |  | X | X | X | X |  |  |  | UNDP | 62000 | Contractual services - comp. | 65 000 |
|  |  |  |  | X |  |  | X |  | X | X | UNDP | 62000 | Professional Services | 60 000 |
|  |  |  |  | X | X | X | X |  |  |  | UNDP | 62000 | UNV (national) | 20 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 62000 | Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 260 000 |
|  | 1.3. Decrease in incursions and illegal activities in the core areas. |  |  | X | X | X | X | X | X | X | NEX | 00123 | Support Services | 500 000 |
|  |  |  |  |  |  |  |  |  |  |  | NEX | 00311 | Equipment | 486 500 |
|  |  |  |  | X | X | X | X | X | X | X | NEX | 00123 | Equipment | 40 000 |
|  |  |  | X | X | X | X | X |  |  |  | NEX | 00311 | Miscellaneous Expenses | 50 000 |
|  |  |  | X | X |  |  |  |  |  |  | UNDP | 62000 | Contractual services -comp | 100 000 |
|  |  | X |  |  | X |  |  |  |  |  | UNDP | 00005 | Contractual services -comp | 50 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 62000 | Contractual services - indiv. | 15 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | Contractual services - indiv. | 10 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 62000 | Contractual services - indiv. | 10 000 |
|  |  | X |  |  |  |  |  |  |  |  | NEX | 62000 | Equipment | 665 500 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 62000 | Support Services | 60 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 62000 | Travel | 20 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 62000 | Local Consultant | 15 000 |
|  |  |  |  |  | X | X | X |  |  |  | NEX | 62000 | Professional services | 47 800 |
|  |  |  |  | X |  |  |  |  |  |  | NEX | 04000 | Professional services | 20 000 |
|  |  |  |  |  |  | X |  |  |  |  | NEX | 04000 | Miscellaneous expenses | 20 000 |
|  |  |  |  | X | X |  |  |  |  |  | NEX | 62000 | Miscellaneous expenses | 20 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 62000 | International consultants | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 2 159 800 |
|  | 1.4. Improved compatibility of planned mining activities, and strengthened cooperation | X |  | X |  |  |  |  |  |  | UNDP | 62000 | Contractual services - comp | 120 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | Local Consultant | 7 000 |
|  |  |  |  |  | X |  |  |  |  |  | NEX | 04000 | Professional services | 10 000 |
|  |  |  |  |  | X | X | X | X | X |  | NEX | 00311 | Contractual services - comp | 100 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 237 000 |
|  | 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities | X |  |  |  |  |  |  |  |  | NEX | 62000 | Support Services | 50 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 04000 | Local Consultant | 6 000 |
|  |  |  | X |  | X |  |  |  |  |  | UNDP | 05000 | Local Consultant | 13 300 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 62000 | Contractual services - comp. | 100 000 |
|  |  | X | X |  |  |  |  |  |  |  | NEX | 04000 | Travel | 25 000 |
|  |  |  |  | X |  |  |  |  |  |  | NEX | 62000 | Travel | 10 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 62000 | Miscellaneous expenses | 20 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 62000 | Professional Services | 30 000 |
|  |  |  |  | X | X |  |  |  |  |  | NEX | 00311 | Contractual services - comp | 300 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 554 300 |
|  | 1.6. Impacts of refugees do not affect the core areas. | X |  | X |  |  |  |  |  |  | NEX | 62000 | Miscellaneous expenses | 30 000 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 04000 | Local Consultant | 15 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 62000 | Contractual services - comp. | 20 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 05000 | Contractual services - comp. | 15 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 80 000 |
| Sub-Total Outcome 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 416 100 |
| 2. Sustainable land use and agricultural revenues of local people increased on the basis of more productive practices. | 2.1. Sustainable land use systems | X | X |  |  |  |  |  |  |  | UNDP | 62000 | International consultant | 30 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | International consultant | 8 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 04000 | Local Consultant | 5 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | Contractual services - comp. | 30 000 |
|  |  |  | X | X | X |  |  |  |  |  | NEX | 04000 | Miscellaneous expenses | 40 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | Equipments | 10 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | Equipment Supplies | 5 000 |
|  |  |  |  | X |  |  |  |  |  |  | NEX | 04000 | Equipment and Furnitures | 10 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 138 000 |
|  | 2.2. Increased agricultural yields |  | X | X |  |  |  |  |  |  | UNDP | 04000 | International Consult. | 30 000 |
|  |  |  | X |  | X | X |  |  |  |  | UNDP | 04000 | contractuel services- indiv | 23 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | Local Consultant | 5 000 |
|  |  |  | X | X | X | X |  |  |  |  | UNDP | 04000 | Contractuel services -compag | 230 000 |
|  |  |  |  | X | X | X | X | X | X |  | NEX | 00311 | Contractual services - comp | 1 093 500 |
|  |  |  |  |  | X | X | X |  |  |  | NEX | 00123 | Contractual services - comp | 110 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 1 491 500 |
|  | 2.3. Improved incomes from agricultural produce sold for higher prices |  |  | X | X |  |  |  |  |  | NEX | 04000 | Miscellaneous expenses | 65 000 |
|  |  |  | X | X |  | X |  |  |  |  | UNDP | 04000 | Contractual services-comp | 60 000 |
|  |  |  |  |  |  |  |  |  |  |  | NEX | 04000 | Miscellaneous expenses | 0 |
|  |  |  | X | X |  | X |  |  | X |  | UNDP | 04000 | Local consultant | 23 000 |
|  |  |  |  | X | X |  | X |  |  |  | UNDP | 04000 | Grant | 130 000 |
|  |  |  |  | X | X |  | X |  |  |  | UNDP | 62000 | Grant | 195 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | Travel | 15 000 |
|  |  |  |  |  | X | X |  |  |  |  | NEX | 00311 | Contractual services - comp | 100 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 00123 | Contractual services - comp | 46 500 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 634 500 |
|  | 2.4. Diversified income sources |  |  |  | X | X |  |  |  |  | NEX | 04000 | Miscellaneous expenses | 35 000 |
|  |  |  |  |  | X | X | X |  |  |  | UNDP | 04000 | UNV (national) | 24 000 |
|  |  |  |  |  | X | X |  |  |  |  | UNDP | 04000 | Equipment/ Procurement MFP | 45 000 |
|  |  |  |  |  |  |  |  | X |  |  | NEX | 04000 | Professionnel Services | 10 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 114 000 |
| Sub-Total Outcome 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 378 000 |
| 3. Local needs for animal protein more fully met using practices that do not damage wildlife | 3.1. More productive animal husbandry, integrated with agriculture |  | X | X | X | X |  |  |  |  | NEX | 62000 | Miscellaneous expenses | 55 000 |
|  |  |  | X | X | X | X | X |  |  |  | UNDP | 62000 | Contract services-Comp | 200 000 |
|  |  | X |  |  |  |  |  |  |  |  | UNDP | 4000 | Contractual services - comp | 110 000 |
|  |  |  | X | X |  |  |  |  |  |  | NEX | 4000 | Miscellaneous Expenses | 60 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 425 000 |
|  | 3.2. Domestication and breeding of wild animals tested and disseminated |  | X | X | X | X | X | X |  |  | UNDP | 04000 | UNV Veterinian | 38 000 |
|  |  |  | X | X | X | X | X |  |  |  | UNDP | 00005 | Contractual services-indv | 86 000 |
|  |  |  | X | X | X | X |  |  |  |  | UNDP | 62000 | Contractual services-indv | 26 000 |
|  |  |  | X | X | X | X | X |  |  |  | UNDP | 00005 | Contractual services-indv | 24 000 |
|  |  |  |  |  |  |  | X |  | X |  | NEX | 62000 | Miscellaneous Expenses | 27 000 |
|  |  |  | X | X | X | X |  |  |  |  | NEX | 00005 | Miscellaneous Expenses | 43 700 |
|  |  |  | X |  | X |  |  |  |  |  | UNDP | 62000 | Contractuel services-comp. | 112 000 |
|  |  |  |  |  |  |  |  |  |  | X | NEX | 62000 | Professional services | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 376 700 |
|  | 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner | X | X | X | X | X |  |  |  |  | UNDP | 62000 | Miscellaneous expenses | 101 000 |
|  |  |  | X |  | X |  |  |  |  |  | NEX | 62000 | Miscellaneous expenses | 65 000 |
|  |  |  | X |  | X |  |  |  |  |  | UNDP | 62000 | Equipment/Supplies wild species | 103 200 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 04000 | Local Consultant | 11 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 280 200 |
| Sub-Total Outcome 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 081 900 |
| 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve | 4.1. Improved medical and para-medical health care |  |  | X | X |  |  |  |  |  | UNDP | 04000 | Equipment (drugs) | 50 000 |
|  |  |  | X |  | X | X |  |  |  |  | UNDP | 04000 | Contractuel services-comp. | 60 000 |
|  |  |  |  |  |  |  | X |  | X |  | NEX | 04000 | Equipment | 20 000 |
|  |  |  |  |  |  |  |  | X |  |  | NEX | 04000 | Miscellaneous Expenses | 5 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | Local consultant | 10 000 |
|  |  |  |  |  | X | X |  |  |  |  | NEX | 00311 | Contractual services - comp | 100 000 |
|  |  |  |  |  |  | X | X | X |  |  | NEX | 00311 | Contractual services - comp | 100 000 |
|  |  |  |  |  | X | X |  |  |  |  | NEX | RDC | Contractual services - comp | 50 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 395 000 |
|  | 4.2. Increased access to health care |  |  |  | X | X |  |  |  |  | UNDP | 04000 | Miscellaneous expenses | 25 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 04000 | Contractual services-comp. | 50 000 |
|  |  |  |  |  | X | X | X |  |  |  | NEX | 00311 | Contractual services - comp | 100 000 |
|  |  |  |  |  |  |  |  | X | X |  | NEX | RDC | Contractual services - comp | 20 000 |
|  |  |  |  |  |  |  |  | X | X |  | NEX | 00123 | Contractual services - comp | 80 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 275 000 |
|  | 4.3. Increased access to potable water | X |  | X | X | X | X | X |  |  | UNDP | 62000 | Contractual services-comp. | 42 500 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 04000 | Contractual services-comp. | 10 000 |
|  |  |  |  | X |  |  | X |  |  |  | UNDP | 04000 | Profesional services | 40 000 |
|  |  |  |  |  | X |  |  |  |  |  | UNDP | 62000 | Travel | 15 000 |
|  |  | X | X | X | X | X |  | X |  |  | NEX | 04000 | Contractuel services-comp. | 137 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Contractual services - comp | 250 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Miscellaneous Expenses | 90 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Contractual services - comp | 170 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Miscellaneous Expenses | 80 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 834 500 |
|  | 4.4. Improved hygiene practices |  |  |  | X |  | X |  |  |  | UNDP | 00005 | Contractuel services-comp | 30 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Contractual services - comp | 150 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00123 | Miscellaneous Expenses | 54 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | RDC | Contractual services - comp | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 264 000 |
| Sub-Total Outcome 4 |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 768 500 |
| 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system | 5.1. Synergy ensured between institutions and between interventions. | X | X | X |  |  |  |  |  |  | UNDP | 62000 | Contractual services-comp | 135 000 |
|  |  | X | X | X | X | X |  |  |  |  | UNDP | 62000 | UNV (national) | 30 000 |
|  |  | X | X |  |  |  |  |  |  |  | UNDP | 00005 | International consultant | 60 000 |
|  |  | X |  |  | X |  |  |  |  |  | UNDP | 62000 | Miscellaneous Expenses | 65 000 |
|  |  |  | X |  |  |  |  |  |  |  | UNDP | 00005 | Local consultant | 10 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Contractual services - comp | 250 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 4000 | International Consultant | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 580 000 |
|  | 5.2. CEGEN’s human and material resources strengthened and well managed. | X | X | X | X | X | X | X | X | X | UNDP | 62000 | Contractual services-indiv. | 108 000 |
|  |  | X | X | X | X | X | X | X | X | X | UNDP | 62000 | Contractual services-indiv. | 72 000 |
|  |  |  |  | X |  |  | X | X | X | X | UNDP | 62000 | Support Services | 152 000 |
|  |  |  |  |  | X | X |  |  |  |  | UNDP | 04000 | Support Services | 79 400 |
|  |  |  |  |  |  |  | X |  |  |  | UNDP | 04000 | Contractual services-comp | 15 000 |
|  |  |  | X |  |  |  |  |  |  |  | NEX | 04000 | Miscellaneous expenses | 15 000 |
|  |  |  |  |  |  |  |  |  |  | X | NEX | 62000 | Miscellaneous expenses | 5 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Miscellaneous Expenses | 180 000 |
|  |  |  |  |  |  | X | X | X | X | X | NEX | 00311 | Contractual services - comp | 400 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 1 026 400 |
|  | 5.3. An operational ecological monitoring system | X | X | X |  |  |  |  |  |  | UNDP | 62000 | Contractual services - indiv. | 72 000 |
|  |  | X | X |  |  |  |  |  |  |  | NEX | 00005 | Miscellaneous expenses | 55 000 |
|  |  | X | X | X | X | X | X |  |  |  | UNDP | 62000 | UNV/GIS | 32 000 |
|  |  | X | X | X | X | X |  |  |  |  | UNDP | 62000 | Contractual services-comp | 230 000 |
|  |  |  |  |  |  |  |  | X |  |  | UNDP | 00005 | International Consultant | 30 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 419 000 |
|  | 5.4. Guaranteed long-term funding for conservation |  |  |  |  |  |  | X |  |  | UNDP | 00005 | Local Consultant | 6 000 |
|  |  |  |  |  |  |  |  |  | X |  | UNDP | 62000 | Miscellaneous Expenses | 10 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 04000 | Professional services | 5 000 |
|  |  |  |  |  |  |  |  | X |  |  | NEX | 62000 | Travel | 15 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 00005 | Travel | 30 000 |
|  |  |  |  |  |  |  |  |  | X |  | UNDP | 00005 | 71200 International Consultant | 30 000 |
|  |  |  |  |  |  |  |  | X | X | X | NEX | 00311 | Miscellaneous Expenses | 500 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 596 000 |
|  | 5.5. Stakeholders better informed and aware of the issues and of resource conservation | X | X | X |  |  |  |  |  |  | UNDP | 04000 | Local Consultant /IEC | 20 000 |
|  |  | X | X |  | X | X | X | X | X |  | NEX | 62000 | Miscelaneous expenses | 56 000 |
|  |  |  |  | X |  |  |  |  |  | X | NEX | 04000 | Miscelaneous expenses | 10 000 |
|  |  |  |  | X |  |  |  |  |  |  | UNDP | 62000 | Contractual services-comp | 10 000 |
|  |  | X |  |  |  |  |  |  |  |  | NEX | 62000 | Travel | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 116 000 |
|  | 5.6. Contribution to a national protected area system |  |  |  |  |  |  | X |  |  | UNDP | 04000 | Local consultant | 5 000 |
|  |  |  |  |  |  |  |  |  | X |  | NEX | 04000 | Miscellaneous Expenses | 5 000 |
|  |  |  |  |  |  |  |  |  | X |  | UNDP | 00005 | Equipment | 25 000 |
|  |  |  |  |  |  |  |  |  |  | X | NEX | 04000 | Professional services | 20 000 |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Sub total | 55 000 |
| Sub-Total Outcome 5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 792 400 |
| Total Programme Budget |  |  |  |  |  |  |  |  |  |  |  |  | 11 436 900 |

# SIGNATURE PAGE

Country: Republic of Guinea

UNDAF Outcome(s)/Indicator(s):	(i) – Improve agricultural production and the proportion of people accessing a minimum caloric intake; (ii) – Improve the living conditions of the people; (iii) Promote good local governance and knowledge of human rights; (iv) Operationalise the mechanism for national conflict resolution and risk & catastrophe management.

Expected Outcome(s)/Indicator (s):	Global concerns and commitments related to the environment integrated into national policies and planning

Expected Output(s)/Indicator(s):	National biodiversity strategy and action plan approved in 2002, and implemented via the Nimba Mountains Biodiversity programme that will conserve the site’s biodiversity through integrated and participatory management until 2013

Implementing partner:			Ministry of Environment, Government of Guinea

(designated institution/Executing agency)

Other Partners:				UNDP-Guinea, UNESCO/WHC, national NGOs

(formerly implementing agencies )

Decentralised governmental technical agencies

International development agencies & NGOs

Agreed by El hadj Theirno Habib Diallo for Government of Guinea: _______________________

Minister of Cooperation

Agreed by Mr. Cheick Abdel Kader Sangaré for the Executing Agency:_____________________

Minister of Environment

Agreed by Mr. Kingsley O. Amaning of UNDP:__________________________________________

UNDP Resident Representative

# ANNEXES

Annex 1 – Comments and responses to comments from GEF Council members to the project proposal

Annex 2 – Monitoring & Evaluation Plan

Annex 3 – Nimba Mountains Stakeholder and Public participation plan

Annex 4 – Table indicative monitoring and evaluation work plan and corresponding budget

Annex 5 – Programme Structure

Annex 6 – Summary of information for selected protected areas: data sheet

Annex 7 – TOR of the project staff and consultants

Annex 8 – TOR of the Steering Committee

Annex 9 – Co- financing letter from the Government

Annex 10 – Co-financing letter from the locale communities

Annex 11 – Budget

Annex 12 – Brief document approved in May 2003

## Annex 1 – Comments from GEF Council members to the project brief; responses to comments

Guinea: Conservation of the Biodiversity of the Nimba Mountains through Integrated and Participatory Management (UNDP, GEF: $3.990 m, Total Cost: $11.889)

Reference to GEF/C.21/Inf.14 May 14-16, 2003

| Comments From GEF Council members | Response | Where in ProDoc |
| --- | --- | --- |
| I. Comments from France |  |  |
| What is the justification for a single nine-year phase while during that time political, economic and ecological situation (mine exploitation) is going to greatly change. We wonder about the duration of the commitment, 9 years, during which the political, economic and ecological situation (mine exploitation) is going to greatly change: is it acceptable in the current procedures of the GEF or isn’t it better to have 2 phases? | To achieve sustainable solutions in a complex situation of biodiversity conservation and mining interests, a long time frame of at least 9 years was deemed necessary. Because political, economic and ecological risks cannot be fully neutralised in advance, the project will be executed in a flexible and iterative manner enabling it to adapt to changing circumstances. It is organised into three internal operational phases whereby during the first phase, the programme will emphasise putting in place CEGEN’s and the programme’s operational infrastructure, developing detailed plans for the reserve’s core areas and for rural development support. Phase two will launch activities designed in phase 1, and continue those already launched, with emphasis on the core areas and the buffer zone. Phase 3 will continue activities launched during the preceding phases, launch any remaining activities, expand activities to the transition area, and consolidate the sustainability of all activities so they may continue after the programme closes. This approach will permit the project to adjust to changing circumstances. Because it is no longer current GEF procedure to approve long-term financial commitments to projects, at the time of brief discussions, UNDP resorted for a one-time cost effectiveness request to the GEF, while it would support the remainder of the funds from its own resources beyond year 3 (US $1.6million). | Sections 4.2 – 4.4 (paragraphs 68-71) explain the internal phasing of the project. |
| II. Comments From Germany |  |  |
| We understand from the project proposal that co-operation with the local population of Mount Nimba Biosphere Reserve is taken into account and key decisions will be taken in consultation with local communities. The project title, however, promises more, namely the participatory management of the biosphere reserve. Our understanding of participatory management is more than consultations with local communities, and includes in particular a transfer of responsibility to the local population. Participatory management can thus be seen as a process of negotiations between the protected area administration and the local communities. Fields of negotiation are e.g. the borders of the protected areas and their buffer zones, the rights and the responsibilities of the various stakeholders, and the kind and degree of the various forms of utilization of the area. The result of such negotiations is a management plan which is as such not a plan what to do, developed by experts, but a process and a management agreement. In order to fulfill its own expectations and goals, we think that the project should re-assess the degree of participation anticipated, and thus also the kind of management plans to be prepared. | Preparation involved consultations, above all, rather than joint development of management plans and other elements at the level indicated by Germany. However during programme implementation, not only will consultations between the project management team and stakeholders be undertaken at Nimba, numerous activities (1.3.2-3, 1.5.1-3, 2.1.1-4, 2.2.1, 2.2.1-2, 3.2.1, 3.3.1, 4.2.2, 5.1.2-4, 5.4.1-2, 5.5.1-2) involve true participation in terms of defining roles, responsibilities and benefit-sharing, and negotiating programme activities. The project was re-assessed during project document (PRODOC) preparation to deepen anticipated participation, and this will again be revisited during the inception workshop. | See Annex 3 on Stakeholder Participation. See also the activities listed in the second column. |
| Project component 3 deals with meeting the need by the local population for animal protein, and project component 4 with improving the health conditions of local communities. These issues are without doubt important for integrated, sustainable development, but are hardly in compliance with GEF’s role as an environmental funding mechanism. As these two components are funded largely through sources provided by other donors, it is suggested to keep them separate from the GEF project, and to treat it at most as associated activities. | While people’s health and livelihood are not in the scope of the GEF mandate on biodiversity conservation, this project, which aims at biodiversity conservation in areas of conflicting mining interests needs, to find a win-win solution among various stakeholders. Indeed such a solution at Nimba for the conflicting interests cannot be found and implemented without addressing all needs within the system boundary encompassing local communities’ sustainable-development needs, government needs for mineral income as well as global biodiversity conservation concerns. Hence the project is to reach a win-win situation both within the protected areas (mining and conservation) as well as surrounding communities (health, agriculture and livelihood) and be able to allow proceed at large for the government through mining without jeopardizing conservation. Also, for the overall project objective to be met, there is a need to look over various components (mining; conservation; livelihood - health and agriculture) that constitute the major elements of the problem tree. This is why if agricultural or health concerns are left out, the project would run the risk of not realising its overall objectives achieved. This is why in designing the project, donors with various mandates - conservation and livelihoods - were consulted and have agreed to participate in this endeavor under the leadership of UNDP and UNESCO. | See the problem tree in the project proposal (Annex 1 to Annex 12 of this prodoc) to understand the inter-dependence of the difference components. |
| We could not get a clear picture on co-financing which contributes after all 66% to the project costs. More information should be given on how these funds are provided, and whether the management of the GEF project has direct access to these funds. | The major donor for the project outside the protected areas is UNDP with its core track monies; and UNDP is the GEF project implementing agency. Among other donors are the mining consortium proposing to extract ore from a part of the Nimba Mountains in the buffer zone. There is an agreed cost-sharing mechanisms among donors for the Nimba project that will be coordinated by UNDP-Conakry. Also more than 60% of co-financing contributions will be coming from UNDP. | See Letters of co-financing UNDP, UNF, UNESCO, FFI, Government of Guinea, etc. |
| There are certain inconsistencies in the project document, and we observed a certain laxity with formulations. There are, for example, differences in the wording of the project components and the project results between the project document and the executive summary. The project proposal includes non-timber products under project component 3, but these are not included in the executive summary. The table on the Programme Output Budget calls component 3 “Sustainable harvesting of bush meat and medicinal plants” what is quite different from what has been described in the text (where the harvest of bush meat is not an issue). | Action was taken to take out the inconsistencies between executive summary and project brief, and the heading in budget. | See Executive Summary of Brief See also renaming of project component 3 in output budget. |
| III. Comments From Sweden |  |  |
| We consider the project highly relevant with its objective of conservation/sustainable use of an area of high global interest. | Yes, that’s completely true |  |
| The focus on traditional medicine and complementarity between modern and traditional medicine is positive. | Agree completely…This is why in a complex situation such a s in the Nimba it is important to look over various components be they for livelihood needs, mining and conservation concerns to achieve sustainable results. |  |
| According to the document Guinea is deeply committed to the project. At the same time a key assumption is that the nucleus of the reserves will be included in the officially protected areas. If Guinea is so committed, why aren’t they already included? | The Nimba Mountains are already a biosphere reserve. However because of mining pressures the biosphere core areas were historically moved around as new mining areas within the Nimba were discovered. Hence to stabilize the situation it is important to bring about a consensus on the final location of the core areas and provide them with strong legal protection. This is why Activities 111 and 112 are to legally define these core areas on the ground and on the map. |  |
| There are a number of general indications of local stakeholder participation in the document, but no description of relevant mechanisms to achieve this? | A stakeholder participation plan has been drawn during ProDoc preparation stage. There will be consultations and processes of achieving agreements on consensual plans and how to share benefits, the role and responsibilities of each group of stakeholders and what incentives for participation. Planning activities are in Output 11, Output 14 and Output 15 | See response to the French concerns above, and Annex 3 (the stakeholder participation plan). |

## Annex 2 - Monitoring and Evaluation Plan

On-going project monitoring will be provided in accordance with established UNDP procedures and will be provided by the UNDP County Office with support from UNDP/ GEF.  Overall supervision of the Project will be the responsibility of the National Project Administrator (NPA).

Internal Monitoring & Evaluation

Tripartite Review (TPR)

The tripartite review (TPR) is the highest policy-level meeting of the parties directly involved in the implementation of a project. The project will be subject to Tripartite Review (TPR) at least once every twelve months by representatives of the Government, the executing agency and UNDP.  The first such meeting will be held within the first twelve months of the start of full implementation. The Project team shall prepare an Annual Project Report (APR) and to submit to UNDP.  The APR must be ready two weeks prior to the TPR.

The APR will be used as one of the basic documents for discussions in the TPR meeting. The National Project Administrator presents the APR to the TPR, highlighting policy issues and recommendations for the decision of the TPR participants.  The NPA also informs participants of any agreement reached by stakeholders during the APR preparation on how to resolve operational issues. Six-monthly APR’s will occur during the first two years of the project to ensure that design and inception activities are closely monitored, and subsequently the APR will be done on an annual basis. Separate reviews of each state component may also be conducted if necessary.  Monitoring and Evaluation Indicators will be built into the project in consultation with UNDP.

Terminal Tripartite Review (TTR)

The terminal tripartite review is held in the last month of project operations. The Project team is responsible for preparing the Terminal Report and submitting to UNDP. It shall be prepared in draft sufficiently in advance to allow review and technical clearance by the executing agency at least two months prior to the terminal tripartite review. The Terminal Report will serve as the basis for discussions in the TTR. The terminal tripartite review considers the implementation of the project as a whole, paying particular attention to whether the project has achieved its immediate objectives and contributed to the broader environmental objective, and decides whether any actions are still necessary.

Project Implementation Review (PIR)

A major tool for monitoring the GEF portfolio and extracting lessons is the annual GEF Project Implementation Review (PIR).  The PIR has become an essential management and monitoring tool for project managers and offers the main vehicle for extracting lessons from ongoing projects.

The PIR is mandatory for all GEF projects that have been under implementation for at least one year at the time that the exercise is conducted.  A project becomes legal and implementation activities can begin when all parties have signed the project document.  The PIR questionnaire is sent to the UNDP country office, usually around the beginning of June.  It is the responsibility of the NPA to complete the PIR questionnaire, with the oversight of the UNDP Country Office.

The project will also be closely monitored by the UNDP Country Office through quarterly meetings, or more frequently, as deemed necessary with the National Project Administrator and the project team. This will allow to take stock and to trouble shoot of any problems pertaining to the project quickly to ensure smooth implementation of project activities.

External Monitoring & Evaluation

Mid-term Evaluations

Independent Mid-Term Evaluations will be undertaken during years three and six to evaluation progress towards the internal phases’ goals (Section I, Part 4, items 4.2 – 4.4). The Mid-Term Evaluation will focus on the effectiveness, efficiency and timeliness of project implementation, highlighting issues requiring decisions and actions, and presenting lessons learned about programme design, implementation and management.  The evaluations will recommend whether and how to proceed to the next phase of the programme, and findings will be incorporated as recommendations for improving implementation during the subsequent phase.  The organization, terms of reference and timing of the mid-term evaluations will be decided after consultation between the parties to the project document.

Final Evaluation

An independent Final Evaluation will take place three months prior to the terminal tripartite review meeting, and will focus on the same issues as the mid-term evaluation.  The final evaluation will also look at early signs of potential impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental goals.  The Final Evaluation should also provide recommendations for follow-up activities.  The organization, terms of reference and timing of the final evaluation will be decided after consultation between the parties to the project document.

Learning and Knowledge Sharing

- To participate in UNDP/GEF networks, organized for Senior Personnel working on projects that share common characteristics, UNDP/GEF shall establish a number of networks, such as Forest Conservation from the year 2002, that will largely function on the basis of an electronic platform.

- To identify and participate in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned, such as the mountain conservation network of the World Conservation Union (IUCN).

- To identify, analyze, share and communicate lessons learned that may be beneficial in the design and implementation of similar future projects. The need to identify and analyze lessons learned is an on- going process, and the need to communicate such lessons is on an as-needed basis, but not less frequently than once every 12 months, UNDP/GEF shall provide a format for categorizing and reporting lessons learned.

- To ensure that the Terms of Reference for consultants recruited by the project incorporate tasks which insure that lessons learned in TOR are captured and streamlined into project mechanisms for documentation and decision making.

Reporting

The Project team will be responsible for the preparation and submission of the following reports:

(a)	Inception Report

The inception report is to be prepared by the Project NPA with the assistance of the project experts as relevant.  The inception report will be prepared no later than three months after project start-up and will include a detailed Work plan and Budget for the duration of the project, progress to date on project establishment and start-up activities and any proposed amendments to project activities or approaches.  The report will be circulated to all the parties who will be given a period of one calendar month in which to respond with comments or queries.  The report will also be reviewed by UNDP and GEF to ensure consistency with the objectives and activities indicated in the Project Document.

- Annual Programme/Project Report (APR)

The Annual Project Report (APR) is designed to obtain and document the independent views of the main stakeholders of a project on its relevance, performance and the likelihood of its success. The APR aims to: a) provide a rating and textual assessment of the progress of a project in achieving its objectives; b) present stakeholders' insights into issues affecting the implementation of a project and their proposals for addressing those issues; and c) serve as a source of inputs to the Tripartite Review (TPR). The main project stakeholders participate in the preparation of the APR.

The APRs will be prepared every six months during the first year of the project, and then annually.  The APRs will detail activities undertaken since the last APR, milestones reached, key results and achievements, problems encountered and any other issues that need to be highlighted.

- Periodic Status Reports

As and when called for by the National Project Administrator, the government or UNDP, the Project Administrator will prepare Status Reports, focusing on specific issues or areas of activity as stipulated by the requesting authority. The request for a Status Report will be in written form, and will clearly state the issue or activities that need to be reported on.  These reports can be used as a form of specific oversight in key areas, or as troubleshooting exercises to evaluate and overcome obstacles and difficulties encountered.  The parties are requested to minimize their requests for Status Reports, and when such are necessary will allow reasonable timeframes for the preparation of these Reports.

- Technical Reports

Technical Reports are detailed documents covering specific areas of analysis or scientific specializations within the overall project.  As part of the Inception Report the Project Administrator will prepare a draft Reports List, detailing the technical reports that are expected to be prepared on key areas of activity during the course of the Project, and tentative due dates.  Where necessary this Reports List will be revised and updated, and included in subsequent APRs.  Technical Reports may also be prepared by external consultants as Final Reports for their technical inputs, and should be comprehensive, specialized analyses of clearly-defined areas of research within the framework of the project and its sites.

- Project Publications

Project Publications will form a key method of crystallizing documenting and disseminating the results and achievements of the Project.  These publications will be scientific or informational texts on the activities and achievements of the Project, in the form of books, journal articles or multimedia publications.  The Publications can be based on Technical Reports, depending upon the relevance, scientific worth, etc. of these Reports, or may be summaries or compilations of a series of Technical Reports and other research.  The Project Administrator will determine if specific Technical Reports merit formal publication, and will also (in consultation with the government and other parties and with the help of external specialists and staff where necessary) plan and produce these Publications in a consistent and recognizable format and identity.  These Publications will form the most visible public output of the Project, and as such should be prepared and presented to the highest scientific and technical standards.

(f)	Project Terminal Report

During the last three months of the project the Project Administrator will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs of the Project, lessons learned, objectives met and missed, structures and systems implemented, etc. and will be the definitive statement of the Project’s activities over the five-year duration.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the Project’s activities.

(g)	Other Publications and Publicity Activities

In order to ensure international dissemination of project results, a high-quality publication of results will be prepared, based upon the Project Terminal Report and previous Project Publications. Finally, it will be useful to hold at least one international workshop at which policy makers in neighboring countries can be made aware of the country’s progress in achieving the project’s goals.

- The WB/WWF management effectiveness tracking tool

The WB/WWF management effectiveness tracking tool is a new requirement that has been introduced since the GEF Council in May 2003 as a side outcome of the information paper to Council on the new strategic priorities for the business planning period FY04-06. The GEF Secretariat requires all projects falling under biodiversity strategic priority 1 (SP-1) to apply this tool. It has been designed for use at the site level, and it is quite adequate for Nimba. The projects are expected to apply this tool at least at three points in the project cycle: in the beginning, during project preparation to establish baseline values; at mid-term and at project completion. The tool allows to monitor a trend: is the project moving things (in this case management effectiveness) in the right direction. The absolute value of the indicator is not of much use, but using the same at several points in the project cycle on the same site allows to compare the values and describe a trend.

Nimba Mountains Monitoring and Evaluation Summary Table

| Monitoring and Evaluation Tool by Semester | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Responsibility |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 |  |
| Monitoring by the project team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project team & NPA |
| Supervisory mission by UNDP-Conakry |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNDP / CO |
| Supervisory mission by UNDP-GEF Regional Coordinator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | UNDP / GEF Regional |
| Co-ordination meetings with co-financing project partners |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project team and NPA |
| Independent evaluation (midterm during first semester of Year 3, and final six months before end of project) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Evaluation team UNDP / GEF Regional and Project team Govt/UNDP/CO |
| Project Steering Committee meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project coordinator NPA |
| Annual Project Report (APR), followed by Tripartite meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NPA Project team |
| Audit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Government /Ministry Cooperation UNDP, Project team |
| WB-WWF management Effectiveness Tracking Tool |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | NPA Project team |

## Annex 3 – Nimba Mountains Stakeholder and Public participation plan

As stated throughout this document, the threats to the NMBR and it biological resources are intimately linked to the livelihoods of local residents, and any lasting solution necessarily entails the genuine collaboration of local villages, economic groups/collectives, local authorities and the decentralised sectoral services and development programmes operating in the zone.  Problem identification and the definition of solutions during the PDF B preparatory phase were highly participatory, being based upon extensive local consultations, several information-sharing meetings and a several-day ‘ZOPP’ workshop in which the problem analysis was reviewed and validated by a range of local actors and the programme’s components were defined in response.

The strategy to be followed during programme implementation will be based upon detailed and site-specific information collection for any community assistance/development action (components 2-4), including consultations with intended beneficiaries (not only heads of RDCs or collectives) and co-designing of specifically tailored assistance projects.  Under component 5, the programme will establish and run forums for communities to communicate their needs, perspectives and concerns related to the overall Reserve.  A similar forum, but pitched at an appropriately different level, will be created to bring together CEGEN with representatives of local communities, local authorities, decentralised sectoral services, development programmes active or interested in the zone, the mining company, UNESCO and MAB representatives and any other relevant stakeholder to co-ordinate interventions, realise synergies and provide input into the NMBR development master-plan. Furthermore, local communities will be involved in developing management plans for the three core areas and in protecting them through village-based patrols.

The participatory processes established during the programme should be able to continue after external support ends because they do not require significant resources particularly once they are running and prove their value to local stakeholders.  Once their value is evident and a culture of dialogue and joint planning is established, this culture of participation can be sustained with little external support.

The following tables present, first, the main stakeholders identified and, second, the stakeholders that will be involved in each activity, as well as which actions will be carried out in the pre-programme, programme and post-programme periods.

List of stakeholders

- The Guinean State

- Ministry of Environment

- Centre for the Management of the Environment of the Nimba Mountains (CEGEN)

- Hired programme personnel

- Sectoral agencies/services (ERIB, NDWF, NDSTR, NDE, NDA, NDL, NDH …)

- Decentralised sectoral services (local authorities)

- Programme Steering Committee

- Rural collectives (RDCs)

- Local residents (farmers, pastoralists/animal breeders, hunters, traditional doctors …)

- Private sector (EuroNimba, Rio Tinto, Forestry companies, Traders … )

- Development partners (USAID, GTZ, AFD/FFEM, Japan, IFAD …)

- International organisations (UNDP, GEF, UNESCO, World Bank, FAO … )

- National and local NGOs (UVIDOZ, other s … )

- International NGOs (FFI, Birdlife International, Conservation International …)

| Specific Objective 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | List of Stakeholders and Participants in Outputs and Activities for Mount Nimba | Before Implementation (Incentives for Participation, Actual Involvement, Roles & Responsibilities) | During Implementation (Incentives for Participation, Involvement, Roles & Responsibilities) | Roles & Responsibilities after the Project (Participation for Sustainability) |
| --- | --- | --- | --- | --- |
| Output 1.1. Boundaries of the core areas recognized, legalized and demarcated |  |  |  |  |
| Activity 1.1.1. Complete the process of legalizing the Core Areas | Government CEGEN RDC and private sector | Consultation at all levels for developing the draft laws | Preparation of the legislation | Monitoring of law enforcement |
| Activity 1.1.2. Demarcate the boundaries of the core areas | Government CEGEN Decentralised services | Consultation at all levels for developing the draft laws | Boundary demarcation IEC | Monitoring of law enforcement |
| Output 1.2. Dynamics of the core areas’ biodiversity known, threats precisely described and management actions identified with participation of buffer zone villages |  |  |  |  |
| Activity 1.2.1. Study the impact of fires, evaluate human impacts on fire dynamics and identify appropriate management responses | CEGEN Decentralised services NGOs | Design of a plan of studies and inventories IEC | Updating of ecological studies and inventories IEC | On-Going patrolling of the core areas IEC |
| Activity 1.2.2. Develop a deeper understanding of the impacts of mining activities, including those related to introduced species | Ministry of Environment CEGEN Development partners NGOs | Consultation and information exchange/dialogue reinforced with project mining team | Updating of ecological studies and inventories Participation in design of Environmental convention | Follow up of the convention |
| Activity 1.2.3. Develop a deeper understanding of conservation priorities, and identify solutions with participation of local communities | CEGEN Decentralised services Local population – RDC | Updating of ecological studies and inventories | Conception of and implementing the master plan with the population | Updating the master plan before the end of year 5 |

| Specific Objective 1. Ecological integrity assured for the three Core Areas of the Nimba Mountains Biosphere Reserve | List of Stakeholders and Participants in Outputs and Activities for Mount Nimba | Before Implementation (Incentives for Participation, Actual Involvement, Roles & Responsibilities) | During Implementation (Incentives for Participation, Involvement, Roles & Responsibilities) | Roles & Responsibilities after the Project (Participation for Sustainability) |
| --- | --- | --- | --- | --- |
| Output 1.3. Decrease in incursions and illegal activities in the core areas |  |  |  |  |
| Activity 1.3.1. Design, equip and organize a patrol and –protection system | CEGEN Local residents/RDC Decentralised services | Consultations with hunters and farmers | Training of ranger-guards Establishment of a patrol system | On-going patrolling of the core areas |
| Activity 1.3.2. Involve local populations in the protection and patrol system | CEGEN Hunters / farmers Decentralised services | Surveys with hunters , farmers and the concerns | Establishment of a patrol system | On-going patrolling of the core areas |
| Activity 1.3.3. Organize co-operation with public law enforcement agents | CEGEN (rangers/guards) Decentralised services | Consultations with hunters, Farmers and agents of public law | Establishment of a patrol system Coordination and consultation in processes and procedures leading to reduction of infractions | On-going patrolling of the core areas |
| Output 1.4. Improved compatibility of planned mining activities, and strengthened cooperation. |  |  |  |  |
| Activity 1.4.1. Monitor developments in the mining project and prepare precise environmental guidelines | Ministry of Environment and others government’s body CEGEN Private sector Steering Committee | Close collaboration with the mining project team | Preparation of the environmental agreement IEC | Monitoring of the environmental agreement with the mining company IEC |
| Activity 1.4.2 Monitor compliance of mining consortium to Convention and program objectives – report to Ministry as necessary | CEGEN Ministry of Environment Private sector Steering Committee | Monitoring of the mining agreement | Setting up of the Nimba Mountains Foundation Resource mobilization for the Nimba Mountains Foundation IEC | Follow up Resource mobilization for the Nimba Mountains Foundation IEC |

| Output 1.5. Management plan prepared and implemented for the three core areas, with full participation of local communities |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity 1.5.1. Prepare and implement a management plan for the World Heritage Site, following consultations on relevant matters with the mining project principals, local populations and relevant authorities in the neighboring countries, and based on data collected above | CEGEN (researchers) Development partners Steering committee | Appropriate consultations within the core areas IEC Study and surveys with the concerned | Design and execution of the management plan IEC | On-going patrolling Monitoring of the management plan |
| Activity 1.5.2. Prepare and implement a management plan for the Bossou ecosystem following consultations on relevant matters with local populations and ERIB | CEGEN (researchers) Development partners Steering committee NGO | Appropriate consultations within the core areas IEC Study and surveys with the concerned | Design and execution of the management plan IEC | On-going patrolling Monitoring of the management plan |
| Activity 1.5.3. Prepare and implement a management plan for the Déré ecosystem following consultations on relevant matters with the National Directorate for Water & Forests, Côte d'Ivoire and local populations | CEGEN (researchers) Development partners Steering committee NGO | Appropriate consultations within the core areas IEC Study and surveys with the concerned | Design and execution of the management plan IEC | On-going patrolling Monitoring of the management plan |

| Output 1.6. Impacts of refugees do not affect the core areas |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity 1.6.1 Liaise with humanitarian agencies to ensure incorporation of environmental concerns in relief work, including siting & sizing of camps and providing appropriate employment & income-generating activities | CEGEN International NGOs UNHCR WFP | Contact relief agencies, gain their attention and confidence | Reduce impacts of refugees on core areas | On-going patrolling reinforced |
| Activity 1.6.2 Develop with humanitarian agencies a refugees’ contingency plan in case of future refugee movements | CEGEN International NGOs UNHCR WFP | Contact relief agencies, gain their attention and confidence | Prepare refugee contingency plan | On-going patrolling reinforced |
| Specific Objective 2. Sustainable land use and Agricultural revenues of local people increased on the basis of more productive practises |
| Output 2.1 Sustainable land use systems |  |  |  |  |
| Activity 2.1.1. Develop a deeper understanding of the social and land-tenure constraints linked to agricultural intensification | CEGEN Development partners Local Communities Farmers Decentralized services NGOs | Collection of statistical agricultural data TOR of Study of the land-tenure and ownership codes | Study of the land-tenure and ownership codes | Continued research into new techniques |
| Activity 2.1.2 Develop capacity for land use planning with local government and local communities | CEGEN Development partners Local communities Farmers Decentralized services NGOs | TOR of Study of the land-tenure and ownership codes Diffusion of critical information to decentralized government bureaus and services, and to local populations | Improvement of farming practices (works to permit irrigated agriculture in low-lying areas, improved seeds) and extension services | Extension services |
| Activity 2.1.3. Develop land use plans, either for each community, or by commune, that take into account Refugee Contingency Plans | CEGEN Development partners Local communities Farmers Decentralized services | TOR of Study of the land-tenure and ownership codes in order to establish the land use plan | Preparation and implementation of land use plans | Monitoring and updating of the land use plans |
| Activity 2.1.4 Disseminate and enforce land use system | CEGEN Development partners Local communities Decentralized services NGOs | Diffusion of critical information to decentralized government bureaus and services, and to local populations IEC | Prepare the guidelines of land use system IEC | Monitoring and updating of the guideline of land use IEC |
| Output 2.2. Increased agricultural yields |  |  |  |  |
| Activity 2.2.1. Support improvements in cultivation methods (soil improvements like soil conservation methods, fertilizers, manures and other inputs, development of low-lying areas for irrigation, introduction of improved seed varieties, etc.) | Farmers Local communities Private sector CEGEN (researchers) Development partners | Collection of statistical agriculture data Studies and data collection | Improvement of farming practices and extension services Marketing of products Access to credit | Continue research to improve extension services Access to credit |
| Output 2.3 Improved incomes from agricultural produce sold for higher prices |  |  |  |  |
| Activity 2.3.1. Improve understanding of marketing channels | Decentralized structures (RDC) CEGEN Private sector | Studies and data collection | Study of market channels and structure | Independent, self-management of rural collectives |
| Activity 2.3.2. Improve storage techniques and how produce is marketed | Decentralized structures (RDC) CEGEN Private sector Extension services | Studies and data collection | Improvement of storage techniques | Improvement of storage techniques |
| Activity 2.3.3. Strengthen the negotiating skills of farmers’ co-ops/communes/other groupings | CEGEN Private sector | Studies and data collection | Improve market outlet structures Training of farmers’ groups | Creation of a federation of farmers’ groups or associations |
| Activity 2.3.4. Facilitate access to credit | CEGEN Private sector | Studies and data collection | Access to credit | Monitoring and evaluation of a credit system Access to credit |
| Output 2.4. Diversified income sources |  |  | . |  |
| Activity 241. Promote local micro-industry | Local communities Local communities CEGEN NGOs | Studies and data collection | Promoting local artisan’s industries | Independent, self-management of rural collectives |
| Activity 242. Encourage the introduction of simple processing technologies of agricultural produce | CEGEN NGOs Private sector | Studies and data collection | Promoting local craft industries and traditional transformation technology for agricultural and gathered products | Independent, self-management of rural collectives |
| Output 3.1. More productive animal husbandry, integrated with agriculture |  |  |  |  |
| Activity 3.1.1. Develop the management skills of animal husbandry co-ops/communes/ groupings | CEGEN Decentralized services Animal breeders local communities | Information and statistical data collection on livestock raising & other animal husbandry activities, and relations between herders and farmers | Organization of animal husbandry activities Improvement of pastures | Continued extension efforts for Herders and other livestock managers and for independent self-management of collectives |
| Activity 312. Facilitate access of individuals or groups raising animals to extension services and inputs | CEGEN Animal breeders/herders Decentralized services | Information and statistical data collection on livestock & other animal husbandry activities, and relations between herders and farmers | Organization of animal husbandry activities Improvement of techniques | Continued extension efforts for herders and other livestock managers and for independent self-management of collectives |
| Output 3.2. Domestication and breeding of wild animals tested and disseminated |  |  |  |  |
| Activity 3.2.1. Develop a deeper understanding of past and current trials to raise wild animals in captivity | CEGEN Hunters Decentralized services NGOs Local communities | Studies of local bush meat trade & hunting techniques (bush fire barriers and others...) Situation analysis to establish the base line. | Studies on various approaches to management and breeding of wild animals | Monitoring of the impact of this animal husbandry on the recovery of faunal species in the Reserve |
| Activity 3.2.2. Establish animal husbandry trials for wild animals | CEGEN Hunters NGOs | Studies of local bush meat trade & hunting techniques ( bush fire and others) Situation analysis to establish the base line | Breeding trials for selected species and progressive replication of successful trials | Monitoring of the impact of this animal husbandry on the recovery of faunal species in the Reserve |
| Activity 3.2.3. Study the technical, economic and social feasibility of these trials | CEGEN, NGOs | Situation analysis to establish the base line | Studies on the economic viability of management and breeding of wild animals | Monitoring of the impact of this animal husbandry on the recovery of faunal species in the Reserve |
| Activity 3.2.4. Progressively replicate breeding schemes for the most promising wild animals | CEGEN Development partners Decentralized services | Situation analysis to establish the base line. Studies and data collection on the credit system | Evaluation of the impact of this animal husbandry on the recovery of faunal species in the Reserve. Progressive replication of successful trials Access to credit | Monitoring of the impact of this animal husbandry on the recovery of faunal species in the Reserve |
| Output 3.3. Wildlife and non-timber forest resources co-managed with local populations in a sustainable manner |  |  |  |  |
| Activity 3.3.1. Raise awareness of those who hunt or collect wildlife of the principles of sustainable management and of enforcement of relevant laws | Ministry of Environment Local communities CEGEN NGOs Decentralized services Private sector | Studies and data collection | Promulgate/ raise awareness of and monitor the enforcement of hunting laws I E C | Successful enforcement of hunting laws and regulations |
| Activity 3.3.2. Promote simple management practices for the most widely consumed wildlife species. | CEGEN NGOs | Studies and data collection | Monitor the enforcement of hunting laws IEC | Successful enforcement of hunting laws and regulations |
| Specific Objective 4. Improved health conditions, in particular among the neighbouring villages subject to constraints from the Reserve |
| Output 4.1. Improved medical and para-medical health care |  |  |  |  |
| Activity 411. Support organizing of focused training for medical and para-medical staff | Government CEGEN Traditional doctors Decentralized services NGOs | Studies on the state and the coverage of health care in the zone | Training of health care personnel and provision of better access to primary health care | Continued training of personnel and monitor their services |
| Activity 4.1.2. Facilitate on-going access to basic medicines | Government CEGEN Decentralized services NGOs | Studies on the state and the coverage of health care in the zone | Training of health care personnel and provision of better access to primary health care | Continued training of personnel and monitor their services |
| Output 4.2. Increased access to health care |  |  |  |  |
| Activity 4..2.1. Contribute to the geographic coverage of health dispensaries and clinics | Government CEGEN Decentralized services NGOs | Study on the base line situation concerning the health in the buffer zone | Construction of health center | Monitor the evolution of local populations’ access to health care |
| Activity 4.2.2. Promote better complimentarity between “modern” and traditional medicines | Government CEGEN Traditional doctors Decentralized services NGOs | Consultations on the role and importance of traditional medicine in local health care | Improve the services provided by traditional doctors | Monitor the evolution of local populations’ access to health care |
| Output 4.3. Increased access to potable water |  |  |  |  |
| Activity 4.3.1. Monitor water quality in context of changes to the environment | Government CEGEN (researchers) Decentralized services NGOs | Updating available statistics on the coverage of improved water-supply sources in the zone | Monitoring of water quality | Ongoing improvement of access to potable water |
| Activity 4.3.2. Identify sources and causes of pollution and execute the needed corrective measures | Government CEGEN (researchers) Decentralized services NGOs | Updating available statistics on the coverage of improved water-supply sources in the zone | Study of the sources of water pollution | On-going improvement of access to potable water |
| Activity 4.3.3. Contribute to the existing network of wells, pumps and water supply systems | CEGEN (researchers) Local communities Decentralized services NGOs | Updating available statistics on the coverage of improved water-supply sources in the zone | Improvement of the network of wells and pumps | On-going improvement of access to potable water |
| Output 4..4. Improved hygiene practices |  |  |  |  |
| Activity 4.4.1. Support initiatives targeting public health and waste treatment | CEGEN Decentralized services Private sector NGOs | Studies and data collection | Promotion of public health initiatives Information- Education -Communication | On-going Information-Education-Communications on hygiene practices |
| Activity 4.4.2. Support education in schools and public awareness initiatives on matters of hygiene | Government CEGEN Decentralized services NGOs | Studies and data collection | Promotion of public health initiatives Information- Education -Communication | On-going Information-Education-Communications on hygiene practices |
| Specific Objective 5. Strengthened capacity of the Reserve’s management structures, mainstreaming of biodiversity conservation, and contribution to national protected area system |
| Output 5.1. Synergy ensured between institutions and between interventions |  |  |  |  |
| Activity 5.1.1. Amend and complete the legal texts related to CEGEN | Government Steering Committee CEGEN Decentralized services | Data collection and information | Updating of the legal texts related to CEGEN | Proper implementation of relevant legal texts. |
| Activity 5.1.2. Establish and run a consultation and planning mechanism with local populations | CEGEN Local communities, NGOs Decentralized services RDC | Information and awareness meetings | Consultation and planning with local residents and other stakeholders | Continuation of dialogue and planning |
| Activity 5.1.3. Ensure complimentarity between relevant institutions | CEGEN Local communities/RDC NGOs Decentralized services Private sector | Data collection and information | Harmonisation of legal texts and consultation of relevant institutions. | Continuation of dialogue and monitoring |
| Activity 5.1.4. Prepare a development master-plan for the Nimba Mountains Biosphere Reserve in collaboration with all stakeholders | Government CEGEN Local communities/RDC NGOs Decentralized services Development partners Private sector | Data collection, information and awareness meetings. | Preparation and implementation of master-plan | Monitoring and updating in collaboration with all stakeholders |
| Output 5.2. CEGEN’s human and material resources strengthened and well managed |  |  |  |  |
| Activity 5.2.1. Implement a staff training programme | Ministry of Environment CEGEN Partners | Consultations on the current status and resources of CEGEN | Conception and execution of a staff training and a M&E program | Proper implementation of the legal texts |
| Activity 5.2.2. Establish a monitoring and evaluation system for CEGEN | Ministry of Environment CEGEN | Consultations on the current status and resources of CEGEN | Monitoring and evaluation of training program Periodic evaluation of the staff of CEGEN | Periodic evaluation of the staff of CEGEN |
| Output 5.3. An operational ecological monitoring system |  |  |  |  |
| Activity 5.3.1. Establish and manage a geo-referenced database on land-use, botanical and faunal inventories and the overall ecosystem | Ministry of Environment CEGEN Decentralized services | Preparation of the necessary material and human resources | Creation and management of a geo-referenced database in a GIS environment Collection of baseline data | Regular updating of the database and monitoring of its management |
| Activity 5.3.2. Ensure data collection necessary for the ecological monitoring system | CEGEN Decentralized services | Preparation of the necessary material and human resources | Collection of baseline data Creation of ecological base line data | Regular updating of the database and monitoring of its management |
| Output 5.4. Guaranteed long-term funding for conservation |  |  |  |  |
| Activity 5.4.1. Establish a sustainable financing mechanism and Foundation (or analogue agency) for the Guinean Nimba Mountains | Government CEGEN Private sector Development partners Local communities Private sector | Consultations with partners and all stakeholders | Creation of the Nimba Mountains Foundation | Significant involvement of the national budget in the financing of natural resources conservation |
| Activity 542. Explore alternative income-generating activities (especially eco-tourism, etc.) | Government CEGEN/Private sector Development partners Local communities/NGOs’ | Consultations with partners and all stakeholders | Institute an eco-development tax | Significant involvement of the national budget in the financing of natural resources conservation |
| Output 5.5. Stakeholders better informed and aware of the issues and of resource conservation |  |  |  |  |
| Activity 5.5.1. Design relevant messages for stakeholders and prepare materials to distribute | CEGEN Local communities RDC Local communities Steering Committee NGOs | Consultations with partners | I E C Preparation of relevant messages for partners | Pursue IEC partnerships when and where it remains necessary |
| Activity 5.5.2. Identify appropriate communication channels | Government CEGEN Development partners Steering Committee Local communities NGOs | Consultations with partners | I E C Identification of appropriate communication channels | Pursue IEC partnerships when and where it remains necessary |
| 5.5.3. Organise environmental awareness meetings | Government CEGEN Development partners Steering Committee Local communities NGOs Local communities | Consultations with partners and all stakeholders | I E C | Pursue IEC partnerships when and where it remains necessary |
| Output 5.6 Contribution to a national protected area system |  |  |  |  |
| Activity 5.6.1. Contribute to establishment of a National Coordinating Committee for Parks | Government CEGEN Development partners Steering Committee NGOs, Local communities | Consultation with partners | Pursue consultation with partners and all stakeholders Political engagement of Government | Government accepts to regularly finance the activities of protected area |
| Activity 5.6.2. Evaluate CEGEN performance and consider expanding mandate to Simandou Mountain, with accompanying revision in legal texts | Government CEGEN Development partners Steering Committee Private sector Local communities | Consultation with partners | Political engagement of Government on the revision of legal texts | Government accepts to regularly finance the activities of protected area |
| Activity 5.6.3. Contribute to review of policy and regulatory frameworks at national level for Protected Areas management | Government CEGEN Development partners Steering Committee Local communities | Consultation with partners Political engagement of Government | Identification of appropriate communication channels to get money from government | Government accepts to regularly finance the activities of protected area |

## Annex 4 – Table Indicative Monitoring and Evaluation Work plan and corresponding Budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team Staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop | Project Administrator UNDP Country Office (CO) UNDP GEF Government/CEGEN | 15, 000 $ | June 2004 |
| Inception Report | Project Team UNDP CO | None | Immediately following inception workshop |
| CEGEN’s ecological monitoring system. Official legal documents setting the boundaries of the core areas Revenue surveys/reports of decentralised sector services from the region Surveys of health and nutrition Program evaluation reports | CEGEN Project team Government CEGEN Project team External consultant CEGEN Project team RDCs and local communities External consultant CEGEN Project team Decentralized services External Consultants CEGEN Project team ERIB RDC’s and local communities Eternal Consultants | To be finalized in Inception Phase and Workshop. 30, 000 $ 20,000 $ 30,000 $ 30,000 $ 50,000 $ | Start, mid and end of project Start, mid and end of project Start, mid and end of project Start, mid and end of project Start, mid and end of project |
| Monitoring and evaluation system | CEGEN Project team Project Administrator GEF technical advisor External consultants | To be determined as part of the annual Work Plans 50 000 $ | Annually prior to APR/PIR and to the definition of annual work plans |
| APR and PIR | Project Team UNDP-CO UNDP-GEF | None | Annually |
| TPR and TPR report | Government/CEGEN UNDP CO Project team UNDP-GEF Regional Coordinating Unit | None | Every year, upon receipt of APR |
| Steering Committee Meetings | Project Coordinator Project Administrator UNDP CO | None | Once a year |
| Periodic status reports | Project team | 5,000 $ | Semester |
| Technical reports | Project team Consultant | 20,000 $ | Yearly |
| Mid-term External Evaluations | Project team UNDP- CO UNDP-GEF Regional Coordinating Unit External evaluation team | 15,000 $ each x 2 = 30,000 $ | Quarter 1 of years 3 and 6 of project implementation. |
| Final External Evaluation | Government/CEGEN Project team, UNDP-CO UNDP-GEF Regional Coordinating Unit External evaluation team | 30,000 $ | Six months before the end of project implementation |
| Terminal Report | Project team CEGEN UNDP-CO External Consultant | 15,000 $ | One month before the end of the project |
| Lessons learned | CEGEN Project team UNDP-GEF Regional Coordinating Unit (suggested formats for documenting best practices, etc) | 36,000 $ (average $4,000 per year) | Yearly |
| Audit | Government/Ministry of Cooperation UNDP-CO Project team | 27,000 $ (average $3,000 per year) | Yearly |
| Visits to field sites | UNDP Country Office UNDP-GEF Regional Coordinating Unit Government representatives | 15,000 $ | Semester (average two visits per year) |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses | US$ 403,000 |  |

## Annex 5 – Programme Structure

## Annex 6 – Summary of information for selected protected areas:  data sheet

| Name of protected area | Conservation of the biodiversity of the Nimba Mountains through integrated and participatory management |
| --- | --- |
| Location of protected area (country and if possible map reference) | Guinea – Nimba Mountain (Lola) – Guinea Forest Region |
| Date of establishment (distinguish between agreed and gazetted*) | Agreed 1980 | Gazetted 1944 |
| Ownership details (i.e. owner, tenure rights etc) | Public Domain/ Guinean government |
| Management Authority | Centre for the Management of the Environment of the Nimba Mountains (CEGEN) |
| Size of protected area (ha) | 145.200 ha |
| Number of staff | Permanent 23 | Temporary 12 |
| Budget | 30 million Guinean francs per year (past Government contribution) |
| Designations (IUCN category, World Heritage, Ramsar etc) | World Heritage Site (designated 1981, on the list of World Heritage in Danger since 1992); MAB Biosphere Reserve since 1980 (boundaries reclassified in 1994); IUCN protected area categories Ia (Nimba Mountains World Heritage Site/Déré Forest), Ia/IV (Bossou Hills), and VI (buffer zone and transition area). |
| Reasons for designation | The diversity and endemism of flora and fauna in the Nimba Mountains complex and the diversity of nature in surrounding areas |
| Brief details of World Bank funded project or projects in PA | Mount Nimba Pilot Project financed by UNDP, UNESCO, and the World Bank (grant from the Government of Japan). The project objectives are: Establishment of a strategy of ongoing protection and conservation of the Reserve; data collection for a baseline on the environmental impact of the mining projects in the vicinity. The results to be obtained are: establishment of a management plan for the reserve; recommendations for limiting cases of negative impacts of mining on the environment ; reaching consensus on the limits and borders of the protected areas and the mining concession; creation of infrastructure (guard posts, weather and hydrological monitoring stations, other), creation of an autonomous authority for managing the site (CEGEN). |
| Brief details of WWF funded project or projects in protected area | N/A |
| Brief details of other relevant projects in PA | (i)- Project (PDF-B) “Conservation of biodiversity in the Nimba Mountains by Integrated and Participatory Management” has the following objectives: strengthening institutional management capacity; integration of nature conservation approaches and practices into local production systems; the sustainable management/utilisation of biodiversity; establishment of a participatory management system with local stakeholders, particularly rural communities, NGOs, and the private sector. (ii) – The Environmental Research Institute of Bossou (ERIB) is financed by the government of Japan. ERIB’s objectives are to carry out research on reserves in the Nimba Mountains and Ziama Biosphere Reserves, to design strategies for the efficient protection and conservation of the Nimba Mountains’ ecosystems in general and primate populations in particular. |
| List the two primary protected area objectives |
| Objective 1 | Protection of endemic species in the core protected areas; protection of biodiversity in a manner compatible with the needs of sustainable development in forested areas. |
| Objective 2 | Reduction of poaching. Increasing rarity of wild animal resources results from the loss of habitat and the pressure of excessive hunting, themselves due to local weak income generation opportunities and rapid population growth. |
| List the top two most important threats to the PA (and indicate reasons why these were chosen) |
| Threat 1 | Agricultural pressures: agriculture covers more than 80% of the local population and slash and burn cultivation remains the most widely practiced agricultural technique |
| Threat 2 | Over exploitation of fauna and game through poaching. The rarity of wildlife results from the loss of habitat as well as the pressures of excessive hunting, both due to a weak local capacity for income generation and rapid population growth. |
| List top two critical management activities |
| Activity 1 | Design and initiate a management plan for core areas of the Reserve following interactive planning and dialogue with local stakeholders (local communities, mining project, relevant authorities of bordering countries, and ERIB, as well as the Water, Forests and Protected Area). |
| Activity 2 | Conceptualise, equip and organize a management and protection system in collaboration with the local population. |

Date assessment carried out:  12 March 2004

Name/s of assessor:  Saramady Touré, PDF B Coordinator, former General Director of CEGEN and National Coordinator of the Nimba Mountains Pilot Project (1989-95), (tsaramady@yahoo.fr) and Mohamed Efas Sylla, Programme Officer and Assistant to the Resident Representative, UNDP-Guinea (mohamed.efas.sylla@undp.org)

| Issue | Criteria | Score | Comments | Next steps |
| --- | --- | --- | --- | --- |
| 1. Legal status Does the protected area have legal status? |  |  | Note: see fourth option for private reserves Some issues related to the classification of central areas in the Déré Forest and the Bossou Hills are being addressed. | Legalization of the reservation boundary lines through legal decrees. |
|  | The protected area is in the process of being gazetted but the process is still incomplete | 2 |  |  |
| 2. Protected area regulations Are inappropriate land uses and activities (e.g. poaching) controlled? |  |  | Implementation of the central areas management plan initiated in 1991 is hampered by the lack of financial resources. | External and national development budget resources should be secured to allow the control and monitoring of the management plan activities. |
|  | Mechanisms for controlling inappropriate land use and activities in the protected area exist but there are some problems in effectively implementing them | 2 |  |  |
| 3. Law enforcement Can staff enforce protected area rules well enough? |  |  | Possible issue for comment: What happens if people are arrested? The police force and local authorities (CRD and public services) collaborate a little regarding the monitoring of central areas. Severe cases of damage to ecosystems are subject to prosecution or exceptionally imprisonment. | A training plan focused on technical aspects of protection and management will allow fill the gaps. |
|  | There are major deficiencies in staff capacity/resources to enforce protected area legislation and regulations (e.g. lack of skills, no patrol budget) | 1 |  |  |
| 4. Protected area objectives Have objectives been agreed? |  |  |  |  |
|  | The protected area has agreed objectives, but these are only partially implemented | 2 |  |  |
| 5. Protected area design Does the protected area need enlarging, corridors etc to meet its objectives? |  |  | Possible issue for comment: Do the protected areas contain different management zones and are these well maintained? Yes different management zones exist but they are not well maintained. |  |
|  | Reserve design features are particularly appropriate for the achievement of major objectives of the protected area | 3 |  |  |
| 6. Protected area boundary demarcation Is the boundary known and demarcated? |  |  | Possible issue for comment: are there tenure disagreements affecting the protected area? Are there contradictions between the boundaries of the protected area and local land tenure practice or customary law? In theory no because protected areas come under the State administered property. But in reality local villages covert the land for agriculture and hunters traditionally hunt inside the core areas of the Reserve. | Setting up pictograms and holding first meetings with trans-boundary authorities. |
|  | The boundary of the protected area is known by both the management authority and local residents but is not appropriately demarcated | 2 |  |  |
| 7. Management plan Is there a management plan and is it being implemented? |  |  | Coordination problems between the institutions responsible for the management of protected areas still persist. Resource constraints have hampered implementation of an early management plan, but this plan needs updating. | Reformulation of the Reserve’s management plan. |
|  | An approved management plan exists but it is only being partially implemented because of funding constraints or other problems | 2 |  |  |
| Additional points | The planning process allows adequate opportunity for key stakeholders to influence the management plan | +1 Yes | The start of the programme should allow to re-launch the management planning process of protected areas. | Elaboration of a Monitoring & Evaluation Guidance. |
|  | There is an established schedule and process for periodic review and updating of the management plan | No |  |  |
|  | The results of monitoring, research and evaluation are routinely incorporated into planning | No |  |  |
| 8. Regular work plan Is there an annual work plan? |  |  | The UNDP/GEF programme should allow the achievement of objectives and ensure the follow up of the work plan. | Implication of research institutions particularly of ERIB at all the stages of the planning process and of the implementation of the management plan. |
|  | A regular work plan exists and actions are monitored against the plan’s targets, but many activities are not completed | 2 |  |  |
| 9. Resource inventory Do you have enough information to manage the area? |  |  |  | Implication of research institutions such as ERIB at all stages of planning and implementation of the work plan Updating scientific information through rapid appraisals and ecological studies. |
|  | Information on the critical habitats, species and cultural values of the protected area is sufficient for key areas of planning/decision making but the necessary survey work is not being maintained | 2 |  |  |
| 10. Research Is there a programme of management-orientated survey and research work? |  |  |  | Inventory of protected species and data collection on various environmental parameters required for setting-up a data base. |
|  | There is considerable survey and research work going on, but it is not directed towards the needs of protected area management | 2 |  |  |
| 11. Resource management Is the protected area adequately managed (e.g. for fire, invasive species, poaching)? |  |  |  | Prerequisites will be taken into account in the programme annual work plan. |
|  | Requirements for active management of critical ecosystems, species and cultural values are known but are not (or are barely) being addressed | 1 |  |  |
| 12. Staff numbers Are there enough people employed to manage the protected area? |  |  | A large part of the Reserve’s staff is based in Conakry and thus is rarely on-site and able to contribute to a minimum level of management. CEGEN’s organigramme is only ~50% filled | Posting the staff and technicians according the new organization chart of CEGEN. |
|  | Staff numbers are inadequate for critical management activities | 1 |  |  |
| 13. Personnel management Is the staff managed well enough? |  |  |  | Implementation of CEGEN staff and technicians training programme. |
|  | Problems with personnel management partially constrain the achievement of major management objectives | 1 |  |  |
| 14. Staff training Is there enough training for staff? Inputs/Process |  |  |  | Implementation of CEGEN staff and technicians training programme. |
|  | Staff training and skills are low relative to the needs of the protected area | 1 |  |  |
| 15. Current budget Is the current budget sufficient? |  |  |  | Mobilisation of external and national development budget financial resources. |
|  | The available budget is inadequate for basic management needs and presents a serious constraint to the capacity to manage | 1 |  |  |
| 16. Security of budget Is the budget secure? |  |  |  | Setting up of a sustainable funding mechanism. |
|  | There is very little secure budget and the protected area could not function adequately without outside funding | 1 |  |  |
| 17. Management of budget Is the budget managed to meet critical management needs? |  |  |  | Planning programme of financial resources by clear attainable objectives |
|  | Budget management is adequate but could be improved | 2 |  |  |
| 18. Equipment Is equipment adequately maintained? |  |  |  | Rehabilitation and construction of infrastructures. |
|  | There is some equipment and there are some facilities but these are wholly inadequate | 1 |  |  |
| 19. Maintenance of equipment Is equipment adequately maintained? |  |  |  | A plan for regular maintenance of infrastructures will be set up. |
|  | There is some ad hoc maintenance of equipment and facilities | 1 |  |  |
| 20. Education and awareness programme Is there a planned education programme? |  |  |  | Harmonization of IEC campaigns with the work pan. |
|  | There is a limited and ad hoc education and awareness programme, but no overall planning for this | 1 |  |  |
| 21. State and commercial neighbours Is there co-operation with adjacent land users? |  |  |  | Develop contacts through participative approach. |
|  | There is limited contact between managers and neighbouring official or corporate land users | 1 |  |  |
| 22. Indigenous people Do indigenous and traditional peoples resident or regularly using the PA have input to management decisions? |  |  | The local population, while originating in the region, does not really meet the classic definition of ‘indigenous’ | Formalize the use of participative approach tools. |
|  | Indigenous and traditional peoples have some input into discussions relating to management but no direct involvement in the resulting decisions | 1 |  |  |
| 23. Local communities Do local communities resident or near the protected area have input to management decisions? |  |  |  | Formalize the use of participative approach tools and involve local communities in the reservations management committee. |
|  | Local communities have some input into discussions relating to management but no direct involvement in the resulting decisions | 1 |  |  |
| Additional points | There is open communication and trust between local stakeholders and protected area managers | Not yet | These are planned, and initial steps have been taken, but they have not been actively pursued yet. |  |
|  | Programmes to enhance local community welfare, while conserving protected area resources, are being implemented | Not yet |  |  |
| 24. Visitor facilities Are visitor facilities (for tourists, pilgrims etc) good enough? Outputs |  |  | Possible issue for comment: Do visitors damage the protected area? No. Paths have been put in place to allow avoiding damages to the ecosystem from visitors. | Elaborate a plan for Eco-Tourism. |
|  | Visitor facilities and services are inappropriate for current levels of visitation or are under construction | 1 |  |  |
| 25. Commercial tourism Do commercial tour operators contribute to protected area management? | There is little or no contact between managers and tourism operators using the protected area | 0 | Possible issue for comment: | Elaborate a plan for Eco-Tourism. |
| 26. Fees If fees (tourism, fines) are applied, do they help protected area management? |  |  | Fees are collected only by ERIB for people visiting the Bossou Hills and is not used to protect the area. No fees are collected for the World Heritage Site or the Déré Forest. | Establish a management committee for resources derived from fees and taxes generated by tourist activities, in consultation with local authorities. |
|  | Some fees are collected while others are not. Fees collected go to the local authority and are not returned to the protected area or its environs | 1 |  |  |
| 27. Condition assessment Is the protected area being managed consistent to its objectives? |  |  | The Déré Forest has been severely degraded, while small areas of the Bossou Hills and World Heritage Site have been degraded too. | Inventory and restoration of degraded areas. |
|  | Some biodiversity, ecological and cultural values are being severely degraded | 1 |  |  |
| Additional points | There are active programmes for restoration of degraded areas within the protected area and/or the protected area buffer zone | +1 yes | The Déré Forest has had severely degraded areas reforested in mid-2004. | Implement these rehabilitation programmes. |
| 28. Access assessment Are the available management mechanisms working to control access or use? | Protection systems (patrols, permits etc) are ineffective in controlling access or use of the reserve in accordance with designated objectives | 0 | Occasionally there is limited protection but by and large, there is no active protection of the Reserves. This score should soon increase. | Establish a joint monitoring team including public forces and local community. |
| 29. Economic benefit assessment Is the protected area providing economic benefits to local communities? | The existence of the protected area has reduced the options for economic development of the local communities | 0 | Possible issue for comment: how does national or regional development impact on the protected area? The Reserve is often perceived by local populations as an impediment to the working of the Nimba iron mine even if compensatory measures have been taken by the Government. The reserve does limit short- and medium-term economic gain in terms of hunting and agriculture. But in the long run, it is more likely to be a positive than negative factor to the local economy. | Develop compensatory measures for local populations. |
| 30. Monitoring and evaluation | There is no monitoring and evaluation in the protected area | 0 |  | Elaboration and implementation of a Monitoring & Evaluation plan. |
| TOTAL SCORE | 39 (out of a maximum of 96) |

## Annex 7 – TOR of the project staff and consultants

I- Context

Adding the Nimba Mountain Complex to the world heritage list led to the Nimba Mountains Pilot Project (Gui/89/004) financed by the UNDP, UNESCO and the World Bank (through a grant from the Japanese Government), as well as the creation of the Centre for the Management of the Environment of the Nimba Mountains (CEGEN) in 1995 as an autonomous management authority.  Despite clear political will to improve its management, the situation around the site remained alarming because of population pressures, including refugees, and because of increased activity by logging companies.

To remedy this, the Government of Guinea requested and obtained founds from UNDP, the Global Environmental Fund (GEF) and the World Heritage Center of UNESCO to implement a program.  A preparatory phase of 12 months (Jan – Dec 2001) developed a program spread across nine years, the time needed to put in place sound management of the Reserve, to ensure effective involvement of the local population and to ensure improved livelihoods of beneficiaries.

The over-all objective of the program is to preserve and protect the core areas of the Reserve in a manner compatible with national need to extract the iron ore deposits of the mountain range.

In order to harmonize operations, mobilise financial resources and guarantee correct program implementation, a multidisciplinary team will be put in place under national administrator who will coordinate program activities.

II- Organizational chart

- Programme Administration / Staff

National administrator

UNV administrative manager

National expert on human resources and accounts management

Monitoring and evaluation expert

Environmental expert / advisor

- Administrative support staff

Logistics officer

Communications agent (radio operator)

Secretaries

Drivers

Security guards

- National professionals

3.1- National experts

Protected areas specialist

Wildlife/fauna specialist

Rural development engineer

3.2- National consultants

Rural development engineer

Economist, specialist in project planning, small and medium enterprise creation

Economist, specialist in credit systems (needed well after inception workshop)

Marketing specialist (needed well after inception workshop)

Environmental law specialist

Rural sociologist

Socio-economic specialist (needed well after inception workshop)

Doctor, specialist in plant remedies

Veterinarian specialising in pig rearing

Specialist in financial management and fund-raising (to be recruited later)

Protected areas specialist

Other specialists (as needed)

- International professionals (consultants)

Specialist in sustainable funding mechanisms

Specialist in socio-economics

Specialist in flora

Specialist in protected areas

Specialist in geographical information systems (GIS)

Specialist in rural development engineering

Other consultants (as needed)

- National UN volunteers

GIS Specialist

Participatory-development specialist

Agronomist

Animal’s health, veterinary specialist

Accountant / management specialist

Program Administration / Management

1- National administrator

Responsibilities

In order to harmonize programme operations, ensure financial management and assure correct implementation of the programme, the national administrator will coordinate and manage programme activities. The national administrator’s office will be based in Lola.  (S)he will make several technical missions within and outside the country.

Under the supervision of the National Coordinator and the Steering Committee, the National administrator will:

- Develop work plans in collaboration with the Programme Steering Committee

- Serve as the technical secretary to the Programme Steering Committee

- Coordinate programme activities including ensuring day-to-day management of activities and ensure the work plans are followed and objectives are achieved at all levels over different time scales

- Plan consultants’ interventions and provide them support

- Manage the programme’s human, financial and physical resources as required by UNDP and the GEF including preparing/finalising programme staff and consultant TOR, overseeing hiring of staff, consultants and casual labour, overseeing of consultants’ and UN volunteers’ technical work, managing procurement of goods and services, establishing financial management procedures in collaboration with the programme accountant, UNDP and other relevant entities

- Supervise the writing of regular technical and financial reports including bi-annual reports for the UNDP/FEM and the Government

- Organize consultations related to the programme to conserve Nimba Mountains World Heritage

- Supervise data collection (activities, budget, periodical reports and evaluation report-writing)

- Establish a programme management information system

- Serve as the contact person for the programme with national Governmental structures and  coordinate activities with Government, preparing the necessary documentation

Qualifications

- MSc. or PhD holder in science, geography, social science, natural resources management or related discipline

- Have at least five (5) years experience of project administration and natural resources management

- Have extensive field work experience

- Be ready to work in the field with a multidisciplinary team

- Possess good communications skills and team-work spirit

- Be physically strong and able to work in hard conditions

- Accept to live in rural conditions

- Be computer literate

- Knowledge of English is an advantage

- Knowledge of the GEF’s and UNDP’s procedures is an advantage

Place: Nimba Mountains (Lola)

2 - UNV Accountant

Responsibilities

The UNV accountant manager collaborates with the national administrator and the UNDP staff. The UNV accountant will perform the following tasks:

- UNV accounting and finance register files of the programme

- Carry out accountability management of the programme and proceed to the bill payments.

- Manage equipments and consumables

- Supervise disbursements

- Prepare financial data for expenses appraisal

- Monitor outstanding in connection with periodic budget revisions and programme plan changes

- Assure regular Bank account monitoring and collect information on money exchange rate, interest rates, procedure and Bank regulation changes

- Collaborate with UNDP financial services on direct payment aspects, also on UNDP procedures changes about national execution and finance management implications.

- Assist superior hierarchy on aspects related to programme’s counts expenditures, procedures changes, exchange rate, costs and fund problems through reports.

- Assure national accountant training

- Carry out any accountability task that will be delegated by supervisions in accordance with the UNDP procedures.

Qualification and skills required

- Account  certificate/finance management

- Good knowledge about the UNDP procedures

- Computer expertise : MS Word, Excel, Access

- French and English expertise

- Ability to work in multicultural environment

- Quick responses to petty cash needs and other operations, quick in taking initiative

- Ability to work under pressure

-     Ability to interact with people from different background

Place:  Nimba Mountains (Lola) Guinea Republic

3- National expert, specialist in Human resources and account manager

Responsibilities

- Assure personnel management and assure establishment of contact between experts and national consultants and other service providers in accordance with the UNDP procedures.

- Assure administrative and financial management in collaboration with the UNV accountant manager

- Assist the UNV accountant manager to plan budgets and animal budgets development for several years

- Make sure that forecasted expenditures are in line with the financial plan, administrative procedures and UNDP/FEM financial requirement

- Work out periodical reports of expenditures

- Carry out programme accountability information, make sure that accountability archives are stored and other important documents also are in place.

- Keeps records on stocks and fixed assets inventory

- Assist programme administrator to organize meetings

- Assure programme logistics

Qualifications

Candidate should be:

- Management BSC holder or equivalent

- Experienced at least three (3) years of projects management as manager, accountant or administrative and finance assistant

- Computer literate (MS Word, Excel, etc)

- Skilled in coordination and team work

- Have knowledge about  UNDP/FEM procedures

Place: Nimba Mountains (Lola)

4- National expert, specialist in Monitoring/Evaluation

Responsibilities:

The candidate should:

- Assist the National administrator conceive an international monitoring/Evaluation system for the programme

- Implement monitoring/Evaluation procedures of the programme

- Assure periodical monitoring/Evaluation of the programme activities

- Set up an information and Evaluation system which allows the programme to acquire the  database necessary for achieving planned activities (financial, material and human resources).

- Collect monitoring data in order to set up an integrated monitoring system and computerize it.

- Collaborate closely with programme’s partners in developing technical programmes and in TOR contracts and agreements drafting.

- Centralize, synthesise and feat reports, information from rural development community (RDC)

- Work out and diffuse guidelines and periodical reports

- Work out quarterly reports on project monitoring.

Qualification

The candidate should have:

- Masters degree in rural economy and/or sociology, natural resource management, statistics or equivalent.

- Have at least five (5) years of project monitoring/Evaluation, natural resources management, integrated rural development experiences and be familiar with the participatory approach in rural accent management

- Be familiar with statistical tools (qualitative and quantitative data analysis)

- Good knowledge of computers, in particular MS Word, Excel, SPSS

Place: Nimba Mountains (Lola)

4- Environmental advisor (counsellor)

Responsibilities

The national expert/environmental councillor is a specialist of legal and institutional issues relevant to the implementation of the programme. In this respect, the environmental expert/councillor, supervised by  national administrator performs the following tasks.

- Identify and collect information on major Government of Guinea texts concerning environment legislation notably the environmental code water, forestry, fauna etc…

- Analyse related situations in the area, particularly juridical issues of the Nimba mountains reserves areas.

- Work out necessary juridical texts, which allow statutes recognition from national legislation.

- Work on land tenure in general, particularly traditional land tenure systems, in order to integrate it in strategies development

- In collaboration with the national sociologist expert, identify and evaluate in terms of legal ramifications, areas occupied by refugees

- Evaluate central and local institutions in terms of  protected areas management.

- Collect all available related documents on Nimba Mountain, both from national and international sources,  to form a database for the programme.

- Organize and manage the programme’s documentation and archives

- Suggest ways and means for solutions to  legal, institutional and land tenure problems

- Prepare and submit  periodic, detailed reports related to his/her competency.

Qualification

- BSC or M.Phil holder (environmental law).

- Field experience in terms of social research or environmental studies is an advantage.

- Have deep knowledge about Agenda 21 and all ratified international document by the country (Guinea) in teams environment

- Have good knowledge about computer tools

Place: Nimba Mountain (Lola)

II- Administrative support

1-Liaison agent

Responsibilities

- Performs travel to the capital to facilitate programme’s personnel based in Lola working conditions.

- Performs administrative formalities for personnel traveling outside the country and for international consultants coming from outside the country (reception at the airport, hotel booking etc)

- Assists programme manager in dealing with banks in Guinea (Conakry)

- Performs liaison function between Conakry and Nimba Mountains through radio, telegraphic and other means of communication

- Carries out automobile park management (fuel management, maintenance) in collaboration with Manager based in Nimba Mountains

- Welcomes and guides visitors/researchers who wish to explore Nimba Mountains.

- Performs other tasks related to the candidate mission required by the national administrator

Qualifications

- Be an accountant or holder of management technician superior  certificate

- Have at least two (2) years experience in logistic or accountant management

Place: Conakry (programme liaison office)

2-Communication agent (radio – telegraphy)

Responsibilities

- Receives and transmit all radio HF communication from the liaison office

- Transmits radio messages and hand official postbags to the person it is addressed to.

- Assists the liaison agent to perform its tasks

- Distributes programme’s post bog, notably toward UNDP, the Ministry of tutelage and other tasks related to the communication agent for the programme.

Place: Conakry (liaison office)

3-Secretaries

Responsibilities

- Typing documents and classifying them

- Registers mailbags “arrival” and “departure”

- Registers mailbag “departure” and “arrival”

- Welcomes visitors

- Performs any other task compatible with the secretary mission

Place: Conakry (Lola and liaison office)

4-Drivers

Responsibilities

- Driving vehicle

- Up-keep of  the vehicle

- Dispersing  project’s postbags

- Perform any other tasks compatible with the driver’s mission when needed by the programme

Place: Conakry and Lola

5-Gatekeepers

Responsibilities

- Secure equipments and other programme’s property during and after the working time

- Control people and equipments entry/entrance and departure.

- Cleaning and weeding project compound/yard

Place: Conakry (Lola and liaison office)

III- National professionals

1.1-National experts

1-Protected areas specialist

Responsibilities

- Define and implement invigilation programme for the central reserve areas

- Participate in central reserves areas boundaries get up

- Reliance the functioning of meteorological and hydrological stations of upper basin of  Cavally (HBC)

- Think up and put in place invigilating systems for the Central reserves

- Involve beneficiaries in invigilation and organize public forces synergism

- Study bush five rate, its impact and identify an appropriate bush five management

- Implement any other measures that can help to overcome or  minimize bush fire consequences.

Qualifications

- Be a diplomat in tropical Ecology, fauna and flora management, forestry or geography engineer

- Have at least 5 years of field experience in reserved areas protection and invigilation and be familiar with the participatory approach system

- Have good knowledge about the operational activities on natural resources management.

- Work out a good coordination and team work systems

- Have conception abilities and be pragmatic

- Have organisational and team work management capacities

Place: Nimba Mountains

2-Wildlife specialist

Responsibilities

- Identify Nimba Mountains fauna preservation system

- Develop an inventory and monitoring plan of major fauna species.

- Develop and implement fauna management plan in collaboration with the beneficiaries, water and forest services, scientists, mining project and neighbour countries

- Provide tools to the coordination programme that allow national orientation of the wildlife sustainable management strategies in the central reserves and prevent new predator pressure or the fauna.

- Study special distribution of the wildlife species in the central reserves areas and evaluate fauna population variations/changes in 10 years

- Keep a watchful eye on endangered species

- Contribute to the ecological integrity preservation of the central reserve areas

- Initiate and popularize fauna species domestication and breeding methods.

Qualifications

- Be zoology or  biology diploma holder

- Have at least five (5) years field work in a reserve or in safari park, good knowledge of Nimba Mountains is an advantage

- Have a good knowledge of new methodologies of animals population monitoring in the tropical forests

- Have at least three (3) years’ field experience in natural resources management, integrated rural development and be familiar with the participatory approach (PA) in country/rural project  management.

Place: Nimba Mountains (Lola)

3-Rural engineering specialist

Responsibilities

- In agreement with local community,  develop and implement appropriate  management plans (PAGI)

- Participate in lowlands plains identification, carrying out studies and supervising  activities

- Make sure that beneficiaries are fully involved at all levels (conception and implementation)

- Ensure that activities are preceded by socio-economic, land tenure systems, soils studies, hydrology and topography surveys.

- Identify field partners (administration, NGOs private) susceptible to intervene in water management and suggest modalities and cooperation conditions.

- Assume water dump monitoring, irrigation and also monitor rainfall of covered areas Assist field roads operator.

Qualifications

- Be a rural engineering diploma holder  or equivalent

- Have at least five (5) years field experience in rural development project (RDP)and be familiar with the participatory approach method in rural accent management

- Have good knowledge about integrated rural development activity implementation and natural resources management, be able to analyse and synthesize LPDA, PNIR and water rights documents.

- Have good coordination plans and team work capability

Place: Nimba Mountains (Lola)

1.2-National consultants

- Rural sociologist specialist

Responsibilities

- Work out periodical report which demonstrates sociological problems of the areas, space occupation and land tenure system issues in the Cavally Upper Basin  (consulting the jurist in charge of institutional and legal matters)

- Study socio-cultural aspects of the beneficiaries and participate in fitting up plans conception, implementation and country, problems constraints related to conservation

- Conceive and put in place a mechanism of socio-economic data collection and analysis a agreement with the monitoring/Evaluation expert

- With agronomist, work out community’s supportive programme in order to prove production techniques such as storage product marketing and reinforce farmer groups negotiation capacities.

Qualifications

- Be a rural economist, rural sociologist diplomat or equivalent

- Have good knowledge of conducting socio-economics surveys, participatory methods and have country/rural accept management experience.

- Have good coordination plans and team work spirit

- Good knowledge of the communities living in the Cavally Upper Basin is an asset.

Place: Nimba Mountains (Lola)

1. 3-National volunteers

1-Cartographer (GIS specialist)

Responsibilities

- Develop adequate geographical information systems (GIS) and compose data base on resources management and integrated rural development

- Make up an atlas of geographical information on Nimba Mountains range and its surrounding areas

- Organize and put in place, in collaboration with the monitoring/Evaluation expert data collection system and analysis.

- Develop terms of reference for building up a cartographic and design room, provide regular satellite information, updated thematic cards production

Qualifications

- Be a geographer, cartographer holder of a diploma or equivalent (with photogrammetry specialization

- Have at least five (5) years field experience in geographical information system (GIS) management or data base on natural resources and integrated rural development management.

- Have good knowledge about activity implementation in natural resources management

- Have good knowledge about computer tools such as MS Word, Excel and SPSS

Place: Nimba Mountains (Lola)

2-Participatory Planning specialist

Responsibilities

- Define rural population communication characteristics

- Draw up information education and communication programme for the local communication on biodiversity preservation

- Develop information exchange channels susceptible to contribute to improve communication flow

- Help the programme to develop and undertake agreements with rural communities, partners and the government

- Develop a comprehensive position that can be communicated regarding the programme that takes into consideration beneficiaries constraints

- Initiates and implements outreach activities

- Provides orientation to the  local population on new ecosystems preservation and improves their making decision capacities in problems solving

- Define and implement women supportive programme

- Give necessary assistance to women, providing orientation and information on family health problems, nutrition etc...

- Ensure a good working conditions for communities in accordance with planned activities

- Promote farmer group’s access to credit systems.

Qualifications

- Be a socio-economics, social sciences, agronomy or equivalent diploma holder

- Have at least five (5) years’ field experience in rural development project extension and be familiar with participatory approach methods in rural accent management

- Have good knowledge about integrated rural development activity implementation

- Have efficient coordination skills and good team work spirit

- Women candidates are welcome

Place: Nimba Mountains (Lola)

2-Agronomist engineer

Responsibilities

- develop and implement agricultural production and agro-forestry strategies, plants health policy, fallow land etc...

- guide local farmers in innovations adoption

- develop  and put in place a research/development programme

- collaborate with the expert in charge of institutional and legal issues, in drawing up land management systems

- participate in geographical information system (GIS), data collection and analysis

- write up periodical reports on biodiversity preservation in Nimba Mountains ranges and surrounding areas.

- Identify constraints related to the performance of the job and suggest alternative solutions.

Qualifications

- Be an agronomist/agronomy, rural engineer holder of a diploma or equivalent

- Have a least three (3) years’ of field experience in rural development projects and be familiar with the participatory approach methods in rural accent management

- Have good knowledge of operational activities, integrated rural development and natural resources management

- Have  good coordination skills  and a good team work spirit

Place: Nimba Mountains (Lola)

3-Animal rearing specialist (animal health, veterinary surgeon)

Responsibilities

- Work out and implement animal rearing and health plans

- Conduct breeding and animal health survey and draw up objectives and strategies for breeding and animal health improvement

- Implement supportive programme towards stockbreeders to improve animal production and rural access to improved pastures management techniques

- Educate stockbreeders on alternative space management, seasonal rotations and bush fire control

- Develop strategic plans for farmers and stock breeders conflict management

- Facilitate veterinary pharmaceutical shop creation for stockbreeders

- Aid stockbreeders to create small production initiatives of alternative dry fodders

- Pay attention to small stock, poultry rearing, health and wildlife breeding

Qualifications

- Be veterinary, zootechnology engineering holder of a diploma or equivalent

- Have at least five (5) years of field experience in rural development project and be familiar with participatory approach methods

- Have good knowledge of operational activities in integrated rural development and natural resources management

- Have good coordination skills and team work spirit

Place: Nimba Mountains (Lola)

4- Multitasking platform management specialist

Responsibilities

The UNV in charge of animation and multitasking platform activities monitoring works closely with the national administrator of the programme and his staff. The multitasking platform manager will perform the following tasks.

- Initiate, monitor and evaluate at village level, activities related to platform installation and its functioning

- Follow up pilot studies of participatory feasibility in the villages wished to acquire a platform

- Assure beneficiaries training and platforms manager communication flow, partners etc...

- Supervise monitoring platform putting up

- Assure monitoring and monthly data collection on platform functioning

- Assist beneficiaries in identifying craftsman and establishing partnership among them

- Assure continuous training of workers for erection of platforms, their assembly and maintenance

- Put in place preventative maintenance systems, spare parts purchasing and stoking, maintenance agreements

- Assist the project to define adequate equipments, for the beneficiaries

- Work out scale charges for the different platform units; craftsman service scale charges (putting up preventive maintenance etc...)

- Put in place a monitoring /Evaluation programme

- Communicate information on a monthly basis  related to platform functioning to the S/E expert and economic states of the beneficiaries.

Qualifications

- Qualified in economics or rural sociology

- Approved participatory methods and animation experience particularly in rural women project

- Rural field work

- Team work mind/spirit

IV- International professionals

1-International wildlife consultant

Responsibilities

- In collaboration with the national fauna expert and protected areas consultant, the international wildlife consultant should identify Nimba Mountains fauna preservation methods

- Provide coordination programme tools

- Study fauna spatial distribution in the central reserve areas and evaluate species population in 10 years.

- Keep a watchful eye on endangered species restoration and stabilization

- Contribute to central reserve ecological areas integrity preservation

- Initiate and popularize wildlife species domesticating and breeding systems

- Improve national counterpart’s performance

- Write up contract end reports

Qualifications

-	Be a zoology diploma holder or equivalent

- Have at least five (5) years of field experience good knowledge of Nimba Mountains reserves is an advantage

- Have a good knowledge of the use of new methodologies of animal population monitoring in tropical forests

- Have at least three (3) years of field experience in natural resource projects management, integrated rural development and be familiar with the participatory approach methods

Place: Nimba Mountains (Lola)

3-Flora specialist

Responsibilities

- Identify Nimba Mountains flora preservation priorities

- Work out a stock list plan and main flora species monitoring

- Establish and implement flora management plans in the three central reserve areas

- Ensure endangered flora restoration and stabilization

- Contribute to the ecological central reserve areas integrity preservation

Qualifications

- Be a qualified botanist (BSC, M.phil or equivalent)

- Have and least five (5) years of field experience. Good knowledge about Nimba Mountain reserves is an advantage

- Have good knowledge about the new studies and monitoring mythologies of vegetal development in the tropical forests.

- Have at least three (3) years of field experience in natural resources management, integrated rural development projects and be familiar with the participatory approach methods in rural accent management

Place: Nimba Mountains (Lola)

4-Protected areas specialist

Responsibilities

- Define ecological and environmental monitoring plans

- At the beginning of the programme, develop ecological and environmental monitoring terms of references

- Define direct and indirect indicators

- Provide information on ecosystem dynamics and agro-pastoral systems of  the Cavally Upper Basin

- Collect data from how land potentialities progress/development, valleys and plains, forestry regeneration progress, soil erosions development, fragile ecosystems preservation etc...

- Take necessary measures for programme goals achievement in terms of ecology and environment preservation.

Qualifications

- Be geography, forestry or equivalent diploma holder(with ecology or protected areas management specialization

- Have at least three (3) years of field experience

- Have good knowledge about natural resource management

- Have efficient coordination system, team work spirit, ability to organize and manage a team or the field

Place: Nimba Mountains (Lola)

5-International consultant, specialist in GIS (to be provided after inception workshop)

6-International consultant rural engineering specialist (to be provided after start-up workshop)

7-International consultant, specialist in protected areas (to be provided after start-up workshop)

8- International consultant, specialist in flora (to be provided after start-up workshop)

9- International consultant, specialist in socio-economist (to be provided after start-up workshop)

10-International consultant, specialist in sustainable funding mechanism (to be provided after start-up workshop)

## Annex 8 – TOR of the steering committee

# Tasks

- provide overall policy guidance for the program;

- Provide support and advice to the program team on implementation of the program activities;

- Provide advice on stakeholder identification and participation and endorse the defined roles for each of the participating agency;

- Ensure participation of stakeholders through liaison with relevant stakeholder groups;

- Review and endorse the program work plan in line with the program document;

- Participate in the start-up workshop as part of the capacity building activities for the program;

- Monitor the performance of the program through evaluation of three monthly reports produced by the program coordinator and program team;

- Facilitate effective inter-agency sharing of information relevant to the program;

- Quality control of technical reports prepared by the national  and international consultants and the program administrator;

- Evaluate and approve all draft reports/policy papers  produced as outputs of the program;

- Liase with government to ensure government commitment to the program and approval of all produced Reports ;

- Facilitate discussions on possible funding sources for the NIP.

- Coordinate and manage the overall program activities and the budget.

- Facilitate coordination of program activities across institutions.

- Review the program activities, and their adherence to the work plan set forth in the program document.

- Review and comment on each year’s proposed work plan and budget

- Take decisions on the issues brought to its notice by UNDP and other cooperating institutions, and advise regarding efficient and timely execution of the program.

- Initiate remedial action to remove impediments in the progress of program activities that were not envisaged earlier.

# Composition

# The Committee shall comprise of high level officials from relevant Government agencies, community groups, non-government organizations, and the private sector.

## Annex 9 – Brief document approved in May 2003 (see attached)

## Annex 10 – Cofinancing letters (see attached)

# Footnotes

The GEF/UNDP project “Conservation Priority-Setting for the Upper Guinea Forest Ecosystem, West Africa” identified the Nimba Mountain complex as one of the highest priorities for conservation in the region.

ERIB’s mandate overlaps with CEGEN’s in that it is responsible for, among other things, managing the 300-hectare Bossou Hills area.  However this area has traditionally and for centuries been managed by the residents of Bossou and in essence as a private community reserve due to its chimpanzee population.  See Annex 12, GEF project brief, (Annex 8).

# Text boxes

Steering  Committee

UNDP

National

Co-coordinator

National  Administrator

Management & accounting department

- UNV International

- National expert

Government

(Ministry Environment)

Administrative personnel support

- Secretaries

- Drivers

- Security guards

- Logistician

Protected Areas Management &

Ecological Monitoring, GIS and Database Unit

National Building Capacities Unit

Rural Development Unit

National Monitoring & Evaluation Expert

This programme will contribute to the protection of the biological diversity of the Nimba Mountains Biosphere Reserve, including the World Heritage Site (officially on the list of Sites in Danger since 1992).  The proposed programme will rely on integrated ecosystem management through participatory approaches according to the philosophy of a biosphere reserve which aims  at conserving globally important biodiversity, and harmonising landscape-level sustainable use of natural resources and sustainable development. The programme will enhance mainstreaming of biodiversity conservation into local and national level sustainable development planning. The programme will also contribute to the development of a national system of protected areas. The programme consists of : (1) support to the protection of the Biosphere Reserve’s three core areas; (2) intensifying agriculture and increasing agricultural income in the buffer zone and transition area of the Reserve; (3) promoting culturally appropriate animal husbandry and sustainable use of wild fauna; (4) improving local health and hygiene conditions, including by promoting complementarity between ‘modern’ and traditional medicines, and sustainable use of traditional medicinal plants; and (5) strengthening the management authority for the Biosphere Reserve - CEGEN - as well as inter-institutional co-ordination & planning mechanisms for CEGEN and national partners including sectoral line agencies, rural development programmes, and the iron ore mining companies.

Budget (US$)			11,436,900

General Management Support Fee________

Total budget:			11,436,900

Allocated resources:		11,436,900

- Government		     330,500

- UNDP TRAC               1,646,400

funds (1+2)

- Other:

  - GEF		  3,660,000

  - WHC	 	     500,000

  - Mining		  4,500,000

  - FFI		     200,000

- In kind contributions

(Gvt-RDC)  		     600,000

Unfunded budget:	-0-

Programme Period November 2004 – Octobert 2013

Programme Component: Sustainable environmental management

Project Title  Conservation of the biodiversity of the Nimba Mountains through integrated and participatory management

Project ID: GUI/03/G31,  GUI/04/001/A/01/99

Project Duration:	 9 years

Management Arrangement:  NEX arrangements