The Republic of The Gambia

Ministry of Health and Social Welfare

Ebola Emergency Preparedness and

Response Plan for The Gambia

April to September 2014

April 2014

Table of Contents

1. Introduction........................................................................................................................... 3

1.1 The Ministry’s response...................................................................................................... 4

1.2 Preparedness and Response Plan......................................................................................... 4

1.3 Goal and Objectives............................................................................................................ 4

2. Proposed interventions.......................................................................................................... 5

2.1 Coordination........................................................................................................................ 5

2.2 Surveillance and Laboratory............................................................................................... 5

2.2.1 Surveillance...................................................................................................................... 5

2.2.2 Laboratory........................................................................................................................ 6

2.3 Case Management and Logistics........................................................................................ 7

2.3.1 Isolation and Barrier Measures........................................................................................ 7

2.3.2 Cleaning and Disinfection................................................................................................ 8

2.4 Communication /Social Mobilization............................................................................... 10

2.4.1. Structure and composition............................................................................................. 11

2.4.2 Activities........................................................................................................................ 12

2.4.3. Targeted districts........................................................................................................ 12 3

- Introduction

The Ministry of Health of the Republic of Guinea officially notified the World Health Organization of the first case of Ebola Viral Disease (EVD) formerly known as Ebola Haemorrhagic Fever on 21 March 2014. This is the first time EVD has been reported in a West African Country. Countries bordering Guinea such as Liberia, Sierra Leone and Mali have also reported suspected and confirmed cases.  Laboratory analysis has characterized the virus as a strain of Ebola Zaire, which is one of the most virulent Ebola viruses.

As of 7 April, a cumulative total of 151 clinically compatible cases, including 95 deaths had officially been reported from Guinea. Laboratory investigations continue at the Institute Pasteur (IP) Dakar laboratory in Conakry (65 samples tested, of which 34 are positive by PCR for Ebola virus) and at the European Union Mobile Laboratory (EMLab) team in Guekedou (36 samples tested/20 positive). Medical observation is continuing for 535 contacts. In addition, as of 7 April, the Ministry of Health and Social Welfare (MOHSW) of Liberia has reported a cumulative total of 5 laboratory confirmed cases and 16 suspected and probable cases of EVD, including 10 deaths. All 5 laboratory confirmed cases have died. The most recent death is in a probable case of EVD from Montserrado. Three cases have occurred in health-care workers, all of whom have died. At present 28 contacts remain under medical observation.

There has been no change in the epidemiological situation of EVD in Sierra Leone. The Ministry of Health and Sanitation of Sierra Leone has confirmed that 2 suspected cases of viral haemorrhagic fever are laboratory confirmed as Lassa fever which is endemic in Sierra Leone. The Ministry of Health of Mali has reported a cumulative total of 6 suspected cases as of 7 April, 2 of which have tested negative for EVD and other viral haemorrhagic fever viruses in assays conducted by the U.S. Centers for Disease Control and Prevention (CDC) in Atlanta. Samples from the 4 remaining suspected cases have also been sent for testing.

In the Gambia, twopeople who travelled from one of the affected areas in Guinea (Macenta) were traced by the surveillance network. They were investigated and found negative for EVD. Given this context and the increased risk of importation of EVD into The Gambia, there is a need to develop a comprehensive preparedness and response plan with particular emphasis on strengthening surveillance at key border points.

  - The Ministry’s response

Two days (23 March 2014) after Guinea had reported the first case of EVD to the WHO, the Ministry of Health and Social and Social (MOHSW) in collaboration with its partners put in place a number of interim preparatory measures:

- An official press release issued by the Ministry on Sunday 23 March 2014 to inform the general public about the situation in Guinea, which was followed by a series of pubic sensitization in the media

- A briefing of stakeholders on the situation in Guinea and on the national response plan

- Reactivation of existing emergency preparedness and management structures and networks

- Reactivation of cross border consultations and deployment of public health officers at strategic border areas with the Republic of Senegal and at the International airport to provide a 24-hour service of sensitization and screening of incoming travelers (v) strengthening of the disease surveillance system to track both active and suspected cases of EVD and

- Country-wide rapid assessment of supplies and resources available on the ground and at health facilities in preparation

2.2	Development of a national preparedness and response plan

  - Preparedness and Response Plan

The above interim measures are, without doubt, critical to ongoing efforts to prevent EVD from spreading into the country, but to effectively prevent and control EVD it was deemed necessary to conduct a rapid and thorough assessment of the available resources and needs.  Thus, a team of health officials conducted a countrywide assessment from 25-31 March during which health facilities, stakeholders and community were visited. This assessment revealed a number of challenges with regards to the state of preparedness for an EVD outbreak:

- Unavailability/inadequate isolation units at the health facilities visited

- Limited/lack of knowledge among health care workers on the signs and symptoms of EVD.

- Limited stock of Personal Protective Equipment (PPE) (gloves, facemask, head cover, apron, gum booths, gowns, etc) and medical supplies (drugs, equipment, etc).  The available stocks of PPEs were leftovers from the H1N1 outbreak and are not specific for EVD.

- Inadequate laboratory capacity to diagnose EVD in the country. Laboratory confirmation can be done only in Dakar, Senegal

- Limited human and financial resource capacity to conduct 24-hour consultations, screening and  sensitization at strategic border areas with Senegal and at the International Airport

- Inadequate awareness about EVD among the general population, particularly in the area of outbreak containment including burial of the deceased.

To ensure a comprehensive and coordinated preparedness and response to Ebola outbreak, the MOHSW developed an operational emergency response plan with a focus on strengthening coordination at the national and district level; intensifying active surveillance (active case search and contact tracing); prompt case management and effective infection control; and public health education/ sensitization.

1.3 Goal and Objectives

 Goal

The goal of the plan is to prevent the importation of Ebola into the country and in the event of a confirmed case reduce morbidity and mortality.

 Specific Objectives

1. To strengthen early detection, reporting and referral of suspected cases through active surveillance to isolation units within facilities

2. To conduct an extended outbreak investigation in order to identify contacts of Ebola patients and to characterize and establish the index case

3. To institute prompt and effective case management of all suspected cases in a controlled environment, while enhancing appropriate infection control measures

4. To create public awareness about Ebola, the risk factors for its transmission, its prevention and control among the community

5. To ensure coordination of the preparedness and outbreak response activities at all levels

- Proposed interventions

The planned interventions include all the activities for improving the preparedness, prompt identification, notification and effective management of cases, effective social mobilization and effective coordination of the epidemic response.

  - Coordination

Objective: To coordinate Ebola preparedness and response activities at all levels for a period of six months

Proposed activities

1. Conduct weekly National Task Force meetings and updates

2. Re-activate and support Regional Task Force meetings in all regions

3. Monitor implementation of an emergency national and regional epidemic preparedness and response plans for Ebola

4. Conduct resource mobilization for preparedness and response activities

2.2 Surveillance and Laboratory

Objective: To strengthen early detection, reporting and referral of suspected cases through active surveillance and conducting extensive outbreak investigation nationwide with special focus on the south bank for a period of six months

2.2.1 Surveillance

1. Adapt standard case definition (SCD), case investigation forms, line listing forms and other surveillance tools(field guide booklets, step-by-step charts, infection control guide)

2. Print and distribute surveillance tools to all health facilities

3. Conduct orientation of health workers (300) on Ebola surveillance and appropriate use of surveillance tools

4. Conduct active case search, contact tracing and follow up in all districts with specific reference to districts with international borders

5. Support 8 regional rapid response team members (RRT) to conduct verification and outbreak investigation of suspected cases/ rumours in all the seven health regions

6. Support 10 national RRT members to conduct verification and outbreak investigation of suspected cases/rumours in all the seven health regions

7. Strengthen daily reporting mechanism from all health facilities

8. Produce weekly/daily update and share with partners

9. Establish and equip a national emergency command centre at EDC/MOHSW

10. Establishand strengthen isolation units at the health facilities

11. Procure 100 PPE for Ebola

12. Provide 3 skin biopsy kits

2.2.2 Laboratory

1. Adapt Laboratory protocol and tools for EVD sample collection

2. Conduct two days orientation for 21 Laboratory Technicians

3. Provide supplies for specimen collection at facility level (vacutainer tubes without anti-coagulants, vacutainer needles, tourniquet, cotton wool, disinfectants, plaster, hand sanitizers, biohazard bags, sharps containers, specimen carrier boxes, cool boxes)

4. Provide supplies for specimen collection at facility level(Needles & syringes, cotton wool, disinfectants)

5. Provide 50 triple packaging for specimen transportation (fridge for temporary storage)

6. Support national sample transportation

7. Support international sample transportation

8. Ensure proper waste management

2.3Case Management and Logistics

Objective: Institute prompt and effective case management of all suspected and confirmed cases so as to reduce morbidity and mortality

2.3.1 Isolation and Barrier Measures

Outside a well set-up isolation unit, the risks to staff should not be underestimated and care should be restricted to that required to make a diagnosis and maintain the dignity and comfort of a patient. It is essential that patients are isolated in a separate area, away from other patients. The area should be well ventilated and have separate toilet facilities because urine and faeces are fluids highly contagious and infective – safe disposal of this sewage is therefore also essential.

The room furniture and equipment must consist of:

- Bed and mattress for each patient. Plastic sheeting to cover the mattress or sleeping mat (It can be easily cleaned and disinfected if it becomes contaminated with infectious body fluids). Bedding for each bed should consist of at least 1 blanket and a bottom sheet. If necessary, the patient or the patient's family can bring the bedding from home.

- One thermometer, one stethoscope, and one blood-pressure cuff per patient with the possibility of disinfecting them after each use with a covered container of alcohol or bleach solution.

- Puncture-resistant containers for collecting used disposable needles, syringes and other sharp instruments.

- Disinfection station with buckets, sprayer, bleach solutions, soap and water.

- Containers with soapy water for collecting used instruments to be sterilized afterwards.

- Containers for collecting protective clothing and infectious waste to be burned.

Staff members who should wear protective clothing (PPE) in the Isolation Room include:

 All doctors, nurses, and health care workers who provide direct patient care to suspected patients.

 All support staff who clean the isolation room, handle contaminated supplies and equipment, launder reusable supplies, and collect and dispose of infectious waste.

 All laboratory staff who handle patient specimens and body fluids from suspected cases. Laboratory support staff that clean and disinfect laboratory equipment used to test specimens.

 Burial teams who remove bodies of deceased patients and prepare them for burial.

 Family members who care for patients.

Outdoors there must be a cupboard with all the stored clean protective clothing to use before entering the room (Supply of clean gowns, aprons, gloves, masks, head covering, shoes covering or rubber boots and eyewear).

Indoors there must be the containers previously mentioned for the contaminated clothing and supplies which must remain in the IsolationRoom, until designated personnel remove them for safe disposal.

2.3.2 Cleaning and Disinfection

Ordinary Household Bleach: The virus is very sensitive to bleach solution. A low-cost disinfection system can be used, based on two bleach solutions: a solution of 1:10 (kills the virus in 1 minute) and a solution of 1:100 (exposure for 10 minutes).

Soap and Clean Water: Scrubbing with soap and water before disinfection removes infectious body fluids and other foreign matter from contaminated items. This makes bleach solutions more effective.

Sterilization: Heat sterilization requires special equipment, such as an autoclave or steam sterilizer. When this equipment is not working or is not available, boiling heat-resilient items in water for 20 minutes will kill the virus.

2.3.3 Treatment and Infection Control Protocols

No specific treatment or vaccine for Ebola is available, so standard treatment for Ebola is still limited to supportive therapy, consisting of:

 Balancing the patient’s fluids and electrolytes: Oral fluid intake or IV Ringer Lactate/Dextrose or Normal saline

 Maintaining their oxygen status and blood pressure

 Treating them for any complicating infections

Replacement of coagulation factors and of platelets may be of value but there is currently little or no evidence to support the use of them.

Other measures if necessary:

 Oral medication includes drugs that alleviate EVD-related symptoms such as pain or fever (Paracetamol oral or IV) and other less common: nausea and vomiting (eg, metoclopramide and promethazine), dyspepsia (e.g. aluminiumhydroxide, cimetidine, ranitidine, and omeprazole), anxiety, agitation, or confusion (e.g. diazepam, chlorpromazine).

 Due to the usual absence of an onsite laboratory capable of safely processing biological samples for alternative diagnoses, empiric oral artemisinin combination therapies for malaria and empiric oral antibiotics (amoxicillin, cotrimoxazole, cefixime, orciprofloxacin) should be considered until definitive diagnosis of Ebola is established and other etiologies of the fever are ruled out.

Standard patient monitoring of vital signs (respiratory rate, blood pressure, and pulse), pulmonary signs (rales), and fluid intake-output ratios must be systematically monitored despite the isolation of the patient.

2.3.4 Referral and Transportation of Suspected and Confirmed Cases

All hospitals (public, private and NGO) are mandated to accept suspected Ebola patients and not to reject them at the door or immediately refer them elsewhere, to avoid further exposure of infected patients.

During the initial phase, all confirmed cases will be referred to designated isolation centres using special ambulances.

2.3.5 Waste Disposal

The threat of infection from used and infected material is serious, and strict procedures for body fluids and excreta must be maintained. Patient excreta, vomit, sputum, blood, and all the objects with which the patient had contact must be disinfected with bleach. Thorough thermal disinfection or the use of bleach is adequate; formaldehyde fumigation can be considered. Proper disposal of needles and other hospital equipment is essential.

Persons with percutaneous or mucocutaneous exposures to blood, body fluids, secretions or excretions from a patient must immediately wash the affected skin surfaces with disinfectant, followed by soap and water. Mucous membranes such as conjunctiva must be flushed with water or eyewash solution. Exposed persons must be considered as contacts and receive medical evaluation, and must be followed up for 21 days for the possible development of symptoms.

2.3.6 Safe Burials

Corpses must be wrapped in sealed leak-proof material (body bag). They must not be embalmed but buried promptly in a sealed casket. Disinfection or incineration of all dirtied belongings of the patient must be immediately performed.

Burial sites must be identified early on, to organize and facilitate transport of dead bodies. Local burial customs must be adhered to as closely as possible provided they do not conflict with good public health practices: avoidance of direct physical contact with corpses or body fluids.

2.3.7 Training of Health Workers

All persons coming into contact with suspected cases or with corpses must be trained in the proper infection control methods. They must be instructed on how to route patients from output to isolation, and on how to manage cases by way of symptomatic relief of symptoms. Surveillance must be combined with health education aimed at limiting contact with patients.

2.4 Communication /Social Mobilization

Objectives:

1. To raise awareness and build knowledge on prevention and control of EVD

2. To promote change of negative cultural beliefs, attitudes and practices

3. To promote community participation in the prevention and control of EVD

4. To strengthen coordination and communication at all levels

The approaches that will be used to implement the communication strategy include:

1. Develop and implement Outbreak Communication and Public Relations

 Facilitate smooth flow of the correct and timely information to the public

 Counteract rumours and misinformation arising from fear/panic and lack of information.

 Build strategic partnerships with the media to develop and disseminate timely and correct information to promote and support disease control programmes including management of rumours and misinformation

 Spell out the key messages, process and channels of communication.

2. To develop and implement strategic behaviour change communication interventions for containment of EVD outbreak. This will focus on:

 Creating public awareness about the cause, recognition, prevention and control of the disease.

 Discouraging negative cultural beliefs and practices that facilitate/promote transmission of the disease.

 Promoting community participation and involvement in educating the public, contact tracing and reporting and monitoring of the outbreak.

 Soliciting both political and civic leadership support and involvement in epidemic containment.

 Building partnership with CBOs, NGOs, Media and existing social structure channels to facilitate public education and provide psychosocial support to the affected families and communities.

2.4.1. Structure and composition

A national communication taskforce exists within the MOHSW and the directorate of health promotion and education is the lead agency. In each region there is a regional communication taskforce.  The taskforce comprises of MOHSW, media, Red Cross, UNICEF, WHO, NGOs and Civil society.

2.4.2 Activities

1. Produce/adapt IEC/BCC materials /messages and translate into key local languages

2. Organize regular radio and TV panel discussion and phone- in programme

3. Organize orientation of media practitioners

4. Organize regular briefing of Media Houses (Print and electronic)

5. Develop and disseminate IEC/BCC materials

6. Develop regular situation report

7. Organize Community sensitization meetings targeting Alkalos, Ward Councilors, Multidisciplinary Facilitation Teams (MDFTs), Technical Advisory Committees (TACs), Religious leaders, Women leaders and youth leaders

8. Train health workers on outbreak communication skills

9. Organize regional and district level sensitization meeting with school authorities

10. Disseminate prevention messages on (Jatakendeya and Werguyaram) GRTS Health programme

11. Production and distribution of communication materials

12. Send SMS messages to mobile phone subscribers through GSM Providers

13. Conduct interactive community based IEC activities (open field days, traditional communicators and community drama groups)

The costed operational plan for control of EVD is attached.

| PREPAREDNESS AND RESPONSE PLAN OF ACTION FOR EBOLA, THE GAMBIA, MARCH TO AUGUST, 2014 |
| --- |
|  | Activity |  | No. of units | Days/Week s/months |  |  |  | Source of funding |  |
| 1. 0 | COORDINATION | Sub-activity |  |  | Number | Unit cost (GMD) | Total (GMD) |  | Comment |
|  | Conduct weekly National Task Force meetings and updates | Mobile phone top up cards | 1 | 6 | 2 | 100 | 1,200 |  |  |
|  |  | Stationery | 1 | 1 | 1 | 15,000 | 15,000 |  |  |
|  |  | Refreshment | 1 | 24 | 15 | 200 | 72,000 |  |  |
|  |  | Fuel for coordination | 2 | 24 | 20 | 55 | 52,704 |  |  |
|  | Re-activate and support Regional Task force meeting | Mobile phone top up cards | 7 | 6 | 3 | 100 | 12,600 |  |  |
|  |  | Stationery | 1 | 1 | 1 | 20,000 | 20,000 |  |  |
|  | Monitor implementation of an emergency national and regional epidemic preparedness and response plans for EVD | Monthly visit to all regions | 7 | 6 | 3 | 300 | 37,800 |  |  |
|  |  | Fuel for monitoring (90 litres/region for 6 months) | 90 | 6 | 7 | 55 | 207,900 |  |  |
|  | Conduct resource mobilization for preparedness and response activities | Meeting with donor partners and stakeholders | 0 | 0 | 0 | 0 | 5,000 |  |  |
|  | Sub total: | 424,204 |  |  |
| 2. 0 | SURVEILLANCE AND LABORATORY |  |  |
|  | SURVEILLANCE: |
|  | Adapt standard case definition (SCD), case investigation forms, line listing forms and other surveillance tools(field guide booklets, step-by-step charts, infection control guide) | Meeting to adapt standard case definition and surveillance tools (lunch for participants) | 1 | 2 | 15 | 1,000 | 30,000 |  | Conference room, Teabreak & Lunch |
|  |  | Print all adapted documents | 1 | 1 | 1 | 150000 | 150,000 |  |  |
|  |  | Distribute printed documents to all health facilities |  |  |  |  |  | Government support |  |
|  | Conduct orientation of health workers(500) on EBD surveillance and appropriate use of surveillance tools | Training of Trainers | 1 | 1 | 35 | 1,000 | 35,000 |  | DSA, transport and training logistics |
|  |  | Cascade training | 1 | 1 | 500 | 450 | 225,000 |  | DSA, transpoort and training logistics |
|  | Conduct active case search, contact tracing and follow up in all regions with specific reference to regions with international border | DSA to surveillance officers to conduct active case search and contact tracing | 1 | 180 | 45 | 250 | 2,025,000 |  |  |
|  |  | Fuel to conduct active case search and contact tracing | 10 | 24 | 45 | 55 | 594,000 |  |  |
|  |  | Risk allowance for surveillance personnel | 1 | 24 | 20 | 750 | 360,000 |  |  |
|  | Support 8 regional RRT members to conduct verification and outbreak investigation of suspected cases/ rumors in all the regions | Risk allowance for regional RRT | 7 | 6 | 8 | 750 | 252,000 |  |  |
|  |  | Fuel to conduct verification and outbreak investigation | 1 | 1 | 2500 | 55 | 137,500 |  |  |
|  | Support 10 national RRT members to conduct verification and outbreak investigation of suspected cases/ rumors in all the 7 regions | DSA to RRT members | 1 | 6 | 8 | 7,000 | 336,000 |  |  |
|  |  | Risk allowance to RRT members | 1 | 6 | 8 | 750 | 36,000 |  |  |
|  |  | Fuel to conduct verification and outbreak investigation | 1 | 6 | 2,500 | 55 | 825,000 |  |  |
|  |  | Procure 1 Toyota Hiluxs for national RRT | 1 | 1 | 1 |  | 2,000,000 |  |  |
|  | Establish and equip a national emergency command centre at EDC/MOHSW | Rehabilitate the existing structure | 1 | 1 | 1 |  |  |  |  |
|  |  | Equip command center with desk tops, work station, hard drives, files, printers, notice board | 1 | 1 | 1 | 150,000 | 150,000 |  |  |
|  |  | Sub total: | 7,155,500 |  |  |
|  | Cross border surveillance activities |  |  |  |  |  |  |  |  |
|  | Conduct trainings for port health workers at all border crossing points and airport on ebola | Training of border surveillance officers | 1 | 2 | 55 | 500 | 55,000 |  |  |
|  | Provide disinfectant for crossing point | Procure disinfectant | 9 | 3 | 10 | 500 | 135,000 |  |  |
|  | Identify isolation units within the airport | Provide isolation units for airport |  |  |  |  |  |  | case management to coordinate |
|  |  | Institute referral system from the airport |  |  |  |  |  | Govt to institute |  |
|  | Procure 100 PPE for EVD |  | 3 | 1 | 1 | 9500 | 28,500 |  |  |
|  | Provide 3 skin biopsy kits |  | 0 | 0 | 0 | 0 | 0 | WHO to advise |  |
|  |  | Sub total: | 218,500 |  |  |
|  | LABORATORY |  |  |  |  |  |  |  |  |
|  | Conduct two days orientation on specimen collection and packaging for 21 Laboratory Technicians | Training of Laboratory technicians | 7 | 2 | 3 | 1,260 | 52,920 |  |  |
|  | Procure supplies for specimen collection at referral centers ( tourniquet, cotton wool, disinfectants, plaster, biohazard bags, sharps containers, gloves, ) | Procure supplies for specimen collection at referral centres |  |  |  |  | 50,000 |  |  |
|  | Vacutainer needle holders | Support laboratory supplies and reagents |  |  | 30 |  |  |  |  |
|  | Vacutainer needles G21 |  |  |  | 500 |  |  |  |  |
|  | Plain Vacutainer tube |  |  |  | 500 |  |  |  |  |
|  | Scapel Blades |  |  |  | 60 |  |  |  |  |
|  | Provide 50 triple packaging for specimen transportation |  |  |  | 50 |  |  |  |  |
|  | Support national sample transportation | Fuel for sample collection | 1 | 1 | 1500 | 55 | 82,500 |  |  |
|  | Support international sample transportation | Fuel for sample transportation to Dakar | 1 | 1 | 2500 | 55 | 137,500 |  |  |
|  |  | DSA for Driver and Laboratory technician | 1 | 6 | 2 | 13,000 | 156,000 |  |  |
|  |  | Risk allowance for sample collector | 1 | 6 | 3 | 750 | 13,500 |  |  |
|  | Ensure proper waste management | Risk allowance to support staff for collection of waste | 1 | 6 | 4 | 750 | 18,000 |  |  |
|  |  | Procure biohazard bags | 1 | 1 | 200 | 16 | 3,200 |  |  |
|  |  | Sub total: | 513,620 |  |  |
|  | CASE MANAGEMENT |  |  |  |  |  |  |  |  |
|  | COORDINATION | Minor Maintenance of 1 National |  |  |  |  |  |  |  |
|  |  | Coordinating vehicle | 1 | 1 | 1 | 100,000 | 100,000 |  |  |
|  |  | Fuel for Coordination vehicles | 1 | 6 | 1000 | 55 | 330,000 |  |  |
|  |  |  |  |  |  |  | 0 |  |  |
|  |  | Stationery(2000) per month for six months) | 1 | 6 | 1 | 2,000 | 12,000 |  |  |
|  |  | Ebola coordinators( 1 PER Hospital and major HC) | 1 | 6 | 15 | 750 | 67,500 |  |  |
|  |  | Risk allowance for 15 staff @ 3000 per month *6) |  |  |  |  | 0 |  |  |
|  |  |  | 1 | 6 | 15 | 3,000 | 270,000 |  |  |
|  |  | Communication (1000 units per month for 6 months) |  |  |  |  | 0 |  |  |
|  |  |  | 1000 | 6 | 15 | 1 | 90,000 |  |  |
|  |  | Sub total: | 869,500 |  |  |
|  | Training Of Trainers | Training of 35 Health Care Workers ( Clinicians from Hospital, Regions) |  |  |  |  |  |  |  |
|  |  |  | 1 | 2 | 35 | 750 | 52,500 |  |  |
|  |  | Cascade training hospital (5 per shift *3 * 15 Hospital and Major Health Centers) |  |  |  |  | 0 |  |  |
|  |  |  | 1 | 1 | 225 | 250 | 56,250 |  |  |
|  |  | Establish isolaton unit within hospital (1 per region) |  |  |  |  | 0 |  |  |
|  |  |  | 1 | 1 | 1 | 300,000 | 300,000 |  |  |
|  |  | Supervision of hospital cascade training(1/hospital *15) | 1 | 3 | 15 | 750 | 33,750 |  |  |
|  |  | Risk incentive for isolation units staff (45) | 1 | 6 | 45 | 750 | 202,500 |  |  |
|  |  | Sub total: | 645,000 |  |  |
|  | Logistics,Drugs & other Medical supplies | Disinfectants | 1 | 1 | 1 | 200,000 | 200,000 |  |  |
|  |  | Fuel for 2 Ambullances for 6 months | 4 | 6 | 100 | 55 | 132,000 |  |  |
|  |  | Risk incentive for 2 drivers + 2 staff per ambullance | 1 | 6 | 4 | 750 | 18,000 |  |  |
|  |  | Cannula |  |  |  |  |  |  |  |
|  |  | Giving sets |  |  |  |  |  |  |  |
|  |  | PPE | 0 | 0 | 0 | 0 | 0 |  |  |
|  |  | Sub total: | 350,000 |  |  |
|  | Procure commodities to support for infection control and discharge package | Tents as isolation facilites for the cases | 0 | 0 | 5 | 0 |  |  |  |
|  |  | Spray pumps | 1 | 1 | 10 | 20,000 | 200,000 |  |  |
|  |  | Beds (Cholera beds) | 0 | 0 | 50 | 0 | 0 | WHO to advise on cost |  |
|  |  | Matresses | 0 | 0 | 50 | 0 | 0 |  |  |
|  |  | Mattress covers | 1 | 1 | 50 | 250 | 12,500 |  |  |
|  |  | Beddings (blankets and sheets) | 1 | 1 | 300 | 600 | 180,000 |  |  |
|  |  | Procure autoclave | 0 | 0 | 5 | 0 | 0 |  |  |
|  |  | Rechargable Lamps | 1 | 1 | 30 | 600 | 18,000 |  |  |
|  |  | Gum boots | 1 | 1 | 25 | 600 | 15,000 |  |  |
|  |  | Dust bins | 1 | 1 | 10 | 1,500 | 15,000 |  |  |
|  |  | Hand washing facilities | 1 | 1 | 15 | 500 | 7,500 |  |  |
|  |  | Overalls for cleaners | 1 | 1 | 20 | 500 | 10,000 |  |  |
|  |  | Basins | 1 | 1 | 30 | 200 | 6,000 |  |  |
|  |  | Jerrycans | 1 | 1 | 30 | 200 | 6,000 |  |  |
|  |  | 100 LITRE drum | 1 | 1 | 30 | 900 | 27,000 |  |  |
|  |  | 20litre buckets | 1 | 1 | 30 | 200 | 6,000 |  |  |
|  |  | Moppers | 1 | 1 | 50 | 150 | 7,500 |  |  |
|  |  | Squeezers | 1 | 1 | 30 | 1,500 | 45,000 |  |  |
|  |  | Mopping buckets | 1 | 1 | 15 | 450 | 6,750 |  |  |
|  |  | Liquid soap | 1 | 1 | 500 | 150 | 75,000 |  |  |
|  |  | Detergent | 1 | 1 | 100 | 350 | 35,000 |  |  |
|  |  | Paraffin for incineration | 0 | 0 | 0 | 0 | 0 |  |  |
|  |  | Sub total: | 672,250 |  |  |
|  | DRUGS | 1 Liter Ringer’s Lactate | 1 | 1 | 500 | 100 | 50,000 |  |  |
|  |  | Paracetamol tablet 500mg) 10 tins per isola | 1 | 1 | 50 |  |  |  |  |
|  |  | Paracetamol iv(500 per isolation units) | 1 | 1 | 500 |  |  |  |  |
|  |  | ORS | 1 | 1 | 1,000 |  |  |  |  |
|  |  | Anti emetics |  |  |  |  |  |  |  |
|  |  | Antibiotics(Assoted) |  |  |  |  |  |  |  |
|  |  | Body bags (20 per isolation unit) to be supplies by partners |  |  |  |  |  |  |  |
|  |  | Sub total: | 50,000 |  |  |
|  | Others | Risk allawance for Waste disposal personnel | 1 | 6 | 15 | 750 | 67,500 |  |  |
|  |  | Fuel for waste disposal vehicles (15 vehicle) | 7 | 6 | 100 | 55 | 231,000 |  |  |
|  |  | waste bags (50 per isolation unit) | 15 | 1 | 50 | 150 | 112,500 |  |  |
|  |  | Sub total: | 411,000 |  |  |
|  | SOCIAL MOBILIZATION AND HEALTH EDUCATION |  |  |  |  |  |  |
|  | Review/update IEC/BCC materials/messages for 2 days | DSA for Communication technicians and experts | 2 | 1 | 20 | 650 | 26,000 |  |  |
|  |  | Pre-testing of the draft messages | 1 | 1 | 6 | 650 | 3900 |  |  |
|  | Validation meeting of draft messages for 1 day |  | 1 | 1 | 25 | 650 | 16,250 |  |  |
|  | Organize weekly radio and TV panel discussion and phone-in programmes country-wide | conduct 5 radio programmes in 7 regions | 7 | 5 | 1 | 800 | 28,000 |  |  |
|  |  | Conduct 12 National TV programmes | 1 | 12 | 1 | 20000 | 240,000 |  |  |
|  |  | Transport refund for panelist | 1 | 3 | 12 | 200 | 7,200 |  |  |
|  |  | Conduct radio 10 (national) programmes | 1 | 10 | 1 | 200 | 2000 |  |  |
|  | Conduct bi-weekly communication coordination meetings (National) | Transport | 1 | 12 | 15 | 200 | 36,000 |  |  |
|  |  | stationery | 1 | 1 | 1 | 12000 | 12000 |  |  |
|  |  | Snacks |  | 12 | 15 | 100 | 18,000 |  |  |
|  | Conduct bi-weekly communication meetings (regional) | Transport | 1 | 12 | 15 | 200 | 36,000 |  |  |
|  |  | Snacks |  | 12 | 70 | 100 | 84,000 |  |  |
|  | Organize one day orientation meeting for media practitioners | Conduct orientation meeting for media practitioners | 1 | 1 | 25 | 200 | 5,000 |  |  |
|  |  | Hire of conference hall | 1 | 1 | 1 | 3000 | 3000 |  |  |
|  |  | Stationery | 1 | 1 | 1 | 5,000 | 5,000 |  |  |
|  |  | Fuel | 2 | 1 | 20 | 55 | 2200 |  |  |
|  | Organize bi-weekly press briefing (print and elctronic) media houses | conduct bi-weekly press briefing | 1 | 1 | 12 | 6000 | 72000 |  |  |
|  | Organize community sensitization meetings targeting alkalos, chiefs, ward councilors, religious leaders, women kafo leaders, MDFTs, TACs and Red Cross Volunteers | Organize orientation meeting with LGAs (governor,chiefs,TACs) | 7 | 1 | 30 | 325 | 68,250 |  |  |
|  |  | DSA for central level | 1 | 7 | 4 | 650 | 18,200 |  |  |
|  |  | Fuel for Central Team | 1 | 1 | 200 | 55 | 11,000 |  |  |
|  |  | Fuel for RHTs | 7 | 1 | 50 | 55 | 19,250 |  |  |
|  |  | Orientation of 875 village heads by district chiefs/PHOs | 1 | 1 | 875 | 200 | 175,000 |  |  |
|  |  | Fuel support for PHOs | 48 |  | 10 | 55 | 26,400 |  |  |
|  |  | DSA for facilitators and coordinators (days) regional level | 7 | 1 | 14 | 650 | 63,700 |  |  |
|  |  | Fuel for RHT | 7 | 1 | 100 | 55 | 38500 |  |  |
|  |  | Orientation of Red Cross Volunteers | 1 | 1 | 350 | 200 | 70,000 |  |  |
|  |  | Regional Facilitators | 7 | 1 | 2 | 200 | 2800 |  |  |
|  |  | Deployment of Red Cross Volunteers | 1 | 5 | 350 | 200 | 350,000 |  |  |
|  |  | DSA for monitors | 1 | 5 | 14 | 325 | 22,750 |  |  |
|  |  | Fuel for Monitors | 1 | 7 | 50 | 55 | 19,250 |  |  |
|  | Train 40 health workers on outbreak communication/ rumour management | Organize 2 days workshop | 1 | 2 | 40 | 650 | 52,000 |  |  |
|  |  | refreshment | 1 | 2 | 40 | 200 | 16,000 |  |  |
|  |  | Stationery | 1 | 1 | 1 | 5000 | 5000 |  |  |
|  |  | Fuel | 2 | 1 | 100 | 55 | 11000 |  |  |
|  |  | DSA for facilitators and coordinators (3 days) Central level | 1 | 3 | 5 | 650 | 9750 |  |  |
|  | Organize regional and district level sensitization meeting with school authorities/teachers Cluster monitors | conduct regional sensitization meeting with 60 cluster monitors school authorities | 1 | 1 | 70 | 325 | 22,750 |  |  |
|  |  | Fuel support to Cluster monitors | 10 |  | 60 | 55 | 33,000 |  |  |
|  |  | refreshment | 1 | 1 | 60 | 200 | 12,000 |  |  |
|  |  | stationery | 1 | 1 | 1 | 5000 | 5000 |  |  |
|  |  | DSA for facilitators (Regional level) | 14 | 1 | 1 | 325 | 4550 |  |  |
|  |  | Fuel for RHPO | 7 | 1 | 50 | 55 | 19,250 |  |  |
|  | Produce and distribute fact sheets and jingles | Produce and distribute coloured fact sheets/leaflets and key messages | 10000 | 1 | 1 | 25 | 250,000 |  |  |
|  |  | Produce and distribute 500 posters for 7 regions | 300 | 1 | 7 | 100 | 210,000 |  |  |
|  |  | Printing and distribution of the step-by-step chart | 200 | 1 | 7 | 100 | 140,000 |  |  |
|  | Production of TV and radio spots on Ebola | Development and production of TV spots | 1 | 6 | 1 | 3000 | 18,000 |  |  |
|  |  | Airing of TV spots for 6 months | 1 | 1 | 1 | 50,000 | 50,000 |  |  |
|  |  | Development and production of radio spots | 1 | 1 | 1 | 10000 | 10000 |  |  |
|  |  | Airing of radio spots for 6 months | 1 | 1 | 1 | 30,000 | 30,000 |  |  |
|  | Send SMS text messages to mobile phone subscribers and prevention messages | Send SMS to the general public using GSM companies | 0 | 0 | 0 | 0 | 0 |  |  |
|  | Monitoring and supervision of communication activities nationwide (fuel and communication cards) | conduct monitoring and supervisory exercise in all regions | 1 | 6 | 1 | 20000 | 120000 |  |  |
|  |  | Fuel/Cash power support to community radio stations | 1 | 1 | 9 | 5000 | 45000 |  |  |
|  |  | Sub total: | 2,544,950 |  |  |