Government of The Gambia

2019 Annual Work Plan

NAME OF PROGRAMME / PROJECT:  Participatory Community-level Assessment and Feasibility Study for a PUDC model in the Gambia

| UNDAF OUTCOMES: | By 2021, accelerate inclusive and sustainable economic growth to reduce poverty and inequality for the vulnerable groups |
| --- | --- |
| EXPECTED CP OUTCOME: |  |
| UNDAF ACTION PLAN OUTPUT | Capacity of national and subnational-level institutions strengthened to deliver improved basic services, formulate pro-poor and gender-sensitive strategies and plans. |
| EXPECTED PROGRAMME OUTPUTS: |  |
| IMPLEMENTING PARTNER: | Ministry of Finance and Economic Affairs GoTG , Office of the President and UNDP |
| RESPONSIBLE PARTIES: |  |

_________________________________			__________________________

Name

Title								Date

Agreed by (Government):

________________________________				__________________________

Nessie Golokai Gould						Date

Resident Representative a.i.

Agreed by (UNDP)

Annual Work Plan - Participatory Community-level Assessment and Feasibility Study for a PUDC model in the Gambia

Year: 2019

| Related CP outcome: CP Output: |
| --- |
| EXPECTED OUTPUTS And baseline, associated indicators and annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Cash Transfer Modality | Budget Description | Amount |
| Output 1.1: Develop a PUDC through wide participatory processes Indicator 1.1: Inter-grated local livelihoods and employment creation prodoc designed and validated on the feasibility study Baseline: Zero draft Target: Programme validated and approved, Source of Data: NDP, CCA Timeline for target: June 2019 | Activity Result 1.1: Capacity of national and subnational-level institutions strengthened to formulate an emergency Community Development Programme (PUDC) that will deliver improved basic services, formulate pro-poor -sensitive strategies and plans to accelerate economic growth and bridge the inequality gap. |
|  | Action 1.1.1: Organize high-level study -tour to the Republic of Senegal for best practice learning | X |  |  |  | OP, MOFEA, UNDP | UNDP/TRAC 2 | NIM-RSS |  | 35,000 |
|  | Action 1.1.2: Recruit Technical Assistant who provide guidance to the process | X | X |  |  | UNDP | UNDP/TRAC 2 | NIM-RSS |  | 45,000 |
|  | Action 1.1.3: Undertake participatory level community assessment and programme feasibility, targeting study and validate the report | X | X |  |  | OP, MOFEA, UNDP | UNDP/TRAC 2 | NIM-RSS |  | 100,000 |
|  | Action 1..1.4 Using already developed ERM framework for NDP prepare guidance note on governance and risk management mechanisms for government financing | X | X |  |  | OP, MOFEA, UNDP | UNDP/TRAC 2 |  |  | 23, 277 |
|  | Action 1.1.5 Organize high level workshop for political and sectoral buy-in into the PUDC model |  | X |  |  | OP, MOFEA, UNDP | UNDP/TRAC 2 | NIM-RSS |  | 10,000 |
|  | Total-Output One | 213, 277 |
| Output 2: Finalized PUDC document use to create awareness for acceptance and fund raising to commence implementation Indicator 1.1: PUDC donors identified and partnership engagement modalities developed Baseline: None Target: Mapping completed, investment projects identified Source of data: NDP, CCA Time-line for Target: June to December 2019 | Activity Result 2.1: Identify IFI /funding partners and raise funding to commence process of initial set up of PUDC |
|  | Action 2.1.1 Identify potential partners and travel to create awareness and raise funding |  |  | X | X | OP, MOFEA, UNDP | UNDP/TRAC 2 | NIM-RSS |  | 30,000 |
|  | Action 2.1.2: Establish initial setup of PUDC |  |  |  | X | OP | UNDP/TRAC 2 | NIM-RSS |  | 30,000 |
|  | Total Output 2 | 60,000 |
| Output 3: Project Management, Partnerships, communications and monitoring Indicator 1.1: Baseline: Target: | Activity Result 3.1: Programme Communications and Partnership |
|  | Activity Result 3.2: Project management |
|  | Action 3.2.1: UNDP Project Staff (Direct Project Cost) |  |  |  |  | UNDP | UNDP | Agency | Staff & Misc costs 74500 61300 | 30,000 |
|  | Total Output 3 |  |
| PROJECT TOTAL |  |  |  |  |  |  |  | 303,277 |

IMPLEMENTATION ARRANGEMENTS

The program will be implemented under the national implementation modality. The Ministry of Finance and Economic Affairs will assume direct responsibility for the implementation, under the Division of Development Planning (DDP) will manage and co-ordinate the activities of this program. Supported by the Technical Advisor, the Director, Plan Coordination, as focal points will report to MFDP and UNDP on the production of outputs, achievement of objectives and the use of resources provided by UNDP. Accordingly, the MFDP will follow national systems and procedures and in reference to the national implementation guidelines on accounting, financial reporting and auditing shall be responsible for maintaining records on all implementation actions, including financial records to the extent possible that they do not contravene UNDP financial rules and regulations.

UNDP will support the implementation of this program, particularly in the - Participatory Community-level Assessment and Feasibility Study for a PUDC model in the Gambia. It will provide support services in the recruitment of staff and in the training and monitoring. In line with UNDP’s Executive Board decision 98/2 “all costs associated with the delivery of other resources funded program at country level are to be fully covered through cost recovery mechanisms”. In this regards, General Management Service fee of approximately 8% if applicable will be charged on non-core resources mobilized in the implementation of this program and Direct project Costs (DPCs) on UNDP Implementation Support Services.

A Project Board comprising Secretary General, Permanent Secretaries of -MOFEA, Local government, Works & Infrastructure, Director General PAU, Director of Development Planning, UNDP RR . Other stakeholders may be added as the project evolves.

Executive – the Office of the Secretary General as Chair of the Program Board and UNDP Country Director as co-chair will be responsible for the ensuring that the program is delivering value for time and resources; the Executive chairs the Project Board meetings.

Program Manager – to be based at Office of the President will plan and oversee the program’s implementation, ensuring overall guidance, quality assurance and will ensure compliance with UNDP rules and procedures; the NPM will ensure that the program realizes the results described in the AWP under NIM modality; furthermore, the NPM will work closely with the Program support team, helping to define responsibilities of the assigned Government project personnel and other specialist program teams, ensuring progress reporting to the program board.

Program support – this will be the Project Team based at Office of the President and supported by UNDP project team to:- coordinate the development of the annual workplan, procurement and M&E plans; setting up and maintaining project documentation; updating plans and assessing impact of changes; defining and maintaining project management standards, taking minutes of meeting and compilation of project reports in consultation and inputs from the technical team comprising of implementing Responsible Parties and supported by the program team.

Senior Supplier – this role, to be played by the Deputy Resident Representative at UNDP will ensure the design, development and procuring the project’s products, ensuring compliance to applicable procurement rules and procedures;

Project Assurance - This will be the Programme Specialist Poverty and Inclusive Growth, working with project management unit Team; will ensure adherence to quality systems; ensure UNDP reporting compliance, assesses all aspects of the project’s performance and products, working on behalf of the project board and keeping it fully informed.

Implementing Agency Capacity Assessment

The implementing Partner (IP) of the project, is MOFEA Micro assessments conducted in 2017 ranked low Risk rating. Direct Cash Transfer (DCT) applies.

Responsible Parties (RPs), List RP and their risk rating and applicable cash transfer modality.

Financial Disbursement and Reporting

Financial Accountability: The Implementing Partner shall be responsible for ensuring that the allocated resources for the Annual Work Plan are utilized effectively in funding the envisaged activities. It shall have a tracking system that it will maintain records and controls for the purpose of ensuring the accuracy and reliability of the Annual Work Plan's financial information. The tracking system in place shall ensure that envisaged disbursements are within the approved budgets. The tracking system shall track the disbursements and the commitments besides capturing expenditure records through direct payments and support services made by UNDP on behalf of the Implementing Partner.

Cash Transfer (NEX Advance) modality: Direct Cash Transfer (NEX Advances) will be applied according to the AWP activities, from which funds XXX will incur expenditures. At the end of each quarter (calendar), replenishment of NEX advances will be granted by the UNDP upon submission of the financial report of the prior quarter expenditures. The harmonized financial tool i.e. the Funding Authorization and Certificate of Expenditure (FACE) will be used as the financial reporting and request instrument. UNDP financial rules and regulations will apply on NEX Advance management, i.e.  80% of all previous outstanding NEX Advance/s made to the MFDP under all UNDP programs/projects must be accounted for with auditable supporting documents before the next NEX Advance is made to the MFDP.

Direct payments: As agreed and reflected in the AWP, UNDP country office shall make direct payments to third parties/vendors for services procured by the Implementing Partner and Responsible Parties in accordance with the Annual Work Plan. Funds will be disbursed to vendors or third parties for obligations incurred by the XXXXX on the basis of requests signed by the designated official of the MOFEA. At the request of MOFEA, Direct payments will also be made to vendors or third parties for obligations incurred by UNDP as support services of activities agreed with MOFEA. The MOFEA or a designated official will sign the request for direct payment. For UNDP to procure the goods and services included in the AWP, MFDP will draft the technical specifications for goods and the terms of reference for the services to be procured. Documentation of payment by the Country Office must be made available to the MFDP. A register for such requests shall be maintained to facilitate follow-up.

Agency Implementation – UNDP as a Responsible Party conducts expenditure from requisition through to disbursement with no cash being transferred to the implementing partner. However, the implementing partner has full programmatic control and so full control over expenditures – refer to Letter of Agreement between UNDP and the Government of Liberia for the Provision of Support Services dated 26 April 2013.

Cost recovery: The cost of the support services provided by UNDP CO will be recovered from the program according to the Direct Project Cost (DPCs) guidelines based on the Blanket Letter of Agreement signed between the formal MPEA and UNDP on the provision of support services.

Financial Reporting: UNDP at the end of each calendar quarter will submit to the MFDP if requested a detailed expenditure report generated from UNDP Global Integrated System (Atlas) for all program transactions and supporting documents can be availed when necessary. The MFDP should verify the disbursements and revert to UNDP for any correction to be made for any erroneous transaction. On quarterly basis, UNDP will submit to the MFDP the Combined Delivery Report (CDR) for verification and signature as a true record of quarterly expenditure report.

Fiduciary Compliance: In managing the Annual Work Plan resources, the MFDP has fiduciary and compliance responsibilities to UNDP. It also has compliance responsibility for UNDP’s reporting procedures. On the other hand, UNDP CO has the overall fiduciary responsibility for UNDP funded programs and projects.

Procurement of Goods and Services: Liberia's Government established rules and procedures governing procurement may be used when Government procures, as long as it does not contravene UNDP's rules and procedures. However, UNDP must be informed of procurement processes within the MFDP and when necessary UNDP must be represented in procurement committees that are held to evaluate quotations and bid offers for technically complex or big procurements.

Ownership of equipment, supplies and other properties financed from the UNDP funding shall be considered as UNDP’s, unless title is transferred on purchase.  Matters relating to the transfer of ownership by UNDP shall be determined in accordance with the relevant policies and procedures of UNDP.

The Assurance Requirements: The UN Harmonized Approach to Cash Transfer to implementing partner’s framework which provides guidance on assurance activities will be followed to plan and implement project assurance activities.  The project shall be subject exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP. Should the biennial Audit Report of the Board of Auditors of UNDP to its governing body contain observations relevant to the project, such information shall be made available to the Donors.

The project must be audited once in its lifetime (OIL). The objective of the audit is to provide the United Nations Development Program Administrator with the assurance that United Nations Development Program resources are being managed in accordance with the financial regulations, rules, practices and procedures for the project the annual work plan activities, management and implementation arrangements, monitoring evaluation and reporting provisions and the requirements for implementation in the areas of management, administration and finance.

The United Nations Development Programme will audit the program by sub-contracting private auditors to carry out the audit exercise. The Implementing Partner and Responsible Parties will ensure that final accounts of the year under audit are submitted to United Nations Development Programme by the end of January of the following year.

Thus an audit of this project must confirm and certify that:

- Disbursements are made in accordance with the Annual Work Plan;

- Disbursements are valid and supported by adequate documentation;

- An appropriate system for internal control is maintained by the Implementing Partner and can be relied upon;

- Annual Work Plan financial reports are fair and accurately presented;

- The Annual Work Plan monitoring and evaluations reports are prepared as required;

- Annual Work Plan disbursements are duly verified by the implementing partner and

- The procurement, use control and disposal of non-expendable equipment’s are in accordance with Government or UNDP requirement.

The United Nations Development Programme takes the responsibility to audit the project. A reputable firm sub-contracted by UNDP will conduct the audit. Funds for audit expenses are budgeted within the Annual Work Plan. In the event of such an audit, the Implementing Partner will ensure that auditors are given all records and information that they will need to perform a meaning full performance audit.

It is the responsibility of the MFDP to ensure that all audit observations are attended adequately. The MFDP may include the activities of this program in the normal audit for their use. UNDP activities for procurement of goods and services shall be subjected exclusively to the internal and external auditing procedures provided for in the financial regulations, rules and directives of UNDP.

# Monitoring Framework and Evaluation

Tracking of the achievement of benchmarks/indicators for each activity will monitor the performance of the Program. Monitoring of specific Program activities will be the responsibility of the MFDP. The aim will be to provide timely information about the progress, or lack thereof, in the production of the outputs and achievement of the Program objectives. Monitoring and evaluation will be undertaken in accordance with standard UNDP policy (http://stone.undp.org/undpweb/eo/evalnet/docstore3/yellowbook/documents/full_draft.pdf).  MFDP will produce quarterly progress and financial reports according to standard UNDP procedures and format, and/or as required by the UNDP Country Office, formats refer to the National Implementation (NIM) Toolkit.

The mechanisms that will be used to monitor the Program will include:

- Quarterly progress reports, including also both technical and financial information, prepared by the Implementing Partner; the format of the report shall follow UNDP standards;

- Annual progress report, including also both technical and financial information, prepared by the Implementing Partner at the end of the year; the format of the report shall follow UNDP standards;

- Final report including also both technical and financial information, prepared by the Implementing Partner at the end of the year; the format of the report shall follow UNDP standards;

- Field visits undertaken jointly by Implementing Partner and United Nations Development Programme.

- An evaluation of the activities implemented under the program may be carried out as part of the Outcome Evaluation during the program cycle.

RISKS

Risks identified under this project include:

- A non-functioning Program Board can affect the effective implementation of AWP;

- Lack of consolidated M&E plan of all UNDP programs and earmarked resources to conduct monitoring and field visits may affect effective oversight role of MFDP as Government Coordinating Agency;

- Non submission on a timely basis of AWP progress/status reports;

Mitigating Factor(s):

- Timely establishment of Project Board members

- Develop and implement a composite monitoring and evaluation plan;

- Tying additional release of funds to the receipt of reports

LEGAL CONTEXT

The country programme document 2013 – 2017 (CPD) and respective multi-year programs shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement between the Government of Liberia and the United Nations Development Programme, signed by the parties on 27 April 1977. Revisions may be made to this project with the signature of the UNDP Resident Representative only, provided he or she is assured the other signatory of the project have no objection to the proposed changes, in the case of revisions which do not involve significant changes in the immediate objectives, output or activities of the project, but are caused by the rearrangement of inputs already agreed to or by cost increases due to inflation.

PUBLICITY AND PUBLICATIONS

Unless UNDP requests or agrees otherwise, the Implementing Partner and other collaborating parties shall take all appropriate measures to publicize the fact that the project has been funded by UNDP. Information given to the press, project beneficiaries, all related publicity materials, official notices, reports and publications, shall acknowledge that the activity was carried out with funding from the UNDP, and shall display in an acceptable way the UNDP logo. In addition, all publications must be reviewed by UNDP before publication, and shall bear the appropriate UNDP disclaimer.

‘

Annexes:

Annex 1: Project Staff

ANNEX 1: Project staff cost

|  | Name of Position | International/National | Status | Number of Months | Proforma Cost |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |
|  | Total |  |  |  | XXXX |

# Footnotes

Refer to Standard Level of Agreement (SLA) between MPEA and UNDP on provision of Support Services

# Text boxes

Brief Description

The funds will be used for a Participatory Community-level Assessment and Feasibility Study for a PUDC model in the Gambia . This will include a community engagement component and infrastructure needs assessment. The new government of the Gambia has just completed  and launched its new National Development Plan (NDP 2018-2021), the Plan rests on eight strategic priorities- Restoring good governance, human rights citizens’ empowerment; stabilizing the economy, stimulating pro-poor growth; modernizing agriculture and fisheries; investing in people through quality education and health; building infrastructure and restoring energy to accelerate growth; promoting inclusive and culture centred tourism; reaping the demographic dividend through youth empowerment and job creation and making the private sector the engine of growth, transformation and job creation. In addition to the eight priorities, there are seven crosscutting critical enablers which complement the strategic priorities of the plan. The government uses the National Development Plan, to domesticate and serve as an instrument for the realizing the Sustainable Development Goals and the First Ten Year Implementation Plan of the African Agenda 2063

The feasibility study will examine the viability of a PUDC solution in Gambia and assesses whether it is likely to become a vehicle for promoting accelerated community development in line with the pro-poor objectives of the government. Specifically, it will seek to answer:  The rationale and why a PUDC might be needed, how it fits into the government’s current national development plan and long-term vision; what resources are likely to be mobilized, from where; what level of support is needed to get it started; what are the likely benefits and outcomes for the Gambia and the communities, specifically the economic and social returns from the PUDC. It will identify potential partners and implementation modalities including targeting

Total resources required

Total allocated resources:

UNDP Regular

- Government	In Kind

In-kind Contributions		_________

Programme Period:

Key Result Area (Strategic Plan)	______________

Atlas Award ID: XXXXX Project ID XXXXX

Start date:			15th February 2019

End Date			31st December 2019

PAC Meeting Date		13/02/21

Management Arrangements		DIM

Nat. Prog. Manager

Project Board

Senior Beneficiary

Executive

– Chair

UNDP- Co-Chair

Senior Supplier

Project Assurance

UNDP Programme Specialistt -

Technical Advisor

International/as applicable

Project Organisation Structure

TEAM A

TEAM C

TEAM B