[Plus logos of other financing partners]				 draft ver 04  200215

United Nations Development Programme

Country:    THE GAMBIA

PROJECT DOCUMENT

Project Title: GAMBIA PROTECTED AREAS NETWORK AND COMMUNITY LIVELIHOODS

UNDAF Outcome: Pillar 1, Outcome 3 – Environmental sustainability and disaster risk reduction systems and services operationalized

Expected CPAP Outcome: Outcome 2 – Sustainable livelihood security enhanced for the disadvantaged groups through the promotion of income diversification opportunities and better management of environmental resources

Expected CPAP Outputs: Output 2.3 – Sustainable use of environmental resources enhanced

Implementing Partner: Office of the President

Executing Entity: Department of Parks and Wildlife Management (DPWM) of the Ministry of Environment, Climate Change, Water Resources & Wildlife (MECCWW)

Implementing Agency: United Nations Development Programme (UNDP)

Responsible Partners: Department of Parks & Wildlife Management, Department of Agriculture (Nema), National Environment Agency, Ministry of Environment, Climate Change, Water Resources & Wildlife and Ministry of Finance and Economic Affairs

Agreed by :

Date/Month/Year

Agreed by :

Date/Month/Year

Agreed by (UNDP):

Date/Month/Year

CONTENTS

Project Summary

Acronyms and Abbreviations							  4

1	SITUATION ANALYSIS							  5

1.1	Introduction 									  5

1.2	The Gambia environment							  6

1.2.1	The physical environment						  6

1.2.2	Land cover and land use						  7

1.2.3	Ecosystems and biodiversity						  8

1.2.4	The socio-economic environment					13

1.2.5	Policy and institutional context for biodiversity management	15

1.2.6	Ecosystem functions and services					20

1.3	Threats and impacts to the Gambia environment			21

1.4	The Gambia’s response – the Baseline Project				23

1.5	Remaining challenges and outstanding gaps 				26

2	STRATEGY									28

2.1	Project Rationale and policy conformity					28

2.1.1	The GEF alternative and incremental reasoning			28

2.1.2	Project sites								30

2.1.3	Stakeholder analysis							37

2.1.4	Fit with GEF Focal Area Strategy and Objectives 			39

2.1.5	Conformity with UNDP and UNDAF					40

2.2	Project Objective, Outcomes and Outputs/Activities			40

2.2.1	Project Objective and Components					40

2.2.2	Project Outcomes 							42

2.2.3	Indicators								43

2.2.4	Project Outputs and Activities						45

2.3	Assumptions and Risks							48

2.4	Cost effectiveness 								50

2.5	Expected Global, National and Local benefits				50

2.6	Gender strategy								51

2.7	Project consistency with National Priorities/Strategies 			52

2.8	Sustainability of project results						53

2.9	Environmental and social safeguards 					54

3	PROJECT RESULTS FRAMEWORK 					56

4	TOTAL BUDGET AND WORK PLAN					59

5	MANAGEMENT ARRANGEMENTS 					61

6	MONITORING FRAMEWORK AND EVALUATION				64

7	LEGAL CONTEXT 								68

ANNEXES

1	Terms of Reference for key project personnel

2	Capacity assessment scorecard

3	Letters of pledge

4	Social and Environmental Screening Procedure (SESP)

5	Tracking Tools

ACRONYMS AND ABBREVIATIONS

[needs update]

ANRWG	Agriculture and Natural Resources Working Group

BBWR		Bao Bolong Wetland Reserve

BESPOR	Basic Education Support for Poverty Reduction

CBD		Convention on Biological Diversity

DoA		Department of Agriculture

DPWM		Department of Parks and Wildlife Management

FAO		Food and Agriculture Organization

FTI		Fast Track Initiative

GDP		Gross Domestic Product

GEAP		Gambia Environment Action Plan

GEF		Global Environment Facility

GER		Gross Enrolment Ratio

LDC		Least Developed Country

LRR		Lower River Region

IUCN		International Union for the Conservation of Nature

JNP		Jokadu National Park

KWNP		Kiang West National Park

MDG		Millennium Development Goal

MoA		Ministry of Agriculture

MECCWP	Ministry of Environment, Climate Change, Water Resources and Parks

MSGBC	Mauritania-Senegal-The Gambia-Guinea Bissau-Conakry Basin

NBSAP	National Biodiversity Strategy and Action Plan

NBR		North Bank Region

NEA		National Environment Agency

NEMA		National Environment Management Act

Nema		National Agricultural Land and Water Management Development Project

NEMC		National Environment Management Council

NRM		Natural Resources Management

PAs		Protected Areas

PCR		Primary Completion Rate

SLM		Sustainable Land Management

TDS		Total Dissolved Solids

UNDP		United Nations Development Programme

URR		Upper River Region

VDC		Village Development Committee

1	SITUATION ANALYSIS

1.1	Introduction

The Government of The Gambia has sought the support of UNDP to obtain GEF funds to address two major threats, namely, deforestation driven by domestic fuel and construction needs; and, poor/unsustainable agricultural practices which are undermining ecosystem functions.

The Gambia is a small, narrow country enclosed by the Atlantic Ocean in the west and Senegal on the three remaining sides. Its land area of 10,000 km2 extends about 330 km from its eastern border to the coast and between 20 and 48 km along its north-south axis. The country’s terrain is flat, with the highest point at 53 m above sea level. The country can be divided into three major biological regions – the marine system and coastal zone on the Atlantic Ocean in the west, the east-to-west running River Gambia and related freshwater and estuarine ecosystems, and the terrestrial ecosystems in the remaining stretches of land behind the coast and to the north and south of the river.  Despite its small size, the Gambia harbours biodiversity that is globally significant as well as biodiversity and natural resources of great significance at national and local level.  In fact, the Gambia is dependent on its natural environment and ecosystem services for its quality of life and its economic viability.  The natural environment, in all its forms, is a valuable economic asset as it provides food and other necessities for Gambians.  According to the NBSAP - “The Gambia is endowed with a high diversity of plant and animal species.   The components of biodiversity embrace the wild fauna and flora and associated ecosystems as well as the domestic species, including plant varieties and land races of domestic animals that have been bred and developed for thousands of years by farmers, as well as species that are dependent on the agricultural systems developed and maintained by humankind”.  These valuable biodiversity and ecosystem services assets are at risk and in spite of the significant response by the government, the risk remains, hence the need for GEF incremental assistance to overcome the identified threats.

The resulting project will work to expand and better connect the cluster of three target PAs (Bao Bolong Wetland Reserve, Jokadu National Park, and Kiang West National Park) and put in place effective management to provide a refuge for nationally and globally relevant biodiversity and natural ecosystems; and to introduce biodiversity-friendly natural resource and land management practices in communities around the three target PAs, to begin restoring vital natural resources into productive landscapes and thereby reduce the pressures local communities exert on the PA system.

The project will focus on the communities surrounding the three PAs (i.e. in buffer zones) that exert significant pressure on the integrity of these PAs. The targeted stakeholders are primarily farmers and their households, totalling an estimated 70,000 people. Working closely with and through the MoA’s National Agricultural Land and Water Management Development Project (Nema), the project will introduce biodiversity-friendly sustainable land and natural resource management practices, to reduce the pressures (unsustainable wood/ mangrove extraction; land conversion for shifting cultivation; incidence and severity of wild and forest fires) that these communities exert on the targeted PAs; and to begin restoring vital resources into the production landscape matrix, improving natural ecosystem integrity and connectivity.

The project will promote its sustainable natural resource utilisation practices by building on work initiated through a GEF-funded PA early action grant that led to the creation of the Gambia National Protected Area Partnership and Network (GamPAN).

The project contributes directly to the GEF BD-1: Improve Sustainability of Protected Area Systems, to safeguard the most important areas and biodiversity by strengthening the management of and expanding a key subset of existing PAs in biodiversity-rich regions in the Gambia.  It also advances a number of goals of the CBD PoWPA as well as a number of CBD Aichi Targets.

1.2	The Gambia environment

1.2.1	The physical environment

The Gambia lies between 13.79o and 16.82o West longitude and entirely within 13o North latitude. With a surface area of about 11,300 km2, the country is bounded by Senegal to the North, South and East and by the Atlantic Ocean to the West.  The Gambia is thus a narrow strip of land within Senegal, widest at its westerly end towards the ocean, narrowing to about half this width at its eastern end, 480 km inland. The country is bisected by the River Gambia and Banjul is the administrative centre and capital situated on an island on the south bank at the mouth of the river.

The geology of the Gambia is relatively recent from the Tertiary and Quaternary periods. The country is generally low-lying with altitudes mostly below 60 m above sea level.  The combination of low-lying topography, poorly drained soils and abundant water provide unique and diverse habitats.

The soils are primarily influenced by the hydrology.  In the western third of the country, where the river water is salty or brackish, the soils are clay and alluvium and heavily impregnated with salt.  The only vegetation that thrives in such conditions is mangrove forest.  In the freshwater areas, the soils are often light alluvium and are more fertile and these have been used for rice production for centuries.

The Gambia climate is characterized by a long dry season from October to early June and a short rainy season from mid-June to early October.  Average annual rainfall ranges from 850 mm to 1,200 mm and average temperatures range from 18o to 33oC.  Relative humidity is around 68% along the coast and 41% inland during the dry season and generally above 70% throughout the country during the wet season.

In the dry season, north easterly winds dominate, resulting in generally cloudless skies and the presence of dust particles in the air.  During the wet season, south westerly monsoon winds, combined with heat on the continent, give rise to the formation of thundery activities, usually accompanied by strong winds, heavy rain and severe lightning.  Climate hazards include torrential rainfall, storms (wind, thunder and dust), drought, cold spells, heat waves, intra-seasonal drought and unseasonal rains.  Some of these hazards are projected to increase in frequency and intensity, and become more widespread.  In fact, climate change constitutes one of the greatest barriers to national development, poverty alleviation, and achievement of the MDGs because the productive base of the economy depends on climate-sensitive activities such as crop production, livestock rearing, fisheries, forestry (biodiversity), energy, and water resources.

The Gambia is blessed with abundant water resources which comprise seasonal rains, storage in ephemeral ponds and depressions, the River Gambia and two aquifer systems underlying the entire country.  The country is further distinguished by its location in the central part of the coastal sedimentary basin known as the Mauritania-Senegal-Gambia-Guinea-Guinea Bissau Basin which add up to make The Gambia a focal point of extensive regional surface and groundwater systems.  These water resources provide the basis for sustaining life and promoting socioeconomic development.

The River Gambia enters The Gambia at Fatoto, bisects the country into two narrow strips of land, which vary in width from 48 km at the Atlantic Coast, to 24 km in the eastern region, and continues down to the Atlantic Ocean.  Major tributaries include the Sandougou, Nianija, Sofaniama, Bao and Bintang bolongs.  The estuary is fully mixed with no evidence of stratification.  There is, however, a moving interface separating the saline/brackish water from the freshwater mass along the river.  As a result of seasonal low flows, the interface can shift from a maximum penetration of 250 km upriver in the dry season to less than 100 km upriver in the rainy season.  For agricultural purposes, points along the river with a salt concentration of 1ppt demarcate the salt water / freshwater interface, also referred to as the salt front, or the saline limit.

River ecology is divided into two different zones, estuarine and freshwater, which in turn largely determine the riparian vegetation pattern.  In the lower estuary, mangroves dominate the riverside, with extensive reed belts in the in-between zone, while where the water is fresh, the banks are lined with gallery forest.

Groundwater resources are stored in the phreatic aquifer, and the semi-confined aquifer, which are both of pliocene age.  The Shallow Sandstone Aquifer is estimated to hold 125 million m3 of good quality water.  The sandstone aquifer is estimated to hold reserves of good quality water in the order of 80,000 m3.  Recharge of the aquifers is mainly by infiltration from rainfall and from lateral flow from Senegal.  Groundwater in The Gambia tends to be slightly acidic with pH values mostly ranging from 5.0 to 6.5.

In 2007, The Gambia reached the MDGs target with up to 85.2% of the population having access to safe sources of drinking water.  However, demand for water is expected to exceed the available recharge in the shallow aquifer by 2020.

1.2.2	Land cover and land use

The country is divided into four main agro-ecological zones – the Sudano-Sahelian zone, with its characteristic savannah woodlands and which covers 8,035.31 km², or about 75% of the total land area; the Sudanian transitional woodlands which cover 2,070.37 km2; the Guinean woodlands which cover 506.92 km2, and the Sahelian open savannah which covers 70.4 km2.  Land use changes during the past decades in The Gambia can be summarised as follows -

- Savannah: the total forested lands have increased due to a reversion of former agricultural land (mainly fallow land) into secondary tree and shrub savannah and the increased community participation in forest management.

- Woodlands: closed and open woodland has reduced by over 3.1% per year due to forest degradation and conversion into agricultural land.

- Mangroves: the mangroves have suffered a rampant die-back since the beginning of the 1970 reducing the total area by more than 10%. This is mainly due to the reduced flushing effect leading to hypersalinity and fungal infections.

- Fallow areas: the fallow areas have decreased by almost 4.4% due to conversion into tree and shrub savannah, agriculture with no trees or, to a lesser extent, into agriculture with trees.

- Agriculture with trees: the class remained relatively unchanged although a proportion was converted into agriculture with no trees and almost the same proportion was added from fallow areas and woodland.

- Agriculture with no trees: the class increased by about 1.3%.

- Others: the western parts of the country have the highest percentage of land classified ‘others’ with increasing tendency, whereas up-river this category decreases due to migration patterns both internal and external.

Thus, while the area under trees and shrub savannah increased by 7.1% between 1980 and 1993, the area under savannah woodland and fallow decreased by 2.9% and 4.45% respectively, over the same period.  Overall, woodland cover in The Gambia progressively decreased to 57% since 1968. The annual rate of deforestation was estimated to be about 7%, however, this has been re-estimated to be about 5%.

Like the rest of the Sahelian countries, The Gambia’s vegetation is dominated by savannah woodland.  The Guinea Savannah, characterized by broad-leafed trees, is dominant in the west of the country and it then thins into the Sudan Savannah, characterized by shrubs and grasslands, and moving to the east of the country.  Gallery forests and mangroves dominate the coastline vegetation, with the latter extending inland to the saline limit of the estuary.

Figure X.	Land use / land cover of the Gambia

More than 40% of the country’s total land area is under forest, which can be classified further into open and closed woodlands, with closed and open woodland accounting for not more 10% and the remainder consisting of Savannah woodland.  Despite the above categories of open and closed woodlands, further distinction can be made based on composition and structure.  Sudanian woodland dominates with Guinea woodland confined primarily to the south western part of the country.  Guinea woodland now appears in small relic patches, which have considerable biodiversity value for numerous species of flora and fauna.

The topography of The Gambia, another major determinant of land use, reveals three distinct levels or zones: the river with its associated tributaries and mangrove vegetation, the extensive lowlands forming the river’s floodplain and the upland plateau, which extends into Senegal.  The patterns of land use in The Gambia, to a large extent, correspond to the vegetation zones across the country. The vegetation zones in turn are largely determined by the rainfall patterns of the different parts of The Gambia.  In general, the wetter western half of the country including the western parts of the Lower River Region, have thicker land forest covers of bigger tree species.  On the other hand, the drier hinterlands, especially the north bank of the River Gambia, receive scantier rainfall and are covered mainly with shrubs and Savannah grasses.  In the landuse category, agriculture covers about one-third of all Gambian land.

1.2.3	Ecosystems and biodiversity

Despite its small size, The Gambia is endowed with rich and varied ecological systems – closed and open woodlands, trees and shrub savannah, wetland ecosystems, grassland savannah, offshore islands, marine and coastal ecosystems and agricultural ecosystems and as recently as three decades ago the country was covered by dense forest, estimated at 47% of the total land area of the country.  The forest was diverse and rich in wildlife, providing habitats for a variety of animals including large mammals.  This project is focussed on ecosystems on either side of the River Gambia, inland from the coastal and estuarine zones but still under some tidal influence.  The key ecosystems of interest are wetlands and forests and, to a lesser extent, grasslands.

Wetland ecosystems

Wetlands in The Gambia are temporal or permanent water-logged areas covering an estimated 20% of the country’s total land area.  They include 6.4% of Mangrove forest, 7.8% of uncultivated swamps, and 3.2% of cultivated swamps (NBSAP,1999).  Wetlands are used for agriculture (rice & horticulture) and grazing areas, but are also unique habitat to various specialized wildlife, fish and plants.  The most important specialized plants are the six mangrove species – Rhizophora mangle, Rhizophora racemosa, Rhizophora harisonii, Avicenia africana, Laguncularia racemosa and Conocarpus erectus.  Wetlands remain the sites where most wildlife species such as the hyena, pigs, leopards, etc, seek refuge.  The Bao Bolong wetlands in the North Bank Region have been designated as the first Ramsar site in the country and contain rare species like Panthera pardus , and Hippotragus equines.  The degradation of wetlands leads to the extinction of many wildlife species, the abandonment of potential rice growing zones, loss of habitats and biodiversity and serious mangrove dieback.  The most devastating pressure on the wetlands of the Gambia is the construction of anti-salt dams and dykes which lead to salinization, acidification and mangrove dieback.

Forests and vegetation

The Gambia is a flat land and the country is divided into four main agro-ecological zones viz. Sahelian (70.4 km2), Sudano-sahelian (8,035.31 km2) Sudanian (2,070.37 km2) and Guinean (506.92 km2) zones with four corresponding vegetation types: open savannah, savannah woodlands, savannah woodlands/woodlands transitional and woodlands. The Sudano-sahelian zone with its characteristic savannah woodlands constitutes about 75% of the total land area. Like the rest of the Sahelian countries, The Gambia’s vegetation is dominated by savannah woodland. The Guinea Savannah, characterized by broadleaf trees, is dominant in the west of the country. The Guinea Savannah thins into the Sudan Savannah, characterized by shrubs and grasslands, and moving to the east of the country.  Gallery forests and mangroves dominate the coastal vegetation, with the latter extending inland to the saline limit of the estuary.

The terrestrial vegetation consists of closed woodlands, open woodlands, gallery forests, and tree and shrub savannahs, belonging to two major biomes/ecoregions: the relatively moist Guinean Savannah (Guinean Forest-Savannah Mosaic Ecoregion; approximately in the western third of the country) and the drier Sudanian-Savannah (West Sudanian-Savannah Ecoregion; approximately in the eastern two-thirds of the country).

More than 1,000 plant species (of which 124 are trees) have been recorded from the Gambia including several globally threatened and near-threatened taxa.  These include the Dry Zone Mahogany Khaya senegalensis and the Muninga Pterocarpus erinaceus.  However, the original thick forests and rich ecosystems of The Gambia have almost disappeared as a result of forest exploitation and biodiversity loss is significant (see section 1.3).

During the long Gambian dry season, bushfires are a common feature of the rural landscape and more than 70% of the country’s forests and grasslands suffer through such bushfires.  The Lower River Region has the highest incidence of fires while the Central River Region and the West Coast Region have a lower incidence probably as a positive result of community participation.  One of the results of constant fires in forest ecosystems is a change in tree species composition to assemblages which are more fire tolerant.  This change in tree species is changing the habitat and driving dependent wild animals almost to extinction.

Table X.	Changes in forest cover between 1946 and 2015

|  | 1946 | 1968 | 1980 | 1993 | 1998 | Est. 2005 | Projected 2015 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Closed woodland (%) | 60.1 | 8.0 | 1.3 | 1.1 | 0.7 | 1.5 | 2.8 |
| Open woodland (%) | 13.3 | 17.6 | 10.7 | 7.8 | 6.2 | 12.0 | 12.2 |
| Savannah (%) | 7.8 | 31.7 | 24.8 | 31.8 | 34.6 | 31.5 | 25.0 |
| Total forest cover (%) | 81.2 | 57.3 | 36.8 | 40.7 | 41.5 | 45.0 | 40.0 |
| Population density (persons per km2) | 25.0 | 35.0 | 57.0 | 91.0 | 108.0 | 132.0 | 225.0 |

The table above indicates that deforestation after 1946 showed a peak in the later 1990s.  The standing volume in open woodland was reduced and the closed woodland began to disappear.  Less dramatic changes took place in the tree and shrub savannah where the forest cover of 1998 is almost similar to that in 1993 and is even expected to increase as from the year 2000.  According to the National Forest Assessment (NFA), area comparisons between 1981/82 and 1997/98 inventories and the NFA 2009/10 illustrate that the 1981/82 indicated 505,300 ha total forest area, or 44% of the total area of Gambia (1,130,000 ha); whereas the NFA 2009-2010, adjusted to include the same classes, indicates roughly that forest cover is 423,000 ha, or 37% of the total area of The Gambia.  This means that since 1983, 7% of forest cover has been lost.  One of the most significant losses (accounting for 73% of the overall forest loss) has occurred in mangroves, which were previously estimated to be approximately 67,000 ha and are now estimated to be 35,700 ha – a loss of roughly 47% of their previous cover.  This translates to 1,080 ha of mangroves lost each year, an alarming rate of decline over the last 30 years. These results therefore indicate that there is a net decrease of 97,000 ha of forest and other wooded land from 1997/98 to 2009/10 with the species composition being narrowed even further.  In spite of some uncertainty regarding data accuracy, the table shows a process of continuing forest degradation and biodiversity drain that started in the early 1950s.

One other significant cause of forest loss and degradation is land conversion – shifting cultivation, clearance for agriculture due to high population pressure, institutional deforestation as a result of exploitative policies, bushfires, and illegal exploitation.  In the 1970s/80s, large areas were cleared for groundnut cultivation particularly in the North Bank Region and specifically in the Niumis, Baddibus and Fulladu districts in the Central River Region.  The forest vegetation of The Gambia at that time was rich in wildlife, as it constituted the habitat for a variety of large mammals which nowadays are rare or locally extinct.  The forest cover which encompassed these wildlife habitats has been decimated with most of the big trees logged and the coastal gallery forest has disappeared.

Rangelands and grasslands

Livestock rearing in The Gambia is on an extensive free-range system in open grasslands and in rangelands. Due to the high stocking density and the incidence of annual bushfires, which consume most of the feed resources, there is always a scarcity of animal feed during the dry months of the year.  The convergence and concentration of livestock in and around isolated pockets of remaining grazing areas after wild fires lead to overgrazing and eventually soil erosion.

Degradation and depletion of rangeland resources threatens the growth of the livestock sub-sector and exacerbates degradation of the natural resource base.  Rangeland occupies 40% or 400,000 ha of the country’s total area, of which about 60% or 240,000 ha is used for pasture practicing transhumance.  Rangeland resources are often characterized by poor drainage, rocky topography and low soil fertility.  While transhumance of livestock (particularly cattle) is practiced in order to increase access to pasture and water especially during the dry season, it also exposes livestock to increased incidence of disease.  There is a high potential for improving rangeland resource management, as well as for improving production of feed resources through animal feed gardening, production of forage crops and utilization and preservation of crop residues.

Species and biological diversity

Currently, a total of 3,335 species have been recorded in The Gambia as listed in the table below.  This is quite a small number in this part of the tropics, where one would expect to find hundreds of thousands of floral and faunal species.

Table X.	Gambian species according to taxonomic group (from NBSAP, op.cit.)

| TAXONOMIC GROUPS | SPECIES RECORDED IN THE GAMBIA |
| --- | --- |
| Plasmodium | 1 |
| Omycedes | 4 |
| Arachnids | 7 |
| Insects | 784 |
| Crustaceans | 6 |
| Molluscs | 10 |
| Echinoderms | 1 |
| Fishes | 627 |
| Amphibians | 33 |
| Reptiles | 74 |
| Mammals | 125 |
| Birds | 566 |
| Fungi | 78 |
| Ferns | 12 |
| Cycads | 1 |
| Conifers | 1 |
| Flowering plants | 1,005 |
| Total | 3,335 |

In terms of animal species, 125 mammals, 488 birds, 74 reptiles, 33 amphibians, 627 fishes, 78 dragonflies and 173 butterflies have been recorded. Of the known bird species, 13 are near-threatened and 10 globally threatened.  Some 25% of Gambian bird species are Palaearctic migrants, with Gambia’s wetlands being an important stepping stone of the East Atlantic Flyway and wintering ground.  Most large game animals have long been hunted to local extinction and these include elephants, lions, and even common species such as Buffon’s Kob Kobus kob and Red River Hog Potamochoe rusporcus.  However, a number of species of global significance do remain and these include Leopard Panthera pardus, Red Colobus Procolobus badius, Guinea Baboon Papio papio and a population of reintroduced Chimpanzee Pan troglodytes.  Some globally significant species such as the Atlantic Humpback Dolphin Sousa teuszii and the African Manatee Trichechus senegalensis are dependent on the River Gambia and its associated mangrove wetlands.  The same mangrove environment, with its tidal influence, serves as an important spawning and nursery ground for more than 114 species of fish.

Threatened, endangered and other species at risk

The status of many species has been discussed above.  The considerable decline in large mammal species numbers, has been discussed and it was noted that 13 species of mammals had become locally extinct in recent times.  It is to be noted that a similar number are considered to be threatened with extinction.  However, there are some significant differences between species.  For example, while a negative trend has been noted for porcupines, Guinea fowls, bush bucks and antelopes, some of these trends have slowed recently and a positive trend can be observed for monkeys, baboons, grass cutters, warthogs, bush fowls and hyenas.

A few species like the Roan antelope (Hippotragus equinus) and Campbells Mona monkey (Cercopithecus mona campbelli), Wild dogs (Lycaon pictus) and Lion (Panthera leo) do not have a resident population in The Gambia, but they migrate seasonally from neighbouring countries.  Other large mammals like the hippopotamus (Hippopotamus amphibius), Sitatunga (Taegelaphus spekei) and West African manatee (Trichechus senegalensis), are still present but in small populations and threatened with extinction. The Leopard (Panthera pardus) is locally extinct or extremely rare and it is unlikely that breeding occurs in The Gambia.  The West African manatee (Trichechus senegalensis) and the Red Colobus Monkey (Colobus badices) are endangered in The Gambia and recognized as such internationally.

Table X.	Status of Gambia’s large mammals and primates

| Scientific Name | Common Name | Status |
| --- | --- | --- |
| Phacocherus aethiopicus | Warthog | Common |
| Potamocherus porcus | Red-river | Extinct |
| Hippopotamus amphibious | Hippopotamus | Localized |
| Giraffa Camelopardalis | Giraffe | Extinct |
| Ourebia ourebi | Oribi | Rare |
| Tragelaphus scriptus | Bushbuck | Common |
| Tragelaphus spekii | Sitatunga | Rare |
| Hippotragus equines | Roan | Rare vagrant |
| Kobus ellipsiprymnus | Waterbuck | Rare (vagrant) |
| Kobus kob | Kob | Extinct |
| Damiliscus lunatusa | Wester Korrigum | Rare |
| Tragelapus oryx derbianus | Derby eland | Extinct |
| Syncerus caffer | Buffalo | Extinct |
| Loxodonta Africana | Elephant | Extinct |
| Trichechus senegalensis | Manatee | Common |
| Lycanon pictus | Wild dog | Extinct |
| Aonyx capensis | Cape clawless otter | Rare |
| Crocuta crocuata | Spotted hyaena | Common |
| Hyaena hyaena | Striped hyaena | Extinct |
| Panthera leo | Lion | Extinct |
| Panthera pardus | Leopard | Rare |
| Leptailurus seval | Serval | Rare |
| Caracal caracal | Caracal | Rare |
| Profelis aurata | Golden cat | Rare |
| Gazelles thomsonii | Thomson gazelles | Extinct |
| Equus grevyi | Zebra | Extinct |
| Damaliscus lunatus | Topi | Rare (Vagrant) |
| Damaliscus corrigum | Hartebeest | Extinct |
| Papio papio | Baboons | Locally Common |
| Cercopithecus aethiops | Calithrax | Locally Common |
| Colobus babius | Red colobus | Locally Common |
| Cercopithecus mitis | Blue monkey | Rare |
| Galo senegalensis | Bush baby | Common |
| Erthrocebus patas | Red patas | Locally common |
| Pan troglodytes | Chimpanzee | Extinct |

Among internationally threatened species identified by IUCN as keystone/flagship species, are some Gambian fauna.  For example the Red Colobus (Piliocolobus badius teminckii) can be considered as a keystone species in remnant gallery and riverine forest patches.  In addition, the Nile crocodile (Crocodylus niloticus) can also be considered as a keystone species in fresh or temporary fresh water isolated areas.  The spotted hyena (Crocuta crocuta) can function as a keystone species on land almost everywhere except directly along the coastal fringe.  Among the avifauna, the osprey (Pandion haliaetus) can serve as a suitable flagship species for Palearctic migrants, and the Fin Foot (Podica senegalensis), Pels fishing owl (Scotopelia pelii) and the Spur-winged goose (Plectropterus gambianus) are other suitable flagship species.

1.2.4	The socio-economic environment

The Gambia gained independence on 18 February 1965 and attained republican status in April, 1970. There are three arms of Government: the Executive, the Judiciary and the Legislature, headed by a President who, like the National Assembly members, is elected every five years.  The Gambia is divided into Eight Local Administrative Regions: Western Coast Region (headquarters in Brikama), Lower River Region (headquarters in Mansakonko), North Bank Region (headquarters in Kerewan), Central River Region South  (headquarters in Janjangbureh), Central River Region North (headquarters in Kuntaur)  and Upper River Region (headquarters in Basse).  In addition there are two urban local government authorities (Banjul and Kanifing Municipality).  For local level administrative purposes the country is further divided into 42 districts.

Demography

The population of The Gambia is 1.88 million. At the last census in 2013 it was just over 1.36 million growing at 2.8% per annum.  Between the 2003 and 2013 censuses the population grew at a rate of 3.33% as highlighted in Table X below.  With this growth rate, the population is expected to double in 21 years.  Given the small size of the country, The Gambia is one of the most densely populated countries in Sub-Saharan Africa, with an average population density of 176.1 per km2 in 2013.  However, population density varies in different parts of the country ranging from a low of 50.9 per km2 in the Lower River Region to 5057.5 per km2 in the Kanifing area of Greater Banjul.  In recent years high internal migration into Western Region and Greater Banjul has increased the uneven distribution of the population within the country.  This is evidenced by the fact that while the population sex ratio is 50.5 female to 49.5 males for the country, there are more males in Banjul (54.2), Kanifing (50.3) and Brikama (50.2).

Table X.  Population growth in The Gambia

| Year | Total Population | Male | Female | Growth Rate (per annum) |
| --- | --- | --- | --- | --- |
| 1901 | 90,404 | na | na |  |
| 1911 | 146,101 | 73,793 | 72,309 | 4.9 |
| 1921 | 210,611 | 111,020 | 99,591 | 3.7 |
| 1931 | 199,520 | 104,894 | 94,626 | -0.5 |
| 1951 | 279,686 | na | na | 1.7 |
| 1963 | 315,486 | 160,849 | 154,637 | 1.0 |
| 1973 | 493,499 | 250,386 | 243,113 | 4.6 |
| 1983 | 687,817 | 342,134 | 345,683 | 3.4 |
| 1993 | 1,038,145 | 519,950 | 518,195 | 4.2 |
| 2003 | 1,360,681 | 670,841 | 689,840 | 2.8 |
| 2013 | 1,882,450 | 931,199 | 951,131 | 3.33 |

The population of The Gambia is made up of several ethnic groups. The largest of these are the Mandinka, who make up 33% of the total population, followed by the Fula (17%), Wolof (13%), Jola, Serahuli and Serere.  The Gambia is predominantly Muslim, but there is a significant Christian community and indigenous beliefs are also practised.

The Gambia is one of the least developed countries ranking 172th out of 187 countries for 2013 according to the Human Development Index. Poverty still remains a major challenge with nearly half of the population living on less than US$1.25 per day. The Gambia, like many Least Developed Countries (LDCs), continues to face the difficult challenge of financing its development priorities without exploitable natural resources except for the forestry, fishing and biodiversity sectors.

The Gambia has made significant strides in improving access to basic and secondary education through increasing the enrolment rate of pupils and addressing gender equality, with gender disparities eliminated in the early grades.  Over 200 new schools have been built around the country over the past 10 years.

Health care delivery in The Gambia is inhibited by a number of challenges comprising inadequacy of facilities and services at the tertiary level, against a background of severe human resource shortages and lack of essential drug supplies.  These, coupled with budgetary constraints and high levels of poverty, result in major bottlenecks in the health sector management.

Agriculture and natural resources in the economy

The Gambian economy is predominantly agrarian with agriculture accounting for nearly 30% of GDP and providing direct employment for about 63% of the country’s population, primarily through smallholder subsistence agriculture.  Agriculture is the main source of income for about 72% of the extremely poor rural households.  However, agricultural production is highly seasonal and rain-fed.  Rainfall in The Gambia is erratic and lasts for only three months.  Although endowed with adequate surface and underground water, the percentage of arable land under irrigation has been estimated at between 3% and 6%.

Agriculture is largely dependent on climate sensitive resources and activities such as crop and livestock production, fisheries, energy and water resources.  Domestic crop production provides only 50% of the country’s annual cereal needs and the remainder, rice in particular, is provided through commercial imports.  Agricultural production and productivity is generally low and this is attributed to the rapidly declining soil fertility, poor environmental conditions and the lack of appropriate technologies especially for women.  Deforestation, biodiversity and habitat loss, are exacerbated by climate change and when coupled with low investment in agriculture, compound the numerous constraints faced by farmers.  Consequently, the  food produced lasts not more than six months for most smallholder farmers, leaving them in a state of food insecurity for the remainder of the year.  All these factors pose serious challenges to the attainment of sustainable agriculture in The Gambia.

The Agriculture and Natural Resources sector employs 75% of the population and contributes about 30% to the GDP.  However, the productivity of the sector is not fully utilized and is occasioned by continuous depletion of the natural resource base due largely to human activities.  Access and ownership of land especially by women are faced with key challenges.  Furthermore the unclear and sometimes conflicting tenure systems and frameworks hinder women from investing in land for the future. The farming system remains largely conventional and based on rain-fed subsistence production with high reliance on external inputs thereby compromising the resilience capabilities of the population.  Low levels of knowledge, poor technology used (labour and time saving technologies), poor incentives and limited public investment in the sector, hinder youth participation and engagement in the sector.

Local government

Rural administration of the country is under the jurisdiction of the Ministry of Local Administration, Traditional Rulers and Lands, which supervises Governors at the Regional Headquarters, Head Chiefs (Seyfolu) at the District Headquarters, and Village Heads (Alkalolu) at the Village level.

There are three types of authorities within the Local Government System - Banjul City Council, Kanifing Municipal Urban-District Council, and six Area Councils, one for each Region.

A Council is composed of a majority of elected Councillors together with traditional and nominated members.  The Regional Governor is the Council Chairman.  Administrative responsibility for running the Council rests with the Town Clerk for Banjul City and Kanifing Municipality, and with a Local Government Officer for the Regional Councils.

1.2.5	Policy and institutional context for biodiversity management

The Gambia is adequately supplied with policies, legislation and regulations for the management of natural resources.  In general, these align well with national strategic frameworks including The Gambia Incorporated Vision 2020, the Poverty Reduction Strategy Paper, the Program for Accelerated Growth and Employment (PAGE 2012-2015) and other national and various donors’ strategic frameworks.

Specific policies and legislation

The Gambia Environmental Act and Action Plan (GEAP-II, 2009-2015) serves as the national umbrella environmental framework, and calls for “the protection of existing forest and vegetative cover… [and the] conservation of coastal wetlands”.  Another important strategic document is the Agricultural and Natural Resources Policy (ANRP, 2009-2015) which lists the “sustainable and effective management of natural resources” among its four strategic objectives and has led to the strengthening of the ANRWG at NEA.  Likewise, the National Action Programme (NAP) to Combat Desertification in The Gambia (2000) is a comprehensive and integrated framework for addressing the physical, biological and socio-economic aspects of desertification, land degradation and drought.  The National Climate Change Adaptation Plan of Action (NAPA, 2007) recognises the need to promote and strengthen integrated management of the coastal and terrestrial zones and to preserve biological diversity and ecological assets.  The Gambia Biodiversity Policy 2003 and the National Biodiversity Strategy and Action Plan (NBSAP, 1999) seek to “discourage uncontrolled extension of agricultural land into …virgin forests, wetlands, marginal areas and other environmentally sensitive areas” and “develop sound grazing management system”.

The ANR Sector Policy Framework (2009-2015) gives the sector vision as: “a sharpened focus on transformation of the sector from a traditional low output, subsistence economy with centralized structures, to a modern, market led sector with efficient value chains, diversified production base and effective decentralized structures and sustainable effective management of the natural resource base of the sector”.   While the devolution of power to local government authorities is the subject of a policy enacted by the Local Government Act (2002), and it establishes a new decentralized local government system with more opportunity for the participation of civil society in decision-making at local level.  These decentralized structures will improve natural resources management efficiency and outputs by ensuring coordination among interventions at regional, district, ward and village levels.

Among other relevant policies is the Medium-Term Soil Fertility Policy, with objectives to intensify measures to address erosion and land degradation through community-based integrated watershed management and to develop a land tenure system which will make land more accessible to farmers particularly women.

The current Forest Policy (2006-16) envisages that 30% of the total land area should be covered by forests, and that 75% of this should be sustainably managed either by communities or the state.  The Forest Act (1998) which is under review (the 2010 draft Forest Bill is still to be approved) considers the Gambian Forest Management Concept (GFMC) as the model management concept for the sustainable management of forest reserves.  The model aims to provide a comprehensive framework for enhanced implementation of sustainable forest management through community forestry.

The latest Wildlife Policy of 2003 aims at increasing the proportion of protected areas to 10% of national land territory in recognition that biodiversity resources are an integrated live-support system for many Gambians and the resources contribute significantly to living standards.  The policy provides the vision for the sector for the next 20 years and is in conformity with the maintenance of environmental sustainability and socioeconomic transformation as targeted by the Vision 2020.

The main objectives of the Fisheries Policy (2009-2013) include an increase in fish supplies of at least 30% over present levels to meet food security needs of the country particularly the vulnerable populations; providing artisanal fisheries with appropriate advice; providing data and information on a continuous basis to improve policy, planning and investment in productivity in the sector; and providing appropriate legislation, guidelines and practices with adequate monitoring.

Key institutions

A number of institutions with responsibilities for biodiversity management exist principally under the Ministry of Environment, Climate Change, Water Resources, Wildlife and Parks; the Ministry of Fisheries; the Ministry of Agriculture; the Department of Forestry in the Office of The President and the Ministry of Regional Administration, Lands and Traditional Rulers.  Each of these institutions interacts independently with the local government administrative structures at the divisional, district and village levels.  As a means of enhancing integration of the efforts of these different sectors and to minimize conflicts of interest and duplication in resource use, the government has sought to institutionalize coordination at the policy, sectoral and operational levels.  Current institutional mechanisms for coordination are:

- the National Environmental Management Council (NEMC)

- the National Water Resource Council (NWRC)

- the Gambia Environmental Action Plan (GEAP) process and the National Environment Agency (NEA) Sectoral Working Groups

- the Divisional Coordinating Committees (DCC)

- Local Government Authorities (District Authorities)

The lead biodiversity management institutions are described briefly below.  They are then included again in Table X which lists all key stakeholders and identifies the role they will play in the project.

The Department of Parks and Wildlife Management (DPWM), of the Ministry of Environment, Climate Change, Water Resources, Wildlife and Parks (MECCWWR), has a mandate to: (1) protect and conserve The Gambia's remaining wild fauna as well as their natural environment for the present and future; (2) create educational and leisure facilities for present and future populations through prudent use of wildlife resources; (3) preserve archetypal natural examples of Gambian flora and fauna with the aim of preserving genetic diversity; (4) accumulate and dispense revenue, which has built up from the use of our wildlife resources to the Government as well as to nearby rural communities; and (5) inform the public about the value of conserving wildlife and get their acceptance of the need for wildlife conservation as a viable alternative to the use of land.

The operation and management of the sector is guided by the National Wildlife Policy of the Gambia (Ministry of Environment, Parks and Wildlife, February 2013) which also espouses the vision for the sector for the next 20 years in conformity with the maintenance of environmental sustainability and socioeconomic transformation as outlined in The Gambia’s long-term development framework – The Gambia Incorporated Vision 2020.

The Department currently has a staff complement of 170 staff, 115 of which are on its permanent pay roll.  Staff capacity includes a mere eight professionals who have attained Diploma level and two with a Masters qualification.  This is a concern.

The National Environment Agency (NEA) is responsible for the implementation of the Gambia Environment Action Plan (GEAP), the main national policy framework for the sustainable management of the country’s natural resources and the environment.  It also has a regulatory function being responsible for directly enforcing environmental legislation.  The GEAP calls for: (i) the protection of existing forest and vegetative cover; (ii) conservation of coastal wetlands; and (iii) reduction of land degradation and soil erosion in upland areas.  The GEAP aims at integrating environmental concerns into the country’s overall social and economic development strategy.  It addresses three main areas - i.e. natural resources, energy and environmental health.  It was developed and adopted in 1992/1993 in a highly participatory manner.  As part of the GEAP, an Environmental Information System Strategy was developed within the NEA as the focal point to coordinate its implementation.  This strategy has identified the need for up-to-date and reliable environmental information for decision-making and sustainable development planning across various sectors.

While NEA has an oversight mandate for the environment, institutional responsibility for efforts to conserve and manage the country’s natural resources cuts across a number of departments.

The Department of Fisheries administers the Fisheries Act which aims to provide the management of fisheries and development of the fishing industry in The Gambia.  The Fisheries Regulations Act, 1995 similarly provides supports to management of both the artisanal and industrial fisheries subsectors.  The sector plays a significant role in providing vital cheap and quality protein, about 40% of the total animal protein consumed in the country.  It is also a major source of raw fish material for fish processing establishments operating in the country.  In 2008, 190 tonnes were imported with a total CIF Value of USD23,500 while exports amounted to 2,182 tonnes with corresponding CIF value of USD1,700,000.  The sub-sector has witnessed a huge expansion in the number of fisheries economic units (FEU) operating in the coast and along the river banks and estuaries.  The number of canoes operating in the country increased from 1,299 in 1983 to 1,969 canoes in 1997.  By 2006, an estimated 86% of canoes were motorized.  Demersal fish species are experiencing increased fishing pressure while the abundant pelagic resources are grossly under-exploited.  Aquaculture and industrial production remain largely under-developed. The Department currently has a staff complement of 90 including five professionals.

The Department of Forestry, under the Office of The President has the mandate to : (1) maintain forest resources through mapping, classification and programmes to encourage the public to prevent bush fires, make multiple use of forest land, plant trees and establish private plantations; (2) bring the most promising forestland, including mangroves, under active management by applied research, developing guidelines for sustainable forest management and assisting communities in the establishment of their management structures; (3) rehabilitate forestland and establish fast growing plantations and woodlots.  The Department’s operational management has recently shifted to a more participatory and partnership resource management approaches.  In this regard it has been building alliances with related sectors, setting in motion some of the changes that are needed to meet the re-aligned programme direction.  These changes include decentralization in line with the on-going Local Government Reforms (LGR) to divisional offices, adoption of a more integrated intervention process (Community Based Forest Resource Management) and the introduction of the forest communication concept and monitoring and evaluation unit to improve the level of knowledge about development issues and activities within the organisation for an effective forest resource management.  The programme focus of the department is centred around State Plantations, Joint Forest Park Management, Forest Management & Protection, Community Forestry, Ecotourism, national tree planting & Farm Border Planting.

The Department of Agriculture (DoA) is the largest department within the Ministry of Agriculture, and the main interface with farmers.  It comprised eight service units: the Communication, Education and Extension Services (CEES), the Food Technology Services (FTS), the Agricultural Engineering Services (AGS), the Agribusiness Services (ABS), the Plant Protection Services (PPS), the Horticultural Technical Services (HTS), and the Soil and Water Management Services (see below).  There are six agricultural regions in which there is a Regional Agriculture Directorate headed by a Regional Agricultural Director who is supported by subject matter specialists in soil conservation, crop production, pests and diseases, communication, and food and nutrition.  Each of the six agricultural regions is divided into districts in which the focal point for extension work is the District Extension Centre (DEC), supervised by a District Extension Supervisor (DES).  The DES is responsible for supervising the work of the Village Extension Workers (VEWs) who operate from Village Extension Centres (VECs).  Originally, DES provided only crop extension services but in recent years this has been broadened towards the concept of multi-disciplinary extension activities covering both crops and livestock.  Two key service units: Soil and Water Management Services and Planning Services play pivotal roles in biodiversity management.

The Soil and Water Management Services (SWMS) is a specialized unit of the DoA responsible for addressing soil and water management and conservation issues, and is involved in field investigations and surveys, design and planning, and executing specific civil works under on-going projects.  The SWMS has specialised sections responsible for: (i) engineering; (ii) soil and land evaluation; (iii) agronomy; (iv) mechanical operations; (v) cartography; and (vi) monitoring and evaluation.  These sections together form the basis for a multi-disciplinary approach to soil and water conservation.  The unit operates from its main office at Yundum with outstations at Jenoi and Sapu.  During project execution it establishes and maintains temporary field stations.

The SWMS through its long-time engagement in soil conservation and water management on all forms of terrain in the country has gathered a wealth of experience enabling it to handle conventional soil and water conservation works of any magnitude.  It was the key partner in LADEP implementation, and was judged (by AfDB) to have performed very well on engineering and community participation, and satisfactorily on soils and agronomic follow-up.  The unit has collaborated with NGOs and other donor organizations like EDF, UNDP, FAO, etc, involved in land management activities for sustainable agricultural use.  Since its establishment in the late 1970s, the unit has also been involved in lowland development activities using funds from USAID and GTZ. It has likewise undertaken erosion control and gully stabilization activities in the uplands through funding from USAID, EDF, NGOs, and the Rural Finance and Community Initiative Project.

The Planning Services Unit (PSU) of the MoA provides policy advice to the Ministry and helps in identifying and preparing agricultural investment programmes and projects. It collects extensive agricultural data and its national agricultural data centre conducts national agricultural sample surveys and publishes a statistical yearbook of Gambian agriculture.  In addition, it monitors ongoing investment operations and conducts selected evaluation studies. It has four sections namely: Project Planning, Policy Formulation, National Agricultural Statistics, and Monitoring and Evaluation.

The National Agricultural Research Institute (NARI) has 12 research programmes and a network of experimental sites undertaking research activities into cereal crops, roots and tubers and agro-forestry.  It cooperates closely with other national and sub-regional projects including: International Crop Research Institute for Semi-Arid Tropics; International Institute for Tropical Agriculture; Semi-Arid Food Grain Research and Development; and Africa Rice Development Association (WARDA).

The objectives of the Department of Community Development (DCD) within the Ministry of Local Administration, Traditional Rulers and Lands, are to promote participatory community self-help in the identification, planning, implementation, evaluation and management of programmes and projects that will better enable communities to address their basic social welfare needs.  In particular DCD aims to support community development activities that contribute to livelihood diversification through income generating activities such as handicrafts, vegetable gardening and cottage industries using appropriate technologies that add value to locally available products.   DCD also assists with developing/strengthening village and community level institutions so as to better facilitate their participation in decision-making, and to give them the skills needed to plan, implement and evaluate multi-sectoral projects of particular benefit to their communities.  DCD supports the design of action-oriented proposals based on identified community needs, and then takes a proactive role in attracting government, NGO, bilateral and multi-lateral funding for such proposals.  DCD covers the whole country through a network of divisional Community Development Officers, supported by district level Community Development Assistants.

1.2.6	Ecosystem functions and services

As noted above, forests and wetlands are two predominant ecosystem types in the Gambia.  Forests are considered as one of the Gambia’s primary natural resources offering a range of functions and services often determined by the dominant tree species within the forest.  Wetlands constitute an important feature of the Gambian environment and they provide a vast array of ecosystem services, primarily food production.  The impact of forests and wetlands on biodiversity, carbon and nutrient storage, water quality and quantity, soil conservation, forage production, and in addition to their recreational importance cannot be underestimated.

According to TEEB, ecosystem services are the direct and indirect contributions of ecosystems to human well-being supporting human survival and quality of life.  Ecosystem services from the Gambian terrestrial, estuarine and coastal environment are summarized in the following Figure.

Figure XX.	Ecosystem services in the Gambia

| SUPPORTING Nutrient cycling: Natural processes, especially water, serve as agents for nutrient cycling; plants capture and store nutrients temporarily Soil formation: Ecosystem processes generate and preserve soils and renew their fertility Primary production: Forests, wetlands and mangroves serve as the basis of the food chain |
| --- |
| PROVISIONING Food: Small-scale agricultural land, forests, wetlands and estuarine areas provide food directly or indirectly by providing forage for other species which in turn serve as food for humans; insects serve as honey producers Fresh water: Water provides life support, habitat, transport system Wood and fibre: Forests (including mangroves), carefully managed for sustainability, provide wood and other traditional materials Medicine: Forests provide traditional medicinal herbs and remedies Habitat: Forests, wetlands and estuaries provide habitat for mammals, birds, insects and reptile species Biodiversity: natural ecosystems maintain the viability of gene-pools, and biological diversity; natural agents disperse seeds | REGULATING Climate regulation: Forests and other vegetation sequester CO2, moderate weather extremes and impacts, and contribute to climate stability Flood regulation: Vegetative land cover soaks up rainwater and mitigates flood events and run-off Water purification: Riparian vegetation filters nutrients and other impurities from run-off water, providing waste management and detoxification Erosion control: Forests and other vegetation bind soil and prevent erosion Pest control: Birds control insect pests; some plants inhibit plant pests; natural systems regulate disease-carrying organisms | CULTURAL Aesthetic: Forests, the coastal fringe, wetlands and other natural ecosystems provide a pleasing and appealing environment Spiritual: Natural landscapes are mystical and inspirational. Places sacred in the traditional, spiritual, religious, ritual or mythological sense Educational: Natural ecosystems serve as outdoor teaching laboratories; they provide for intellectual development Recreational and tourism: The forests and various land formations provide opportunities for swimming, hiking and other outdoor pursuits. The natural environment attracts visitors (tourists) |

1.3	Threats and impacts to the Gambia environment

The Gambia faces a number of highly inter-related challenges and pressures on its ecological resources, land and ecosystem services.  Since land and natural resources provide livelihood support for an estimated 75% of the population, pressures from a high population growth rate are expected to increase and when coupled with drought and poor agricultural practices, they constitute a serious threat to both environment and livelihoods.

Already evident is the rate of deforestation which has been estimated at 7% per year; and soil erosion (by water and wind) which is estimated at 12.5 t/ha/yr and affecting land throughout the country.  Furthermore, previously fertile land on the edge of the flood plain has been transformed into barren mudflats due to saline encroachment, evaporation and the drying of potential acid-sulphate soils.  According to the GEAP, land degradation and desertification are the leading cause of environmental degradation in The Gambia.

Over the past three decades, biological resources have been the subject of misuse and over-exploitation by people.  Recent population trends have accelerated and deepened the process of over-exploitation and consequently the degradation of natural resources in The Gambia.  Further destruction of indigenous woody tree species such as Khaya senegalensis, Pterocarpus erinaceus, Cordila africana, Prosopis africana, Terminalia macroptera, Diosphyrus mespiliformis, and Danielia oliver is taking place in many parts of The Gambia.  And, deforestation is in turn having a severe impact on large mammal species which are also subjected to heavy hunting pressure. The spread of agricultural activity and in particular the devastating cumulative effect of forest fires has resulted in the degradation of the natural vegetation and a reduction in both animal food and habitat.

Ecosystems are being degraded, and species and genetic diversity have been lost at an alarming rate due to the impact of a growing human population with its increasing demands on resources.  Many species have now become rare or locally extinct and a once biologically diverse country has in the last three decades become much less diverse in terms of species and ecosystems.  Over the period, the country has lost 13 species of mammals and an unknown number of plant species.  Human population density coupled with the overall decline in annual average rainfall of 25-30% and increasing poverty have been the main driving force for environmental and natural resource degradation and loss of biodiversity.

Deforestation is rampant throughout the country, resulting primarily from the domestic demand for fuel and timber (for housing and fencing).  Forests in the Gambia provide 85% of domestic energy needs in the form of fuel wood – with over 90% of the population dependent on biomass as fuel.  Each Gambian uses 0.6 kg of firewood per day and in urban areas the per capita consumption of charcoal is 0.09 kg per day.   The national fuelwood demand is estimated at around 242,370 tonnes annually and certain species like Pterocarpus sp. (Rosewood) and Prosophis sp. (iron wood) are preferred for fuelwood and charcoal because of their high calorific value.  The volume of fuelwood available in the country according to a study by the Energy Division in 2004 was about 88,000 m3 and 60% of the demand has to be met through importation.

The high demand for domestic energy has resulted in indiscriminate tree felling without regard to their slow replacement.  Species like Combretum and Termanalia are particularly threatened by cutting, burning, poisoning or lopping for branch wood in order to ensure a regular fuelwood supply to households and urban markets.  As the population increased, the total forest cover decreased, firstly at an accelerating rate between 1946 and 1980 and then at a more constant rate from 1980 to the present day.

Table X below provides a summary of fuelwood trends starting from 1983 and projected to 2013.  As can be seen, the standing stock, which is the forest cover, and the annual increment, are both depleting at a fast rate due to high population growth and increased demand. The seriousness of the situation is evident with the deficit steadily growing because the increment is declining.

Table X.	Fuelwood trend 1983-2013 in m3

| Description | 1983 | 1993 | 2003 | 2013 |
| --- | --- | --- | --- | --- |
| Standing stock | 16,620.0 | 11,049.5 | 7,652.2 | 4,576.4 |
| Increment | 302.0 | 272.0 | 153.0 | 95.2 |
| Consumption | 430.0 | 485.1 | 696.4 | 999.8 |
| Deficit | 128.0 | 213.1 | 543.4 | 909.6 |
| Population | 687,800 | 1,026,800 | 1,461,400 | 1,800,000 |

Illegal harvesting of thatch grasses and the cutting down of tree branches to collect wild fruit is another common and unsustainable method of natural resource utilization often perpetuated by cross-border poachers at e.g. Bao Bolong on the north bank.  Shifting cultivation and itinerant farming practices enable a sizeable population to establish ownership over every single strip of land and this leads to further fragmentation of wildlife habitats and the destruction of migratory corridors.  Illegal logging of timber and fuelwood is rampant in particular with the present economic consideration in wood re-export.  Unregulated charcoal production activities demonstrate the increased dependency on natural resources by the population for their livelihood.  Land tenure rights and the demand for land outside traditional farming areas are also steadily leading to the massive cutting down of forests and mangroves.

Hunting is an important economic and social activity in rural areas as bush meat forms an important part of the diet of the local population. However, hunting, which in most cases fails to observe breeding seasons, has had a catastrophic impact on wildlife numbers.  Coming on top of the extensive habitat loss such as through deforestation, hunting is leading to local extinction.  The hunting method, where-by a large strip of forest is set on fire and a large congregation of hunters awaits emerging wildlife which are killed indiscriminately destroyed both the habitat and the wildlife and it has now been banned by the Banjul Declaration.

Poor and unsustainable agricultural practices are also undermining ecosystem functions.  The State of The Environment Report for the Gambia (1997) revealed that the cultivable land area had extended into forest areas from 274,000 ha in 1980 to 336,200 ha in 1988.  Rice is the main crop grown, but there are also rainfed millet, maize and sorghum - all grown for subsistence.  Peanuts are also grown for cash and there is some vegetable production.  Agricultural practice includes: high-input deep tillage that leaves top-soils exposed in the dry season; shifting cultivation (slash-and-burn) regimes that require the conversion and use of large areas; and, the widespread use of fire for preparing ground in the planting season.  In fact, at least 80% of the standing biomass is consumed by fires in any given year, and up to 91% of the forest area is exposed to fire at least once every 2 years.  This kills off any regeneration, retards the growth of most tree species and transforms the tree composition from mixed species to fire tolerant species.  Moreover, the introduction (in pursuit of food self-sufficiency) of newly developed dryland NERICA rice has compounded the pressure on natural ecosystems by creating a new incentive for slash-and-burn land conversion.

Thirdly, excessive populations of free-ranging livestock (cattle, sheep, and especially goats) are leading to significant overgrazing.  These pressures are exacerbated by the prevailing poverty and food insecurity and the rapid growth (2.3%) of the country’s human population, which is amplifying demand for land and natural resources and shortening fallow periods in shifting cultivation regimes.  The loss of natural ecosystems is particularly severe on the northern side of the River Gambia (North Bank Region) where many areas are already devoid of vital natural resources such as livestock forage and firewood.  Of great concern is the projected worsening situation on the south side of the river.

Conservation in The Gambia still faces many challenges in the face of an increasing demand for environmental goods and products such as food, water, housing materials and land.  In the absence of any significant improvement in the livelihood of many rural Gambians, their continued exploitation of the natural resource base is inevitable and unsustainable and points to a grim future for biodiversity and its dependent human populations.

As a result of this widespread degradation, the country’s protected areas, which retain an important share of natural resources, are experiencing huge and increasing pressures from the local population.  There are increasing demands for wood extraction, wildlife hunting, slash-and-burn farming (with accidental wild fires) and the loss of mangroves.

The long-term solution will be to (a) establish effective PA management in the cluster of three PAs (JNP, BBWR, KWNP), for these to serve as a cornerstone for biodiversity conservation and safeguarding ecosystem services, integrity and resilience in the Gambia; and (b) in parallel, reduce the pressures by applying community-based sustainable land and natural resource management in communities adjacent to PAs.

1.4	The Gambia’s response – the Baseline Project

The Government has taken a number of steps, on its own and with assistance, to address these threats, firstly through expansion of the PA system and strengthening of management processes, and secondly through the gradual integration of sustainable land management practice with agricultural and rural development initiatives.

Nine protected areas have been legally established in the Gambia, including one community managed reserve, which together cover 64,276 ha – 6% of the national territory.  These PAs are managed by the Department of Parks and Wildlife Management (DPWM) under the Ministry of Environment, Climate Change, Water Resources, Wildlife and Parks.  The national PA system integrates the principal habitats and ecosystems found in the country, including mangrove ecosystems, gallery forests, off-shore islands, littoral forests, tidal zones, as well as open and dense savannah woodlands.  Three wetland PAs are designated under the Ramsar Convention while six PAs are recognised as Important Bird Areas.  In addition, there are 66 gazetted and demarcated national forest parks covering 51,000 ha and managed by the Department of Forestry.  A further 150,000 ha of forest reserve exist of which 18,000 ha are under community management.  The national goal is to increase the PA area to 10% by 2020 and there are also plans to declare 131,000 ha in the country’s north-west a UNESCO Man & Biosphere Reserve.

Over the five years of the project period, the Department of Parks and Wildlife Management will invest USD625,000 of national resources into PA management, research and development, environmental education and the promotion of ecotourism.  WWF Gambia will invest USD400,000 in improving the governance of marine and coastal resource management, and will continue to support capacity strengthening of DPWM and community livelihoods around selected PAs.  The National Environment Agency (NEA) and its Agricultural and Natural Resources Working Group (ANRWG) will continue to coordinate cross-sectoral integration, with an estimated baseline investment of USD100,000.

It must also be recognized that a number of regional initiatives are also working towards enhancing the effectiveness of PA management in The Gambia.  These include the Regional Marine and Coastal Conservation Programme for West Africa (PRCM), which is a joint effort by IUCN, WWF, Wetlands International and the International Foundation for the Banc d’Arguin (FIBA) in partnership with the Sub-regional Fisheries Commission (CSRP).  The PRCM is active in seven West African countries including Cape Verde, Gambia, Guinea, Guinea Bissau, Mauritania Senegal and Sierra Leone, and currently boasts a membership of more than 90 partner institutions including government departments, research centres, professional organisations, and NGOs.  The PRCM provides a focused and integrated regional dynamic for environmental governance including a broad spectrum of stakeholders from across the ecoregions.

PRCM, in partnership with the MAVA Foundation, supported Phase II of the Integrated Coastal and Marine Project (ICAM, 2009-2011), which supported oyster hunters in Tanbi Wetlands Complex and successfully implemented village banking and women’s gardening in Bao Bolong Wetland Reserve. PRCM, in partnership with FIBA, also supported park committee meetings as well as marine surveillance and patrolling within Niumi National Park, Tanbi Wetlands National Park and Tanji Bird Reserve. The Regional Network of Marine Protected Areas in West Africa (RAMPAO) supports effective management of coastal and marine PAs in PRCM countries, providing guidance, support and resources for PA management planning, PA business planning, ecological gap analyses and eco-regional planning. RAMPAO, inter alia, facilitated the preparation of a report on Sacred Natural Sites and Biodiversity Conservation in the Gambia.

With regard to sustainable land management, the baseline investment over the 5-year project period is estimated at about USD16-17 million.  The Ministry of Agriculture (MoA) and the National Agricultural Research Institute (NARI) receive about 2.7% (about USD5.6 million) and 0.1% (about USD200,000), respectively, of the annual government budget, and it is estimated that some 5% of MoA and 20% of NARI budgets are linked to SLM.

More importantly in terms of scale are a plethora of donor-funded rural/agricultural/livestock development projects implemented through the MoA, which focus on productivity increases, agricultural technologies and processing, access roads to markets and rice fields, small livestock promotion, vegetable gardens, water management and irrigation. This includes, most notably, a project launched in early 2013, the National Agricultural Land and Water Management Development Project, known as Nema, and worth USD64.9 million.  Nema is financed mainly by IFAD and the Islamic Development Bank and executed through the MoA Soil and Water Management Services. The objective of Nema is to increase rural incomes by improving the productivity of farming.  This is to be achieved by purposeful investments in public economic infrastructure including water control structures, access roads and markets, developing vegetable gardens, adding new lowland rice production areas and facilitating controlled tidal irrigation, coupled with the capacity of farmers to manage productive assets within their watershed and achieve better agricultural commercialisation.  An estimated 25% of Nema’s USD64 million are earmarked for SLM and this project will be working in close cooperation with Nema in its efforts towards SLM.

The Forest & Farm Facility (FFF) Phase 2 Project was launched in 2012 with an estimated USD700,000 for the Gambia.  It is hosted by NEA/ANRWG and involves FAO, the World Bank, IUCN and IIED working on sustainable farm and forest management, mainly by supporting the Department of Forestry in the designation and setting up of additional community forests, wood lots and orchards.  However, past rural/agricultural/livestock development projects, including those that had SLM as part of their objectives, have delivered only marginally on environmental sustainability aspects – and have to date largely ignored biodiversity and protected area considerations.

The following table provides a summary of the current baseline activities and investments in response to the threat of environmental degradation.

Table X.	Baseline activities and investments

| BASELINE ACTIVITIES | COORDINATION / IMPLEMENTATION | FUNDING SOURCE | BUDGET (in USD) |
| --- | --- | --- | --- |
| PA management, research and development, environmental education and the promotion of ecotourism | Department of Parks and Wildlife Management | National budget | 625,000 |
| Improving governance of marine and coastal resource management; support capacity strengthening of DPWM and community livelihoods around selected Pas | WWF Gambia | INGO | 400,000 |
| Coordination and cross-sectoral integration | National Environment Agency (NEA) | National budget | 100,000 |
| Gambia Biodiversity Management and Institutional Strengthening Project | DPWM | World Bank/GEF | 950,000 |
| Regional Marine and Coastal Conservation Programme for West Africa (PRCM) | IUCN, WWF, Wetlands International, International Foundation for the Banc d’Arguin (FIBA), Sub-regional Fisheries Commission (CSRP) | INGO | 284,000 |
| Project supporting oyster gatherers in Tanbi Wetlands Complex; and providing village banking and women’s gardening in Bao Bolong Wetland Reserve | PRCM with MAVA Foundation - Phase II of Integrated Coastal and Marine Project (ICAM, 2009-2011) | INGO | 350,000 |
| Supporting committee meetings, marine surveillance and patrolling within Niumi NP, Tanbi Wetlands NP and Tanji Bird Reserve | PRCM with FIBA | INGO | 112,000 |
| Supporting effective management of coastal and marine PAs, providing guidance, support and resources for PA management planning, business planning, ecological gap analyses and eco-regional planning; facilitate preparation of a report on Sacred Natural Sites and Biodiversity Conservation in the Gambia | Regional Network of Marine Protected Areas in West Africa (RAMPAO) | INGO | 95,000 |
| Aims to address interlinked problems of rural poverty, food insecurity and land degradation; improve livelihoods by promoting community-based watershed/landscape management approaches, enabling resource-poor communities to reverse declining land productivity and overcome the causes and negative impacts of land degradation on the structure and functional integrity of lowland and upland ecosystem resources. It supports farmer-centred conservation agriculture validation trials and demonstrations of tree planting, reafforestation, upland conservation, anti-salinity dykes, inter-village roads, anti-hippo dykes and the establishment of an SLM Investment Framework – GAMSIF – for strategic planning, prioritisation and implementation of targeted investments. The main outputs of the project include operational national and regional level Sustainable Land Management (SLM) Platforms comprising a multi-level partnership of stakeholder institutions promoting SLM; | Ministry of Agriculture | National budget | 1,400,000 |
|  |  | GEF | 4,400,000 |
| 20% of NARI core budget is estimated to be linked to research on Sustainable Land Management initiatives and food security issues. This initiative is more directed to soil enrichment trials such as agro-forestry and farm border plantings | National Agricultural Research Institute (NARI) | National budget | 40,000 |
| National Agricultural Land and Water Management Development Project (Nema) - investments in water control structures, access roads and markets, developing vegetable gardens, adding new lowland rice production areas, facilitating controlled tidal irrigation, enhance farmers capacity to manage productive assets within their watershed and achieve better agricultural commercialisation | Ministry of Agriculture, Soil and Water Development Unit | IFAD, Islamic Dev Bank | 16,000,000 |
| Forest & Farm Facility (FFF) Phase 2 project - designation and setup of additional community forests, wood lots and orchards | NEA/ANRWG | FAO, World Bank, IUCN, IIED | 700,000 |
| Food and Agricultural Sector Development Project (FASDEP)- upland soil and water conservation, agro-forestry, livelihood improvement through support to horticulture, livestock and aquaculture enterprises | Ministry of Agriculture | GAFSP | 28,000,000 |
| West African Agricultural Productivity Project (WAAPP-1C) - strengthening research and extension through capacity building and infrastructure support, support to farmer organizations and livelihood improvement | Ministry of Agriculture | WB | 12,000,000 |
| MDG 1C - investment in water control infrastructure for rice and vegetables, provision of production inputs (fertilizers and seeds), improved access to extension services, investment in post-harvest machinery and enhanced market access | Ministry of Agriculture | EU FAO | 7,000,000 |
| Gambia Commercial Agriculture and Value chain management project (GCAV)-investment in livelihood improvement through enhanced value chain management in rice and vegetables, access roads | Ministry of Agriculture | WB | 16,000,000 |
| Enhancing Resilience of Vulnerable Coastal Areas and communities to climate change programme-reduce the vulnerability of coastal communities to flooding, erosion and climate change | National Environment Agency | GEF/UNDP | 8,900,000 |

The value of the above baseline is estimated to be USD97,356,000.  Of this, GEF support has amounted to USD14,250,000 and the remaining USD83,106,000 is considered as co-financing for this project and this is discussed further in section 2.1.1 below.

1.5	Remaining challenges and outstanding gaps

In spite of the impressive response by The Gambia to the threats and impacts on biodiversity, natural resources and ecosystem services, many challenges remain and help is required to overcome barriers which are impeding effective PA management and sustainable land and natural resource management in the targeted areas.

Without additional help, PA management will remain exceedingly weak in an important subset of the country’s PA system, most notably on the northern side of the River Gambia, where pressures on terrestrial and wetland PA resources are becoming critical.  This locality comprises the newly-designated Jokadu National Park (JNP) which will remain without surveyed demarcation, without park infrastructure and with no management planning.  It also includes the Bao Bolong Wetland Reserve (BBWR), which is demarcated but will remain with inadequate staffing, infrastructure, equipment and planning. The two PAs, which are separated by a 10 km gap, will become disconnected due to increasing habitat loss between them.  In addition, further loss of terrestrial and wetland ecosystem services on the north shore will lead to an increase of cross-river exploitation pressures in Kiang West National Park (KWNP) on the opposite southern shore of the River Gambia. KWNP benefited from relevant investment in the past through a series of projects and is arguably the best managed PA in The Gambia.  But it is also the only PA in The Gambia harbouring significant stretches of natural terrestrial habitats (including forests) and is therefore under mounting pressure from logging and conversion pressures that the current management capacity and infrastructure (39 ill-resourced local rangers) cannot wholly stem.  Lastly, under the baseline scenario, the institutional capacity of the relevant ministerial departments will remain too limited to develop and implement viable alternatives to the continuing degradation of the natural resource base of The Gambia’s PAs.  This is in spite of the ongoing DPWM/World Bank/GEF Gambia Biodiversity Management and Institutional Strengthening Project, which is discussed in section XXXX below.

Under the baseline scenario, on the north side of the river, land conversion is expected to move down to the river to the BBWR’s river-border woodlands, mangroves and wetlands and extend into the remaining natural ecosystems in JNP.  On the southern shore, KWNP and the surrounding areas of semi-natural ecosystems will suffer increased exploitation and conversion pressures. The protected areas in place will not be able to stem these pressures and further habitat fragmentation and degradation can be expected.  In parallel, large-scale agricultural/rural development initiatives – most notably Nema – will continue to advance productivity without duly considering environmental sustainability, biodiversity and protected area aspects.  While this may lead to short-term gains in community livelihoods and food security, it does not respond adequately to the severe and ongoing deterioration of the natural resource base, and will not help reduce the exploitation and development pressures that local communities exert on biodiversity and the integrity and connectivity of the protected area system.

In summary, the barriers that stand in the way of successful protection and management of biodiversity, natural resources and ecosystem services in The Gambia, are:

- Insufficient financing for the national PA system. The financial resources available for PA management in The Gambia, including in the targeted PAs, remains insufficient. However, the ongoing DPWM/World Bank/GEF Gambia Biodiversity Management and Institutional Strengthening Project is presently looking into potential financing options and financial mechanisms.

- Inadequate PA operationalization. Although the DPWM conducted consultations and the PA has been welcomed by local communities, JNP is not yet fully gazetted, not demarcated, and not yet equipped with formally adopted management plans and management structures. BBWR has long been gazetted and a management plan has been developed, but the PA is not yet demarcated on the ground and provided with only very basic village-level PA headquarters and only 28 poorly trained and equipped local rangers. KWNP is arguably the best managed PA in the Gambia having received repeated project investment since its establishment in 1991, leading to full on-the-ground demarcation around its perimeter, the construction of PA headquarters and related facilities and housing, the development of a full management plan and business plan, and access points staffed with 39 local rangers; but as indicated above, this is still inadequate to stem increasing pressures.

- Small size of PAs, edge effects and risk of fragmentation. The PAs in the Gambia are small, accessible from many sides and surrounded by numerous communities. Through the increasing degradation of ecosystems between PAs, these are also exposed to increasing habitat fragmentation. This calls for the inclusion of further PA areas and of corridors into the national PA network/system, including through an assessment of gaps, risks and opportunities, e.g. related to the national forest parks and community-based forest reserves.

- High resource exploitation and land conversion pressures from surrounding communities due to the perceived lack of alternatives, poor capacity and consequential poor land and natural resource management practices, which include the use of fire for land clearing and the traditional value of large livestock herds. These are key community-related barriers. Relations of DPWM with communities are excellent, however, and in PAs that are operational (such as KWNP), ecosystems are still in a much better condition than outside, reflecting the effectiveness of interventions even at prevailing relatively modest levels. It is important to note that poverty as such is not a key driver/barrier – in fact, biodiversity pressures are highest in those areas where rural populations have graduated to a more mechanised agriculture that provides them with better income, yet at the same time has led to severe resource depletion in the wider landscape with consequent pressures on PA resources.

- Limited integration of environmental sustainability (especially biodiversity, protected areas, sustainable natural resource use – but even sustainable land management practices) into the majority of rural/agricultural development programmes/projects; this is reflected in the type of investments commonly undertaken and largely linked to (a) the productivity and mechanised agriculture-focused training and focus of responsible professionals; (b) limited contribution of credible SLM and biodiversity specialists in agricultural programmes/projects and related planning; and (c) ineffective cross-sectoral coordination mechanisms. This has already in the past led to a misalignment of agricultural development actions with PA management concerns (such as the promotion of rice terraces in critical wetlands in PA core zones).

It is these barriers that the project will address.

2	STRATEGY

2.1	Project rationale and policy conformity

2.1.1	The GEF alternative – incremental reasoning

As noted above (section 1.4) the Gambia’s response to the identified threats and barriers has been a significant investment of over USD97.5 million.  After deducting the USD14.25 million invested by the GEF, the co-financing baseline is an impressive USD83.25 million.  However, the response has left some gaps which can be remedied through the increment provided by the GEF for this project.  This increment, from the GEF Trust Fund resources, added to the co-financing baseline, constitutes the GEF Alternative.  The table below summarizes the baseline, notes the gaps remaining, lists the project activities which will address the gaps and calculates the increment and budgetary implications.

Table X.	Project activities addressing remaining challenges incremental to the baseline

| CO-FINANCING BASELINE ACTIVITIES (NON-GEF) | GAPS AND BARRIERS REMAINING | ALTERNATIVE PUT IN PLACE BY PROJECT | INCREMENTAL COSTS |
| --- | --- | --- | --- |
| Component 1: Strengthen national PA network planning and PA management effectiveness in a cluster of priority PAs Outcome 1 - Gazettement of a c. 5000 ha expansion of JNP to connect to BBWR, and of a c. 10,000 ha expansion of KWNP Outcome 2 - Enhanced management effectiveness in both existing and added PA areas |
| PA management, research and development, environmental education and the promotion of ecotourism Improving governance of marine and coastal resource management; support capacity strengthening of DPWM and community livelihoods around selected PAs Coordinate cross-sectoral integration Regional Marine and Coastal Conservation Programme for West Africa (PRCM) Support park committee meetings, marine surveillance and patrolling within Niumi NP, Tanbi Wetlands NP and Tanji Bird Reserve Support effective management of coastal and marine PAs, providing guidance, support and resources for PA management planning, business planning, ecological gap analyses and eco-regional planning; facilitate preparation of a report on Sacred Natural Sites and Biodiversity Conservation in the Gambia The value of the above baseline is estimated as USD1,616,000 | Under the baseline scenario, PA management will remain exceedingly weak on the northern side of the River Gambia, where pressures on terrestrial and wetland PA resources are becoming critical. The newly-designated Jokadu NP will remain without demarcation on the ground, park infrastructure and management planning; and Bao Bolong Wetland Reserve will remain without adequate staffing, infrastructure/ equipment or planning. The two PAs, separated by a 10 km gap, will become disconnected due to habitat loss. There will be an increase in cross-river pressures in Kiang West NP - mounting exploitation (logging) and conversion. Institutional capacity of relevant departments will remain too limited to develop and implement viable alternatives to the continuing degradation of the natural resource base of PAs. | Strengthening management effectiveness in the three PAs to address existing and emerging threats to global and local ecosystem and biodiversity values. 10,000 ha expansion to the east and west of KWNP; 5,000 ha expansion of JNP that will connect it to BBWR. Basic PA offices, adequately equipped and staffed, in JNP and BBWR. Institutional and technical capacities - planning, administration, conflict resolution, monitoring, enforcement, etc.). Demarcation of on-the-ground boundaries of JNP and BBWR, as well as of the newly added PA areas. Following community consultations, multi-year PA management and business plans will be prepared or updated to provide: zonation and related regulations; sustainable use of natural resources by local communities; PA governance, including co-management and conflict resolution mechanisms; effective law enforcement governing natural resource exploitation and wildlife poaching; basic ecological monitoring systems. Revised PA Programme of Work and Action Plan. Determine relevant ecological representation gaps, and assess the forest park estate to identify sites that merit biodiversity conservation; consider climate change scenarios and biodiversity adaptation measures. | The GEF alternative for Component 1 (Outcomes 1 and 2) will cost USD???? of which USD???? is from GEF and USD1,616,000 is from co-financing |
| Component 2: Improve land and natural resource management in and around the targeted cluster of priority PAs Outcome 3 - Improved forest cover, habitat integrity and connectivity across the targeted PA cluster and surrounding landscapes (c. 60,000 ha) Outcome 4 - Enhanced diversity, sustainability and reliability of community livelihoods |
| Support oyster hunters in Tanbi Wetlands Complex; village banking and women’s gardening in Bao Bolong Wetland Reserve Various Sustainable Land Management activities in MoA and research in NARI National Agricultural Land and Water Management Development Project (Nema) - investments in water control structures, access roads and markets, developing vegetable gardens, adding new lowland rice production areas, facilitating controlled tidal irrigation, enhance farmers capacity to manage productive assets within their watershed and achieve better agricultural commercialisation Forest & Farm Facility (FFF) Phase 2 project - designation and setup of additional community forests, wood lots and orchards Food and Agricultural Sector Development Project (FASDEP)- upland soil and water conservation, agro-forestry, livelihood improvement through support to horticulture, livestock and aquaculture enterprises West African Agricultural Productivity Project (WAAPP-1C)-strengthening research and extension through capacity building and infrastructure support, support to farmer organizations and livelihood improvement MDG 1C- investment in water control infrastructure for rice and vegetables, provision of production inputs (fertilizers and seeds), improved access to extension services, investment in post-harvest machinery and enhanced market access Gambia Commercial Agriculture and Value chain management project (GCAV)-investment in livelihood improvement through enhanced value chain management in rice and vegetables, access roads The value of the above baseline is estimated as USD81,490,000 | Land conversion on the north side of the river will move to the BBWR’s woodlands, mangroves and wetlands and extend to the west into the remaining natural ecosystems in JNP. On the opposite southern shore, KWNP and surrounding areas will suffer increased exploitation and conversion pressures. There will be further habitat fragmentation and degradation. Large-scale agricultural developments (Nema) will continue to advance productivity without due consideration of environmental sustainability, biodiversity and PA aspects. While this may lead to short-term gains in community livelihoods and food security, it does not respond adequately to the severe and ongoing deterioration of the natural resource base, neither will it help reduce exploitation and development pressures that local communities exert on biodiversity and the integrity and connectivity of the protected area system. | With a focus on communities surrounding the three (farmers and their households, totalling an estimated 70,000 people), working closely with MoA’s Nema Project, introduce biodiversity-friendly sustainable land and natural resource management practices, to reduce pressures such as unsustainable wood extraction, land conversion for shifting cultivation, the incidence and severity of fires, that these communities exert on the targeted PAs. Restore vital resources into production landscape matrix, improve natural ecosystem integrity and connectivity. Establish nurseries and plant suitable fruit, forage, firewood and multi-purpose trees and vegetation; pilot conservation tillage agriculture; establish inter-cropping regimes and nutrient-rich plants and hedges in degraded farmland; establish agro-forestry regimes and village woodlots and shelter belts; revisit fire and grazing practices; replant mangroves in degraded wetlands; pilot new salt-tolerant wet rice varieties to reduce land conversion for dry rice production; promote and distribute fuel efficient stoves; and increase bee farming and horticulture. Agreements with local communities will form the basis of these community-based interventions. Implementation plans to define: the rights and responsibilities of communities and the project, and areas where community interventions will be implemented; prescriptions for suitable biodiversity-friendly NRM and SLM practices; resource-sharing mechanisms; extension support; monitoring and compliance mechanisms. A monitoring system will provide relevant and science-based information on the state of natural resources of national and global significance and socio-economic conditions in the target areas. Catalyse the integration of biodiversity and PA aspects as well as of SLM and NRM into this large-scale agricultural and rural development. | The GEF alternative for Component 2 (Outcomes 3 and 4) will cost USD???? of which USD???? is from GEF and USD81,490,000 is from co-financing |

2.1.2	Project sites

This project will contribute to the national goal of increasing the PA area to 10% by adding some 15,000 ha to the protected estate, making the new total of PAs as 7.4%.  It will do this in a focus area comprising three nearly contiguous PAs, namely – Kiang West National Park (KWNP), Bao Bolong Wetland Reserve (BOWR) and the newly-designated Jokadu National Park (JNP).  This “hub” of protected areas experience similar problems relating to threats and pressures of degradation but they differ in frequency and magnitude.  All suffer bushfires, illegal tree felling, agricultural encroachment, overgrazing, illegal hunting, salinization of riverine wetlands and mangrove die-back, and these problems are exacerbated by increasing population pressure and poverty.  These project sites will serve as a cornerstone for biodiversity conservation and for safeguarding ecosystem services, integrity and resilience in The Gambia.  In parallel, they will also serve to demonstrate community-based sustainable land and natural resource management in localities adjacent to PAs.

2.1.2.1	Kiang West National Park and the south bank

The park

The Kiang West National Park (11,526 ha) was established in 1987 to provide for the protection, conservation and management of the ecological integrity, diverse wildlife, natural habitats and natural heritage resources and to offer opportunities for economic, recreation, education and scientific purposes.  It lies on the southern bank of the River Gambia and comprises vast areas of semi-natural ecosystems and one of the most important reservoirs of wildlife in The Gambia today. The park is on a low-lying plateau which supports a degraded savannah dominated by open Combretum and Pterocarpus erinaceus woodland with occasionally taller trees such as Adamsonia digitata and Ceiba pentandra and a layer of Andropogon grasses.  Most of the ecosystems within the park are closed-canopy woodlands particularly around the western part.  The PA is a good representation of the Gambian ecosystems/ecoregions, with the upland ecosystems on the southern and western borders and wetlands and mangrove swamps on the north and east.  Although the major part of the park is dry deciduous woodland and Guinea savannah, there are extensive stretches of mangrove creeks and tidal flats.

The River Gambia, the main source of surface water, is tidal and saline in this area throughout the year, consequently, the bolongs in the area, such as Jarin, Jali and Nganingkoi bolongs are also tidal and saline throughout the year.  Towards the river, the plateau is cut by the tidal inlets of bolongs which are heavily vegetated with mangrove stands comprising Rhizophora racemosa, Avicennia africana, Rhizophora mangle and Laguncularia racemosa.  Here there is a typical zonation from Mitragyna inermis, Acacia seyal woodland to saltmarsh.

The Kiang West National Park was the first protected area in the Gambia to have a formal management plan prepared in 1992. The park infrastructure development was supported by ANR USAID project, which was phased-out in 1994. However, basic infrastructure such as headquarters and office complex with education centre do exist, as well as forest infrastructure and fire lines. The staff complement is the highest in the Gambia with about 37 in total.  Public cooperation has been achieved through the establishment of an active management committee formed from the surrounding communities together with the DPWM.

Conservation values

The park is one of the foremost wildlife reserves in the country and offers a significant natural habitat for species such as the Caracal (Caracal caracal), Serval, Bushbuck (Tragelaphus s. scriptus), and Common Duiker (Sylvicapra grimmia).  Other recorded mammals include the African clawless otter (Aonyx capensis), Leopard (Panthera pardus pardus), Marsh Mongoose (Atilax paludinosus), Serval (Leptailurus serval), Spotted hyaena (Crocuta crocuta), Warthogs (Phacochoerus africanus), and West African manatee (Trichechus sengalensis).  West African manatees and Bottlenose and Humpback Dolphins are sometimes observed around the northern side of the park along the river.  Roan Antelope are mainly periodical visitors from southern Senegal. The Park has the largest concentration of primates in the Gambia. These include Western Guinea baboons and olive baboon, vervet monkeys, red patas, bush babies and calitrix monkeys, and red colobus (Colobus badius badius).  Leopards are also reported in the area.

Over 250 bird species have been recognized in the park.  Keystone species include the Brown neck parrot, black bellied bustard, Battelor eagle, Marshal eagle and the large falcon (one species).  There are 21 birds of prey, including eagle, falcons, hawks and vulture species.

The park's reptile species include the African rock python (Python sebae), and Chelonians are represented by Bell’s Hinged-Back Tortoise (Kinixys belliana nogueyi), an interesting species found in the savannah woodlands. West Africa Nile crocodile (Crocodylus niloticus), Nile monitor (Varanus niloticus), Puff adder (Bitis arietans), Royal python (Python regius), Spitting cobra (Naja nigricollis), green mamba, olive sand snake, bush snake, wolf snake, armitage skink, night adder and West African or Mud Terrapin also occur in the flooded area adjacent to the bolongs.

Communities

The park is under-populated with only five villages (total population just under 5,000) located near the park boundary around its eastern, western and southern periphery.  The village structure is more or less the same as in other Gambian settlements with all development issues taken care of by the Village Development Committee (VDC).

Table X.	Population distribution of the five villages

| Village | Population | Total Population |
| --- | --- | --- |
|  | Male | Female |  |
| Batelling | 189 | 214 | 403 |
| Dumbutu | 730 | 397 | 1,127 |
| Bajana | 444 | 242 | 686 |
| Kuli Kunda | 528 | 287 | 815 |
| Jali | 1137 | 642 | 1,779 |
| Total | 4,810 |

Source -  Gambia Bureau of Statistics (GBOS)

These communities comprise subsistence farmers and community-based fishermen.  The main crops cultivated are rice, maize, sorghum and groundnuts.  In recent years, water melon and beans are also intensively cultivated as additional cash crops together with firewood collection.  The area is heavily populated with livestock, both cattle and small ruminants.  Horticultural activities are practiced by the women mainly during the dry season, still employing traditional farming systems and tools such as animal traction and hoes.  Another important activity is fishing and the fishermen living within villages around the park use a variety of small scale fishing gear.  Catches are sold at the village market or used for home consumption.

All communities complained of low yield of all crop types with a reduction of up to 40% for most crops and up to 60% for rice in some areas compared to 10 years ago. The main reasons advanced were land degradation, low soil fertility, soil erosion, drought, limited labour availability due to rural-urban drift and destruction of crops by wild animals. Increasing agricultural production on a sustainable basis therefore is a buffer towards future encroachment into the park in search of farmland as a result of unsustainable and inadequate farming systems/resource management.

Tourism is well established in the area at the adjacent Tendaba Camp with natural and cultural attractions.  The re-introduction of certain animal species may be possible and will create an added attraction for visitors.

Main threats

Fire is a major threat to the ecological resources as well as to the communities.  As a result, there are strict laws and a high level of sensitization, awareness raising and cooperation to counter the threat of wildfires.  In addition, an increased effort is required on the part of PA management to reduce the fire risk and raise public awareness further on both the effects of bush fires and the legal implications.

KWNP is the only PA in Gambia harbouring significant stretches of natural terrestrial habitats (including forests) and is therefore under mounting exploitation (from logging) and conversion pressure.  The PA already serves as an important grazing area for livestock, rice cultivation and beekeeping with the periphery utilized for crop cultivation.

2.1.2.2	Bao Bolong Wetland Reserve and the north east

The reserve

Bao Bolong is a tidal wetland complex located on the north bank of the River Gambia, across the river from another protected area, the KWNP.  It extends from the river to The Gambia’s borders with Senegal and offers the potential for bilateral cooperation on biodiversity.  It consists of six major bolongs (tributaries) between Salikeni and Katchang villages.  Together they form a wetland complex of approximately 22,000 ha.

The Bao Bolong Wetland Reserve (BBWR) was declared in 1996.  It is protected by the Wildlife Conservation Act and the Banjul Declaration, both of 1977 and it has also been nominated as a wetland of international importance under the Ramsar Convention.  However, it is not officially gazetted to date and awaits better definition of its proposed boundaries. It has no physical demarcation on the ground.

Until 1997 there were no DPWM staff assigned to the area, activities within the area were uncontrolled and there was evidence of degradation through unlicensed hunting, timber extraction and uncontrolled burning. The initial emphasis of the DPWM staff was on establishing co-operation with communities utilizing the wetland for farming, grazing and fishing activities.  This was a similar management structure to that successfully employed in Niumi National Park and Kiang West National Park whereby a management committee is formed from the peripheral communities in conjunction with the DPWM.  Strict laws against bush fires were among the early measures put in place.

Conservation values

The ecological significance of Bao Bolong lies in the fact that there are three distinct wetland ecosystems – mangrove forest, salt marsh and savannah woodland - all occurring in very close proximity at several locations.  The mangrove forests are characterised by Rhizophora racemosa , Rhizophora mangle and Avicennia africana.  The mudflats support Sesuvium portulacastrum, Sporobolus spicatus, Paspalum vaginatum and  Diplachne fasca.  The principal species of grasses in the grass savannah of intermittent flooding areas are Phragmites karka, Echinocloa pyramidalis and Cyperus papyrus.  Riparian and fringing savannah-woodland and woodland species include Daiella oliveri, Ptericarpus erinaceous, Terminalia albida,  Parkia biglobosa ,  Bombax costatum, etc.  Shrubs and small trees mainly include Ficus spp, Philostigma thonningii, Terminalia avicennoides,  Anthostema senegalensis,  Nauclea latifolia  and grass species of mainly Andropogon tectorum,  A. gayanus,  Beckeropsis uniseta  and  Pennisetum subangustu.

The mangrove ecosystems are an important breeding site for many species of fish.  In addition, the BBWR is frequented by many mammal species in particular hippopotamus (Hippopotamus amphibius), manatees (Trichechus senegalensis), white-cheeked otters (Aonyx capensis) and the sitatunga (Tragelaphus spekii).  Two species of crocodile are also present within the reserve - the Nile crocodile (Crocodylus niloticus and the Dwarf crocodile Osteolaemus tetrapsis.

The BBWR is rich in avifauna and over 268 species have been reliably observed at various locations and in various habitat types within the wetland complex.  Relevant species include: Egretta gularis, Poicephalus senegalux, Psittacula kraneri, Egretta garzetta, Ciconia episcopus, Halcyon senegalensis, Scopus umbretta, Streptopelia decipiens, Ardeola ralloides, Lxobrychus minutus, Ardea goliath, Ceryle rudis, Egretta alba, Lepoptilos crumeniferus, Vanellus spinosus, Nycticorax nycticorax, Merops hirundineus, Cinnyricinclus leucogaster, Ardea cinerea, Bucorvus abyssinicus, Haliaetus vocifer, Ceryle maxima, Ibis ibis, Pelicanus rufescens, Coracias garrulus, Buteo augurals, Milvus migrans, Terathopius ecaudatus, Threskiornis aethipica, Vanellus spinosus, Alcedo cristata, Calidris minuta, Halcyon malimbica, Sarkidiornis melanota, Plectropterus gambensis, Dendrocygna viduata, Anas  querquedula, Anas acute, Nettapus auritus, Anas clypeata, Apus affinis, Tringa hypoleucos, Lamprotornis candatus, and Anhinga rufa.  The resident threatened bird species include the pelican, and spoon bill.

Fish species present in the Bao Bolong area include Ethmalosa fimbriota, Sphreana sp., Polydactylus quadrifilis, Arius sp., Fonticulus elongatus, Pomadasys peroteti, Pseudotolithus bracygnathus, Crassostrea gasar.  The area’s mangrove ecosystem provides an important fish breeding ground and its tributaries are an important source of fish (e.g. African tilapia) for local communities.  Also present are crabs (Callinectes sp.) and the area also provides significant habitats for other aquatic animals such as the Cape clawless otter, the West African Manatee, the Nile crocodile, Sitatunga, etc.  Other wildlife include the spotted hyena, the bushbuck and the duiker as well as a number of primates (Red colobus, Patas and Green vervet monkeys).

Communities

The Reserve is surrounded by 25 villages and a further village exists within the reserve boundaries with a combined population of 51,556 (GBOS, 2013 Population and Housing Census).  The Village Development Committee serves as the entry point and partner for development initiatives.  Due to its proximity to large towns such as Farafenni and to neighbouring Senegal, diverse socioeconomic activities are undertaken by communities.

The adjacent population relies on the reserve for the supply of a number of domestic requirements.  These include the production of rice, millet and groundnuts, fishing, provision of timber and wood for cooking, fencing, roofing and other construction and the grazing of stock. The main economic activities are rice cultivation, fishing, straw weaving, horticulture and ecotourism.  The reserve is also home to secret shrines and sites of cultural importance.

Communities practice upland cultivation of maize, sorghum, water melon and groundnuts.  The area is also famous for pumpkin production targeting Senegal and urban markets in the Gambia. They also grow lowland rice and carry out vegetable gardening, livestock-raising, fishing and fuel-wood collection as sources of food, income and livelihood. Horticultural activities play an important role in income generation, particularly for women. The use of traditional farming systems and tools is high, but the use of machinery, especially for ploughing, is also common and sustainable land management practices need to be promoted to minimize soil degradation due to inappropriate tractor ploughing and uncontrolled use of herbicides.  The main problem facing farmers in the area is the loss of soil fertility due mainly to erosion, inappropriate tractor ploughing and herbicide applications.  In addition, salt intrusion particularly into lowland rice fields located in the PA remains problematic.

Fishing is an important activity mainly for local consumption but also as a modest commercial activity with some marketing outside the immediate locality. The fishermen living within villages around the park use a variety of small scale fishing gear.

Under the traditional system of land tenure, local residents claim ownership of certain areas of the wetland complex and the surrounding lands comprise communal farmlands, private agricultural land and residential areas.  In order to maintain good public relations, certain resource exploitation practices by the communities (e.g. fishing for local use, harvesting of thatch grass and fencing materials and cultural practices) are allowed as long as they stay within sustainable limits.

Ecotourism comprises birdwatching, wildlife viewing, fishing and canoeing.  A limited ecological and ecotourism assessment of the area was undertaken in December 1993 to provide an indication of its potential role for ecotourism.

Main threats

As a result of the increasing salinity over much of the area, there are no immediate perceived development threats to the reserve.  However, the relatively high population leads to a lot of pressure on the reserve resources.  For example, the intensive cropping and the farming techniques used in combination with the practice of burning off crop residues prior to cultivating the land, result in a loss of soil fertility.  One main concern is the destruction caused by wildlife on agricultural crops. This is a matter of great concern and often leads to serious conflicts between farmers and conservation officers.

There is a considerable level of hunting activity within the Bao Bolong Wetland Reserve, both by local villagers and non-locals. The sustainability of these activities needs to be ascertained, but it is not compatible with the objectives of the conservation status of the area.  Waterfowl seem to be the main group affected, including pelicans, although mammals and reptiles, including crocodiles and snakes are also under pressure.

The tidal flats have also been the subject of low cost communal dike building schemes for fresh water retention and rice production. Challenges to sustainable land management include low level of conservation farming, inadequate access to quality production inputs including drought resistant and early maturing varieties, soil erosion and saline intrusion.

2.1.2.3	Jokadu National Park and the north west

The park

The Jokadu National Park (JNP) of 15,028 ha is a newly-designated protected area.  It is located on the northern bank of the river and is one of the most beautiful mangrove forest stands in the Gambia comprising 90% wetlands and used mostly for only fishing.  It is the wetland system fringing the river from Jurunku village in Upper Niumi to Kinteh Kunda Jannehya in Lower Badibou.  It also includes forest areas on the landward part near Tambana village, adjacent to Kumali Forest Park.  The ecosystem types include mangrove stands, mangrove vegetated islands, creeks, forest, and swamps.

Conservation values

Five species of mangroves are recorded namely Rhizophora mangle, Rhizophora harisonii, Laguncularia racemosa, Conocarpus erectus and Avicennia nitida.  Other species of flora include Schoenoplectus spp, Paspalum vaginatum, Sesuvium portulacastrum, Typhae australis, Phragmites autralis, Pterocarpus erinaceus, Terminalia avicenoides, Terminalia macroptera, Nauclea latifolia, Combretum glutinosum, Combretum micrantum, Cassia siberiana, Detarium senegalensis, Strophantus samentosus, Lophira lancealata, and Schlerocaryabirrea (also used to feed cattle).

The park is also home to many animals and plants like Crocodiles, Monkeys, wild ducks, manatees and Warthogs and it is a common habitat providing refuge to Hyenas.  Porcupine and leopard are rare, while antelope and Kobs have disappeared from the area.  There is a high fisheries diversity and availability with the upwelling water providing a year-round habitat for Manatees. This upwelling of nutrient-rich water has a major positive influence on fish diversity.  Oysters and clams are abundant including the rare Crassostrea rufa.  The largest ever count of flamingo (400 individuals) in the Gambia was recorded at one of the confluences in JNP.  That alone qualifies the park as a Ramsar site, however, more than 40 species of migratory birds frequent the park every winter.

Communities

The Park spans three administrative districts, with the population estimated at close to 30,000 who constitute direct resource owners and users. The village of Kemoto, located on the opposite side of the river is also participating in the Park.  The communities, which are guided by the VDCs in the management of PA resources, comprise farmers who cultivate maize, millet, groundnuts, melons and beans as well as lowland rice and vegetables, and livestock rearing.  They also fish and collect fuel-wood.  All are important sources of food and income and constitute the principal livelihood activities.  The communities practice fairly intensive agriculture using animal traction.  Fishing is an important economic activity with catches sold in villages and markets.  The principal markets in the area are the Loumos (weekly markets) of Kerr Patteh and Ndungu kebbeh, Kerewan and Barra.

Main threats

This newly-designated national park (JNP) remains without demarcation on the ground, no park infrastructure and no management planning. It is separated by a 10 km gap from BBWR and there is a threat of advancing habitat loss between them.  Land degradation characterized by increasing salinity and low soil fertility are the key problems highlighted by communities.

2.1.3 	Stakeholder analysis

Stakeholders have been involved in project formulation from the concept stages.  Under the leadership of the DPWM, the Government and UNDP supported two national workshops in 2012, where stakeholders were invited to contribute to the planning of the project and to the definition of its objectives.  Participants included a wide range of representatives from government, local communities, NGOs, private sector and international organizations.  In addition, preliminary social assessment activities were conducted and several local stakeholder meetings were held at each of the proposed sites.  Local communities and regional authorities have expressed a strong interest in the project and they have been involved further in the formulation stages.

The following table lists the key stakeholders, summarizes their mandate and identifies their prospective role in project implementation.

Table X.  Stakeholder participation in project implementation

| STAKEHOLDER / PARTNER | MANDATE AND ROLE IN PROJECT | SPECIFIC AREA OF INVOLVEMENT |
| --- | --- | --- |
| Department of Parks and Wildlife Management (DPWM) of the Ministry of Environment, Climate Change, Water Resources & Wildlife (MOECCWW) | DPWM is entrusted with the conservation, management,monitoring and development of biodiversity and wildlife resources in the country, both in and outside of protected areas and in production landscapes. DPWM is the lead government agency for implementing the CBD and hosts the National Focal Points for the CBD and PoWPA/CHM/SBSTTA, as well as for CMS, AEWA, Biosafety, the African/Algiers Convention and RAMSAR. DPWM has five functional units: Directorate, Conservation Education and Extension Unit, Parks and Protected Area Management Unit, Research, Crop Damage Assessment and Control Unit, and Surveillance Unit. DPWM is a member of ANRWG (see below) and is pivotal for better integrating biodiversity conservation and PA management matters into land use planning in general and into agricultural and sustainable land management around PAs. | DPWM will be the leading executing partner and will provide the NPD. It will be responsible for project activities’ coordination and implementation in collaboration with other stakeholders to ensure the successful execution of all project components and Outputs. |
| Agriculture and Natural Resources Working Group (ANRWG) of the National Environment Agency (NEA) | The Agriculture and Natural Resources Working Group (ANRWG) hosted by NEA is the umbrella body for development initiatives related to agriculture and natural resources including PA-related matters. NEA is mandated to ensure that this initiative is implemented in a coordinated and complementary manner with existing and planned initiatives in the ANR sector | The ANRWG will serve as the Project Steering Committee |
| Ministry of Agriculture (MOA): Soil and Water Management Services (SWMS) and Department of Agriculture (DOA) | The Ministry of Agriculture is responsible for supporting and promoting the agricultural industry and for establishing a coherent legal, regulatory and enabling framework for agricultural development. The MoA and its agencies are therefore critically important for integrating biodiversity matters into agricultural development projects at all stages – in conjunction with the ANRWG. The DoA,is responsible for overall extension service delivery and is also relevant in the promotion of sustainable land and waterscape management and the adoption of value added initiatives to enhance market value of products. The MoA hosts and implement a variety of agricultural development projects most notably the National Agricultural Land and Water Management Development Project (Nema). | The MoA Nema project is one of the project’s co-financing partners. It will be involved particularly in the implementation of Outputs xxxx |
| Department of Fisheries (DOFI) of the Ministry of Fisheries and Water Resources | The Department of Fisheries plans, coordinates and executes actions in the sector, develops fisheries management plans and elaborates the necessary laws and regulatory mechanisms. Fisheries are extremely relevant in the localities of the project because of the importance of fisheries resources in terms of both utilisation and recruitment (oysters, fish, etc.). The fisheries sector is important as a key livelihood component for communities | DOFI will be involved through the PSC (ANRWG) in general; and more specifically in Outputs xxxx |
| Department of Forestry (DOF) at the Office of the President | DoF is responsible for marketing forest products, and for managing the forest resources in the country – in general as well as in national forest parks and reserves including those under joint or devolved forest management schemes. Partnership with the project will enhance community participation and increase the possibility of FPs & CFs designations in PA networks | Member of PSC (ANRWG). DoF will also be involved in Output xxxx when forest parks and reserves are assessed for biodiversity conservation / PA designation potential |
| Municipalities and local authorities in the targeted PAs communities | The office of the Governor is the highest body of government in the region and is responsible for overseeing all development activities in the administrative area. Will be involved through local consultative committees such as the MDFTs and TACs at the regional/municipal levels. Will have a role in monitoring the implementation and facilitating smooth implementation of all regional/municipal development activities. | Members of PSC or PSC sub-committees for the three project localities. Particular interest in Outputs xxxxx |
| NGOs, national and regional associations and local community groups | NGOs (national and regional), CVOs and similar bodies increasingly play an important role in environmental conservation in The Gambia. Locally relevant groups will serve as agents in facilitation, sensitization and capacity strengthening of communities in project aspects relevant to their areas of expertise. They will also participate in the design and implementation of the project’s site-level components, such as the establishment and/or strengthening of community-based natural resource management agreements and on PA co-management plans. | Particular involvement in Outputs xxxxx |
| Local communities, women and vulnerable groups | Communities are the key participants in the project as well as the main beneficiaries. They are central in decision-making, and will take the lead in PA management and protection. Gender and vulnerable groups, and related social issues, will be fully considered, and gender accountability is a cross-cutting issue that will be tracked as part of the M&E system. Special attention will be paid to gender issues in developing socioeconomic indicators, and in the capacity-building activities. General benefits resulting from enhanced natural resources management will directly benefit women in particular, who bear a significant share of the workload in rural households | Will be involved directly in the identification and implementation of project related livelihood interventions. More specifically, they will participate in Outputs xxxxxxx |
| Sahel Wetland Initiative | This is a new youth CBO based in Dumbutu. They are already working with 17 communities in Kiang West project locality, mainly in the area of tree nurseries, beekeeping general environmental awareness raising. They also have relationships with neighbouring cross-border communities. | Will be involved in raising awareness and mobilization of youths, particularly in Outputs xxxxx |
| Kiang West Dolla Kaffo | This local CBO is a congregation of 5 village-associations focusing on a wide range of rural development issues. They undertake mangrove and Gmelina planting and facilitation of seedling acquisition to member villages. The Kaffo (organization) has its own tree nursery and undertakes beekeeping (own 50 hives). The Kaffo undertook also dyke construction against salt intrusion. It will serve as a good partner in the project’s SLM initiatives such as agro-forestry. | Specific involvement in Outputs xxxxxx |
| Cashew Growers Association | The Association is charged with the promotion of cashew growers and other small businesses within the community and can become involved in the project’s alternative income generation initiatives. | Participation in Output xxxx |
| Agency for the Development of Women and Children (ADWAC) | ADWAC is based in the community and it is active in capacity building, horticulture, small ruminants multiplication, community forestry scheme and agro-forestry. The association promotes governance and gender equity as well as the cause of the disabled. | Can partner the project’s work under Output xxxx |
| Njawara Agricultural Training Centre | The Centre works with communities on sustainable farming by capacity building, provision of early maturing and drought resistant crop varieties, woodlots and orchards. The Centre’s main routine activities include vegetable gardening, water supply and salinity control. It also provides small grants for self-reliance activities. | Can partner the project under Output xxxx |
| WABSA | Local NGO housed in the DPWM Headquarters. The NGO’s mandate includes community empowerment in the preservation of the natural heritage of the country, be it wildlife, birds or habitats. The NGO concentrates more on in community sensitization, capacity building and the initiation of community protected area scheme. WABSA will be a key partner in facilitation, sensitization and capacity strengthening of communities | Will partner the project under Output xxx |
| National Agricultural Research Institute (NARI) | National Agricultural Research Institute (NARI)’s research programmes cover cereals and grains, horticulture, livestock, and agro forestry. Compared to the institute’s Long Term Plan, the current research program places a relatively greater emphasis on diversification, yield and horticulture, whereas research on livestock, fisheries, and business channels, marketing and land tenure are neglected. | NARI will be contracted to lead research in particular in the area of SLM under Output xxx |
| University of The Gambia (UTG) | The University of The Gambia is the highest and the main professional capacity building institution for professionals in the country. The most important faculty for the project is the Agriculture Faculty which has an interest in SLM. | UTG may be approached to organize a special short-term tailored-made module for the DPWM under Output xxx |
| Management Development Institute (MDI) | The MDI is a very versatile training institution dealing mainly with the technician cadre. Apart from public officers’ managerial and administrative courses, the institute is very instrumental in the capacity of private sector and youth population. The main courses of relevance to the project include management and research. | MDI will collaborate with UTG and DPWM on short-term courses to be carried out under Output xxx |
| National Training Authorities (NTA) | The NTA is a public office responsible of skills training and training quality in The Gambia. The authorities are also responsible to oversee training module contents and also certification. The NTA is also mandated with the evaluation of certificates. | Under Output xxx, NTA will collaborate in finalizing training modules and certification under Output xxx |
| Department of Community Development (DCD) | The objectives of DCD are to promote participatory community self-help in the identification, planning, implementation, evaluation and management of programmes and projects that will better enable communities to address their basic social welfare needs. In particular, DCD aims to support community development activities that contribute to livelihood diversification through income generating activities such as handicrafts, vegetable gardening and cottage industries using appropriate technologies that add value to locally available products. DCD also assists with developing/strengthening village/community level institutions so as to better facilitate their participation in decision-making, and to give them the skills needed to plan, implement and evaluate multi-sectoral projects of particular benefit to their communities. DCD covers the whole country through a network of regional Community Development Officers, supported by district level Community Development Assistants. | Will partner the project in its work at community level - motivation, mobilization and raising awareness on project related livelihood interventions. More specifically, DCD will participate in Outputs xxx |

The agencies named above were all part of the stakeholder consultations and have indicated willingness/readiness to collaborate/partner with the project in their areas of comparative advantage to attain common objectives.

2.1.4	Fit with GEF Focal Area Strategy and Objectives

The project directly addresses BD-1: Improve Sustainability of Protected Area Systems, to safeguard the most important areas and biodiversity by strengthening the management of and expanding a key subset of existing PAs in biodiversity-rich regions in the Gambia.

The GEF defines a sustainable protected area system as one that: a) effectively protects

ecologically viable representative samples of the country’s ecosystems and provides adequate

coverage of threatened species at a sufficient scale to ensure their long term persistence; b) has

sufficient and predictable financial resources available, including external funding, to support

protected area management costs; and c) retains adequate individual and institutional capacity to

manage protected areas such that they achieve their conservation objectives.  The project targets all three of these GEF sustainability requirements.

GEF promotes the participation and capacity building of indigenous and local communities in the design, implementation and management of protected area projects through established frameworks such as indigenous and community conserved areas.  It also promotes protected area co-management between government and indigenous and local communities.  The project follows this GEF approach fully.

The project responds to the significant and growing pressure on natural resources and the conversion of natural ecosystems in the Gambia, including in the country’s protected areas, which is increasingly undermining the status of biodiversity and related ecosystem services.    This will be combined with the adoption of more sustainable natural resource utilisation practices.  The project will build programmatically on work initiated through a GEF-funded PA early action grant that led to the creation of the Gambia National Protected Area Partnership and Network (GamPAN).

Finally, the project will contribute towards the achievement of CBD Aichi Targets 5, 11 and 12, by increasing the coverage of the national PA system and further strengthening the management of existing PAs, and thereby reducing the loss, degradation and fragmentation of natural habitats and forests, and enhancing the conservation prospects of globally threatened species.  It also contributes to Targets 7 and 14, by working towards more sustainable land management (agricultural and grazing/browsing practices), thereby safeguarding and restoring ecosystem services vital for local populations.

2.1.5	Conformity with UNDP and UNDAF

The UNDP Country Office in The Gambia is a key player in sustainable environmental management in the country.  It has been working with the national government for the last 10 years to strengthen the technical and managerial capacities of environment-related institutions such as the National Environment Agency, and the Department of Parks and Wildlife Management.  During the period 2007-2011, the CO supported the updating of the Gambia Environment Action Plan and the State of the Environment Report.

The project fits within the UNDP strategy for The Gambia.  It is consistent with the 2012-2016 UNDAF Outcome 3.0 Environmental sustainability and disaster risk reduction systems and services operationalised and Output 3.1 National policies and laws available on low carbon emission and climate resilient development pathways and natural resources management developed and implemented.  The project equally falls under the 2012-2016 CPAP, particularly Outcome 2 Sustainable livelihood security enhanced for disadvantaged groups through the promotion of income diversification opportunities and better management of environmental resources, and Output 2.3 Sustainable use of environmental resources enhanced.

2.2	Project Objective, Outcomes and Outputs/Activities

2.2.1	Project Objective and Components

The Project Objective is:

To expand and strengthen the management of priority protected areas in The Gambia, including through enhanced community-based natural resource management

As such, the Objective seeks one ultimate result, namely, the expansion and strengthening of the PA system, and it proposes to achieve this by enhancing community-based natural resource management (CBNRM).

In order to achieve the project Objective, address the identified barriers, and strive for the targeted results, the project intervention comprises two components.

Component 1 :  Strengthen national PA network planning and PA management effectiveness in a cluster of priority PAs

The component targets the expansion of the PA system and the improved management of both existing and new PAs.  The focus of this work will be around Jokadu National Park (JNP, 15,028 ha), Bao Bolong Wetland Reserve (BBWR, 22,000 ha), and Kiang West National Park (KWNP, 11,526 ha).  The expansion of the PA system will take place through a c. 5,000 ha expansion of JNP to connect to BBWR, and of a c. 10,000 ha expansion of KWNP.

The project will strengthen the management effectiveness in the three PAs to address existing and emerging threats. To that aim, two new areas to be added to the national PA estate will be delineated and subsequently legally gazetted: a c. 10,000 ha expansion to the east and west of KWNP, and a c. 5,000 ha expansion of JNP that will connect it to BBWR through a band along the River Gambia.  Basic PA offices will be established and adequately equipped and staffed in JNP and BBWR (KWNP already has adequate PA offices) – with institutional and technical capacities being built through targeted training on all relevant aspects of PA operations to ensure that field staff meet necessary competencies (planning, administration, conflict resolution, monitoring, enforcement, etc.).  Moreover, the on-the-ground boundaries of JNP and BBWR – as well as of the newly added PA areas – will be demarcated using a ring of recognisable, valuable and useful tree species forming a clear boundary that local communities respect and protect.

Following in-depth community consultations, multi-year PA management plans will be prepared for BBWR and JNP and the KWNP management plan will be updated.  The management plans will provide for: zonation and related regulations for strict protection and sustainable use of natural resources by local communities; PA governance, including co-management and conflict resolution mechanisms; effective law enforcement governing natural resource exploitation and wildlife poaching; and basic ecological monitoring systems for targeted habitats and species.

The project will also prepare a revised PA Programme of Work and Action Plan.  The process will entail an ecosystem coverage assessment conducted under the project of the current national PA network to determine relevant ecological representation gaps, and an assessment of the forest park estate to identify sites that merit inclusion in the PA system for biodiversity conservation purposes; it will in the process consider the climate change scenarios and biodiversity adaptation measures proposed by the UNDP-WCMC/GEF PARCC project and any relevant ecological gap assessments conducted under RAMPAO.

Component 2 : Improve land and natural resource management in and around the targeted cluster of priority PAs

The component has a focus on the communities surrounding the three above PAs (i.e. in the buffer zones) that exert significant pressure on the integrity of these PAs.  The targeted stakeholders are primarily farmers and their households, totalling an estimated 70,000 people.  Working closely with and through the MoA’s National Agricultural Land and Water Management Development Project (Nema), the project will introduce biodiversity-friendly sustainable land and natural resource management practices, to reduce the pressures (such as unsustainable wood/ mangrove extraction, land conversion for shifting cultivation, the incidence and severity of wild and forest fires) that these communities exert on the targeted PAs.  This will begin restoring vital resources into the production landscape matrix, improving natural ecosystem integrity and connectivity.  To achieve the latter, the project will establish nurseries and plant suitable fruit, forage, firewood and multi-purpose trees and vegetation; pilot the latest conservation tillage agriculture; establish inter-cropping regimes and nutrient-rich plants and hedges in degraded farmland; establish agro-forestry regimes and village woodlots and shelter belts; revisit fire and grazing practices; replant mangroves in degraded wetlands; pilot new salt-tolerant wet rice varieties to reduce land conversion for dry rice production; promote and distribute fuel efficient stoves; and increase bee farming and horticulture.

Agreements will be entered into with local communities that will form the basis of these community-based interventions to be undertaken by the project.  Implementation plans will be developed that will define: the rights and responsibilities of communities and the project, and areas where community interventions will be implemented; prescriptions for suitable biodiversity-friendly NRM and SLM practices; resource-sharing mechanisms; extension support; and, monitoring and compliance mechanisms.  Through Nema the implementation of the above community-based interventions will be a critical thrust of the project. The project will devise a monitoring system to provide relevant and science-based information on the state of natural resources and socio-economic conditions in the target areas.

Lastly, the collaboration with Nema will also catalyse the integration of biodiversity and PA aspects as well as of sustainable land and natural resource management into this large-scale agricultural/ rural development endeavour more widely.  It is through the close integration of the project with Nema that more sustainable and biodiversity-friendly strategies and SLM/NRM practices will be promoted and rolled out.  As Nema has substantial resources, including for SLM activities, the comparatively small GEF budget is meant to be catalytic to achieve this integration – through the co-location of the two projects, supported by targeted studies, concrete collaboration proposals and joint activities.

2.2.2	Project Outcomes

The two Project Components have given rise to the following four Outcomes –

Outcome 1 - Gazettement of a c. 5000 ha expansion of JNP to connect to BBWR, and of a c. 10,000 ha expansion of KWNP

The Outcome seeks:

formal confirmation of the expansion of the PA network

The estimated total cost of Outcome 1 is USDXXXXX.   Of this, USDXXXXXXXXX is from the baseline (co-financing) and USDXXXXXXXX is from GEF.

Outcome 2 - Enhanced management effectiveness in both existing and added PA areas

The Outcome seeks:

improvement in planning and management effectiveness

The estimated cost of Outcome 2 is USDXXXXX.   Of this, USDXXXXXXXXX is from the baseline (co-financing) and USDXXXXXXXX is from GEF.

Outcome 3 - Improved forest cover, habitat integrity and connectivity across the targeted PA cluster and surrounding landscapes (c. 60,000 ha)

The Outcome seeks:

improvement in ecosystem health and integrity

The estimated cost of Outcome 3 is USDXXXXX.   Of this, USDXXXXXXXXX is from the baseline (co-financing) and USDXXXXXXXX is from GEF.

Outcome 4 - Enhanced diversity, sustainability and reliability of community livelihoods

The Outcome seeks:

more secure livelihoods for communities

The estimated cost of Outcome 4 is USDXXXXX.   Of this, USDXXXXXXXXX is from the baseline (co-financing) and USDXXXXXXXX is from GEF.

2.2.3	Indicators

Two types of indicators are proposed for consideration and confirmation by the Inception Workshop.  Firstly, impact or result indicators which measure achievement and effectiveness and which will help determine whether the Objective and the Outcomes have been achieved.  These are summarised in the table below and carried in the LogFrame in Section 3.  Secondly, process indicators which measure effort, efficiency and performance by the project implementers.  These too are summarized in the table below, but they are not included in the LogFrame.

The choice of impact indicators was based on three key criteria: (i) their pertinence to the assumption inherent in the Logframe;  (ii) the feasibility of obtaining / producing and updating the data necessary to monitor and evaluate the project through those indicators; and, (iii) their direct relevance to the Objective and Outcomes, more so than for Outputs (which are self-evident).

As will be noted from the table below, it has not always been possible to determine the baseline for each of the key indicators and information and survey work is required at the project Inception Phase so as to establish some baselines and set a departure point for some project activities.  These surveys are planned under the appropriate Outputs.

Process indicators do not measure an end point but the progress towards an end point or a result.  Although some of the proposed process indicators relate to progress towards the Objective and Outcomes, the majority are relevant to the management effort, application of resources, and methodology employed in implementing the project.

To the extent possible, quantitative indicators have been selected, however, where this was not possible, qualitative indicators have been selected instead.  All indicators, both impact and process, are considered to satisfy the ‘SMART’ criteria.

Table X.	Indicators for consideration at the Inception Workshop

| IMPACT INDICATORS FOR THE OBJECTIVE AND OUTCOMES (also entered into Section 3 : Strategic Results Framework / LogFrame) |
| --- |
| INDICATOR | BASELINE | TARGET | RATIONALE AND COMMENTS |
| The result sought by the Objective is the expansion and strengthening of the PA system; and it proposes to achieve this by enhancing community-based natural resource management (CBNRM) |
| Impact 0.1 Increase in the extent of the protected estate | Current overall protected estate is 64,276 ha. At the project locality, KWNP is 11,526 ha, BBWR is 22,000 ha, and JNP is 15,028 ha | Extension of the protected estate by an additional 15,000 ha (5,000 in JNP and 10,000 ha in KWNP) making a total of some 74,276 ha protected. | This is a key impact/result of the project. It will be measured through the gazettement of additional protected areas. |
| Impact 0.2 Increase in the number of people who feel that they have a significant role in managing natural resources | Current level is unknown but expected to be 0%. | 20% by Mid-Term; 50% by end of project | This is an impact Indicator measuring the success of the project’s efforts to establish meaningful co-management. Baseline to be set by survey at Inception Phase. Measured by repeat surveys. |
| INDICATOR | BASELINE | TARGET | RATIONALE AND COMMENTS |
| The impact sought by Component 1 is enlarged protected estate and stronger PA planning and management effectiveness |
| Impact 1.1 Extent of the protected estate [similar to Impact Indicator 0.1 above] | Current overall protected estate is 64,276 ha. At the project locality, KWNP is 11,526 ha, BBWR is 22,000 ha, and JNP is 15,028 ha | Extension of the protected estate by an additional 15,000 ha (5,000 in JNP and 10,000 ha in KWNP) making a total of some 74,276 ha protected. | This Indicator is specific to the Outcome 1 target of new protected areas; it is measurable in hectares protected, possibly through remote sensing. |
| Impact 1.2 Enhanced level of management effectiveness | Latest METT scores are: KWNP - XX; BBWR - XX ; JNP – XX | Increase in METT scores by 10% for BBWR and KWNP and 40% for JNP | This Indicator is specific and relevant to the Outcome 2 target of improving the management effectiveness for the three PAs. Subsequent tracking will measure improvement in effectiveness. |
| INDICATOR | BASELINE | TARGET | RATIONALE AND COMMENTS |
| The impact sought by Component 2 is stronger land and natural resources management, through community involvement |
| Impact 2.1 Turn-around and/or maintenance of the conservation status of key indicator species | The baseline will be established through the selection of two animal and two plant indicator species in each of the three project sites | Recovery or maintenance of the conservation status (as measured by viable populations) of key indicator species | This Indicator is relevant to the Outcome 3 target of improved ecosystem integrity. It can be measured through indicator species which will be selected scientifically during the inception phase of the project. |
| Impact 2.2 Number of producers organizations, women’s groups, trade and farmers’ associations and CBOs that applied improved technologies or management practices as a result of project Assistance | The baseline will be established through survey work at the Inception Phase of the project. Expected to be low, in the region of 0-5% | An increase in the numbers using improved technologies and management practices leading to at least 50% use | This Indicator is directly relevant to Outcome 4 and can be measured quantitatively by surveying and re-surveying the relevant constituents. This is an Impact Indicator, albeit on a modest scale. |
| Impact 2.3 Level of awareness, sensitivity and understanding of the value and vulnerability of natural resources | There is a certain level of awareness but it is not deep. The baseline will be established through survey at the Inception Phase | An improvement of 20-50% in awareness and understanding as measured by a repeat survey. | This Indicator measures a foundational element in the search for protection and management of biodiversity and natural resources. It is relevant to Outcomes 3 and 4, and becomes redundant if other elements are successfully put in place. |

| PROCESS INDICATORS OF PERFORMANCE (by the PMU and the project implementation teams) |
| --- |
| INDICATOR | TARGET | MEANS OF VERIFICATION |
| Project implementation aims to be participatory, achieve efficiency in the use of resources and observe UNDP’s corporate goals |
| Process 1 Participation at village level | Opportunities for participation at village level will be maximised. | Village level participants and their role in implementation planned in AWPs and recorded in PIRs |
| Process 2 Cost effectiveness | The Government contribution in kind will be utilized to keep costs to a minimum. Likewise, preference will be given to local expertise who will be engaged at a lower cost. These actions will be taken without placing the project’s success in jeopardy. | Co-financing will be tracked and recorded and reported. The PM will carry out individual staff performance assessments annually |
| Process 3 Involvement of women and youth | Implementation of the Gender and Youth Strategy as in Section 2.6 with gender considerations mainstreamed and embedded in the project implementation process. | To be measured by the ratio of women and youth participating according to AWPs and PIRs |
| Process 4 Human rights | Recognition and respect of customary rights, including the rights of traditional use. | To be measured by survey of community representatives |
| Process 5 Governance | Institutional capacity strengthening at central government and local village level leading to enhanced governance of natural resources management. | This will be covered by the various capacity building activities under the mainstream Outputs and Activities |
| Process 6 Prevention/recovery from natural disasters | Nothing that the project does will reduce The Gambia’s resilience to natural disaster. | Potential implications of the project activities on DRR will be assessed at the AWP level |

2.2.4	Project Outputs and Activities

Output 1.1  Revised PA Programme of Work and Action Plan

The Output will carry out an ecological survey and assessment of the current national PA network to record the existing situation and likely trends, determine relevant ecological/biodiversity gaps, level of representativeness, ecosystem health, status of key species, ecosystem services provided, etc.  Similarly, it will also assess the forest park estate to identify sites that merit inclusion in the PA system for biodiversity conservation purposes.  The work will be carried out by a small team of specialists working under the coordination of the DPWM and comprising expertise in forest ecology, wetlands ecology, species at risk, ecosystem services and socio-economic aspects.  Special attention will be paid to socio-economic dimensions including current land occupation, land use and likely sustainability and gender aspects, including livelihood provision.  The initial results expected under this Output will include full report/s recording the findings and proposing remedial, recovery and protective measures and initiatives on a prioritized basis.  The proposed measures and initiatives on a prioritized basis will form the core of a draft PA Programme of Work and Action Plan which will be put out for discussion.  Following this consultation period, the ultimate result from this Output, namely the Gambia Protected Areas Programme of Work and Action Plan, will be published in hardcopy and digital formats and will provide the strategic context and foundation for the rest of the project work and work for the immediate future for the DPWM.  It is therefore essential that work under this Output starts as early as possible in the project’s timescale.

Output 1.2  Gazettement of the two PA expansions (JNP expansion to connect to BBWR and expansion of KWNP)

Building on the survey and assessment work carried out under Output 1.1, work under this Output will focus on the targeted expansion of JNP to connect with BBWR (estimated to be 5,000 ha) and the expansion of KWNP to the west and east (estimated to be a total of 10,000 ha).  The work will be led by DPWM and will recruit a Working Group comprising local experts and community representatives.  Negotiations will be carried out with current land owners and land occupiers/users identified in the surveys under Output 1.1.  Criteria will be proposed, discussed and agreed for the final delineation of the new boundaries.  The criteria will include: recognition and safeguarding of valuable ecosystems and ecosystem services, dependence on natural resources for livelihoods, natural and recognizable features to serve as boundaries, etc.  The Output will carry out the cadastral survey of the agreed boundaries of the existing PAs together with the proposed extensions.  The results of the survey will be demarcated on the ground through the physical planting and nurturing (by local community members under contract) of a boundary of recognisable, valuable and useful tree species that local communities will respect and protect.  The tree specimens will be produced by the Output in special community nurseries under contract.

The Output will also build the justification case for Government to endorse the proposed expansion and provide the required expertise to draft the new decrees and develop any other legal instruments required for the formal gazettement of the modifications to the two PAs.

Output 2.1  Strengthened institutional and technical capacities in the target PAs to address existing and emerging threats

This Output seeks to put in place the capacity, mechanisms and tools necessary for the effective co-management and sustainability of the three targeted PAs (including their expansions) and their benefits for biodiversity and local communities.  The work will be led by an expert in PA management recruited by the project to lead a Working Group comprising a number of specialists with the required skills, as well as representatives of key partners and stakeholders.

The work will be organized under three main thrusts as follows:

A)  Institutional strengthening at central level by increasing human capacity

- Train DPWM central staff on all aspects of PA governance, planning, management and co-management, community liaison and negotiation in addition to compliance and performance monitoring and law enforcement

- Select and train central staff in research and monitoring of ecosystem health, biodiversity conservation and ecosystem services provision

B)  Institutional and human capacity building at community level

- Train and equip community leaders in relevant aspects of PA management to enable an equal partnership with DPWM for meaningful co-management

- Train and support selected CBOs and select individuals to effectively manage natural resources and PAs

- Develop and implement regulatory frameworks and procedural guidelines for co-management through CBNRM in selected protected areas

- Procure equipment for communities to implement CBNRM activities

C)  Technical and other capacity/facilities at the PA level

- Establish and equip Park HQ and offices for each of JNP and BBWR

- Construct and equip information/education centres for each of the three PAs

- In collaboration with relevant communities, develop Management Plans for each of the three PAs comprising clear objectives, targets and bottom lines for land and resource use including zonation and related regulations for co-management, protection and sustainable use of natural resources by local communities

- Recruit and train appropriate staff with the required technical and management capacity for planning, administration, monitoring, enforcement, community liaison, co-management, negotiation and conflict resolution

- Provide necessary equipment such as uniforms and protective clothing, mobility means (including vehicles and boats), communication equipment (hand held sets, base radios, mobiles, etc) and monitoring equipment to enable implementation of the Management Plan

- Construct and maintain access roads in PAs

Output 3.1  Biodiversity and PA aspects as well as sustainable land and natural resource management effectively mainstreamed into the large-scale National Agricultural Land and Water Management Development Project (Nema)

The Output seeks the mainstreaming of biodiversity, SLM and NRM considerations into the MoA Nema Project.  It will do this by working from within MoA and Nema by establishing a Working Group comprising leaders and other key people to be led by an outside expert recruited by the project.  After identifying and recording the benefits to the country, government and communities of such mainstreaming particularly in terms of sustainable development and enhanced livelihoods, the WG will review existing policies, legislation and procedures and identify gaps and opportunities for instilling a natural resources, land, water and biodiversity sustainability ethic into the day-to-day operations of the Ministry and Nema.  The identified opportunities will be trialled and evaluated before being written up in a guidance handbook.  The initiative will be “exported” beyond the immediate MoA and Nema confines to their stakeholders and partners, particularly local authorities, public agencies, NGOs and CBOs.  This will be done in a collaborative manner so as to achieve ownership of the approach.  The operations and key decisions of Nema will continue to be informed and assessed for mainstreaming performance by the project.  It is intended to co-locate the project with the Nema Project so as to facilitate the necessary interaction for mainstreaming.

Output 3.2  Recommended NRM and SLM practices implemented by local communities under the community-based management agreements, with extension support provided

The Community Liaison Specialist engaged by the project will advise and assist Village Development Councils to make provision for natural resources protection and management as one of their core functions.  The project will assist with the setting up of Village Environment Committees or similar groups as appropriate for participatory management of protected areas and buffer zones.  These committees will be led and coordinated by an Environment Coordinator in each village or group of villages who will be provided with training on environmental protection and management principles and methodologies, SLM and NRM.  Committees will be assisted by the project to implement protected areas management plans, monitoring (see Output 3.3 below), the use of bio-rights funds, and other instruments so as to achieve the maximum benefits with the minimum of impacts.

In pursuit of SLM, the project will work with individual landowners and farmers to experiment with innovative approaches which enhance productivity and lower the impact on land and water.  Among the approaches to be trialled will be conservation agriculture, organic farming, integrated crop  management, recycling compost and other natural fertilizer, cover crops, soil enrichment, natural pest and predator controls, bio-intensive integrated pest management, climate smart agriculture and other techniques which will arise from participatory brainstorming with community members.  The project will provide the necessary expertise and cover the costs of participatory workshops.

The project will also provide support for environment-friendly activities such as woodlots, agro-forestry and farm-border plantings, homestays and guided hiking and other ecotourism activities (wildlife viewing, safari hunting, river rafting, sport fishing, bird watching, cultural heritage, corporate retreats, boating, etc.), expansion of apiculture, possibly sericulture (silk), cultivation and processing of medicinal plants, access to early maturing and drought resistant crop varieties, tree nursery development, etc.  This assistance will be targeted in particular to those required to change land use practices (with a resulting loss in income) so as to avoid land degradation.

In support of initiatives under this Output, the project will prepare and implement environmental education programmes in schools and throughout the communities using radio, television and other mass media.

Output 3.3   A monitoring system in place in the target areas

The Output will develop, set up and initiate the implementation of an Environment Monitoring System (EMS) at the three project sites so as to record and keep up to date relevant and accurate information on the state of natural resources and socio-economic conditions and provide a basis for adaptive management decisions on PA management, land use / rural development and biodiversity protection.  The application of the EMS will extend into compliance monitoring and monitor the effectiveness of the law enforcement programme; it will help identify trends and ensure that any changes in biodiversity-important areas remain within pre-determined, acceptable limits.  Key indicator species (e.g. hippo) will be among the tools that will be used as appropriate, as will remote sensing through satellite imagery.

The EMS will be developed by a Working Group led by a Natural Resources Monitoring Expert and comprising representatives of the main providers as well as the main users of the ultimate information.  The approach and methodology to be used, the principles and objectives, and the capacity and know-how requirements will be developed. This will include modalities for involving senior school students and community members in the collection of samples and data such as through simple transects to monitor changes in vegetation physiognomy, and road strip count surveys to determine population status of large mammals.  The students and community members, who will be given appropriate training, will be under the technical guidance of the DPWM to perform this important function.  Working with the relevant authorities, the Working Group will test the EMS at selected pilot localities following training and capacity enhancements of local personnel. After implementing any necessary refinements and adjustments, the Monitoring System, will be handed over to the DPWM, after any further necessary training and capacity building.

In developing the system, the Working Group will explore the use of remote sensing together with on-ground measurements and observations, including indicator species. Among the inputs for this Output, the project will assist with the procurement of any necessary monitoring equipment and training for its use, and the implementation and evaluation of the trials at local level.  The project will also develop a handbook for ecological/biodiversity monitoring, print the handbook and distribute it in hard copy as well as DVD.

Output 4.1  Agreements with local communities secured for community-based sustainable land and natural resource management and related plans developed

The project Community Liaison Specialist will work with Village Development Councils, Village Environment Committees, Environment Coordinators (see above under Output 3.2) or equivalent at project sites, and through them with each community, so they can obtain the maximum benefit from their participation in the co-management of PAs and their adoption of sustainable land management approaches.  The initiative will also ensure the sustainability of project benefits.

Working with community representatives, the Community Liaison Specialist will draft a Heads of Agreement to serve as the basis for discussion with communities on the proposed covenant between Village Councils / Communities and the DPWM for CBNRM.  The agreement will include clauses on (a) reciprocal rights and responsibilities of the communities and the project (later the DPWM), and areas where community interventions will be implemented; (b) prescriptions for suitable biodiversity-friendly NRM and SLM practices; (c) resource-sharing mechanisms; (d) extension support; and (e) monitoring and compliance mechanisms.  The agreement will also keep in mind the need to provide income support for those negatively affected by the agreement, and this will be done by the project as described under Output 3.2 above.  Other incentives and concessions will be built into the agreement to convey a strong message that PAs and natural resources conservation are of benefit to communities.

The above activities will be underpinned by a thorough media campaign focussing on the economic and social benefits accruing from biodiversity protection, SLM and NRM. Following an extensive public discussion and consultation process seeking a consensus on the above elements, the Heads of Agreement will be reviewed and refined and enshrined into the legally-binding Covenant between Village Councils / Communities and DPWM, with the collaboration of the Department of Forestry and the MoA.

2.3	Assumptions and Risks

The following risks, identified in the PIF, have been confirmed together with their respective mitigation measures as potential threats to the project.

| RISK | SEVERITY | LIKELI-HOOD | MITIGATION MEASURES PLANNED |
| --- | --- | --- | --- |
| The Government of The Gambia fails to mobilise and allocate sufficient political will and resources to maintain the protected area system and introduce effective sustainable land and natural resource management regimes | High | Medium | GOTG has expressed its commitment to the project; the project falls within a number of its priorities, especially with regard to the promotion of SLM. GOTG only recently announced investment of $100 million in agriculture by 2020 and a share of this will be directed to sustainable practices, which will reduce the pressures on natural resources and ecosystems and the PA system. Furthermore, PA system co-management will be driven by invested local people trained by this project. The project will also construct linkages between communities and government to encourage continued budget allocations and provide institutional mechanisms for direct participation by civil society in communication of needs and requests for sufficient support. Finally, the project will build on the ongoing work of the DPWM/World Bank/GEF Gambia Biodiversity Management and Institutional Strengthening Project on financing options and mechanisms to identify possible income sources |
| Institutional programming among key agencies, ministries and other stakeholders and partners is not properly aligned, thereby undermining the coherence of agricultural/community development projects in the target areas and protected area governance in particular | Low to moderate | Low | The project will be embedded in the MoA’s large and well-resourced NEMA project, with and through which it will work in local communities on sustainable land and natural resource management. This is expected to facilitate a good coherence of this and similar large development initiatives with the project’s biodiversity / PA objectives. Mechanisms for conflict resolution will be established from the outset; the monitoring and evaluation framework will be sufficiently sensitive to determine partnership functionality |
| Participation of all key stakeholders, particularly communities, is not achieved; meaningful and effective partnerships not achieved | Low | Low | Tentative target communities have already expressed their strong interest in the project. The monitoring and evaluation framework will be sufficiently sensitive to determine partnership functionality including that with local communities; strong and supportive framework for the project management team with a meaningful M&E framework that feeds back into annual work plans |
| Livelihood dependency of resource users may be detrimental to conservation and sustainable land management actions | Moderate to high | Medium | The community-based collaborative management approach will comprehensively address the issue by specific programmatic interventions that work to maintain or improve environmental services while simultaneously identifying socially acceptable and environmentally benign income opportunities for community members. The DPWM has valuable and positive on-the-ground experience to corroborate the viability of the approach |
| Absorptive capacities in the government, especially within the lead executing agency, may be limited and will delay or hinder implementation of project activities | Moderate to high | Medium | Critical training will be provided at the onset of the project to the lead agency on the UNDP-GEF procedures, results-based management and implementation. The project is moreover expected to be embedded in the larger and well-resourced NEMA project of the Ministry of Agriculture, assuring positive synergies and opportunities for professional exchange and synergies and economies of scale |
| The diverse impacts of climate change on natural and productive ecosystems and species-level biodiversity may undermine the project objectives | Low | Low | This is an unavoidable risk, any impacts of which can only be mitigated, to the best degree possible, by integrating climate change in the planning and execution of project activities from the start. In doing so the project will build – inter alia – on the recommendations emanating of the NEA/UNEP-WCMC/GEF project Evolution of Protected Area Systems with regard to Climate Change in the West Africa Region, considering most notably (at the PA system and/or individual PA levels): adaptive planning and management in a context of growing climate-induced ecosystem changes; increasing/restoring and diversifying available habitats in preparation for ecosystem change; adapting the notion of alien species; promoting/assisting target species dispersal such as by enhanced habitat permeability and connectivity; promoting maintenance of ecosystem functions; and reducing climate change impacts through direct management measures (such as preventive fire management or manipulation of microclimates by modifying vegetation structure). In the process, the climate change resilience areas identified by this regional project will be considered in the context of PA system planning and the related ecological coverage assessment. It must be highlighted though that no country-specific risk mitigation options have to date been formulated by the project for The Gambia and that important questions remain regarding national-scale impacts of climate change and the most appropriate biodiversity adaptation measures; any new results or recommendations in this context of the NEA/UNEP-WCMC/GEF project will be considered as they emerge. At the same time, 6 of the 9 PAs in The Gambia have already included some climate change aspects in their management plans. |

Further consideration of risks will be carried out by the project during the Inception Phase.  Furthermore, the UNDP ATLAS base for this project will set up a Risk analysis and assessment system which will be reflected in the relevant section of the annual PIRs for the project.

2.4	Cost effectiveness

The cost effectiveness of this project will be ensured by the following elements that have been included in project design.

- The project approach involves the development or refinement of policies, legal mechanisms, approaches, processes and other tools at the upstream level in a participatory approach. These will then be tested at the local level, where land and natural resources are under threat, before they are rolled out for adoption nationwide. In this way, wholesale adoption of these tools and approaches will only take place after they have been tried and tested and are therefore both more reliable and more acceptable.

- The project will focus its interventions on the three localities selected because of identified values or threats of degradation. This will maximize the visible impacts and allow the beneficiary locations to act as models for the protection and management of biodiversity and natural resources nationwide.  The project will implement on-the-ground interventions in cohesive and contained localities, rather than in geographically dispersed areas, and this will reduce operational costs significantly.

- The project will place equal emphasis on assisting compliance as well as enforcement which will require less intense and less costly levels of monitoring and prosecution. This will allow the project to work effectively with local communities and stakeholders to share management responsibilities and costs, as well as to develop sustainable economic activities that can benefit these partners and generate revenue streams from wise use of natural resources. This is more cost effective than an exclusionary strategy which is likely to be unacceptable by the majority, costly to enforce and unlikely to be sustainable.

- Close coordination with on-going projects.  Some of these projects have only recently closed or are still under implementation and have accumulated practical experiences with aspects of natural resource use which are going to be invaluable for this project. While the focus on the three selected PAs is unique to this project, many of the experiences and models developed by these other projects are still relevant.  In addition, the close integration of the project with Nema will achieve further cost-savings through the co-location of the two projects, supported by targeted studies, concrete collaboration proposals and joint activities.

2.5	Expected Global, National and Local Benefits

The project will bring a number of benefits to local communities through the improved conservation of ecosystems and biodiversity in their environment.  These include food and water provision security, the retention of soils and arable land, reduced erosion, improved rice paddy farming, secure opportunities for livelihood diversification through increased tourism, maintenance of river-border tidal ecosystems with their natural resources, such as mangroves which contribute to protecting the shoreline, oyster banks and nurseries for fish populations.  Fishermen and oyster collectors will thus benefit from the protection of critical habitats, and tourism entrepreneurs will benefit from the protection of landscapes and natural resources, which depend on an effective and well maintained PA estate.  The project will build upon and complement the efforts of the Government to conserve and sustain The Gambia’s biodiversity and ecosystem services through collaboration with local communities thus improving their quality of life while protecting ecosystems and species of global significance.

Institutional strengthening and capacity building by the project will also be visible at the communities levels.

At the national level, indirect use benefits brought about by an improved conservation of ecosystems and species will include stabilisation of ecosystem services, mitigation of natural disasters including floods, carbon sequestration and soil nutrient retention.  Beyond biodiversity values, the non-use benefits of a well-managed PA system will contribute to the preservation of community values, of unique landscapes and of associated cultural heritage.  The project will leave a legacy of stronger institutions and enhanced capacities in the DPWM directly, and in the MoA and elsewhere within the government sector.  It will enhance capacity and upskill many officials and decision-makers responsible for the management of natural resources and the provision of the public good.

An important national benefit of the project is the co-management approach which better reflects the situation on the ground and the impacts caused by the communities, mostly through necessity. The project will foster better and more effective collaboration between the national government and local communities, as equal partners, for the protection and management of biodiversity and natural resources.  This can be replicated throughout The Gambia.

The direct global environment benefits of the project will include the conservation of globally important habitats and globally threatened species.  At the ecosystem level, this includes the extensive wetlands, the large swathes of mangrove forest, and the gallery forests along the River Gambia.  The global benefits of the project will also include the conservation of ecosystems that host a number of important species, including mammals which are rated as Endangered or Vulnerable in the 2004 IUCN Red List of Threatened Animals.  These include Chimpanzee (Pan troglodytes), Red Colobus (Procolobus badius) and Wild Dog (Lycaon pictus) which are considered endangered; and African Golden Cat (Profelis aurata), Lion (Panthera leo), Red-fronted Gazelle (Gazella rufifrons) and West African Manatee (Trichechus senegalensis) which are classified as vulnerable.

Additional information about endemic species is provided in section 1.2 on environmental context. It should also be noted that The Gambia is listed in WWF’s globally important Ecoregions under Tropical and Subtropical Grasslands, Savannahs and Shrublands under Guinean Forest/Savannah mosaic.  In addition, The Gambia is also mentioned as a locality for the Guinean Mangroves Terrestrial Ecoregion which stretches from Senegal to west of the Dahomey Gap.

2.6	Gender strategy

The project will adopt UNDP’s commitment to gender equality and women’s empowerment not only as human rights, but also because they are a pathway to achieving the project’s goal of protecting and managing biodiversity and natural resources on a sustainable basis.

Gender equality and women’s empowerment will be mainstreamed into project activities, ensuring that women have a real voice in project governance as well as implementation.  Women will participate equally with men in any dialogue or decision-making initiated by the project and will influence decisions that will determine the success of the project and ultimately the future of their families.

Further to the overall mainstreaming of gender equality measures into the general conduct of the project, the following table summarizes specific areas for women’s participation.

Table X.	The involvement of women in project implementation

| PROJECT ACTIVITY | INVOLVEMENT |
| --- | --- |
| Output 1.1 Revised PA Programme of Work and Action Plan | Women will serve on technical, management and advisory committees and working groups as appropriate |
| Output 1.2 Gazettement of the two PA expansions | Women will serve on technical, management and advisory committees and working groups as appropriate |
| Output 2.1 Strengthened institutional and technical capacities in the target PAs | Women will be among the PA personnel and community members to benefit from the project’s efforts in capacity building |
| Output 3.1 Biodiversity and PA aspects as well as sustainable land and natural resource management effectively mainstreamed | Women will serve on technical, management and advisory committees and working groups as appropriate |
| Output 3.2 Agreements with local communities secured for community-based sustainable land and natural resource management | The project will ensure that although its entry point to communities is the Village Development Committee, women and women’s groups are also consulted, outside the VCD structure if necessary, so as not to lead to disadvantage. |
| Output 3.3 A monitoring system in place | Women, together with other community members, will be trained to take an active part in the monitoring system |
| Output 4.1 Recommended NRM and SLM practices implemented by local communities | Women will be encouraged in women’s groups or as individuals, to benefit from the project and apply improved technologies and land management practices. They will also be specifically targeted by the project’s Alternative Income Generation scheme |

2.7	Project consistency with National Priorities/Strategies

The project will contribute to the implementation of key relevant international environmental agreements acceded to by The Gambia – most notably the Convention on Biological Diversity.  In this connection, the project is consistent with the NBSAP which calls for improved protected area management effectiveness and an increase in the total protected land area from 4.9% to 10% by 2020.

The project is also in line with other nationally formulated priorities and strategies.  Foremost among these is the Vision 2020 which sees “a well-balanced ecosystem” as fundamental to achieving the national goal of Middle Income Country status by 2020.

The Government has manifested its commitment to the realization of Vision 2020 and SLM through the promulgation of various national and sectoral policies and plans in tandem with the objectives of the MDGs.  The majority of these consider SLM as the priority tool towards alleviating poverty and achieving food self-sufficiency.   A  Roadmap for the integration of SLM, including forestry and wildlife, into national strategic frameworks includes inter-alia the wholesale submission of the action plans and their investment plans as content elements of the Vision 2020.  This is also reflected in the Poverty Reduction Strategy Paper first put out in 1994 which was succeeded by the Program for Accelerated Growth and Employment (PAGE) for 2012-2015 which aims to achieve the Millennium Development Goals on poverty reduction and environmental sustainability.

Other national instruments that the project is in harmony with, include the following:

- The Gambia Environmental Action Plan (GEAP-II, 2009-2015) which calls for “the protection of existing forest and vegetative cover… [and the]…conservation of coastal wetlands”.

- The Agricultural and Natural Resources Policy (ANRP, 2009-2015) which, amongst its four strategic objectives, lists the “Sustainable and effective management of natural resources”  and which is complemented by the Gambia National Agricultural Investment Plan(GNAIP 2009-2015) whose sustainable land management and biodiversity related interventions are coordinated under the ambit of the ANRWG at NEA.

- The National Climate Change Adaptation Plan of Action (NAPA, 2007) which recognises the need to promote and strengthen integrated management of the coastal and terrestrial zones and to preserve biological diversity and ecological assets.

- The Gambia Biodiversity Policy 2003 which arose from the NBSAP and which amongst its priorities asks to “discourage uncontrolled extension of agricultural land into …virgin forests, wetlands, marginal areas and other environmentally sensitive areas” and “develop sound grazing management system”.

The project will equally contribute towards the achievement of CBD Aichi Targets 5, 11 and 12, by increasing the coverage of the national PA system and further strengthening the management of existing PAs, and thereby reducing the loss, degradation and fragmentation of natural habitats and forests, and enhancing the conservation prospects of globally threatened species; furthermore Targets 7 and 14 by working towards more sustainable land management (agricultural and grazing/browsing practices), thereby safeguarding and restoring ecosystem services vital for local populations.

2.8	Sustainability of project results

The project has been designed to optimize the prospects for sustainability of its products and results and pave the way for replication and sustainability will be promoted through a mix of strategies, principally building on the development of a strong appreciation within government institutions of the importance of managing an appropriate PA network combined with long-term realisation of the economic and other benefits of PAs.  The close integration of biodiversity / PA activities with the Nema project will prepare the ground for integrating the challenges of biodiversity loss into agricultural development more widely.  The development of the revised PA Programme of Work and Action Plan and of the financial mechanism work under the current DPWM/World Bank/GEF Gambia Biodiversity Management and Institutional Strengthening Project is expected to help support the financing of the PA system.  The project will also adopt a highly participatory and consultative approach in the design and implementation of its sustainable resource management outputs to foster ownership over project strategies and results especially from local communities.

1.	Environmental sustainability:  This project is about environmental protection (with a focus on protected areas), and the planned interventions will ensure that biodiversity loss is turned around and that impacts are reduced, mitigated and offset as necessary, thus reducing pressures on ecosystem services and valuable natural resources many of which are of global significance. The project will raise awareness of innovative ways of getting the most benefit from land with the minimum of impact on a sustainable long-term basis.  This will change the way land is used – ensuring the compatibility of production practices with sustainable land management into the future. The sustainability of forests, wetlands, and arable lands will be assured through the mutual gains and benefits that are to be made.

2.	Institutional sustainability:  The project will influence the policies and operations of a number of government agencies responsible for biodiversity protection, primary production and land use management. The project will see tools and mechanisms developed and applied within the three target protected areas and their immediate surroundings.  At the same time, capacity will be enhanced to secure the implementation and application of the new tools and methodology. Since the new developments will be carried out with the full participation of local government, the private sector, communities, and the people who work the land, a deep sense of ownership will be generated.

The project strategy will anchor the policy and regulatory reform process in MECCWW, NEA, MoA, DoF, etc – which are responsible for various aspects of land use and natural resources planning and management.  While specifically enhancing the capabilities of these key agencies to take sustainability into account in land use planning, management, licensing, etc, the project will also strengthen the capacity of local authorities which have been empowered with administrative responsibilities for land use planning and management, and which must also regulate land use. Such a two-pronged approach is critical to ensure effective implementation of the new paradigm of sustainable land management with no impact on the broad catchment level for the long term and enhance sustainability.

3.	Financial sustainability: The project will be making the case for all stakeholders to start seeing sustainable land management as making economic as well as ecological sense.  Recognition of the economic gains that will arise from the application of SLM tools and mechanisms together with the ownership that will be achieved in the project products will lead to a protective stance from land users, and this will augur well for the sustainability of the project products, services and benefits. The participating partners have confirmed their commitment to sustain the new management measures that will be put in place under the project and which render sustainable land management as the choice land use over the longer term.  The project will also benefit from the significant level of co-funded baseline initiatives.  It will demonstrate good practice which will then be emulated by these other initiatives.

2.9	Environmental and social safeguards

UNDP procedures require projects to provide environmental and social safeguards and associated policies and procedures so as to prevent and mitigate undue harm to people and their environment and strive to develop benefits in the development process.  More specifically, safeguard policies and procedures are designed to avoid, mitigate, or minimize adverse environmental and social impacts of projects and strategies, and to implement projects and strategies that produce positive outcomes for people and the environment.

The project has been subjected to the Social and Environmental Screening Procedures (SESP) which concluded that the project has many environmental and social benefits, and possibly some impacts and risks, however, while the benefits are long-term, the negative impacts are predominantly indirect and temporary.  The full result of the screening process is in Annex X.

Protection and management scenarios for natural resources will be developed in both forest and wetland environments.  They will be enshrined in management plans which will be produced in full partnership with Village Councils and communities.  These plans (which will be founded on ecosystem and social surveys) are aimed to have long term benefits at the social and environmental levels and implementation of priority actions will be through empowerment of councils and communities.  Long-term social and environmental benefits arising from project activities are expected to be positive and beneficial.

However, there could also be temporary “negative” impacts, for example, on some land users who may be required to change land use practices so as to obtain sustainability, and on some hunters and firewood gatherers who may be required to limit their extraction activity.  The project will strive to avoid these temporary negative impacts and project design incorporates a scheme which supports ecosystem-friendly activities and promotes ecotourism initiatives to mitigate any impacts arising.

Project design has incorporated full consideration of social and environmental issues, ensuring that any limited and temporary negative impacts are outweighed by the positive and long-term benefits.

3	PROJECT RESULTS FRAMEWORK

| This project will contribute to achieving the following Country Programme Outcome as defined in CPAP: Outcome 2 – Sustainable livelihoods security enhanced for the disadvantaged groups through the promotion of income diversification opportunities and better management of environmental resources |
| --- |
| Country Programme Outcome Indicators: ????????? |
| Primary applicable Key Environment and Sustainable Development Key Result Area (same as that on the cover page, circle one): 1. Mainstreaming environment and energy OR 2. Catalyzing environmental finance OR 3. Promote climate change adaptation OR 4. Expanding access to environmental and energy services for the poor. |
| Applicable GEF Strategic Objective and Program: BD-1: Improve Sustainability of Protected Area Systems; BD-2: Mainstream Biodiversity Conservation and Sustainable Use into Production Landscapes, Seascapes and Sectors |
| Applicable GEF Expected Outcomes: ????????? |
| Applicable GEF Outcome Indicators: ?????????? |
|  | Indicator | Baseline | Targets End of Project | Source of verification | Assumptions and Risks |
| Project Objective To expand and strengthen the management of priority protected areas in The Gambia, including through enhanced community-based natural resource management | Impact 0.1 Increase in the extent of the protected estate | Current overall protected estate is 64,276 ha. At the project locality, KWNP is 11,526 ha, BBWR is 22,000 ha, and JNP is 15,028 ha | Extension of the protected estate by an additional 15,000 ha (5,000 in JNP and 10,000 ha in KWNP) making a total of some 74,276 ha protected | Formal notification of protected status | Assumptions: Risks: |
|  | Impact 0.2 Increase in the number of people who feel that they have a significant role in managing natural resources | Current level is unknown but expected to be 0% - to be confirmed by survey at inception phase | 20% by Mid-Term; 50% by end of project | Survey of a representative sample of community members at inception and repeated at MTR and TE |  |
| Outcome 1 Gazettement of a c. 5000 ha expansion of JNP to connect to BBWR, and of a c. 10,000 ha expansion of KWNP | Impact 1.1 Extent of the protected estate [similar to Impact Indicator 0.1 above] | Current overall protected estate is 64,276 ha. At the project locality, KWNP is 11,526 ha, BBWR is 22,000 ha, and JNP is 15,028 ha | Extension of the protected estate by an additional 15,000 ha (5,000 in JNP and 10,000 ha in KWNP) making a total of some 74,276 ha protected | Formal notification of protected status | Assumptions: Risks: |
|  | Outputs: Output 1.1 – Revised PA Programme of Work and Action Plan Output 1.2 – Gazettement of the two PA expansions (JNP expansion to connect with BBWR and expansion of KWNP) |
| Outcome 2 Enhanced management effectiveness in both existing and added PA areas | Impact 1.2 Enhanced level of management effectiveness | Latest METT scores are: KWNP - XX; BBWR - XX ; JNP – XX | Increase in METT scores by 10% for BBWR and KWNP and 40% for JNP | GEF BD Tracking Tools applied at MTR and TE | Assumptions: Risks: |
|  | Outputs: Output 2.1 – Strengthened institutional and technical capacities in the target PAs to address existing and emerging threats |
| Outcome 3 Improved forest cover, habitat integrity and connectivity across the targeted PA cluster and surrounding landscapes (c. 60,000 ha) | Impact 2.1 Turn-around and/or maintenance of the conservation status of key indicator species | The baseline will be established through the selection of two animal and two plant indicator species in each of the three project sites | Recovery or maintenance of the conservation status (as measured by viable populations) of key indicator species | Scientifically designed ecological survey recording population, sex ratios, age cohorts, recruitment rate, etc | Assumptions: Risks: |
|  | Outputs: Output 3.1 – Biodiversity as well as PA Aspects as well as sustainable land and natural resources management effectively mainstreamed into the large-scale National Agricultural Land and Water Management Development Project (Nema) Output 3.2 – Recommended NRM and SLM practices implemented by local communities under the community-based management agreements, with extension support provided Output 3.3 – A monitoring system in place in the target areas |
| Outcome 4 Enhanced diversity, sustainability and reliability of community livelihoods | Impact 2.2 Number of producers organizations, women’s groups, trade and farmers’ associations and CBOs that applied improved technologies or management practices as a result of project Assistance | The baseline will be established through survey work at the Inception Phase of the project. Expected to be low, in the region of 0-5% | An increase in the numbers using improved technologies and management practices leading to at least 50% use | Survey to be carried out at Inception, MTR and TE | Assumptions: Risks: |
|  | Impact 2.3 Level of awareness, sensitivity and understanding of the value and vulnerability of natural resources | There is a certain level of awareness but it is not deep. The baseline will be established through survey at the Inception Phase | An improvement of 20-50% in awareness and understanding as measured by a repeat survey. | Survey to be carried out at Inception, MTR and TE |  |
|  | Outputs: Output 4.1 – Agreements with local communities secured for community-based sustainable land and natural resources management, and related plans, developed |

4	TOTAL BUDGET AND WORKPLAN

Summary of Funds:

| SOURCES | Amount Year 1 | Amount Year 2 | Amount Year 3 | Amount Year 4 | Total |
| --- | --- | --- | --- | --- | --- |
| GEF |  |  |  |  |  |
| Donor 2 (UNDP) |  |  |  |  |  |
| Donor 3 (cash and in-kind) Government |  |  |  |  |  |
| Donor 4 (WWF) |  |  |  |  |  |
| TOTAL |  |  |  |  |  |

5	MANAGEMENT ARRANGEMENTS

UNDP Country Office

UNDP is the GEF Implementing Agency (IA) for the project which will be implemented over a period of four years and will have the Ministry of Environment, Climate Change, Water Resources & Wildlife (MECCWW) as the Executing Agency / Implementation Partner.  Other government and non-government organizations will also play important roles in implementation. The project will be executed in the NIM modality in line with the Standard Basic Assistance Agreement (SBAA) between UNDP and the Government.

As GEF Implementing Agency, UNDP Country Office (UNDP-CO) is ultimately accountable and responsible for the delivery of results through the PEB.  UNDP will provide the day-to-day oversight and quality control over project deliveries and shall provide project cycle management services that will include the following:

- Providing financial and audit services to the project

- Overseeing financial expenditures against project budgets approved by PEB,

- Ensuring that activities including procurement and financial services are carried out in strict compliance with UNDP/GEF procedures,

- Ensuring that the reporting to GEF is undertaken in line with the GEF requirements and procedures,

- Facilitate project learning, exchange and outreach within the GEF family,

- Contract the project mid-term and final evaluations and trigger additional reviews and/or evaluations as necessary and in consultation with the project counterparts.

National Project Director

The Director of the Department of Parks & Wildlife Management (DPWM) will serve as the National Project Director (NPD). The NPD will ensure continued cohesion between the project and the mandate of the DPWM and provide additional linkages and interactions with high level policy components within the Government.  In this way, the DPWM as the lead agency will be in a good position to assume responsibility on behalf of the government and follow up on, supervise and coordinate the contributions of the government. The NPD will not be paid from project funds, but will represent part of the government in-kind contribution to the project.

Among the duties and responsibilities of the NPD are the following:

- Form part of the Project Executive Board

- Serve as a focal point for coordination of the project with implementing agencies, UNDP, Government and other partners

- Ensure that Government inputs for the project are available and that project activities are in line with national priorities

- Lead and coordinate partners in the selection of the Project Manager

- Coordinate with the Project Manager and facilitate his/her work and that of all project staff

- Ensure that the required project work plan is prepared and updated and distributed to the relevant Government entities

- Represent the National Executing Agency at project meetings and annual reviews

- Lead efforts to build partnerships for the support of outcomes indicated in the project document

- Support resource mobilization efforts to increase resources in cases where additional outputs and outcomes are required

Project Executive Board

Project governance will be through the Project Executive Board (PEB) which will be convened by UNDP in consultation with the government and will serve as the project’s governance and decision-making body. The PEB, will comprise The NPD and representatives of MECCWW, UNDP, the Nema Project and other entities, such as beneficiaries, as agreed between UNDP and the Government.  The PM will also be in attendance at PEB meetings. It will meet as necessary, but not less than once every 12 months, to review project progress, approve project work plans (including budgets) and approve major project deliverables. The PEB is responsible for ensuring that the project remains on course to deliver products of the required quality to meet the outcomes defined in the project document. The PEB’s role will include: (i) overseeing project implementation; (ii) approving all project work plans and budgets, as put forward by the PM, for submission to the UNDP Regional Centre in Istanbul and the GEF Unit in New York; (iii) approving any major changes in project plans or programmes; (iv) providing technical input and advice; (v) approving major project deliverables; (vi) ensuring commitment of resources to support project implementation; (vii) arbitrating any conflicts within the project and/or negotiating solutions between the project and any parties beyond the scope of the project; and (viii) overall project evaluation.

As with other NIM projects, the project will be audited through the regular external (UN Board of Auditors) or internal audits (audits managed by UNDP’s Office of Audit and Investigations).

Technical Advisory Group

The PM will be supported by a Technical Advisory Group (TAG) which will provide advice and support on any technical aspects, in particular the reviewing and drafting of Terms of Reference and reviewing the outputs of consultants and other subcontractors.  The TAG will be made up of representatives of key implementing partners, stakeholders and beneficiaries as well as some individuals and organizations selected in recognition of their particular expertise or interest in the project.  The TAG will also include traditional rulers as representatives of relevant local adjacent communities.  Expertise sought will range from institutional, legal, policy development, land use planning, ecosystem services, biodiversity values and vulnerability, community involvement, private sector involvement, capacity building, etc.  The PM will attend TAG meetings to the extent possible. The TAG will meet as required and will be based centrally.  The TAG will regulate its own procedures but it is proposed that the Chair will be selected by consensus and will become an ex officio member of the PEB meetings (see above) to contribute technical advice.  In addition to providing advice to the PM, the TAG will also advise the PEB, and the key Implementing Partners – on request as well as on the TAG’s own initiative.  TAG members will not be paid from project funds but their contribution will be recognized as a contribution in-kind.

Project Management Unit

A Project Management Unit (PMU) will be set up to provide the day-to-day coordination and administration of the project.

The project will hire a Project Manager who will lead the PMU and report to the Project Executive Board (PEB).  He/she will work in close collaboration with the NPD to ensure cost efficient, technical and administrative project operations.  The PM is accountable to the PEB for the overall quality, timeliness and effectiveness of the activities carried out, as well as for the use of funds.

In addition to the Project Manager, the PMU will comprise the Administration and Finance Assistant (AFA), a Community Liaison Officer and the two Project Experts, one to lead the PA Team (Component 1) and one to lead the SLM Team (Component 2).  Terms of Reference for key project personnel are in Annex X.

Project staff will be recruited using standard UNDP recruitment procedures. The PM, with the support of the AFA, will assume the lead responsibility for the upstream activities and capacity elements of the project as well as provide oversight and coordination among the key Implementing Partners at the various project sites, namely, Kiang West, Bao Bolong and Jokadu.  The PM will liaise and work closely with all partner institutions to link the project with complementary national programmes and initiatives. While overall responsibility for project implementation will rest with the PMU, site-specific interventions will be supported by the relevant government technical agencies such as Ministry of Agriculture in the case of sustainable livelihood interventions, Department of Forestry in case of woodlots, habitat regeneration, tree/mangrove planting, Department of Community Development for community mobilization at project sites and Department of Fisheries for related wetlands and fisheries development matters. These technical agencies will be represented in the Technical Advisory Group (TAG).

Many outputs will require technical know-how and expertise most of which will be obtained through consultancies and contracts with individuals and companies.  Often, as described in Section 2.2.4 above, the expert will lead or coordinate a working group made up of representatives from the key stakeholders.  A list of all the delivery contracts envisaged is in Annex X.

The PM will collate the input from the key Implementation Partners and produce Annual Work and Budget Plans to be approved by the PEB at the beginning of each year. These plans will provide the basis for allocating resources to planned activities. The PM will further produce collated quarterly operational reports and Annual Progress Reports (APR/PIR) for submission to the PEB and forwarding to the UNDP/GEF. These reports will summarize the progress made by the project against the expected results, explain any significant variances, detail the necessary adjustments and serve as the main reporting mechanism for monitoring project activities.

The Project Manager will be remunerated from government contribution.

Local Advisory Committees

A Local Advisory Committee (LAC) will be set up at each of Kiang West, Bao Bolong and Jokadu. The LACs will be set up by the PM, in consultation with key local stakeholders.  Each will comprise representatives of the local Implementing Partners (Districts and Municipalities), relevant central government organizations the private sector, NGOs, communities and individuals known to possess valuable expertise. The LACs, which will be chaired by a nominee of the respective District, will perform a similar task to the central Technical Advisory Group (see above) and provide advice and support to the PM and others involved in project implementation.

The diagram on the next page is a summary of the implementation framework and relationships.

Figure X.	Project implementation and management framework

6	MONITORING FRAMEWORK AND EVALUATION

The project will be monitored through the following M& E activities.  The M& E budget is provided in the table below.

At Project start:

A Project Inception Workshop will be held within the first 2 months of project start with those with assigned roles in the project organization structure, UNDP Country Office and where appropriate/feasible regional technical policy and programme advisors as well as other stakeholders.  The Inception Workshop is crucial to building ownership for the project results and to plan the first year annual work plan.

The Inception Workshop will address a number of key issues including:

- Assist all partners to fully understand and take ownership of the project.  Detail the roles, support services and complementary responsibilities of UNDP CO and RCU staff vis à vis the project team.  Discuss the roles, functions, and responsibilities within the project's decision-making structures, including reporting and communication lines, and conflict resolution mechanisms.  The Terms of Reference for project staff will be discussed again as needed.

- Based on the project results framework and the relevant GEF Tracking Tool if appropriate, finalize the first annual work plan.  Review and agree on the indicators, targets and their means of verification, and recheck assumptions and risks.

- Provide a detailed overview of reporting, monitoring and evaluation (M&E) requirements.  The Monitoring and Evaluation work plan and budget should be agreed and scheduled.

- Discuss financial reporting procedures and obligations, and arrangements for annual audit.

- Plan and schedule Project Board meetings.  Roles and responsibilities of all project organisation structures should be clarified and meetings planned.  The first Project Board meeting should be held within the first 12 months following the inception workshop.

An Inception Workshop report is a key reference document and will be prepared and shared with participants to formalize various agreements and plans decided during the meeting.

Quarterly:

- Progress made will be monitored in the UNDP Enhanced Results Based Managment Platform.

- Based on the initial risk analysis submitted, the risk log will be regularly updated in ATLAS.  Risks become critical when the impact and probability are high.  Note that for UNDP GEF projects, all financial risks associated with financial instruments such as revolving funds, microfinance schemes, or capitalization of ESCOs are automatically classified as critical on the basis of their innovative nature (high impact and uncertainty due to no previous experience justifies classification as critical).

- Based on the information recorded in Atlas, a Project Progress Report (PPR) can be generated in the Executive Snapshot.

- Other ATLAS logs can be used to monitor issues, lessons learned etc...  The use of these functions is a key indicator in the UNDP Executive Balanced Scorecard.

Annually:

- Annual Project Review/Project Implementation Reports (APR/PIR):  This key report is prepared to monitor progress made since project start and in particular for the previous reporting period (30 June to 1 July).  The APR/PIR combines both UNDP and GEF reporting requirements.

The APR/PIR includes, but is not limited to, reporting on the following:

- Progress made toward project objective and project outcomes - each with indicators, baseline data and end-of-project targets (cumulative)

- Project outputs delivered per project outcome (annual).

- Lesson learned/good practice.

- AWP and other expenditure reports

- Risk and adaptive management

- ATLAS QPR

- Portfolio level indicators (i.e. GEF focal area tracking tools) are used by most focal areas on an annual basis as well.

Periodic Monitoring through site visits:

UNDP CO and the UNDP RCU will conduct visits to project sites based on the agreed schedule in the project's Inception Report/Annual Work Plan to assess first hand project progress.  Other members of the Project Board may also join these visits.  A Field Visit Report/BTOR will be prepared by the CO and UNDP RCU and will be circulated no less than one month after the visit to the project team and Project Board members.

Mid-term of project cycle:

The project will undergo an independent Mid-Term Evaluation at the mid-point of project implementation.  The Mid-Term Evaluation will determine progress being made toward the achievement of outcomes and will identify course correction if needed.  It will focus on the effectiveness, efficiency and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation and management.  Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.  The organization, terms of reference and timing of the mid-term evaluation will be decided after consultation between the parties to the project document.  The Terms of Reference for this Mid-term evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF.  The management response and the evaluation will be uploaded to UNDP corporate systems, in particular the UNDP Evaluation Office Evaluation Resource Center (ERC).

The relevant GEF Focal Area Tracking Tools will also be completed during the mid-term evaluation cycle.

End of Project:

An independent Final Evaluation will take place three months prior to the final Project Board meeting and will be undertaken in accordance with UNDP and GEF guidance.  The final evaluation will focus on the delivery of the project’s results as initially planned (and as corrected after the mid-term evaluation, if any such correction took place).  The final evaluation will look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental benefits/goals. The Terms of Reference for this evaluation will be prepared by the UNDP CO based on guidance from the Regional Coordinating Unit and UNDP-GEF.

The Terminal Evaluation should also provide recommendations for follow-up activities and requires a management response which will be uploaded to PIMS and to the UNDP Evaluation Office Evaluation Resource Center (ERC).

The relevant GEF Focal Area Tracking Tools will also be completed during the final evaluation.

During the last three months, the project team will prepare the Project Terminal Report. This comprehensive report will summarize the results achieved (objectives, outcomes, outputs), lessons learned, problems met and areas where results may not have been achieved.  It will also lay out recommendations for any further steps that may need to be taken to ensure sustainability and replicability of the project’s results.

Learning and knowledge sharing:

Results from the project will be disseminated within and beyond the project intervention zone through existing information sharing networks and forums.

The project will identify and participate, as relevant and appropriate, in scientific, policy-based and/or any other networks, which may be of benefit to project implementation though lessons learned. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects.

Finally, there will be a two-way flow of information between this project and other projects of a similar focus.

Communications and visibility requirements:

Full compliance is required with UNDP’s Branding Guidelines.  These can be accessed at http://intra.undp.org/coa/branding.shtml, and specific guidelines on UNDP logo use can be accessed at: http://intra.undp.org/branding/useOfLogo.html. Amongst other things, these guidelines describe when and how the UNDP logo needs to be used, as well as how the logos of donors to UNDP projects needs to be used.  For the avoidance of any doubt, when logo use is required, the UNDP logo needs to be used alongside the GEF logo.   The GEF logo can be accessed at: http://www.thegef.org/gef/GEF_logo.   The UNDP logo can be accessed at http://intra.undp.org/coa/branding.shtml.

Full compliance is also required with the GEF’s Communication and Visibility Guidelines (the “GEF Guidelines”).  The GEF Guidelines can be accessed at: http://www.thegef.org/gef/sites/thegef.org/files/documents/C.40.08_Branding_the_GEF%20final_0.pdf.  Amongst other things, the GEF Guidelines describe when and how the GEF logo needs to be used in project publications, vehicles, supplies and other project equipment.  The GEF Guidelines also describe other GEF promotional requirements regarding press releases, press conferences, press visits, visits by Government officials, productions and other promotional items.

Where other agencies and project partners have provided support through co-financing, their branding policies and requirements should be similarly applied.

M& E workplan and budget

| Type of M&E activity | Responsible Parties | Budget US$ Excluding project team staff time | Time frame |
| --- | --- | --- | --- |
| Inception Workshop and Report | Project Manager UNDP CO, UNDP GEF | Indicative cost: 10,000 | Within first two months of project start up |
| Measurement of Means of Verification of project results | UNDP GEF RTA/Project Manager will oversee the hiring of specific studies and institutions, and delegate responsibilities to relevant team members | To be finalized in Inception Phase and Workshop | Start, mid and end of project (during evaluation cycle) and annually when required |
| Measurement of Means of Verification for Project Progress on output and implementation | Oversight by Project Manager Project team | To be determined as part of the Annual Work Plan preparation | Annually prior to ARR/PIR and to the definition of annual work plans |
| APR/PIR | Project manager and team UNDP CO UNDP RTA UNDP EEG | None | Annually |
| Periodic status/ progress reports | Project manager and team | None | Quarterly |
| Mid-term Evaluation | Project manager and team UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | Indicative cost: 40,000 | At the mid-point of project implementation |
| Final Evaluation | Project manager and team, UNDP CO UNDP RCU External Consultants (i.e. evaluation team) | Indicative cost : 40,000 | At least three months before the end of project implementation |
| Project Terminal Report | Project manager and team UNDP CO local consultant | None | At least three months before the end of the project |
| Audit | UNDP CO Project manager and team | Indicative cost per year: 3,000 | Yearly |
| Visits to field sites | UNDP CO UNDP RCU (as appropriate) Government representatives | For GEF supported projects, paid from IA fees and operational budget | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses | US$ 187,000 (+/- 5% of total budget) |  |

7	LEGAL CONTEXT

This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement between the Government of Gambia and the United Nations Development Programme, signed by the parties on February 2nd, 1977. The host country implementing agency shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement.

UNDP Gambia is playing a key role on overall donor – government coordination through its Aid Harmonization Coordination Unit and its lead role in the Development Partners Coordination Group (DPCG). At the national scale, UNDP draws its interventions from the UNDAF (UN Development Assistance Framework) and the UNDP Common Cooperation Framework (CCF). Both documents support and feed into the EDPRS, which is the guiding development strategy at country level. The CCF specifically includes environment as a cross-cutting issue.

The UNDP Gambia Resident Representative is authorized to effect in writing the following types of revision to this Project Document, and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document.

The Implementing Partner (DPWM) shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The Implementing Partner (DPWM) agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

# Footnotes

For UNDP supported GEF funded projects as this includes GEF-specific requirements

Department of Parks and Wildlife Management (1998) The Gambia National Biodiversity Strategy and Action Plan.  Ministry of Agriculture and Natural Resources, Banjul.

Department of Water Resources  (2009)  National Adaptation Programme of Action (NAPA).  Government of The Gambia

Parry, et al  (2007)  Impacts, adaptation and vulnerability. Contribution of Working Group II to the Fourth Assessment Report of the Intergovernmental Panel on Climate Change.

Gambia Bureau of Statistics  (2006)  MDG Status Report.  Government of The Gambia

Sillah, J.  (2014)  Project Proposal Biodiversity Hotspots.  WWF

Sillah, J.  (2007)  Ecology and Climate Change of the Mangrove Ecosystems of Mauritania, Senegal, Gambia, Guinea Bissau, Guinea and Sierra Leone.  IUCN

Sillah, J.  (1999)  Forest Resources and Plantations in The Gambia.   FAO

Department of Parks and Wildlife Management (1998) The Gambia National Biodiversity Strategy and Action Plan.  Ministry of Agriculture and Natural Resources, Banjul.

Sillah, J.  (2013)  Fire Management in The Gambia for the Fouta Djallon Watershed Management Project.  FAO

Sillah, J.  (1999)  Action Plan on Forest and Wildlife Management, NAD-Gambia : Forest Resources and Plantations.   FAO

Department of Forests  (2010)  National Forest Assessment.  Government of The Gambia and FAO

Sillah,  J. (1999)  Forest Resources and Plantations in The Gambia.  FAO

Ministry of Agriculture  (2010)  Gambia National Agricultural Investment Plan (GNAIP).  Government of The Gambia

Sillah, J.  (2007)  Ecology and Climate Change of the Mangrove Ecosystems of Mauritania, Senegal, Gambia, Guinea Bissau, Guinea and Sierra Leone.   IUCN

Sillah, J.  (2007)  Ecology and Climate Change of the Mangrove Ecosystems of Mauritania, Senegal, Gambia, Guinea Bissau, Guinea and Sierra Leone.  IUCN

Gambia Bureau of Statistics (2014)  The Gambia 2013 Population and Housing Census Preliminary Results. Government of The Gambia

Gambia Bureau of Statistics  (2014)  Trends in Population Growth. Government of The Gambia

United Nations Development Programme  (2014)  Human Development Report 2014 - Sustaining Human Progress: Reducing Vulnerabilities and Building Resilience.  UNDP, New York

Gambia Bureau of Statistics  (2011)  Integrated Household Survey - Income and Expenditure Assessment 2010. Government of The Gambia

Government of The Gambia  (2010)  The Gambia National Agricultural Investment Plan ( GNAIP- 2011-2015). Banjul

World Food Programme  (2011)  Comprehensive Food Security and Vulnerability Analysis (CFSVA).  Banjul

United Nations Development Programme  (2011)   United Nations Development Assistance Framework (UNDAF 2012-2016).  United Nations System in The Gambia

World Food Programme (2012)   Daa Nyeeno: Food Security and Market Information Bulletin for The Gambia. Volume 2, Issue 4.   Banjul

Government of The Gambia  (1996)   Vision 2020, The Gambia Incorporated.  Banjul

These correspond to the five Administrative Regions except for the Central River Region, which is divided into two agricultural divisions Central River North and Central River South.

The Economics of Ecosystems and Biodiversity (TEEB).  See http://www.teebweb.org/resources/ecosystem-services/

Sillah, J  (2002)  Forest and Tree Management in West Africa: Evolving Approaches and Future Prospects in Gambia. USAID

Sillah, J (in press)  Integrated Financing Strategy (IFS) for Sustainable Land Management (SLM) in The Gambia.   UNCCD (draft under review)

National Environment Agency  (2010)  Gambia Environment Action Plan (GEAP) 2009 – 2010.  Government of The Gambia

Energy Division  (2004)  Energy Division Report.  Government of The Gambia

Department of Forests  (1999)  Study on Forest and Wildlife Management.  Government of The Gambia

Energy Division, op.cit.

Department of Forests,  op. cit.

Department of Parks and Wildlife Management  (2007)  Bao Bolong Management report 2007.  Government of The Gambia

Wildlife Unit  (1977)  The Banjul Declaration.   Government of The Gambia

National Environment Agency  (1997)  State of The Environment Report for the Gambia, 1997.  Government of The Gambia

Sillah, J (2014)  Natural Resources Management with Relevance to Biodiversity Degradation in The Gambia. WWF

The LogFrame is based on the general assumption that if (1) there is a meaningful extension of the protected estate; and (2) there is adequate capacity for the implementation of Protected Areas management plans; and (3) there is on-the-ground implementation of a Sustainable Land Management approach in the areas bordering the PAs, thus achieving an effective level of contiguous buffering on an ecologically viable scale;  then the Gambia landscape will be much less vulnerable to loss of biodiversity and land degradation, with significant benefits to local communities.

SMART = Specific, Measurable, Achievable, Relevant and Time-bound

Department of Parks and Wildlife Management (1998) The Gambia National Biodiversity Strategy and Action Plan (GBSAP)

The Gambia Incorporated Vision 2020

See: Republic of the Gambia (2006) Poverty Reduction Strategy 2007-2011.  International Monetary Fund

Objective (Atlas output) monitored quarterly ERBM  and annually in APR/PIR

All outcomes monitored annually in the APR/PIR.

Summary table includes financing of all kinds: GEF financing, cofinancing, cash, in-kind, etc...

See UNDP Bureau of Management (2003) Country Office Support For Effective Project Management: Working Paper #3- National Project Directors Manual

Terms of Reference for key project personnel are in Annex 7

# Text boxes

Brief Description

The aim of the project is to enhance the sustainability and effectiveness of a cluster of three target PAs, namely, Jokadu National Park (JNP), Bao Bolong Wetland Reserve (BBWR), and Kiang West National Park (KWNP), at providing protection to globally significant biodiversity in the Gambia.   This will be achieved first, by expanding and better connecting the three PAs, and emplace effective management to provide a refuge for national and globally relevant biodiversity and natural ecosystems; and, secondly – to introduce biodiversity-friendly natural resource and land management practices in communities around the three target PAs, to begin restoring vital natural resources into productive landscapes and thereby reduce the pressures local communities exert on the PA system.  In doing so, it will provide protection to an additional 15,000 ha of forest and wetland.  In addition, land and natural resource management in and around the targeted cluster of priority PAs will be strengthened through the involvement of local communities.

Total resources required           	6,144,310

Total allocated resources:		________________

- Regular:

  - GEF			1,324,310

  - UNDP (IA)		120,000

  - Government		4,500,000

  - Other			200,000

  - In-kind			________________

Total Co-financing			4,820,000

Programme Period:		              48 months

Atlas Award ID:			______________

Project ID:			5529

PIMS #				5000

Start date:

End Date

Management Arrangements		______________

PAC Meeting Date			______________

Project Executive Board ____________________________

National Project Director, MECCWW, Nema Project, UNDP, Beneficiaries reps, etc

UNDP

Energy and Environment Group at Country Office, UNDP/GEF Regional Technical Advisor

Project Assurance ____________________________

Office of the President, National Environment Agency, Min Finance & Economic Affairs

National Project Director

Technical Advisory Group ____________________________

Technical advice, problem solving, information exchange -

Min Agriculture, Forestry, Fisheries, PA Management, Village Councils

Project Management Unit ____________________________

Project Manager, Administration and Financial Assistant, Community Liaison Officer, Project Experts X2

Implementation Team One:

Upstream activities

_________________

Headed by Project Manager –

involving DPWM, Nema, NEA, MoA, MECCWW, DoF

Outputs

1.1  Revised PoWAP

1.2  Gazettement

2.1  Capacity building

3.1  Mainstreaming in Nema

Implementation Team Three:

SLM

_________________

Headed by SLM Expert –

involving MoA, Nema, Forestry, Village Councils, Communities, Farmers

Outputs

3.2  NRM and SLM

4.1  Communities

Implementation Team Two:

Protected Areas

_________________

Headed by PA Expert –

involving DPWM, Forestry, the 3 PAs, Village Councils

Outputs

1.1  Revised PoWAP

1.2  Gazettement

2.1  Capacity building

3.3  Monitoring System