## Work Plan
Annual Workplan 2021
Project Title: Support to Project Coordination and Monitoring of the United Nations Peacebuilding Fund (PBF) Projects in Guinea-Bissau
Output | Baseline/Target | Activity/Subactivity | Geographical location (city) | Expected results | Status | 2021 | [11 empty] | Responisble Party | Budget 2020 | Account n. | Commitments to date | Expenditure to date (USD) | Overall comments & Action Points [updated at the end of each month]
[6 empty] | J | F | M | A | M | J | J | A | S | O | N | D |  | UNDP |  |  |  | April | May | June
Outcome 1: The effective developpment, implementations, monitoring, oversight of peacebulding projects and the overall strategic direction of the PBF portfolio in Guinea-Bissau is ensured | [18 empty] | 269385
Output 1.1: PBF Secretariat operations are running | [18 empty] | 227805
Indicator 1.1.1: Prodoc approved in 2019 | Baseline 1.1.1: Target 1.1.1: 1 | A 1.1.1: Prepare and help to ensure approval of new Prodoc for PBF Secretariat 2022-2023 |  | Secretariat project for 2022 reflecting the Secretariat main goal dully approved by all parties involved | On-going | [13 empty] | 0 | bar: 2021 O to 2021 D
|  | Prepare the Secretariat project's annual report and share for approval |  | Annual report approved | On-track | [12 empty] | Coodinator | 0 | bar: 2021 S to 2021 O
|  | Based on annual report findings define goals, priorities and objectives for 2022/2023 |  | Elements for the new project identified | On-track | [12 empty] | All staff members | 0 | bar: 2021 O
|  | Share the draft proDoc and budget with PBSO/ RCO/UNDP for comments |  | All parties involved in the approval process | On-track | [12 empty] | Coordinator | 0 | bar: 2021 O
|  | Share the final version with RC for approval |  | ProDoc approved and financed | On-track | [12 empty] | Coordinator | 0 | bar: 2021 N
Indicator 1.1.2: Office has full complement of Staff | Baseline 1.1.2: 4 Target 1.1.2:4 | A 1.1.2: Evaluate and renew staff contracts |  | All staff members developed their performance objectives, accompanied during the year are dully appraised | Off-track | [13 empty] | 151305
|  | Set performance objectifs for each staff |  | All staff members have goals, deliverables and priorities defined | Off-track | [12 empty] | Staff Member/ Coordinator | 0 | bar: 2021 A
|  | Prepare AWP |  | Every staff member has own wp defined | Off-track | [12 empty] | Staff Member | 0 | bar: 2021 A
|  | Proceed to mid-time review |  | Goals, deliverables and priorities revisited regularly | On-track | [12 empty] | Staff Member/ Coordinator | 0 | bar: 2021 O to 2021 N
|  | Proceed to annual evaluation |  |  | On-track | [12 empty] | Coordinator/RC | 0 | bar: 2021 D
|  | Staff Salaries | [15 empty] | AFA/Coordinator | 61800 | 60000
[18 empty] | AFA/Coordinator | 56308 | 71500
[18 empty] | AFA/Coordinator | 19725 | 71400
[18 empty] | AFA/Coordinator | 13472 | 71400
Indicator 1.1.3: PBF Secretariat Staff attend approved trainings | Baseline 1.1.3: Target 1.1.3: 3 training completed | A 1.1.3:Staff Attend Approved Trainings |  |  | Off-track | [13 empty] | 31500
|  | Assess the capacity building needs |  | The training need for each staff member is identified | [13 empty] | Staff Member/Coordinator | 0 | bar: 2021 A
|  | Prepare the Secretariat annual training plan |  | The annual training plan is approved by the RC and shared with finance unit for disboursement | [13 empty] | Coordinator | 0 | bar: 2021 A
|  | Staff Members attend the training |  | Staff capacity is strenghthen | [13 empty] | Staff Member | 21000 | 72100
[18 empty] | UNDP | 10500 | 71600
Indicator 1.1.4: Office equipment are available and operational | Baseline 1.1.3: Target 1.1.4: 4 new computers by the end of 2021 | A 1.1.4:Office equipped/oprtional with purchases of equipment supplies and fuel |  |  | Off-track | [13 empty] | 45000
|  | Conduct office equipment/suplly need assessment |  | Needs identified and cotation obtained | On-track | [12 empty] | AFA/Coordinator | bar: 2021 J
|  | Share the procurment plan with Procurement Unit |  | Equipement and supllies timely bought | Partially on-track | [12 empty] | AFA | bar: 2021 A
|  | Regular follow-up with procurement unit |  | IT equipment purchased | On-track | [12 empty] | AFA | 20500 | 72200 | bar: 2021 M
|  |  |  | Office furniture replaced | On-track | [12 empty] | AFA | 9500 | 72200 | bar: 2021 M
|  |  |  | Stationery and office supply available | On-track | [12 empty] | AFA | 5000 | 72500 | bar: 2021 J
|  |  |  | Fuel and oils | On-track | [12 empty] | AFA/Driver | 10000 | 72300 | bar: 2021 M
Output 1.2: Effective project implementation, communication and coordination enabled to ensure proper Oversight, Coherence and Complementarity between Projects | [18 empty] | 26000
Indicator 1.2.1: Monthly Meetings Held | Baseline 1.2.1: 8 Target 1.2.1: 10 | A 1.2.1: Convene and facilitate monthly coordination meetings with RUNOS |  |  | Partially on-track
Indicator 1.2.2: Quality Reports Submitted by the Deadline | Baseline 1.2.2: 7 Target 1.2.2: 9 | A 1.2.2: Convene and facilitate 2 evaluation workshops per year to help RUNOS prepare Mid-year and Annual Reports |  |  | Partially on-track | [13 empty] | 2000 | bar: 2021 M; 2021 O
|  | Identifiy approriate meeting rooms and get the cotations |  | List of available meeting rooms ready to share | Partially on-track | [12 empty] | AFA/D | 0 | bar: 2021 M
|  | Follow-up with PU the selection process and the agreement signature |  | Agreement timely signed | On-track | [12 empty] | AFA | bar: 2021 M
|  | Conduct the workshop |  | Service provided | On-track | [12 empty] | M&E/Coordinator/AFA | 1333 | 71400 | bar: 2021 M; 2021 O
|  |  |  | Purchase/produce stationeries | [13 empty] | AFA | 667 | 72500
Indicator 1.2.3: UN Leadership provided quality support and documentation to make decisions | Baseline 1.2.3: Target 1.2.3: 1 update per semester | A 1.2.3: Review and support finalisation of Half-year, Annual Reports and Final Reports of RUNO projects |  |  | On-track | [13 empty] | 0
|  | Prepare the project cycle calendar ans dhare with NUNOs/RUNO's |  | Reports timely uploaded on mptfo gateway | On-track | [12 empty] | M&E | 0 | bar: 2021 J; 2021 N
|  | Provide needed support to NUNOs/RUNOs |  | Documents reviewed for submission | On-track | [12 empty] | M&E | 0
|  | Formulate 1 pager with updates to be shared with UN leadership and national autorities |  | All stakeholders updated on PB projects activities | On-track | [12 empty] | Coordinator | 0 | bar: 2021 J; 2021 N
|  | A 1.2.4: Support the development of TORs for consultants and for the Final Evaluations of RUNO projects |  |  | On-track | [13 empty] | 0
|  | Review projects ToRs for consultants |  | PBF Secretariat inputs included | [14 empty] | 0
|  | Share the TOR with PBSO for quality assurance |  | PBSO informed and inputs included | [14 empty] | 0
|  | A 1.2.5: Attend monthly UNCT meetings as requested and Senior Management retreats and provide briefs and advice on PBF and general peacebuilding issues |  |  | On-track | [12 empty] | Coordinator | 0 | bar: 2021 J to 2021 D
|  | A 1.2.6: Contribute to SG, PBC briefings and other reports and support PBC and or PBSO monitoring missions |  |  | On-track | [12 empty] | Coordinator | 12000
|  | Identify needs/support |  | Beneficiary supported | [13 empty] | Coordinator | 4000 | 72100 | 2000 | bar: 2021 F
|  | Financially support PBSO/PBC mission |  | Technical team supported | [13 empty] | PU | 8000 | 71600
|  | A 1.2.7: Hold phone meetings with PBSO as required to provide updates on Project Implementation as well as inform PBSO of the changing political context and support |  |  | On-track | [12 empty] | Coordinator | 0
|  | A 1.2.8: Participate in PBSO convened meetings on PBF management, as requested |  |  | On-track | [12 empty] | Coordinator/M&E | 12000 | 71600
|  | A 1.2.9: Coordinate PBF business with Heads of Agencies and support the coordination role of the RC in the context of peacebuilding programming, including coordinating UN submissions to GYPI, clarifying the PBF added value/ niche in Guinea-Bissau and ensuring complementarity with other support | [16 empty] | 0
|  | Coodinate PBF business with RC/O, head of agencies and government | [16 empty] | 0 | bar: 2021 A; 2021 S
Coordinate UN priority investment identification, proposal submission | bar: 2021 A
Clarify PBF added value&niche and ensure synergies
|  | Support RC coordination role |  |  | On-track | [12 empty] | Coordinator | 0 | bar: 2021 J to 2021 D
Output 1.3: Enable effective development of new project design (with appropriate emphasis on gender mainstreaming) | [18 empty] | 15580
Indicator 1.3.1: New Projects Developed |  | A 1.3.1: Design, convene and facilitate effective stakeholder consultation processes for identification of priorities to be supported by the PBF and for new project development |  |  | On-track | [12 empty] | Coordinator | 15580 | bar: 2021 A
|  | Elaborate ToR for consultation process: activities&consultant |  | Consultant hired | On-track | [12 empty] | Consultant | 6000 | 71300 | bar: 2021 M
|  | Conduct the consultation |  | Necessary stationaries supplied | [13 empty] | AFA | 2250 | 72500
|  |  |  | Travel conducted | [13 empty] | PU | 3500 | 71600
|  |  |  | All identified stakeholders consulted | On-track | [12 empty] | Coordinator | 0 | bar: 2021 M
|  | Share consultation findings and recomendation with RC/UNCT/Goverment/CSO |  | Consultation report elaborated | [13 empty] | Coordinator | 3830 | 72200
Indicator 1.3.2: New Projects have at least 30% of funds allocated to Gender Issues or support Women’s Empowerment | Baseline: Currently higher than 15% Target: 30% of project budgets dedicated to Gender Issues or suport Women’s Empowerment | A 1.3.2: Advise, support and review project proposals for submission to PBF and ensure that PBF-funded projects incorporate peacebuilding best practices and respond to PBF quality criteria. It also requires ensuring that at least 30% of the total PBF envelope is allocated to gender issues and / or support for women's empowerment |  |  | Partially on-track | [12 empty] | M&E/Coordinator
Outcome 2: The agencies implementing PBF funded projects are able to deliver on the implementation, monitoring and evaluation of effectively designed peacebuilding projects and effectively communicate the results of their interventions | [18 empty] | 220820
Output 2.1: Capacity-building of RUNOs and implementing partners enabled through tailored technical support and training | [18 empty] | 50000
Indicator 2.1.1: Number and type of training event convened | Baseline 1.1.1: Target 1.1.1: | A 2.1.1: Provide technical support (trainings) to the UN agencies, government and CSOs on formulation of Peacebuilding projects proposals and initial project implementation |  | UN Agencies, CSO and Gov skills to formulate quality proposal strenghtned | On-going | [13 empty] | 20000 | bar: 2021 A to 2021 D
|  | Conduct a need assessment survey and identify interested agencies |  | Capacity building needs identified | On-track | [13 empty] | 0 | bar: 2021 M
|  | Recruit consultant(s) |  | Consultant with relevant skills timely hired | Off-track | [13 empty] | 16000 | 71200 | bar: 2021 J to 2021 J
|  | Conduct the training |  | All interested agencies trained | Off-track | [13 empty] | 4000 | 71600 | bar: 2021 A
Indicator 2.1.2: Satisfaction with technical assistance provided | Baseline: 65% satisfaction Target: 80% satisfaction | A 2.1.2: Convene Training events in Peacebuilding Project Design, Implementation and Monitoring. Example topics include PB Mainstreaming; Innovations and cutting-edge approaches to Peacebuilding; nexus between climate change/environment, gender, and/or human rights based approaches and peacebuilding; National Reconciliation Models; Mediation skills training; Dialogue Design and methodologies; |  |  | Off-track | [13 empty] | 30000
|  | Conduct CSO, Gov capacity assessment |  | Capacity building plan elaborated | [13 empty] | Coordinator/consultants | 8000 | 71600 | bar: 2021 A
|  | Recruit consultant(s) |  | International Consultant hired | [13 empty] | PU | 8000 | 71200 | bar: 2021 M
|  |  |  | LConsultant with relevant skills timely hired | [13 empty] | PU | 6000 | 71300 | bar: 2021 M
|  | Convene trainings |  | Necessary supplies purchased | [13 empty] | AFA | 2500 | 72500
|  |  |  | All interested agencies trained on relevant thematics | Off-track | [12 empty] | Consultants | 5500 | 72200 | bar: 2021 J to 2021 A
Output 2.2: Strengthen social communication and peacebuilding advocacy: Increase awareness by national authorities, civil society and wider public of Peacebuilding Priorities and results | [18 empty] | 68400
Indicator 2.2.1: Communication Strategy developed | Baseline: 1 Target: 1 updated | A 2.2.1: Assist RUNOs and UN System with communication strategies to ensure visibility of PBF activities as well as the PBF’s visibility with print, TV, Radio and social media posts. Advance General Peace Advocacy, such as 21 September activities. SDG 16 |  | Visibility of PBF and PBF funded activities enhanced through targeted actions | Partially on-track | [13 empty] | 18000
|  | Develop and share with recipients agencies Communication Strategy for PBF funded projects |  | All activities implemented by PBF recipients timely shared with Secretariat and PBF visibility ensured | [13 empty] | M&E/Coordinator | 4000 | 72200 | bar: 2021 A to 2021 M
|  | Develop visibility strategy |  | Activities to enhance PBF visibility identified and dully implemented | [13 empty] | Coordinator/M&E | 2000 | 72500 | bar: 2021 A
|  | Prepare ToR for September 21 and international conflict resolutions day celebrations |  | PBF secretariat participates and contributes to peace&conflict resolution day celebration | [13 empty] | Coordinator | 10000 | 72100 | bar: 2021 A; 2021 S to 2021 O
[18 empty] | Coordinator | 2000 | 71600 | bar: 2021 A; 2021 S to 2021 O
Indicator 2.2.2: Facebook posts developed and posted/reposted | Baseline: 25 Target: 60 | A 2.2.2: Organize and facilitate national stakeholder meetings to ensure periodic updates on the implementation of the PBF portfolio. It includes public project presentations events to socialize new projects and/or closing projects |  |  | Partially on-track | [12 empty] | PBF Secretariat | 10000
|  | A. 2.3.4 |  | Gov aware of project activities and project implementation level | [14 empty] | 2250 | 72200
|  | Prepare periodic report to be share with local stakeholders | [16 empty] | 2500 | 72500
[19 empty] | 2750 | 72100
[18 empty] | M&E/Coordinator | 2500 | 71600
Indicator 2.2.3: Number of Knowledge Products developed. | Baseline: 0 Target: 3 | A 2.2.3:Maintain and regularly update a mapping of actors in peacebuilding and the existing gaps and programmatic entry points for project formulation identification |  |  | Partially on-track | [13 empty] | 10000
|  | Recruit consultant(s) |  | ToR ready | [13 empty] | Coordinator | bar: 2021 A
|  |  |  | Consultant with relevant skills recruited | [13 empty] | PU | 10000 | 72100 | bar: 2021 J
|  |  |  | Consultancy held | [13 empty] | Consultant | bar: 2021 J
|  | Set up the database |  | Freindly and intuitive database system in place | [13 empty] | Consultant | 0 | bar: 2021 A
|  | Establish SOP for regular updating |  | Rules established for regular updating | [13 empty] | Coordinator | 0 | bar: 2021 J
Indicator2.2.4: Number of emblemetic stories produced (video/text) | Baseline: 0 Target: 3 | A 2.2.4: Assist RUNOS in the development of stories in videos that feature emblematic stories and instructional videos that arise in implementation of projects |  | Lessons learned database set-up | [14 empty] | 15400
|  | Recruit consultancy firm |  | ToR ready | [13 empty] | M&E/Coordinator | 10500 | 72100 | bar: 2021 A
|  | Prepare script and equipment |  | Script ready | [13 empty] | M&E | bar: 2021 M
|  | Data collection mission |  | DSA timely disbursed | [13 empty] | AFA | 3500 | 71600
|  |  |  | Emblematic stories registered | [13 empty] | Firm | bar: 2021 M
|  | Development of the content and edition |  | Stories largely diffused | [13 empty] | M&E/Coordinator | 1400 | 72500 | bar: 2021 J
Indicator 2.2.5 Number of newsletters about the main PBF interventions in Guinea-Bissau produced and disseminate | Baseline: 0 Target: 2 | A 2.2.5 Develop semiannual newsletters about the main PBF interventions in Guinea-Bissau |  | Main PBF interventions in country dissiminated | [14 empty] | 15000
|  | To be included under the new Communications Strategy; Discussions with Communications focal points from recipient agencies | [15 empty] | M&E | bar: 2021 A
|  | Production/Edition of the semiannual newsletter based on texts and images shared by RUNOs to Secretariat |  | Newsletter disseminated among stakeholders | [13 empty] | M&E | 15000 | 72100 | bar: 2021 J; 2021 D
Output 2.3 Strengthen the PBF project and portfolio level monitoring and evaluation | [18 empty] | 102420
Indicator 2.3.1: % of Projects and completed log frames | Baseline: ? Target: 80% | A 2.3.1: Assist RUNO with on-going tailored technical assistance in M&E, including assistance in preparing and reviewing project results framework and M&E methodologies, ensuring their usability and coherence and looking for synergies in monitoring, data collection and analysis |  |  | Partially on-track | [13 empty] | 0 | bar: 2021 J to 2021 D
Indicator 2.3.2: # of Structures M&E | Baseline Target | A 2.3.2: Organize and conduct structured M&E visits to project sites. This can include organizing monitoring missions alone, with PBF Coordinator or with national focal point ministries to review the implementation of the PBF portfolio |  | PBF Secretariat and national focal point aware of the implementation level and project impact in the field | Partially on-track | [12 empty] | M&E | 11000
|  | Define Joint Workplan with project teams and TT |  | Joint workplan endorsed by all intervenients | [13 empty] | M&E/Coordinator | bar: 2021 A
|  | Prepare the TOR mission |  | TOR clearly defines mission objectives | [13 empty] | M&E | bar: 2021 M
|  | Conduct mission |  | DSA timely disbursed | [13 empty] | AFA | 1000 | 72300
|  |  |  | Report of mission shared with RC, head of agencies and government | [13 empty] | Coordinator | 10000 | 71600 | bar: 2021 M to 2021 J; 2021 O to 2021 N
Indicator 2.3.3: Put in place portfolio level data collection and analysis system | Baseline: 0 Target: 1 per project | A 2.3.3: Put in place portfolio level data collection and analysis methodologies, including perception surveys and community-based monitoring, as appropriate, to ensure there is higher level data and analysis on issues that the PBF aims to contribute to through its various projects |  | Portfolio level data collection system setup | Partially on-track | [13 empty] | 86420
|  | Prepare data collection and analysis methodologies strategy |  | Data to be collected, methodology, prioritary locations clearly defined | [13 empty] | Coordinator/M&E | bar: 2021 A
|  | ToR for community-based monitoring |  | CBMS identified | [13 empty] | Coordinator | bar: 2021 A
|  | ToR for consultancy ready |  | Consultancy NGO identified | [13 empty] | Coordinator | 77000 | 72100 | bar: 2021 M
|  | Missions conducted |  | DSA timely disbursed | [13 empty] | AFA | bar: 2021 M
|  |  |  | CBMS established | [13 empty] | M&E/coordinator | 9420 | 71600 | bar: 2021 M to 2021 J; 2021 O to 2021 N
|  | A 2.3.4: Put in place regular PBF project review and trouble-shooting mechanisms to ensure that implementation challenges are discovered and addressed early or reporting to UN management and PBSO for further action |  |  | On-going | [12 empty] | Coordinator
|  | Needs assessment |  |  | On-track | [12 empty] | Coordinator
|  | Letter to government to reactivate the structure | [15 empty] | RC/Coordinator | bar: 2021 A
|  | Identify members of Technical Team |  |  | Off-track | [12 empty] | Government/Coordinator | bar: 2021 A
|  | Launch |  |  | Off-track | [12 empty] | PBF Secretariat | bar: 2021 A
Indicator 2.3.5: Portfolio level evaluation conducted | Baseline 1.1.2: Target 1.1.2: | A 2.3.5: Support project evaluations and lessons learned. Includes accompanying field data collection of current and future project evaluations |  |  | Off-track | [12 empty] | M&E | 5000 | bar: 2021 J to 2021 A; 2021 D
|  | Field mission |  | DSA timely disbursed | [13 empty] | AFA | 5000
|  |  |  | Project evaluation field mission followed | Off-track | [12 empty] | M&E | bar: 2021 A to 2021 M
Project Management | [18 empty] | 42300
Rent | [18 empty] | 12740 | 73105
Common Services | [18 empty] | 6000 | 73125
Cost Recovery | [18 empty] | 6000 | 74599
IT | [18 empty] | 8000 | 72400
Car Supllies | [18 empty] | 5000 | 73410
Road taxes | [18 empty] | 1360 | 74505
Driver uniform | [18 empty] | 200 | 74530
Misc | [18 empty] | 3000 | 74500
[19 empty] | 532505 |  |  | #REF!
[19 empty] | 37275.35 |  |  | #REF!
[19 empty] | 569780.35 |  |  | #REF!
Note on U31: Guie-Aissatu Monteiro Ndjai: correct:72805

## M&E Plan
Indicators by results | Alignment with UNPAF Outcome/Output | Baseline/Target | Means of verification [method of data collection] | Data collection process [How do you expect to collect the data? Please identify key actions to be undertaken] | Data storage [Where and how do you store the data collected?] | Responsible for data collection [Institution and job title] | Data collection (D) M&E visits [Defined with stakeholders](V) | [23 empty] | Budget | Actual Expenditure
[7 empty] | 01 21 | 2 21 | 3 21 | 4 21 | 5 21 | 6 21 | 7 21 | 8 21 | 9 21 | 10 21 | 11 21 | 12 21 | 01 22 | 2 22 | 3 22 | 4 22 | 5 22 | 6 22 | 7 22 | 8 22 | 9 22 | 10 22 | 11 22 | 12 22
PBF Reporting deadlines | [11 empty] | 15 |  |  |  |  | 15 | [6 empty] | 15 |  |  |  |  | 15
External Evaluation
Outcome 1: The effective developpment, implementations, monitoring, oversight of peacebulding projects and the overall strategic direction of the PBF portfolio in Guinea-Bissau is ensured
Outcome indicator 1a: Evaluation of PBF Secretariat by UN Leadership, RUNOS, and national stakeholders |  | Baseline 1a: 65% of respondents fully or partially satisfied Target 1a: At least 75% of respondents fully or partially satisfied | Survey. One per Semester | 1-The questionnaire exists since 2019 but can be adapted to collect additional aspects 2. Submit the questionnaire before the semiannual reporting period. 3. Analyse the results and insert in the semiannual report | Data to be stored in an excel file in PBF Secretariat sharepoint | PBF Secretariat Coordinator and M&E Officer
Output 1.1: PBF Secretariat operations are running
Indicator 1.1.1: Prodoc approved in 2019 |  | Baseline: Target: 1 | PBF Secretariat documents and records/MPTFO | M&E Officer to gather information on PBF Secretariat sharepoint and MPTFO Gateway | PBF Secretariat sharepoint | PBF Secretariat Coordinator
Indicator 1.1.2: Office has full complement of Staff |  | Baseline: 3 Target: 5 | PBF Secretariat documents and records | PBF Secretariat Coordinator to keep record of all staff evaluations and renewal of contracts | PBF Secretariat sharepoint | PBF Secretariat Coordinator
Indicator 1.1.3: PBF Secretariat Staff attend approved trainings |  | Baseline: Target: 2 trainings completed | PBF Secretariat quarterly team meetings records | Information to be recorded by PBF Secretariat Coordinator on the Secretariat Sharepoint. M&E Officer to gather information and report. | PBF Secretariat sharepoint | PBF Secretariat Coordinator
Indicator 1.1.4: Office equipment are available and operational |  | Baseline: 0 Target: 4 new computers by the end of 2019 | PBF Secretariat quarterly team meetings records | Information to be recorded by PBF Secretariat Coordinator on the Secretariat Sharepoint. | PBF Secretariat sharepoint | PBF Secretariat Coordinator
Output 1.2 Effective project implementation, communication and coordination enabled to ensure proper Oversight, Coherence and Complementarity between Projects
Indicator 1.2.1: Monthly Meetings Held |  | Baseline: 8 Target: 10 | PBF Secretariat documents and records | M&E Officer to record all meetings minutes on PBF Secretariat Sharepoint | PBF Secretariat sharepoint | M&E Officer
Indicator 1.2.2: Quality Reports Submitted by the Deadline |  | Baseline: 7 Target: 9 | MPTFO/PBF Secretariat documents and records | M&E Officer to verify all reports submitted on MPTFO Gateway | PBF Secretariat sharepoint | M&E Officer
Indicator 1.2.3: UN Leadership provided quality support and documentation to make decisions |  | Baseline: Target: 1 update per semester | PBF Secretariat documents and records | Information to be recorded by PBF Secretariat Coordinator on the Secretariat Sharepoint. M&E Officer to gather information and report. | PBF Secretariat sharepoint | M&E Officer
Output 1.3: Enable effective development of new project design (with appropriate emphasis on gender mainstreaming)
Indicator 1.3.1: New Projects Developed |  | Baseline: 6 Target : 2 for 2019 and X for 2020 | MPTFO/PBF Secretariat documents and records | Information to be recorded by PBF Secretariat Coordinator on the Secretariat Sharepoint. M&E Officer to gather information on PBF Secretariat sharepoint and MPTFO Gateway | PBF Secretariat sharepoint | M&E Officer
Indicator 1.3.2: New Projects have at least 30% of funds allocated to Gender Issues or support Women’s Empowerment |  | Baseline: Currently higher than 15% Target: 30% of project budgets dedicated to Gender Issues or suport Women’s Empowerment | MPTFO/PBF Secretariat documents and records | M&E Officer to gather information on Project Documents on sharepoint and MPTFO Gateway | PBF Secretariat sharepoint | M&E Officer
Outcome 2: The agencies implementing PBF funded projects are able to deliver on the implementation, monitoring and evaluation of effectively designed peacebuilding projects and effectively communicate the results of their interventions
Indicator 2a: PBF progress toward implementation by RUNOS is On Track. |  | Baseline: 4% Target: 70% of projects are On Track | Runos' project progress reports | M&E Officer to gather information on Project Documents on sharepoint and MPTFO Gateway | PBF Secretariat sharepoint | M&E Officer
Indicator 2b: Improved PBF project monitoring systems and portfolio level data. |  | Baseline: All projects have M&E plans, but few have data collection instruments Target: New Projects have improved monitoring system with data collection instruments. | Runos' project M&E plans developed and implemented | M&E Officer to gather information on Project Documents on sharepoint and on MPTFO Gateway | PBF Secretariat sharepoint | M&E Officer
Output 2.1: Capacity-building of RUNOs and implementing partners enabled through tailored technical support and training
Indicator 2.1.1: Number and type of training event convened |  | Baseline Target | PBF Secretariat documents and records | Information to be recorded by PBF Secretariat Coordinator on the Secretariat Sharepoint. M&E Officer to gather information and report. | PBF Secretariat sharepoint | PBF Secretariat Coordinator
Indicator 2.1.2: Satisfaction with technical assistance provided |  | Baseline: 65% satisfaction Target: 80% satisfaction | Survey. One per Semester | 1-The questionnaire exists since 2019 but can be adapted to collect additional aspects 2. Submit the questionnaire before the semiannual reporting period. 3. Analyse the results and insert in the semiannual report | Data to be stored in an excel file in PBF Secretariat sharepoint | PBF Secretariat Coordinator and M&E Officer
Output 2.2: Strengthen social communication and peacebuilding advocacy: Increase awareness by national authorities, civil society and wider public of Peacebuilding Priorities and results
Indicator 2.2.1: Communication Strategy developed |  | Baseline: 1 strategy Target: 1 updated strategy | PBF Secretariat documents and records |  | PBF Secretariat sharepoint | M&E Officer
Indicator 2.2.2: Facebook posts developed and posted/reposted |  | Baseline: 25 Target: 60 | Communications and visibility monitoring tool | M&E officer to keep record of facebook posts related to PBF projects in GB | Communications and visibility monitoring tool - PBF Secretariat sharepoint | M&E Officer
Indicator 2.2.3: Number of Knowledge Products developed. |  | Baseline: 0 Target: 3 | PBF Secretariat documents and records | M&E officer to keep record of all Knowledge Products developed on sharepoint (mapping of actors in peacebuilding in GB, studies on status of social cohesion, etc) | PBF Secretariat sharepoint | M&E Officer
Indicator2.2.4: Number of emblemetic stories produced (video/text) |  | Baseline: 0 Target: 3 | PBF Secretariat documents and records | M&E officer to keep record of emblemetic stories produced related to PBF projects in GB on sharepoint | PBF Secretariat sharepoint | M&E Officer
Indicator 2.2.5 Number of newsletters about the main PBF interventions in Guinea-Bissau produced and disseminated |  | Baseline: 0 Target: 2 | PBF Secretariat documents and records | M&E officer to keep record of newsletters about PBF projects in GB on sharepoint | PBF Secretariat sharepoint | M&E Officer
Output 2.3 Strengthen the PBF project and portfolio level monitoring and evaluation
Indicator 2.3.1: % of Projects and completed log frames |  | Baseline: Target: 80% | PBF Secretariat documents and records | M&E officer to keep track and record of PBF projects on sharepoint | PBF Secretariat sharepoint | M&E Officer
Indicator 2.3.2: # of Structures M&E Number of monitoring visits to projects sites |  | Baseline: 0 Target: 4 (2 per semester) | PBF Secretariat documents and records | M&E officer to record all PBF visits on sharepoint | PBF Secretariat sharepoint | M&E Officer
Indicator 2.3.3: Data collection methodologies in place and being analyzed and reported |  | Baseline: 0 Target: 1 per project | PBF Secretariat documents and records | M&E officer to keep track and record all PBF projects M&E Plans on sharepoint | PBF Secretariat sharepoint | M&E Officer
Indicator 2.3.4: Portfolio level evaluation conducted Number of project evaluations finalized |  | Baseline: 0 (2020) Target: 6 project evaluations. | PBF Secretariat documents and records | M&E officer to keep track and record all PBF project evaluations on sharepoint | PBF Secretariat sharepoint | M&E Officer
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indicators are typically taken directly from the Results Framework of the PRODOC, but should be checked in the process to ensure they are SMART (specific, measurable, achievable, relevant, and time-bound). Often, the indicator may need to be revised upon closer examination and according to field realities. If this is the case, be sure any revisions are approved by key stakeholders beforehand, including the PBF Secretariat Reply: Specify if indicators should be disaggregated by gender, age, location, as much as possible.
Note on B1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Currently on hold
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Taken directly from the Results Framework of the PRODOC
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example: Surveys, in-depth Interviews, participants' evaluations, attendance sheets, documents and records, focus groups discussion...
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Be specific and provide details, such as the sampling method, survey type, etc. This column should also indicate whether data collection tools (e.g. questionnaires, checklists) are pre-existing or will need to be developed. For example: "data collection requires WFP to work with INE to design and administer a household survey in Bissau, analyse results, write, validate and disseminate fidings. Data will be collected for baseline and endline purposes."
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For example, will it be stored in a spread sheet, database, hard copies? And where will it be stored?
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: List the people responsible and accountable for the data collection and analysis, e.g., community volunteers, project managers, local partner/s, and external consultants. Use the position title to ensure clarity in case of personnel changes. For example: "UNDP Project Manager" or "External Consultancy to be recruited by WFP"
Note on A28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: http://www.nickmilton.com/2018/01/what-is-knowledge-product.html
Note on A33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the Prodoc was "# of Structures M&E" but we suggested to change in the NCE