SECRETARY-GENERAL’S PEACEBUILDING FUND

PBF PROJECT PROGRESS REPORT TEMPLATE

PBF PROJECT progress report

COUNTRY: GUINEA-BISSAU

TYPE OF REPORT: semi-annual, annual OR FINAL ANNUAL

date of report: 13/11/2019

| Project Title: Supporting Political and Institutional stabilization of the Justice sector for peace consolidation in Guinea-Bissau Project Number from MPTF-O Gateway: 00108261 |  |
| --- | --- |
| PBF project modality: IRF PRF | - If funding is disbursed into a national or regional trust fund: Country Trust Fund Regional Trust Fund - Name of Recipient Fund: |
| List all direct project recipient organizations (starting with Convening Agency), followed type of organization (UN, CSO etc): UNDP; UNICEF. List additional implementing partners, Governmental and non-Governmental: Ministry of Justice and Human Rights; Public Prosecution Service; Supreme Judicial Council; Ministry of Interior; National Committee for the Abandonment of Harmful Practices to Women and Child; Women and Child Institute; Religious Associations; Associations of Traditional Leaders; Voz di Paz/ Interpeace; Etc. |  |
| Project commencement date: 01/01/2018 Project duration in months: 28 months |  |
| Does the project fall under one of the specific PBF priority windows below: Gender promotion initiative Youth promotion initiative Transition from UN or regional peacekeeping or special political missions Cross-border or regional project |  |
| Total PBF approved project budget* (by recipient organization): UNDP : $ 836.740,00 - UNICEF : $ 570.160, 00 - : $ - : $ - Total: 1.406.900 USD - *The overall approved budget and the release of the second and any subsequent tranche are conditional and subject to PBSO’s approval and subject to availability of funds in the PBF account - How many tranches have been received so far: 1 |  |
| Report preparation: Project report prepared by: Cátia Rodrigues Project report approved by: Oumar Diallo Did PBF Secretariat clear the report: Yes Any comments from PBF Secretariat on the report: Has the project undertaken any evaluation exercises? Please specify and attach: |  |

NOTES FOR COMPLETING THE REPORT:

- Avoid acronyms and UN jargon, use general / common language.

- Be as concrete as possible. Avoid theoretical, vague or conceptual discourse.

- Ensure the analysis and project progress assessment is gender and age sensitive.

PART 1: RESULTS PROGRESS

  - Overall project progress to date

Briefly explain the status of the project in terms of its implementation cycle, including whether all preliminary/preparatory activities have been completed (1500 character limit):

As ADR (Alternative Dispute Resolution) mechanisms and RJ (Restorative Justice) practices are new concepts in Guinea-Bissau, the project implementation has been requiring time and thorough preparation. To ensure full participation of stakeholders from both formal and traditional justice systems precise explanations and contextualization had to be programmed. Thus, the first year was mostly dedicated to share the concepts and set the grounds for the implementation: drafting and publishing ToRs, discussing the topics with CSOs and finalizing their micro-projects to be supported under the project. Sensitizations, discussions and awareness raising meetings were also organized to that end. Moreover, delays due to the electoral campaign have played a part in the generalized project implementation during the period November-March. Nevertheless, almost all activities under Output 1 and 2 have been finalized. And mostly only activities under Ouput 3 still need to be implemented. The project has now entered its last stage. Since the last report the following activities have been implemented: the RJ trainings (A1.1.4 and A1.2.3); the ADR trainings (A1.1.4 and A1.2.3); the Mediation draft-law (A1.1.3); the second international conference on RJ and ADR (A1.1.1); sensitization of traditionl and formal justice system actors (A1.1.4 and A1.2.2). Progress has also been made with regards to the selection and finalization of contracts for future consultancies.

Considering the project’s implementation cycle, please rate this project’s overall progress towards results to date:

In a few sentences, summarize what is unique/ innovative/ interesting about what this project is trying/ has tried to achieve or its approach (rather than listing activity progress) (1500 character limit).

This project is innovative and unprecedented as it aims to get all national justice actors to reflect and adopt a new model for conflict management and resolution - based on ADR mechanisms and RJ values and practices - to overcome the inefficiencies of the justice sector and ensure access and delivery of justice quality services to the population. Despite constraints and inefficiencies in the formal and traditional justice systems, both are used by the Bissau-Guinean population, and co-exist. Nevertheless, there is neither a functional mechanism of cooperation envisaging both sides nor a legal framework that sets the pace for it. Thus, through the development of more specific and oriented legal frameworks, and, ultimately, of a mechanism for its implementation, based on experiences gathered through South-South cooperation, the project is playing an important role in peace promotion and consolidation in Guinea-Bissau.

In a few sentences summarize major project peacebuilding progress/results (with evidence), which PBSO can use in public communications to highlight the project (1500 character limit):

The project has had a significant peacebuilding effect, as it helped sensitizing different national actors on ADR mechanisms and RJ values and practices - opening the ground for its institutionalization in Guinea-Bissau. It has placed these topics - these alternative approaches to improve justice application and delivery to reduce impunity nationwide - in the minds of key stakeholders and the national agenda. Furthermore, these alternatives approaches have inspired the national authorities, resulting in a national commitment towards assuming importance of the CAJ (Legal Aid Centres) and the possibility of transforming it into a Public Defensorship - which in a fragile country like Guinea-Bissau is a major peacebuilding effect and indicator. ADR and RJ focus offers an alternative, more comprehensive and more holistic and humanistic approach to justice reform instead of the punitive model that prevails in the formal justice system in Guinea-Bissau, one that is more promissing for sustainable peace. The Mediation Draft-Law was finalized and the Child Protection Code, an important element to strengthen the child protection system, has progressed during the reported period. More 22 institutions working on CP, have approved the last draft of the Code, in two technical seminars. The active participation of traditional and religious leaders was essential. The PBF project is the main support for the results achieved so far in this long-term work, which started in late 2016.

In a few sentences, explain how the project has made real human impact, that is, how did it affect the lives of any people in the country – where possible, use direct quotes that PBSO can use in public communications to highlight the project (1500 character limit):

The project has made real human impact as it allows the Bissau-Guineans to reflect about the kind of justice that is more likely to bring peace to the country and provide additional avenues to pursue justice beyond the punitive model. Most judicial actors had limited knowledge of these concepts and mechanisms - different conceptualizations of justice -, which can truly improve their work and significantly impact society as a whole in a positive manner. The project has been sensitizing top traditional authorities and magistrates to updated models of justice reforms that are more appropriate to the national context. Also, the public is now more aware of their own rights and the importance of engaging women in justice processes, namely in RJ practices and ADR mechanisms, for social peace and progress; and of the impact of nefarious practices affecting women and girls, and how it violates international human rights conventions, which have been inclusively ratified by Guinea-Bissau.

It has also brought to the national agenda the need to reflect on new justice concepts, mechanisms and to improve the population's access to it and make use of ADR mechanisms to solve conflicts. This proves particularly important in a country like this one where the formal justice system is congested and works with severe limitations and the traditional justice system also presents bottlenecks and inefficiencies, often disregarding human rights, especially those relating to women and children.

If the project progress assessment is on-track, please explain what the key challenges (if any) have been and which measures were taken to address them (1500 character limit).

If the assessment is off-track, please list main reasons/ challenges and explain what impact this has had/will have on project duration or strategy and what measures have been taken/ will be taken to address the challenges/ rectify project progress (1500 character limit):

The project envisions the introduction of a new concept of justice in a traditionally conservative and backwards environment. As expected, it has met wide resistance amongst key actors, – both from the traditional and formal systems - because, from the viewpoints of these actors, these changes imply a certain level of "power loss" for each of them. In order to overcome these challenges, the project has been focusing in orchestrating several meetings and discussions between key actors in order to effectively open way for the implementation of activities and ensure their success – so that these are not boycotted. This has posed certain delays in the implementation of activities, and consequently on the achievement of outputs, as its preparation needed to be conducted in a very cautious manner. Through stimulating and promoting dialogue and cooperation between all relevant parties, even with regards to simple issues, the project has been having an enormous impact in attenuating the existent distrust and rivalry between actors from both systems - especially outside Bissau - as well as in finding and opening adequate ways to the creation and implementation of the functional mechanism of cooperation between formal and traditional justice actors. Other challenges that have imposed delays in the implementation relate to the continued political instability; and partners having been involved in election and thus unable to work on the implementation of their activities.

Please attach as a separate document(s) any materials highlighting or providing more evidence for project progress (for example: publications, photos, videos, monitoring reports, evaluation reports etc.). List below what has been attached to the report, including purpose and audience.

  - Result progress by project outcome

The space in the template allows for up to four project outcomes. If your project has more approved outcomes, contact PBSO for template modification.

Outcome 1:  The population benefits from enhanced access to justice through strengthened Alternative Dispute Resolution (ADR) systems within informal and formal justice systems, and a strengthened interface between both systems, in line with international standards of administration of justice and human rights

Rate the current status of the outcome progress:

Progress summary: Describe main progress under this Outcome made during the reporting period (for June reports: January-June; for November reports: January-November; for final reports: full project duration), including major output progress (not all individual activities). If the project is starting to make/ has made a difference at the outcome level, provide specific evidence for the progress (quantitative and qualitative) and explain how it impacts the broader political and peacebuilding context. Where possible, provide specific examples of change the project has supported/ contributed to as well as, where available and relevant, quotes from partners or beneficiaries about the project and their experience. (3000 character limit)?

The project was launched in January 2018 in a context of political and institutional instability that characterized Guinea-Bissau's past year. A new government was only sworned-in at the end of April 2018 and was meant to exercise functions until the following legislative elections, planned for 18th November 2018. However, due to several factors, elections ended up being postponed – from 18th November 2018 to 10th March 2019. Apart from these conjunctural factors, another important aspect that has imposed delays in the project implementation relates to the difficulties in mobilizing Portuguese speaking experts on ADR and RJ from institutions from relevant partners countries, through the South-South cooperation, to come to Guinea-Bissau to conduct key activities due to the political instability in the country. For this reason, the project had to change its strategy in terms of methodology and approach mid-course, thus  launching consultancies to provide the trainings: one on ADR and the other one on RJ.

Having overcame these challenges, all activities are now under implementation. The project is on full-speed and most activities are already completed (A1.1.1, A1.1.2, A1.1.4, A1.1.5, A1.1.6, A1.2.2, A1.2.3), while others are under the last stages of implementation A1.1.3, A2.1.1 and A1.2.4. Experts to implement activities programmed under Ouput 3 have already been selected and contracted. The first team will start working on the Traditional Justice Framework (A1.3.2) in November/ December homebased and whill conduct field work on January. The experts selected to design the cooperation mechanism between the traditional and formal justice sector (A1.3.1) have been selected, contracts are finalized and they will be starting the consultancy early January. Consultants selected to draft the Capacity Building Plan of Traditional Justice Actors have been contracted and will be swiftly mobilized and deployed. An international consultant has also been selected to provide mid-level training on mediation and conciliation techniques to traditional and formal justice system actors and develop a training manual. This consultancy will take place from January until March and will integrate aspects of the Mediation draft-law - part of the exit strategy.

PBF project intervention has contributed to social norms and behavior change affecting women, children and girls’ rights, by continuing partnerships to ensure that communities and families prevent all forms of violence and abuse against children, in particular girls. The success of these interventions was reinforced with the participation of community leaders and influent community members. 135 community child protection committees in 5 regions and 10 regional dialogue safe spaces (ERD), involving 100 influent community men and women (ten per region). The ERDs have supported 170 cases of conflicts, including cases involving children and women, with the participation of community authorities and justice sector.

Outcome 2:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 3:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

Outcome 4:

Rate the current status of the outcome progress:

Progress summary: (see guiding questions under Outcome 1)

  - Cross-cutting issues

| National ownership: How has the national government demonstrated ownership/ commitment to the project results and activities? Give specific examples. (1500 character limit) | The Ministry of Justice and Human Rights has been on the frontline of the project implementation with the support of UNDP and UNICEF. It has been involved in meetings and planification and its suggestions have been mainstreamed in the activities. Its has also provided inputs to the published ToRs and selection of beneficiaries. Its staff played a role in the planification and implementation of activities. Moreover, the project was validated by the the Justice and Human Rights Working Group and its implementation is often discussed at this meetings. The project is consistent with the government's Justice Reform Plan and has proved essential to implementation and success. |
| --- | --- |
| Monitoring: Is the project M&E plan on track? What monitoring methods and sources of evidence are being/ have been used? Please attach any monitoring-related reports for the reporting period. (1500 character limit)? | A Monitoring and Evaluation Plan has been developed and the implementation has been monitored and planned monthly. The Thematic Working Group, which is the mechanism used by the Ministry of Justice and Human Rights to monitor the implementation of projects contributing to the Justice Reform, is also an important project monitoring mechanism as it meets regularly and discusses issues in an inclusive and participatory manner. Also, through the joint meetings between UNDP and UNICEF both agencies have been planning and closely following-up the implementation of activities. Project IPs, such has NGO Interpeace, social assistants form the justice sector (working in the regional courts), judiciary police and the National Committee for the Abandonment of Harmful Practices, have improved their monitoring frameworks and are submitting in a regular basis data and information on cases of violence - both on referred and managed cases. |
| Evaluation: Provide an update on the preparations for the external evaluation for the project, especially if within last 6 months of implementation or final report. Confirm available budget for evaluation. (1500 character limit) | Not applicable. Evaluation is planned to take place at the end of the project after all activities have been fully implemented. |
| Catalytic effects (financial): Did the project lead to any specific non-PBF funding commitments? If yes, from whom and how much? If not, have any specific attempts been made to attract additional financial contributions to the project and beyond? (1500 character limit) | N/A. The RJ and ADR concepts are still new for many donors. Besides it will take time to show the kind of results which will garner the attention of donors. However, it is already visible the transformative effects the project is having on the ground. Once fully understood and grasped, ADR and RJ having been bringing actors together with the aims of taking justice further to ensure social peace and security in Guinea-Bissau. We anticipate that after this project there will be room to captivate other donors to continue support for ADR and RJ as it impact in the country is evident - specially given the weak presence of justice formal institutions out of the capital. |
| Catalytic effects (non-financial): Did the project create favourable conditions for additional peacebuilding activities by Government/ other donors? If yes, please specify. (1500 character limit) | ADR mechanisms and RJ practices have been recognized as valuable approaches to justice. An indicator for this relates to the fact that after 7 years of UNDP subsidizing the legal aid officer's salaries, the Government - despite its well-known financial difficulties - has finally took it on. Also high-level discussions are taking place to review the status of GICJU/ CAJ and the possibility of transforming it into a Public Defensorship. This is a very important catalytic effect that before this project was unthinkable. Moreover the project is highlighting the importance of traditional justice actors in the country and how much these still matter for peace and stability in Guinea-Bissau. |
| Exit strategy/ sustainability: What steps have been taken to prepare for end of project and help ensure sustainability of the project results beyond PBF support for this project? (1500 character limit) | The sustainability of the project rests in the appropriation of a more nuanced understanding of justice by judicial actors. The project will leave behind legal frameworks and mechanisms that will help ensuring women and children's protection and enable the institutionalization of ADR mechanisms and RJ practices that will allow for a more responsive judicial system. The project will legitimize the role of traditional justice providers, ensuring that conflicts are addressed at the lowest level and are not elevated unnecessarily to the formal justice system. Thus it will reduce congestion of the formal justice system and empower communities. This will enhance social cohesion. Moreover, the majority of activities will be continued and consolidated through the Joint Programme and the new project "Placing Women at the Centre of Justice Reform". |
| Risk taking: Describe how the project has responded to risks that threatened the achievement of results. Identify any new risks that have emerged since the last report. (1500 character limit) | Cooperation and communication between actors from the traditional and formal justice systems is highly challenging. There is mistrust and rivalry between them, and both sides tend to discredit one another instead of assuming that both have bottlenecks and shortcomings, thus needing to be further developed and contextualized to offer proper solutions to the population's needs. In this sense, the project has been investing primerly in the promotion of communication and dialogue between both sides, stimulating and securing trust before proceeding to the implementation of core activities. By providing trainings for both, first separately and afterwards bringing them together, we are ensuring a fertile ground for honest dialogue and understanding. There is also difficulty in mobilizing traditional leaders and authorities that speak other than local languages. This has been difficultating the mobilization of expertise for the trainings. In order to mitigate this constraint, the project has been involving national consultants in activities - to, amongts other tasks, facilitate translation from portuguese to Bissau-Guinean creole -, and has been relying on existing contacts to move forward. |
| Gender equality: In the reporting period, which activities have taken place with a specific focus on addressing issues of gender equality or women’s empowerment? (1500 character limit) | Gender considerations, especially in terms of women's participation and, whenever possible, disclosure of specific subjects that directly impact women and girls are always mainstreamed in project actions and activities. While preparing the workshops/conferences/trainings, special emphasis is given to the importance of having women participating and presenting their work, thoughts and suggestions - contributing to enriching the debates. Moreover, several presentations given throughout the project had a particular focus on the importance of fostering gender equality and respect for women and girls in order to consolidate peace and security and ensure inclusive development in the country. Also, the analyses conducted by NGOs Interpeace and Voz di Paz, in three country regions, to assess how traditional justice addresses violence against children and women has provided important evidence showing that an important work needs to be done among traditional rulers to ensure that human rights are mainstreaming in their approaches to solve community issues involving children and women. |
| Other: Are there any other issues concerning project implementation that you want to share, including any capacity needs of the recipient organizations? (1500 character limit) | After 18 months working with UNDP, UNICEF and the Ministry of Justice and Human Rights for the project implementation, the UNV Project Officer has recently left the post and Guinea-Bissau. It will be essential to find a replacement as soon as possible in order to ensure proper implementation and project closure in accordance with the schedule agreed with PBF under the project extension. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document or any amendments- provide an update on the achievement of key indicators at both the outcome and output level in the table below (if your project has more indicators than provided in the table, select the most relevant ones with most relevant progress to highlight). Where it has not been possible to collect data on indicators, state this and provide any explanation. Provide gender and age disaggregated data. (300 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 The population benefits from enhanced access to justice through strengthened alternative dispute resolution systems within informal and formal justice systems, and a strengthened interface between both systems, in line with international standards of administration of justice and human rights | Indicator 1.1 Access to and quality of justice of traditional monitored | no survey | 1 survey | 0 | Planned for 2020 through another PBF funded project (Placing Gender at the Centre of Justice Reform in Guinea-Bissau) | N/A |
|  | Indicator 1.2 Quality and frequency of communication between formal and informal justice providers improved | no formal communication mechanism | 1 formal communication mechanism | 0 | Planned for 2020 thorough the consultancy under A.3.2 | N/A |
|  | Indicator 1.3 |  |  |  |  |  |
| Output 1.1 ADR and Restorative Justice Practices in the Formal Justice system legitimized with particular attention to Women and Child Rights | Indicator 1.1.1 Awareness meetings/forums held, and number and type of stakeholders reached | 4 types of stakeholders | 8 types of stakeholders | over 8 types of stakeholders | Took place according to the initial implementation calendar and envisaged over 8 types of stakeholders. 3 main events were held in this specific activity: first international conference on RJ; second international conference on RJ and ADR; and workshop for the validation of INDEP. | N/A |
|  | Indicator 1.1.2 ADR/RJ Law for the Formal Justice Sector drafted | No | Yes | 1 | Activity has already taken place and the Draft-law for Mediation already exists. | N/A |
| Output 1.2 Key Stakeholders in traditional justice sector have increased capacity to engage in ADR and RJ in compliance with Women and Children's Rights | Indicator 1.2.1 Dispute Resolution decisions around child issues mapped | No | Yes | 0 | Final script already submitted anand approved after initial improvements. It is now pending printing for future presentation and dissimination amongst stakeholders in Guinea-Bissau. | N/A |
|  | Indicator 1.2.2 Awareness meetings/forums held, and number of stakeholders reached | 4 types of stakeholders (regulados, judges, law students, prosecutors) | 8 types of stakeholders (regulados, judges, law students, prosecutors) | over 8 types of stakeholders from 6 regions (Cacheu, Gabu, Tombali, SAB, Oio and Quinara) | UNICEF together with partners have worked at the community level to promote child and women’s rights and ensure that dispute resolutions comply with child's rights. Interpeace and VdP also worked to increase respect for human rights, specially women and child's rights, on meditions at local level. | N/A |
| Output 1.3 The collaboration/complementarity between formal and traditional justice system is effective | Indicator 1.3.1 Functional mechanism of cooperation between formal and informal justice actors existing | No | Yes | 0 | Planned for January 2020. Consultants have already been selected and are awaiting for deployment in the field. | N/A |
|  | Indicator 1.3.2 Law on Collaboration/complementarity between Traditional and Formal Legal System drafted | No | Yes | 0 | Planned for December 2019. Consultants have already been selected and are awaiting for deployment in the field. . | N/A |
| Output 1.4 | Indicator 1.4.1 |  |  |  |  |  |
|  | Indicator 1.4.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
|  | Indicator 2.3 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Output 2.4 | Indicator 2.4.1 |  |  |  |  |  |
|  | Indicator 2.4.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
|  | Indicator 3.3 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Output 3.4 | Indicator 3.4.1 |  |  |  |  |  |
|  | Indicator 3.4.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
|  | Indicator 4.3 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |
| Output 4.4 | Indicator 4.4.1 |  |  |  |  |  |
|  | Indicator 4.4.2 |  |  |  |  |  |

PART 2: INDICATIVE PROJECT FINANCIAL PROGRESS

  - Comments on the overall state of financial expenditures

Please rate whether project financial expenditures are on track, delayed, or off track, vis-à-vis project plans and by recipient organization:

How many project budget tranches have been received to date and when do you expect to request the next tranche if applicable: To date, only 1 budget tranche has been received. The next disbursement request will be submited in December.

What is the overall level of expenditure/ commitment against the total budget and against the tranche(s) received so far: The overall expenditure level of UNDP is 498,563.43 USD out of a total of 585,718.00 USD; while UNICEF's is 329,588.04 USD from a total of 399,112.00 USD.

If expenditure is delayed or off track, please provide a brief explanation (500 characters limit): Conjunctural factors, namely the political instability that has engulfed the country in the past years, together with the fact that ADR mechanisms and RJ practices are highly innovative and challenging concepts for the Bissau-Guinean context, have imposed delays in the overall project implementation. It requires time to properly discuss it with local actors, so that they can understand their roles in these processes and how it fits into the local context and contributes to its progress.

Please state what $ amount was planned (in the project document) to be allocated to activities focussed on gender equality or women’s empowerment and how much has been actually allocated to date: The project planneded to allocate 272,582.50 USD (44.2% of total amont for output 1.1 and 43.8% of total amount for output 1.2), out of a total of 657,700 USD (output 1.1, 1.2 and 1.3), for gender equality and empowerment. To date, the project has been able to allocate a total of 224,225.88 USD for direct actions focused on GEWE, 82% of the total amount budgeted.

Please fill out and attach the project document Excel budget Annex showing current project financial progress (expenditures/ commitments to date), using the original project budget table in Excel, even though the $ amounts are indicative only.

Note: commencement date will be the date of first funds transfer.

Maximum project duration for IRF projects is 18 months, for PRF projects – 36 months.