## Sheet1
UNDP | [19 empty] | PROCUREMENT ACTION PLAN
| Data to be provided/completed by Programme/Project | [12 empty] | Information to be updated by Procurement/Operations Team
| Project Nme | Project ID | Type of Supply | High Level Categorizaton | Description of goods, services or works | Unit of Measure | Quantity/ Duration | Estimated Unit Price in USD | Estimated Total Price in USD | Available budget in USD | EstimatedCompletion of Activity | Responsible authorities | Comments | Requisition Docs Ready |  | Issue of Expression of Interest (EOI) /Notification |  |  |  |  | Solicitation Document | [5 empty] | Evaluation of Proposals |  |  | Committee Review/Approval |  |  |  | Contract Issuance
No | [13 empty] | Date | By | DATE | UNDP Web | UNGM | Local Paper | Int.Paper /Media | Issue Date | Deadline for Receipt | Duration (days) | RFQ | RFP | ITB | Single Stage | Two stage | Two stage with Combined Weights | CAP Members receive submission | CAP Meeting Date | Submission to ACP | ACP`s /CPO s approval | Date of Issue | PO | Inst. Contr. | Works | Profes. Serv. | Publ. Transl | Publication | Reprinting | Security | Travel | Other
1 | SE4ALL | 98972 | IC | Human Resources Services | International Consultant specialized on RE policies formulation (Legal framework and action plan) | Qty | 2 | 15000 | 30000 | 30000 | July-30 | Kisito Domingo | UNDP Catalogue |  |  | 2005-02-02 |  |  |  |  | 2005-02-12 | 2005-03-14 | 32 | [6 empty] | 2005-03-12 | 2005-03-12 | 2005-03-12 | 2005-03-12 | 2005-03-12
2 | SE4ALL | 98972 | IC | Human Resources Services | International Consultant specialized on RE policies formulation (Innovative Investment Plans ) | Qty | 1 | 20000 | 20000 | 27720 | July-30 | Kisito Domingo | Non-UNDP Catalogue
3 | SE4ALL | 98972 | IC | Human Resources Services | National Consultant (mini-hydropower and solar expert) | Qty | 2 | 7500 | 15000 | 15000 | July-30 | Kisito Domingo | 2 UNDP Catalogue and 3 Non-UNDP-Catalogue
4 | SE4ALL | 98972 | Services | Office Supplies | Workshop | Qty | 2 | 5000 | 10000 | 15000 | July-15 | Kisito Domingo | UNDP Catalogue
5 | SE4ALL | 98972 | Services | Human Resources Services | International Consulting Firm for hydropower production potential assessment and feasibility studies | Working days | 90 | 1711 | 153990 | 154000 | Aug-30 | Kisito Domingo | UNDP Catalogue
6 | SE4ALL | 98972 | Goods | Motor Vehicles | Vehicles 4x 4 | Amount | 2 | 45000 | 90000 | 100000 | May-30 | Kisito Domingo | UNDP Catalogue
| SE4ALL | 98972 | Services | Human Resources Services | Internatinal Consulting Firm for Annobon solar hybrid system feasibilty studies and Social and Environmental Impact Assessment | Working days | 60 | 1500 | 90000 | 90000 | July-30 | Kisito Domingo | UNDP Catalogue
7 | SE4ALL | 98972 | Services | Human Resources Services | Subcontracts for small hydro plants maintenance | Amount | 2 | 12500 | 25000 | 25000 | June-30 | Kisito Domingo | 2 UNDP Catalogue and 3 Non-UNDP-Catalogue
8 | SE4ALL | 98972 | Goods | Computer Equipment & Accessory | Computer to support PMU | Amount | 2 | 2500 | 5000 | 5000 | May-30 | Kisito Domingo | Non-UNDP Catalogue
9 | SE4ALL | 98972 | IC | Human Resources Services | National Consultant (Project Director) | Month salary | 12 | 3000 | 36000 | 40000 | May-30 | Kisito Domingo | Non-UNDP Catalogue
| SE4ALL | 98972 | IC | Human Resources Services | National Consultant (Financial and Administrative Assistant) | Month salary | 12 | 1500 | 18000 | 24000 | May-30 | Kisito Domingo | Non-UNDP Catalogue
9 | SE4ALL | 98972 | Services | Printed Media | Elaboration and printing | Unestimated | 1 | 10000 | 10000 | 10000 | Set-30 | Kisito Domingo | UNDP Catalogue
| Prepared by: |  |  |  | Approved by:
____________________
| Date:__/___/2017 |  |  |  | _____________________
Date:____/____2017
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International
International

## Sheet3
Accommodation Furniture | Contruction Works
Audio and Visual Presentation | Goods
Batteries and Generators | IC
Cleaning & Janitorial Supplies | Services
Communications Devices & Acces
Computer Equipment & Accessory
Consumer Electronics
Containers and Storage
Data Voice or Multimedia Netwo
Domestic Appliances
Domestic Kitchenware & Kitchen
Electrical Equipmnt & Componen
Electronic Reference Material
Floor Coverings
Foundry Machines and Equipment
Furnaces Commercial & Industry
Heating, Ventilation & AC
Heavy Construction Machinery
Human Resources Services
Industrial Food&Beverage Equip
Industrial Process Machinery
Information Technology Compone
Information Technology Service
Institutional Food Service Eqp
Insurance & Retirement Service
Janitorial Equipment
Lamps and Lightbulbs
Lapidary Machinery & Equipment
Leatherwork Repair Machinery
Luggage, Handbags and Packs
Marine Transport
Marketing and Distribution
Mining and Quarrying Machinery
Mixers - Parts and Accessiory
Motor Vehicles
Non Motorized Cycles
Office and Desk Accessories
Office Machines and Supplies
Office Supplies
Paper Products
Passenger Transport
Personal Care Products
Personal Safety and Protection
Photographic & Recording Media
Photographic Filmmaking Supply
Photography or Video Equipment
Power Sources
Printed Media
Printing & Publishing Equipmen
Raw Material Process Machinery
Signage and Accessories
Software
Specialized Trade Construction
Textile Machinery & Accessorie
Timepieces
Transportation Components
Travel Facilitation
Water and Wastewater Treatment
Well Drilling/Operation Equipm
Window Treatments