## 2021 AWP Budget
Output | Sub-Output | Planned Activity | Budget Description |  | Q1 | Q2 | Q3 | Q4 | Comments
Outcome 1 | Output 1.1 | EWS Consultant | International Consultants | 35000 | 35000 |  |  |  | Shamsul Fakhruddin
Outcome 1 | Output 1.1 | Procurement UHF/VHF interupt devices | Equipment and Furniture | 132500 | 15000 | 117500 |  |  | Equipment to support the ODM and Local Government Authority
Outcome 1 | Output 1.1 | Integration and Installation of Tools | Contractual Services-Companies | 40000 |  |  | 40000 |  | To commence once equipments are procured - Local authority responsible for installation
Outcome 1 | Output 1.2: | Training of beneficiary community members to maintain EWS instruments | Training, Workshops and Conferences | 10000 | 0 | 3000 | 7000 |  | To commence once equipments are procured and installed
Outcome 1 | Output 1.2: | Training of 30 agriculture extension officers, local government and DSC students in PICSA through at ToT | Contractual Services-Companies | 43229.5 |  | 21614.5 |  | 21615 | CIMH/UoR LoA - Gender Inclusive budget
Outcome 1 | Output 1.2: | Training of 30 agriculture extension officers, local government and DSC students in PICSA (60% F; 40% M) | Training, Workshops and Conferences | 8000 |  | 4000 |  | 4000 | Training of New chort of Trainer for PICSA
Outcome 1 | Output 1.2: | Production and dissemination of climate information | Audio Visual&Print Prod Costs | 9000 | 4000 |  | 5000 |  | Printing of climate information, Handout poster flyers, radio ads , Play
Outcome 1 | Output 1.2: | Application of PISCA within targeted communities in Dominica (Planning and Review) | Land Transport | 8000 | 4000 |  |  | 4000 | Transportation of Farmers to and from PICSA traiing venues
Outcome 1 | Output 1.2: | Application of PISCA within targeted communities in Dominica (Planning and Review) | Training, Workshops and Conferences | 8000 |  | 4000 |  | 4000 | Venue, snacks, staionary for PICSA training
Outcome 1 | Output 1.4 | Procurement of EWS equipment | Equipment and Furniture | 220000 | 120000 | 100000 |  |  | Specification obtained from Met Service -Janelle Alexander /Lands and survey -
Outcome 1 | Output 1.4 | Installation, connection and testing of equipment | Contractual Services-Companies | 25000 |  |  | 25000 |  | GIS Consultants
Outcome 1 | Output 1.4: | Capacity development of 10 nationally idetnfied focal points to operate and maintain the EWS, and training of | Training, Workshops and Conferences | 3500 |  |  | 3500 |  | To commence once equipments are procured and installed
Outcome 1 | Output 1.4 | Conduct Public Awareness and Education on the availability and the use of the improved national EWS | Audio Visual&Print Prod Costs | 8000 | 3000 |  | 5000 |  | To commence once equipments are procured and installed - funds to support the play production
Outcome 1 | Output 1.4 | Monitoring |  | 5968.5 |  |  |  | 5968.5 | Funds cover Salary renumeration for M&E support
Outcome 2 | Output 2.1 | Workshops and focus groups to support validation of ADRM | Training, Workshops and Conferences | 10000 |  | 10000 |  |  | Gender Inclusive Budget- finalize ADRM through Validation workshop
Outcome 2 | Output 2.1 | Workshops and focus groups to support validation of ADRM | International Consultants | 10000 | 2500 | 7500 |  |  | Gender Inclusive Budget - finalize ADRM through Validation workshop
Outcome 2 | Output 2.2 | Assess existing and design/modify resilience based micro-finance mechanisms and risk insurance for the agricultural sector | Contractual Services-Companies | 0 |  |  |  |  | Quarterly Advances based on IICA/UNDP LoA
Outcome 2 | Output 2.2 | Micro-Grants Officer | Local Consultants | 15000 | 15000 |  |  |  | Micro Grants Officer over 8 month period
Outcome 2 | Output 2.2 | Micro-Grants | Grants | 280000 | 30000 | 100000 | 150000 |  | % of Rural farmers asccessing grants.
Outcome 2 | Output 2.2 | Capacity building of farmers in accessing and managing micro-finance mechanisms | Contractual Services-Companies | 25835 |  | 25835 |  |  | Quarterly Advances based on IICA/UNDP LoA
Outcome 2 | Output 2.2 | Enhance Market Access: Value Chain analysis and support | Contractual Services-Companies | 26430.45 |  | 26430.45 |  |  | Quarterly Advances based on IICA/UNDP LoA
Outcome 2 | Output 2.3 | Technical Assistance for implementation/Pilot programme | Contractual Services-Companies | 142239.21 | 55788.24 | 65606.97 | 20844 |  | Quarterly Advances based on IICA/UNDP LoA
Outcome 2 | Output 2.3 | Training of agriculture and forestry extension officers in CSA and gender-responsive approaches | Contractual Services-Companies | 22388.19 |  | 18713.19 | 3675 |  | Quarterly Advances based on IICA/UNDP LoA
Outcome 2 | Output 2.4 | Purchase of tools to support AEO and project field work | Equipment and Furniture | 11500 |  | 11500 |  |  | Tools and Equipment to support Agricutural Extension work
Outcome 2 | Output 2.4 | Monitoring |  | 18000 |  | 9000 |  | 9000 | Funds cover Salary renumeration for M&E support
Outcome 3 | Output 3.1 | An exchange to transfer the knowledge and experience in developing the gender strategy in DRR in the agriculture sector (linked with 2.1.1) | Travel |  | 0 | 0 | 0 | 0 | Travel Between Countries
Outcome 3 | Output 3.1 | Conduct community exchanges to mutually learn form experiences and creation of networks | Travel | 6000 |  |  | 3000 | 3000 | 5 community exchanges
Outcome 3 | Output 3.1 | Workshop convened to transfer knowledge and experience in agriculture within the two countries | Training, Workshops and Conferences | 26250 |  |  |  | 26250 | Exchanges between Cuuntries
| Output 3.2 | Produce and distribute communication material to disseminate results and lessons learnt | Audio Visual&Print Prod Costs | 14250 | 14250 |  |  |  | Video Production/publication
Outcome 3 | Output 3.2 | Produce and distribute communication material to disseminate results and lessons learnt | Local Consultants | 18000 |  |  |  | 18000 | Knowledge Management consultant
Outcome 3 | Output 3.1 | Monitoring |  | 4500 |  | 2250 |  | 2250 | Funds cover Salary renumeration for M&E support
Project Management | Project Management | Project Coordinator | Service Contracts-Individuals | 39760 | 9940 | 9940 | 9940 | 9940
Project Management | Project Management | Project Associate | Service Contracts-Individuals | 25000 | 6250 | 6250 | 6250 | 6250
Project Management | Project Management | Gender Specialist | Service Contracts-Individuals | 27500.5 | 6875 | 6875 | 6875 | 6875.5
Project Management | Project Management | Communications Associate | Service Contracts-Individuals | 33332 | 8333 | 8333 | 8333 | 8333
Project Management | Project Management | Laptops and camera | Equipment and Furniture | 0
Project Management | Project Management | PMU travel | Travel | 15000 | 3750 | 3750 | 3750 | 3750 | Project Support to field Activities.
Total Planned Activities |  |  |  | 1327183.35 | 333686.24 | 562098.11 | 298167 | 133232
|  | DPC |  | 132718.335 | 33368.624 | 56209.811 | 29816.7 | 13323.2
Project Management | Project Management | GMS | Facilities and Administration | 106174.668 | 26694.8992 | 44967.8488 | 23853.36 | 10658.56
Total +GMS |  |  |  | 1566076.353 | 393749.7632 | 663275.7698 | 351837.06 | 157213.76