## Progress Monitoring
PROGRESS MONITORING - NAMA PROJECT- DURATION 2015 to 2018
Key Activity Results (Annual Ouputs) | Activities | Key Milestone and Detail Activities & Responsible Person | Quarter / Month of completion | [17 empty] | Budget USD AWP | Budget Target | Quarter 2 2016 Target | Status by 31st March, 2016
|  |  | Year 1(2015) |  |  |  | Year 2 (2016) |  |  |  | Year 3 (2017) |  |  |  | Year 4 (2018) |  |  |  | Year 5 (2019)
|  |  | Q3 | Q4 | Nov | Dec | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Output 1.1 Finalized provincial level inventory tool for energy generation and end-use sectors. | Activity 1.1.1 Review EnerGIS database system of SLSEA and existing national communications data inventory system to identify barriers, gaps, needs, and challenges for data collection and compilation | 1. Develop a reference of historical and projected GHG emissions at the sub-sectoral and provincial levels. 2. Establish operational national and sub-national GHG inventory system (GIS) for the energy sector. 3. Planning and implementation of mitigation actions at sub-national level through the 4 provincial councils. 4. Establish long term frame work by SLSEA and Provincial councils by using comprehensive energy balance and detailed end-use energy consumption data. 5. Recruitment of International consultant and utilize natioanl iventory expert. Responsible Person- PT, SLSEA (IC involvement ¦ ESCo ) |  | X | X | X | X | [13 empty] | 89100 |  | 1. Setting up sub-national/sectoral energy inventory system (focusing on three pilot technologies) | 1. EnerGIS database/tool review completed EnerGIS Database update was completed (for SEA internal purpose)
| Activity 1.1.2 Develop, test, verify, and update the inventory system at sub-national level |  |  | X | X | X | X | X | X
| Activity 1.1.3 Identify and select key focal points and define boundary for the development of inventory system for the collection, compilation and management of baseline data at the municipal/urban/Pradeshiya sabha levels in the Uva, North Western, Central and Southern Province |  |  | X | X | X | X | X | X
| Activity 1.1.4 Test, verify, and deploy web-based data collection for EnerGIS GHG inventory system for energy generation (oil based, thermal, and hydro. Coal and RE) and end-use sectors (energy industry, transport, industry, residential and commercial) at Uva, Central, North Western and Southern Provinces | [6 empty] | X | X | X
Output 1.2 Defined and established sectoral and sub-sectoral reference baseline specific energy consumptions for the energy generation and end-use sector and sub-sectors | Activity 1.2.1 In partnership with national communication inventory team, define and develop parameters, reference baseline and emissions boundary for GHG inventory on energy generation sub-sectors (oil based, thermal, hydro, solar, wind, biomass) and end-use sector and sub-sectors (energy industry, transport, industry, residential and commercial) | [5 empty] | X | X | X | X | X | X | X | [9 empty] | 2. Establishing sectoral / sub-national reference baseline specific energy consumptions & emissions
| Activity 1.2.2 Collect, compile, quality check and analyze data for Uva, Central, North Western and Southern Provinces |  |  | X | X | X | X | X | X
| Activity 1.2.3 Test, verify and establish reference baselines for renewable energy utilization, energy consumption in different end-use sectors and GHG emissions in Uva, Central, North Western and Southern Provinces | [5 empty] | X | X | X | X | X | X | X | X
Output 1.3 Established, operational and updated national and provincial GHG emission inventory system for energy generation and end-use sectors | Activity 1.3.1 Develop and implement steps to regularly update and improve the inventory system | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  | 3. National energy & GHG emission inventory for seleted technologies | 2. Software application has been designed to capture energy data of Tea sector. Inventorizing at SEA
| Activity 1.3.2 Develop and conduct training programs to data management staff to strengthen the data collection efforts for inventory at sub-national level | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X
| Activity 1.3.3 Develop knowledge products on the use of the provincial inventory system for provincial inventory data management staff | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X
| Activity 1.3.4 Develop a strategy for replication to other provinces | [16 empty] | X | X | X
Output 2.1 Developed and published detailed marginal GHG abatement cost curves for the energy generation and end-use sector | Activity 2.1.1 Develop MACC using collected data for energy generation (oil-based, thermal, , hydro, solar, wind, biomass) and end-use sectors (, industry, residential and commercial) for Uva, Central, North Western and Southern Provinces. | 1. Conduct a broad assessment of mitigation options at the sub-sectoral level across the energy generation and end-use sectors. 2. Keep reference for the design of NAMAs for the energy sector. 3.Conduct the detailed sub-sectoral assessment and NAMA design for the sub-sectors biogas, solar PV with storage battery and high efficiency motors for tea factories to identify the effective of the NAMA activities. 4.Establish national voluntary mitigation target and national development goals. 5. Development of marginal abatement cost curves (MACC) for various energy generation technology options and energy efficiency and energy conservation measures in the end-use sectors. 6. Recruitment of International consultant for MACC. 7. Conduct trainings (TOT) and workshops in national and sub-national level.Responsible Person: PT, SLSEA, International Expert-MACC |  | X | X | X | X | X | X |  |  |  | X | X | [6 empty] | 99422 |  | 4. TOT on MACC development (by IC)
| Activity 2.1.2 Develop training program and annual budget on the use of MACC | [5 empty] | X | X | X |  | X |  |  |  | X
| Activity 2.1.3 Develop and implement a strategy to upgrade and update the MACC on a regular basis | [8 empty] | X | X |  |  | X |  |  |  | X
Output 2.2 Completed comprehensive barrier analysis for mitigation options in the energy generation and end-use sector | Activity 2.2.1 Identify and analyze regulatory, technical, financial and social barriers to the implementation of CC mitigation actions in the energy generation and energy end use sectors. | [7 empty] | X | X | X
Output 2.3 Identified and analyzed priority appropriate mitigation actions in the energy generation and end use sector in Sri Lanka | Activity 2.3.1 Develop and implement selection criteria for prioritizing of NAMA in the energy generation and end use sector | [5 empty] | X | X | X | X | X | X
| Activity 2.3.2 Develop a full NAMA design document for each selected NAMAs in the energy generation and end-use sector and identify potential donors for the scalable projects | [5 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Output 2.4 Categorized identified mitigation actions as supported and voluntary | Activity 2.4.1 Review status and lessons learned in developing voluntary and supported NAMAs in Sri Lanka and other countries in the region | [6 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  | Activity 2.4.3 & 2.4.4 completed Also detailed implementaion plans for HEMs,Solar PV and Biogas are ready (including beneficiries selections criteria, test trial methods, implementing approcahes)
| Activity 2.4.2 Develop criteria for categorizing NAMA as supported or voluntary | [6 empty] | X | X | X
| Activity 2.4.3 Design the implementation of the RE NAMAs for bio-digesters (domestic, institutional, industrial), and solar PV net metering combined with battery storage. |  |  | X | X | X | X
| Activity 2.4.4 Design the implementation of EE NAMA in tea factories for the application of efficient motors |  |  | X | X | X | X
Output 3.1 Identified and established fully capable and qualified private and public sector entities in the implementation of climate change mitigation programs and sourcing of funds | Activity 3.1.1 Develop criteria for the selection of public and private stakeholders as potential partners | Develop sector individual plan and criteria (PT and SLSEA) | X |  |  |  | X | [13 empty] | 477678 |  |  | Output 3.1 completed
| Activity 3.1.2 Define and develop business and financial modality, roles and responsibilities of the NAMA Implementing Entity under SLSEA and PPP in the implementation of the each NAMA (bio-digester, solar PV with battery storage, HEM) | Develop good market transformations approach (PT, SLSEA, IE, NE) | X | X | X | X | X
| Activity 3.1.3 Review and suggest sources of potential funding for voluntary and supported NAMA and develop investment platform. | Partner with local banks (PT, SLSEA) | [8 empty] | X
Output 3.2 Updated financial tools that support the implementation of the mitigation actions program in the energy generation and end-use sectors, including sustainable energy guarantee fund, fiscal incentives, feed in tariffs and other options available in Sri Lanka | Activity 3.2.1 Review lessons learned and develop best practices in the use of financial instruments (matching rebate, partial loan scheme) for the scaling up of RE and EE solutions. | PT, SLSEA, Climate Finance Expert (IE) | [14 empty] | X | X
| Activity 3.2.2 Develop and implement financial instruments to support end users for the purchase of bio-digesters, solar PV and high efficiency motors (HEM) as part of the PPP structure using matching rebate and viable business model | Establish partial loan guarantee scheme for the dissemination of RE and EE solutions. (PT, SLSEA assist from Climate Finance Expert) |  | X | X | X | X | X |  |  | X | X
Output 3.3 Implemented NAMA projects | Activity 3.3.1 Implement HEM application in the tea sector and solar PV with battery storage NAMA project in private sector funded modality | Implement HEM and Solar PV as a pilot projects. (PT, SLSEA, ESCo assist) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | Start of HEM & Solar PV trial phase | HEM trial procurement is in progress Solar PV battery procurement is in progress
| Activity 3.3.2 Implement biogas projects in the Uva, Central, Southern and North Western Provinces in PPP modality | Implement biogas as a pilot project. (PT, SLSEA, IE, NE) |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |  | Start implementaion of Biogas | MOUs are put forward for comments/approvals
Output 4.1 Established and operational national registry mechanism for mitigation actions in the energy generation and end-use sectors | Activity 4.1.1 Identify and select focal point as NAMA Supporting Entities (NAMA Secretariat (CCS), National NAMA Coordinating Entity (NCE-ES) at CCS, Sector NAMA Coordinating Entities, NAMA National Registry at NCE-ES, MRV Committee) | 1.Establish Measurment, Reportable and Verifiable (MRV) methodology for on going projects. 2. Conduct trainings and workshops in national and sub national level. (PT, SLSEA, MRV Expert) |  | X | X | X | X | X | X | [11 empty] | 69300 |  | Define the roles and responsibilties of NAMA Supporting Entities, National NAMA Coordinating Entity (NCE-ES), Sector NAMA Coordinating Entities, National Registry & MRV committee | One stakeholder consultation discussion was held. Draft institutional arrangement which is to be finalized with IC comments
| Activity 4.1.2 Define roles and responsibilities of the NAMA Secretariat and NCE and NAMA Registry |  |  | X | X | X | X | X | X
| Activity 4.1.3 Review best practices and recommend institutional arrangement for the setting up of the NAMA Secretariat, NCE and NAMA registry |  |  | X | X | X | X | X | X
| Activity 4.1.4 Develop steps to monitor, evaluate, upgrade the NAMA National Registry and integrate with International NAMA registry |  |  | X | X | X | X | X | X
Output 4.2 Defined key parameters (quantitative/qualitative) to be monitored for the selected appropriate mitigation actions | Activity 4.2.1 Based on the inventory system developed under output 1.3, establish monitoring framework by defining key parameters for bio-digester, solar PV and HEM NAMA to be measured, monitored, recorded and updated on the web-based EnerGIS platform (based on Quality Control and Quality Assurance principles) | [5 empty] | X | X | ⃝ | ⃝ | ⃝ | ⃝ | ⃝ | ⃝ | ⃝ | ⃝ | ⃝ | ⃝
Output 4.3 Designed and implemented MRV system for the selected appropriate mitigation action | Activity 4.3.1 Develop best practices in MRV standards and methodologies for RE (solar PV and biogas) and EE NAMA (HEM) based on established CDM methodologies and IPCC guidelines and principles | [5 empty] | X | X | X | X | X
| Activity 4.3.2 Design and test the MRV system for bio-digesters, solar PV and HEM NAMAs | [5 empty] | X | X | ∆ | ∆ | ∆ | ∆ | ∆ | ∆ | ∆ | ∆ | ∆ | ∆
| Activity 4.3.3 Adopt and develop best practices in monitoring plan for RE (solar PV and biogas) and EE (HEM in tea factories) NAMAs | [11 empty] | X | X | X | X | X | X
Output 4.4 Completed capacity development program for strengthening all public, private (value chains actors) and CSO stakeholders involved in the operation and management of the NAMA program | Activity 4.4.1 Review and document lessons learned | [15 empty] | X | X
| Activity 4.4.2: Development of gender sensitive knowledge products (CD, DVD, training manuals) and gender sensitive training program for all NAMA staff | [15 empty] | X | X | X | X
| Activity 4.4.3: Training on operation and management of the Inventory, MRV system and implementation of the NAMAs |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Project Management |  |  | X | X | X | X | X | X | X | X | [10 empty] | 10500 |  |  | 1. Procurement of International Consultant 2. Procurement of National Consultant/Technical advisory for piloting 3. TOR is being developed for ESCo/local technical supporting company

## Procurement log
PROCUREMENT PLAN- NAMA PROJECT - 2015 Q4 & 2016Q1&Q2
Country Office |  | Sri Lanka |  |  | Instructions: - Only include procurements to be done by UNDP for DIM, Management, support-to-NIM projects and UN Agencies - If you need additional lines, right-click and "Insert" rows, do not copy-paste, to keep drop-down menus & format.
Submitted by: |  | Procurement & Admin Unit
Date: |  | 2016-04-05
Q1 & Q2 | Project Name (acronym or brief name) | Type of Supply | Category | Description of goods, services or works required | Unit of Measure | Quantity | Estimated Unit Price in USD | Estimated Total Price in USD | Requested delivery date (goods, works) or start of services | Finalization of services date | End user of goods, services or works/Location | Procurement Process Status
Civil Works
Goods | NAMA | HEM motors |  | High Efficient Motors and VFDs for 5 factories |  | 25 HEMs 5 VFDs | HEM: 2000 USD VFD: 1600 USD | 70000 | May/June 2016 |  | 5 tea factories (2 from TRI and 3 from Private sector) | RFP evaluation
| NAMA | Solar PV Systems with Battery |  | 14 solar PV systems with battery storage in four different capacities (350W, 750W, 1.25kW and 3.0kW) |  |  | USD 2000 | 30000 | Jun/July 2016 |  | Kotte and Kurunegala Green Zone | EOI
| NAMA | Biogas |  | Biogas Digester units |  | 250 | USD 500 | 125000 | Q2, Q3 & Q4 of 2016 (Starting from June) |  | Uva, NW, Southern and Central Province | Pending MOU signing for fund transfer
Services | NAMA | Professional Service Contract |  | International Expertise (company)on MRV and MACC, NAMA establishment |  |  |  | 91070 | Starting from June/2016 for 12 months |  |  | Completed
| NAMA | Professional Service Contract |  | Energy Service Provider/Company for pilot implementation, reference data inventoring & management, MRV establishment |  |  |  | 35000 | Starting from June/2016 for 12 months |  |  | TOR is being prepared
| NAMA | Local Consultant |  | Consultant/Technical advisor for pilot demo. |  |  |  | 20000 | Starting from April/2016 for 12 months |  |  | Completed
| NAMA | Local Consultant |  | MRV Consultant at CCS |  |  |  | 15000 | Starting from June/2016 for 12 months |  |  | TOR is being prepared
| NAMA | Workshop |  | TOT on Data Management & MACC (Two-day) |  |  |  | 8500 | June/2016' |  |  | TBD

## Risk Log
RISK & ISSUE LOG MONITORING
No. | Descripiton | Date identified | Type | Impact & Probability | Countermeasures/Mgmt Response | Owner | Submitted by | Q1 Update | Q2 Update | Q3 Update | Q4 Update | Status
1 | Still pending in providing basic requiements office space at SLSEA, telephone & water NAMA team | Oct, 2015 | Management | Difficulties in carrying out routine work. | Office space set up |  |  | Office setup ready by early March,2015 |  |  |  | Closed
2 | Delay in finalising TORs & specifications | Oct, 2015 | Management | Delays in initiating the procurement process |  |  |  | Few TORs (IC, HEMs, and Solar PV) were completed. In procurement phase. However, some delays in the overall project |  |  |  | Open
3 | Lack of commitment from CCS | Q1, 2016 | Management | High Impact (Delaying planned activities/project progress) | Recruitment of permanent personnal for CCS coordination/activities |  |  | TOR drafted |  |  |  | Open
4 | Not enough participation for HEMs trial /procurement stage | Q1, 2016 | Technical/Management | Delaying HEM trials | Re-advertised for procurement of HEMs Convincing service providers on the requirement | [6 empty] | Closed
5 | Lack of participation/involvement - biogas programme | Q1, 2016 | Management | Delaying in Biogas piloting | Sector Specialist? | [6 empty] | Open
6 | PT turnover | Q1, 2016 | Management | Delaying overall project | New recruitment | [6 empty] | Closed

## Field visit log
Field Visit Monitoring
No. | VISIT PLANNED DATE | FIELD VISIT |  |  | FIELD REPORT | Follow up Actions | Remarks
|  | PURPOSE OF THE VISIT | Field Visit members | STATUS OF THE VISIT | Status
1 | 2015-05-11 | Pre factory visit for HEM pilot project (Alpitiya Plantation) | Gayan/ Anuruddha | Completed | submitted | Factories have been requested provided technical information with applications for piloting | To be decided for Piloting
2 | 12/11/2015 - 13/11/2015 | Pre factory visit for HEM pilot project (Alpitiya Plantation) | Gayan/ Anuruddha | Completed | submitted | Factories have been requested provided technical information with applications for piloting | To be decided for Piloting
3 | 24/02/2016 - 25/02/2016 | Pre factory visit for HEM pilot project (TRI & Nilakanda factory) | Gayan/ Anuruddha | Completed | pending completion |  | Two TI factories were selected for pilot phase

## Indicator tool
TO BE FILLED QUARTERLY
PROJECT NAME, PROJECT DURATION, ATLAS NO,
Indicator | Baseline (year,month) | PLANNED TARGETS | [15 empty] | Un intended results/Changes achieved | DISAGREGATION OF DATA
|  | End of the project | Annual |  |  |  | Year 1 |  | Year 1 |  |  | year 2 |  |  | year 3 |  |  |  | Year 1 | [5 empty] | Year 2 | [5 empty] | Year 3
|  |  | Y1 | Y2 | Y3 | Y4 | Q3 | Q4 | Total results year 1 | Variance | Remarks | Actual results year 2 | Variance | Remarks | Actual results year 3 | Variance | Remarks |  | M | F | FHH | Differently abled | Youth | District | M | F | FHH | Differently abled | Youth | District | M | F | FHH | Differently abled | Youth | District
Project Outcome
Project Goal:
Outcome 1;
Outcome 2;
Outcome 3;
Outcome 4;
Project Output