# UNDP Project Document

UNDP-GEF Medium-Size Project (MSP)

Governments of Algeria, Armenia, Bangladesh, Bhutan, Burkina Faso, Comoros, Democratic Republic of Congo, Djibouti, El Salvador, Guatemala, Jordan, Kazakhstan, Kyrgyzstan, Lesotho, Lithuania, Nepal, Nicaragua, Niue, Papua New Guinea, Philippines, Romania, Sudan, Swaziland, Syrian Arab Republic, Tajikistan, Trinidad & Tobago, Yemen, Zimbabwe

(and others)

United Nations Development Programme

National Reporting to the CBD: Supporting countries to prepare the Third National Report on Biodiversity

Table of Contents

Section												Page

Section I: Elaboration of the Narrative							4

Section II: Strategic Results Framework							7

Section III: Total Budget and Workplan							8

Section IV: Additional Information							10

-	GEF Medium Sized Project Proposal					10

-	Response to Reviews							17

Section V: Supplemental Annexes								18

Annex 1: List of Countries supported by UNDP in Biodiversity Enabling Activities	18

Annex 2: Draft Format for Individual Country Requests for Assistance			21

-	2A: Summary of Support Provided to Country				24

-	2B: Sample Total Budget and Workplan					25

-	2C: Letter of Request from GEF Operational Focal Point			26

Annex 3: Letters of Request Received from GEF Operational Focal Points		27

Annex 4: Terms of Reference								28

Annex 5: Draft Template for Framework Service Agreement				29

Signature Page:										31

Acronyms

3NR		Third National Report (to the CBD)

CBD		Convention on Biological Diversity

CHM		Clearing House Mechanism

CO			Country Office (of UNDP)

COP		Conference of Parties

DEX		Direct Execution

EA			Enabling Activity

FSA		Framework Service Agreement

GEF		Global Environment Facility

GEFSec		Secretariat of the Global Environment Facility

HQ			Headquarters (UNDP/GEF)

IA			Implementing Agency of the GEF

M&E		Monitoring and Evaluation

MYFF		Multi-Year Financing Framework

NBSAP		National Biodiversity Strategy and Action Plan

NCSA		National Capacity Self Assessment

NEX		National Execution

OFP		Operational Focal Point

SRF		Strategic Results Framework

UNDAF		United Nations Development Assistance Framework

UNDP		United Nations Development Programme

UNEP		United Nations Environment Programme

PART I: Situation Analysis

The Convention on Biological Diversity (CBD) at its Seventh Conference of Parties (COP7) emphasized the priority and importance accorded to national reporting by country parties to the CBD. Decision VII/25B of the CBD calls upon country parties to make all efforts to report in an effective and timely way to the convention.  The CBD also calls upon the GEF to provide financial support to the CBD parties in preparation of their Third National Reports to the CBD.  UNDP as one of the three GEF Implementing Agency has a record of having supported 94 countries in their earlier rounds of reporting to the CBD.  UNDP has also received several requests from countries for assistance in the preparation of Third National Reports on Biodiversity which are due to be submitted to the CBD by 15 May 2005.  Some of the requests are attached in Annex 3 as an indication of country drivenness and country priority accorded to such a project.  This project has been designed in view of the country demand and to enable UNDP to continue to play a leading role in assisting country parties in meeting their obligations to global convention, in this case to the CBD.

As the majority of project funds are allocated against individual country requests from the first set of 49 countries, a second Medium Sized Project will be developed by UNDP and submitted to the GEF for approval of funding in order to assist up to 50 additional countries to meet their reporting obligations under the CBD.  In addition, countries in the process of developing larger national Enabling Activity projects for UNDP/GEF support have the option of seeking funding for the Third National Report preparation as part of their national proposals.

PART II : Strategy

This project has secured approval from the GEF for an envelope of funding that will be used by UNDP to disburse funding of up to $20,000 to individual countries for the preparation of their Third National Reports to the CBD.  Depending on the size of individual country requests, this project will be able to assist at least 49 and possibly more countries. The funding will be approved by UNDP upon receipt by the UNDP/GEF Unit of a satisfactory proposal from the country accompanied by a letter of request issued by the Operational Focal Point of that country.  UNDP will provide overall reporting to the GEF Secretariat on a periodic basis on the status of the global project and the number of country requests disbursed.

At the country level the activities foreseen to be carried out under individual country requests are expected to include (a) a synthesis of biodiversity information, and (b) consultations with stakeholders.  It is expected that a synthesis of biodiversity information will build upon previous activities, studies, experiences, including the NBSAP and earlier National Reports that will be used for the preparation of the Third National Report. The preparation process also foresees extensive consultation with the full range of national stakeholders.  Experience from earlier rounds of Biodiversity Enabling Activities has demonstrated that in addition to financial support some substantive technical support is also be needed by countries.  Therefore, in addition to providing funds to countries in a timely and expedited manner, this project will also commission the development of guidance material to provide substantive assistance to countries.

PART III : Management Arrangements

This project is fully in line with the role of UNDP as the GEF Implementing Agency dealing with capacity development. UNDP has been instrumental in its role as a GEF Implementing Agency for assisting about 94 countries in their Biodiversity Enabling Activity projects, which supported the preparation of the National Biodiversity Strategy and Action Plans.  In addition UNDP is supporting 66 countries in preparation and implementation of additional enabling activity funding in the Biodiversity focal area for consultations towards the Second National Reports, capacity needs assessments in priority areas of the CBD, and for country driven projects to support the establishment and functioning of the Clearing House Mechanism (CHM). UNDP will also be in a position to ensure appropriate linkages with the cross-cutting National Capacity Self-Assessments which are being supported by UNDP in over 110 countries.

UNDP will coordinate with other GEF Implementing and Executing Agencies at the global and country level as required, to ensure that all relevant actors involved in the Biodiversity focal area are consulted.  At the global level, UNDP will provide updates to the GEF Secretariat on a periodic basis on the progress of the umbrella project.  UNDP will also communicate with the CBD Secretariat on a periodic basis about the status of submission of the third national reports of the countries funded under this umbrella project, and follow up if necessary with countries to facilitate the preparation and submission of the third national reports.

In order to accord proper acknowledgement to GEF for providing funding, a GEF logo should appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF should also accord proper acknowledgment to GEF. The UNDP logo should be more prominent -- and separated from the GEF logo if possible.

UNDP proposes to execute this project in accordance with UNDP rules and procedures for direct execution (DEX). DEX by UNDP/GEF HQ was selected as the most flexible and effective mechanism based on (a) the short time frame for completion and submission of Third National Reports by countries (the CBD deadline is 15 May 2005), (b) the small size of individual country requests (not exceeding $20,000 per country) and (c) the large number of countries to be assisted under this project (at least 49 countries).  The project is expected to be financially/ operationally completed within 9-12 months.

Since the Global project will be implemented under the DEX modality, at the country level too COs would also need to use DEX. It will not be possible to use NEX at the CO level for execution as doing so would require separate NEX projects to be created in Atlas by COs under the DEX global project.  Entering the funds in Atlas as NEX projects at the CO level would create complications as the grants ($20,000 only) would be treated as a project instead of an Activity in Atlas.  If there are cases where countries raise objections to DEX procedures and prefer the flexibility of NEX, it is recommended that the entire grant amount be sub-contracted by the CO to the relevant lead National Agency. A sub-contract would allow government agencies the same flexibility for managing funds as under an individual NEX project.

Specific responsibilities for management at various levels are described below.

UNDP/GEF/Biodiversity Cluster/ Project Management Unit (HQ) will be responsible for:

- Technical and financial approval of respective country 3-6 page requests for funding entitled “Proposals for preparation of the Third National Report on Biodiversity: GEF Additional Funding for Biodiversity Enabling Activities” (“proposal”);

- For each approved proposal, HQ will establish a separate Atlas Activity in the form of a grant, and will provide authorization to the respective UNDP/Country Office (CO) for the corresponding Chart of Accounts to be charged. This authorization will be regarded as the framework service agreement (FSA) between UNDP/GEF, the CO and the respective Government to incur expenditures.  (Please refer to draft FSA attached in Annex 5 of this document);

- HQ will be responsible for overall financial and budgetary oversight to ensure there is no over-expenditure, and track budget revisions and financial and operational completion of the project.

- HQ will review final reports but is not accountable for the quality and content.

UNDP/GEF POSI will be responsible for execution oversight/ ensuring OBR issuance of ASL.

UNDP/CO, in accordance with the FSA, will be responsible for:

- specific approval of grant expenditures in Atlas in line with the approved proposal including its financial ceiling;

- issuing payment to respective government responsible for preparation of Third National Report on Biodiversity;

- Ensure quality and effective delivery of the Third National Report on Biodiversity to the CBD and HQ;

- Management of respective project activity including confirmation to HQ regarding operational and financial completion of the activity.

Respective Government – in accordance with the FSA, the Government body recipient of grant funding will:

- operationalize the activities in accordance with the approved proposal;

- report expenditures to CO, including financial and operational completion.

- Ensure technical quality and timely completion, submission to CO, HQ and CBD of the Third National Report to the CBD

PART IV : Monitoring and Evaluation Plan and Budget

UNDP/GEF will review individual country proposals and will award funding amounts upon receipt of eligible proposals providing an outline of the activities to be carried out, outputs to be achieved, time-frame and budget.

Funds will be awarded to countries through UNDP Country Offices who will be responsible for monitoring project progress as per individual country proposals.

Standard UNDP M&E procedures will be applied.

Audit:  Standard DEX audit procedures will be applied

PART I : Logical Framework Analysis

The Objective of the Project is:

- To enable country parties to undertake their national reporting obligations towards the CBD

The Project will have the following expected Outcomes:

- At least 49 countries produce Third National Reports (3NRs)

- Guidance material is available to assist countries in the preparation process

Table 2: Indicative Outputs, Activities and quarterly workplan

| Outputs | Activities | Q1 Mar – May 05 | Q2 Jun –Aug 05 | Q3 Sep – Nov 05 | Q4 Dec 05 – Feb 06 |
| --- | --- | --- | --- | --- | --- |
| 1.1 Countries supported in preparation of 3NRs | 1.1.1 Assist countries in preparing funding requests | 30 countries | 40 countries | All countries | All countries |
|  | 1.1.2 Approve funding to countries | 20 countries | 30 countries | 40 countries | All countries |
|  | 1.1.3 Assist countries in implementation of activities for 3NR | 20 countries | 30 countries | 40 countries | All countries |
|  | 1.1.4 Additional country demand assessed and 2nd MSP prepared if necessary |  |  | 2nd MSP prepared (if needed) | 2nd MSP approved by GEFSec |
| 1.2 Guidance material is available to assist countries | 1.2.1 Guidance material prepared | Guidance material prepared and available |  |  |  |
|  | 1.2.2 Additional guidance needs identified based on experience with initial set of countries | Additional guidance needs identified | Additional guidance produced (if needed) |  |  |

| Work Plan and Budget |
| --- |
| Award: 00039377 |
| Award Title: PIMS 3456 BD MSP: Global 3NR Third National Reports to CBD |
| 1. Project ID: 00044131 |  |  |  |  |  |  |  |  |  |
| Project Objective/Atlas Output/Project = PIMS 3456 BD: Global 3NR Third National Reports to CBD |
| Project Outcome/Atlas Activity | Responsible Party | Source of Funds | ERP/ATLAS Budget Description | Amount 2005 (USD) | Amount 2006 (USD) | Total (USD) |  |  |
| ACTIVITY 1: Contract for preparation of guidance document | GEF | GEF | 71200 | International consultants | 20,000 |  | 20,000 |  |  |
|  |  |  |  | sub-total | 20,000 | 0 | 20,000 |  |  |
| ACTIVITY 2: Latvia (B0558) 3NR produced | CO Latvia | GEF | 72600 | Grants | 17,000 | 0 | 17,000 |  |  |
|  |  |  |  | sub-total | 17,000 | 0 | 17,000 |  |  |
|  |  |  |  | sub-total |  |  | 0 |  |  |
| ACTIVITY 3: Kazakhstan (B0552) 3NR produced | CO Kazakhstan | GEF | 72600 | Grants | 20,000 |  | 20,000 |  |  |
|  |  |  |  | sub-total | 20,000 | 0 | 20,000 |  |  |
| ACTIVITY 4: Philippines (B0428) 3NR produced | CO PHI | GEF | 72600 | Grants | 20,000 |  | 20,000 |  |  |
|  |  |  |  | sub-total | 20,000 | 0 | 20,000 |  |  |
| ACTIVITY 5: Tajikistan (B0576) 3NR produced |  | GEF | 72600 | Grants | 20,000 |  | 20,000 |  |  |
|  |  |  |  | sub-total | 20,000 | 0 | 20,000 |  |  |
| ACTIVITY 6 - 50: (add information as country proposals are approved <$20,000) | CO TBD___ | GEF | 72600 | Grants | 0 |  | 0 |  |  |
|  |  |  |  | sub-total | 0 | 0 | 0 |  |  |
| ACTIVITY 7: add information as country proposals are approved <$20,000) | CO TBD | GEF | 72600 | Grants | 0 |  | 0 |  |  |
|  |  |  |  | sub-total | 0 | 0 | 0 |  |  |
| ACTIVITY 8: add information as country proposals are approved <$20,000) | CO TBD | GEF | 72600 | Grants | 0 |  | 0 |  |  |
|  |  |  |  | sub-total | 0 | 0 | 0 |  |  |
|  |  |  |  | TOTAL Authorized | 97,000 | 0 | 97,000 |  |  |
|  |  |  |  | Total available | 903,000 |  | 903,000 |  |  |
| Requests for funding anticipated from:Governments of Algeria, Armenia, Bangladesh, Bhutan, Burkina Faso, Comoros, Democratic Republic of Congo, Djibouti, El Salvador, Guatemala, Kazakhtsan, Kyrgyzstan, Lesotho, Lithuania, Nepal, Nicaragua, Niue, Papua, New Guinea, Philippines, Romania, Sudan, Swaziland, Syrian Arab Republic, Tajikistan, Trinidad & Tobago, Yemen, Zimbabwe (and others) |  |  |

Request for GEF Funding

Medium-sized Project proposal

Agency’s Project ID: PIMS 3456

GEFSEC Project ID:

Country: Global (See indicative country list in Annex 1)

Project Title: National Reporting to the CBD: Supporting countries to prepare the Third National Report on Biodiversity

GEF Agency: UNDP

Other Executing Agency(ies):

Duration: 12 months

GEF Focal Area: Biodiversity

GEF Operational Program: OP 1, 2, 3, 4, 13

GEF Strategic Priority: CB 1 – Enabling Activities (Biodiversity)

Estimated Starting Date: 11 April 2005

Implementing Agency Fee: $146,000

| Financing Plan (US$) |
| --- |
| GEF Project/Component |
| Project | 1,000,000 |
| PDF A* | 0 |
| Sub-Total GEF | 1,000,000 |
| Co-financing** |
| GEF Agency |  |
| Government |  |
| Bilateral |  |
| NGOs |  |
| Others |  |
| Sub-Total Co-financing: |  |
| Total Project Financing: | 1,000,000 |
| Financing for Associated Activity If Any: |

Record of  endorsement on behalf of the Government:

| Details on following page and in Annex 3. |  |
| --- | --- |

| This proposal has been prepared in accordance with GEF policies and procedures and meets the standards of the GEF Project Review Criteria for a Medium-sized Project. |
| --- |
| Yannick Glemarec Deputy Executive Coordinator | Tehmina Akhtar, Technical Adviser, Biodiversity, UNDP/GEF Project Contact Person |
| Date: 2 February 2005 | Tel. and email: (212) 906 5460 tehmina.akhtar@undp.org |

Contribution to Key Indicators of the Business Plan:  At least 49 countries will be assisted in preparation of Third National Reports on Biodiversity in order to meet their national reporting requirements to the Convention on Biological Diversity.

Record of  endorsement on behalf of the Governments:

| See attached letters of request from countries in Annex 3. |  |
| --- | --- |
| Country | Name | Date |
| Armenia | V. Ayvazyan, Minister, Ministry of Nature Protection | 4 February 2005 |
| El Salvador | Hugo Barrera, Minister, Ministry of Environment and Natural Resources | 17 January 2005 |
| Guatemala | Licda Ana Luisa Noguera, Executive Secretary, National Council on Protected Areas, CONAP | 31 January 2005 |
| Lesotho | J.T. Metsing, Principal Secretary, Ministry of Tourism, Environment and Culture | 12 January 2005 |
| Nepal | Damodar P. Parajuli, Joint Secretary and Chief Foreign Aid Department, Ministry of Forests and Soil Conservation | 7 February 2005 |
| Nicaragua | Jose Santos Mendoza A., GEF Focal Point and Secretary General, Ministry of Environment and Natural Resources (MARENA) | 20 January 2005 |
| Papua New Guinea | Wari Iamo, Secretary, GEF Operational Focal Point, Department of Environment and Conservation | 7 February 2005 |
| Swaziland | J.D. Vilakati, GEF National Operational Focal Point, Swaziland Environment Authority, Ministry of Tourism, Environment and Communications | 7 January 2005 |
| Tajikistan | Abduvahit Karimov, GEF Operational Focal Point, State Committee on Environment and Forest Resources Neimatulo Safarov, CBD Focal Point, National Biodiversity and Biosafety Center | 11 January 2005 10 January 2005 |
| Trinidad and Tobago | Earl Nesbitt, Permanent Secretary, Ministry of Public Utilities and the Environment | 21 January 2005 |
| Zimbabwe | M. Sangarwe, Secretary for Environment and Tourism, | 27 January 2005 |

PART I -  Project Concept

A - Summary

This umbrella project is designed to assist at least 49 countries in the preparation of their Third National Reports on Biodiversity in order to meet their national reporting requirements under the Convention on Biological Diversity (CBD).  This project, through its umbrella approach, is intended to provide expedited assistance to countries and reduce transaction costs of individual requests.  Its benefits will include enabling country parties to the CBD to improve the quality and timeliness of their reporting as called for under Decision VII/25B of the CBD at its Seventh Conference of Parties.

###### B - Country ownership

- Country Eligibility

Please see list of countries in Annex 1 along with the dates of ratification of the CBD. These countries are all parties to the CBD and have worked with UNDP as a GEF Implementing Agency for assistance during the Enabling Activity and and/or Additional Funding Phase. This list is intended to be indicative of the level of country demand that UNDP expects to meet.

- Country Drivenness

UNDP has received several requests and inquiries from countries for assistance in the preparation of their Third National Reports on Biodiversity.  Some of the requests are attached in Annex 3 as an indication of country drivenness and country priority accorded to such a project.

###### C – Program and Policy Conformity

- Program Designation and Conformity

This project is in line with GEF’s Strategic Priority 1 for Capacity Building (CB1), which supports Enabling Activities. The project is also broadly relevant to all Biodiversity Strategic Priorities and Operational Programmes.

The project proposes an umbrella approach, a new modality for providing assistance to countries in undertaking additional enabling activities in the biodiversity focal area of the GEF.  The project is specifically designed to assist at least 49 countries in the preparation of their Third National Reports for meeting their national reporting requirements under the Convention on Biological Diversity (CBD). This approach provides opportunities to the GEF and UNDP for managing the biodiversity enabling activities more strategically. Other important benefits include: improved support services to countries, reduced administration burden on countries and Implementing Agencies, reduced transaction costs for the GEF, and improved quality of programming. Finally, this global project will aim to ensure synergy between the GEF enabling activities, the GEF’s strategic approach for capacity building as implemented through a number of ongoing National Capacity Self-Assessments (NCSA) in countries, and national reporting requirements and guidelines of the CBD.

- Project Design

The project is designed to secure approval from the GEF for an envelope of funding that will be used by UNDP to disburse funding of up to $20,000 to individual countries for the preparation of their Third National Reports.  Depending on the size of individual country requests, this project will be able to assist at least 49 and possibly more countries. The funding will be approved by UNDP upon receipt by the UNDP/GEF Unit of a satisfactory proposal from the country accompanied by a letter of request issued by the Operational Focal Point of that country.  The format for individual country requests is attached in Annex 2.  UNDP will provide overall reporting to the GEF Secretariat on a periodic basis on the status of the global project and the number of country requests disbursed.

At the country level the activities foreseen to be carried out under individual country requests are expected to include (a) a synthesis of biodiversity information, and (b) consultations with stakeholders.  It is expected that a synthesis of biodiversity information will build upon on previous activities, studies, experiences, including the NBSAP and earlier National Reports that will be used for the preparation of the Third National Report. The preparation process also foresees extensive consultation with the full range of national stakeholders, including local and indigenous groups, in order to ensure perspectives of all national stakeholders are taken into account in the preparation of the Third National Report.

Experience from earlier rounds of Biodiversity Enabling Activities, which were assisted through the Biodiversity Planning Support Programme (BPSP), as well as experience in other focal areas which have global projects with central support units, has demonstrated that in addition to financial support some substantive technical support is also be needed by countries.  Therefore, in addition to providing funds to countries in a timely and expedited manner, this project will also commission the development of guidance material to provide substantive assistance to countries.

The guidance material could be developed in the form of a short and user friendly guide that includes some of the following elements: (a) a suggested methodology on how countries could manage the “process” of preparation including synthesizing information, undertaking consultations with stakeholders, and validating information to be included in the report, (b) draw upon some best practice examples of earlier reporting to the CBD (First and Second National Reports, and NBSAPs) and (c) provide links to relevant thematic material available.  Detailed terms of reference for guidance material will be prepared at a later stage and circulated to the GEF Secretariat, CBD Secretariat and other GEF Implementing Agencies for their inputs. The work will be commissioned through a qualified institution or individual(s) with thorough knowledge of the CBD and its requirements, and understanding of consultative and analytical processes. It is expected that substantive guidance will enhance quality and result in greater level of standardization of the Third National Reports preparation process.  The production of the guidance material will be commission and completed within the first six weeks of project implementation.

The Objective of the Project is therefore:

- To enable country parties to undertake their national reporting obligations towards the CBD

The Project will have the following expected Outcomes:

- At least 49 countries produce Third National Reports

- Guidance material is available to assist countries in the preparation process

- Sustainability (including financial sustainability)

The project is expected to enable immediate assistance to countries to meet their national reporting requirements under the CBD and is not expected to continue its inputs over the long term. However the project foresees that sustainability of the project results will be improved by building upon existing knowledge and capacities within countries. It is expected that the preparation of Third National Reports in individual countries will build upon the achievements, capacity and knowledge generated in earlier enabling activity projects. In particular the synthesis of biodiversity information foreseen in the preparation of the Third National Reports is expected to utilize an earlier body of knowledge as well as be informed by lessons learnt and good practices identified in planning, preparation, analysis, and participatory processes undertaken in earlier enabling activities.

- Replicability

The timely and effective preparation of the Third National Reports by country parties to the CBD will help to increase global knowledge about biodiversity and enable countries to learn from each other, and for the CBD to draw upon this knowledge for further analysis, planning and priority setting.

- Stakeholder Involvement

Stakeholder involvement is emphasized in the CBD’s Decision VII/25B as an important consideration in the preparation by countries of their Third National Reports.  By emphasizing a participatory and consultative preparation process for the Third National Reports in countries, the project will support wider involvement of key national stakeholders, including local and indigenous communities where relevant, to benefit from their knowledge and to ensure that their views and concerns are reflected in the preparation of the national report. This consultative process will ultimately help to broaden and mobilize the constituency for biodiversity within individual countries.

- Monitoring and Evaluation

UNDP/GEF will review individual country proposals and will award funding amounts upon receipt of eligible proposals providing an outline of the activities to be carried out, outputs to be achieved, time-frame and budget.

Funds will be awarded to countries through UNDP Country Offices who will be responsible for monitoring project progress as per individual country proposals.

Standard UNDP M&E procedures will be applied.

###### D - Financing

  - Financing Plan

The project will assist a number of countries in securing GEF enabling activity funding for the purpose of meeting their convention related obligations in the Biodiversity Focal Area.  Enabling Activity funding is full cost funding provided by the GEF.

  - Cost Effectiveness

The project will be cost effective by providing assistance to a large number of countries in a timely and expedited manner while keeping administrative costs low.

  - Co-financing

While in-kind or in-cash co-funding may be allocated by individual countries in addition to the support sought from the GEF, this cannot be estimated at present. All co-funding indicated by countries will however be tracked as individual country requests are received and will be reported to the GEF.

### E -  Institutional Coordination and Support

  - Core Commitments and Linkages

This project is fully in line with the role of UNDP as the GEF Implementing Agency dealing with capacity development. UNDP has been instrumental in its role as a GEF Implementing Agency for assisting over 90 countries in their Biodiversity Enabling Activity projects, which supported the preparation of the National Biodiversity Strategy and Action Plans.  In addition UNDP is supporting 66 countries in preparation and implementation of additional enabling activity funding in the Biodiversity focal area for consultations towards the Second National Reports, capacity needs assessments in priority areas of the CBD, and for country driven projects to support the establishment and functioning of the Clearing House Mechanism (CHM).

UNDP will also be in a position to ensure appropriate linkages with the cross-cutting National Capacity Self-Assessments which are being supported by UNDP in over 110 countries.

  - Consultation, Coordination and Collaboration between and among Implementing Agencies, Executing Agencies, and the GEF Secretariat, if appropriate.

UNDP will coordinate with other GEF Implementing and Executing Agencies at the global and country level as required, to ensure that all relevant actors involved in the Biodiversity focal area are consulted.  At the global level, UNDP will provide updates to the GEF Secretariat on a periodic basis on the progress of the umbrella project.

UNDP will also communicate with the CBD Secretariat on a periodic basis about the status of submission of the third national reports of the countries funded under this umbrella project, and follow up if necessary with countries to facilitate the preparation and submission of the third national reports.

F -	Budget

| Output/Cost category | Unit Cost | Total Funding ($) |
| --- | --- | --- |
| Preparation of 49 Third National Reports | < $20,000 | $980,000 |
| Contract for preparation of guidance document |  | 20,000 |
| Total |  | $1,000,000 |

Note: Unallocated funds will be returned to the GEF Secretariat upon completion of the project.

#### Response to Reviews

A - Convention Secretariat

The following comments were received from the CBD Secretariat on 11 February 2005 and have been addressed by UNDP:

| Comment | Response |
| --- | --- |
| We welcome the proposal. |  |
| On the main body of the proposal, we would suggest adding one paragraph under "Monitoring and Evaluation" (6, C, Part I), which reads: “UNDP will follow up with the CBD Secretariat on a periodic basis about the status of submission of the third national reports of the countries funded under this umbrella project, and work if necessary to facilitate the preparation and submission of the third national reports.” This addition is meant to make sure that those countries provided with the fund will submit their reports within the timeframe set in the country project request. | The suggested paragraph has been added under Section E “Institutional Coordination and Support”, sub-section 2) “Consultation, Coordination, and Collaboration between and Among IAs and ExAs, and the GEF Secretariat as appropriate”. |
| On Annex 2 (Draft Format for Individual Country Requests for Assistance), Under the "Objective", in the second sentence, the last phrase starting from "according to the format..." should be updated by "according to the format provided at www.biodiv.org/world/nr-guidelines.asp?t=t". This amendment is suggested to avoid the possible use of the old guidelines by some countries. The guidelines contained in the documents presented to COP 7 have been revised as required by decision VII/25 B and the finalized guidelines for the third national report were distributed to Parties in July 2004. | This has been done. |
| Also in Annex 2, under "Activities to Be Carried Out", in the bracket following the first bullet, we suggest inserting "relevant databases and sources of information" after "First and Second National Reports". This insertion will help us find more information later on. | This has been done. |

Annex 1: List of Countries supported by UNDP in their Biodiversity Enabling Activities and/or Add-ons

| Name of country | Date of Ratification of the CBD |
| --- | --- |
| Albania | 05/01/1994 a |
| Algeria | 14/08/1995 rtf |
| Angola | 01/04/1998 rtf |
| Antigua & Barbuda | 09/03/1993 rtf |
| Argentina | 22/11/1994 rtf |
| Armenia | 14/05/1993 acp |
| Azerbaijan | 03/08/2000 apv |
| Bangladesh | 03/05/1994 rtf |
| Belize | 30/12/1993 rtf |
| Benin | 30/06/1994 rtf |
| Bhutan | 25/08/1995 rtf |
| Bolivia | 03/10/1994 rtf |
| Botswana | 12/10/1995 rtf |
| Brazil | 28/02/1994 rtf |
| Bulgaria | 17/04/1996 rtf |
| Burkina Faso | 02/09/1993 rtf |
| Burundi | 15/04/1997 rtf |
| Cambodia | 09/02/1995 acs |
| Cape Verde | 29/03/1995 rtf |
| Central African Republic | 15/03/1995 rtf |
| Chad | 07/06/1994 rtf |
| Chile | 09/09/1994 rtf |
| Comoros | 29/09/1994 rtf |
| Congo | 01/08/1996 rtf |
| Cook Islands | 20/04/1993 rtf |
| Costa Rica | 26/08/1994 rtf |
| Democratic Peoples’ Republic of Korea | 26/10/1994 apv |
| Democratic Republic of Congo | 03/12/1994 rtf |
| Djibouti | 01/09/1994 rtf |
| Dominica | 06/04/1994 rtf |
| Ecuador | 23/02/1993 rtf |
| El Salvador | 08/09/1994 rtf |
| Equatorial Guinea | 06/12/1994 acs |
| Ethiopia | 05/04/1994 rtf |
| Fiji | 25/02/1993 rtf |
| Gabon | 14/03/1997 rtf |
| Grenada | 11/08/1994 rtf |
| Guatemala | 10/07/1995 rtf |
| Guinea | 07/05/1993 rtf |
| Guinea-Bissau | 27/10/1995 rtf |
| Guyana | 29/08/1994 rtf |
| Honduras | 31/07/1995 rtf |
| India | 18/02/1994 rtf |
| Islamic Republic of Iran | 06/08/1996 rtf |
| Jamaica | 06/01/1995 rtf |
| Jordan | 12/11/1993 rtf |
| Kazakhstan | 06/09/1994 rtf |
| Kiribati | 16/08/1994 acs |
| Latvia | 14/12/1995 rtf |
| Lebanon | 15/12/1994 rtf |
| Lesotho | 10/01/1995 rtf |
| Liberia | 08/11/2000 rtf |
| Madagascar | 04/03/1996 rtf |
| Malaysia | 24/06/1994 rtf |
| Maldives | 09/11/1992 rtf |
| Mali | 29/03/1995 rtf |
| Marshall Islands | 08/10/1992 rtf |
| Mexico | 11/03/1993 rtf |
| Micronesia, Federated States of | 20/06/1994 rtf |
| Mongolia | 30/09/1993 rtf |
| Nauru | 11/11/1993 rtf |
| Nicaragua | 20/11/1995 rtf |
| Niger | 25/07/1995 rtf |
| Nigeria | 29/08/1994 rtf |
| Niue | 28/02/1996 acs |
| Oman | 08/02/1995 rtf |
| Palau | 06/01/1999 acs |
| Paraguay | 24/02/1994 rtf |
| Peru | 07/06/1993 rtf |
| Philippines | 08/10/1993 rtf |
| Rwanda | 29/05/1996 rtf |
| Saint Kitts & Nevis | 07/01/1993 rtf |
| Saint Vincent & The Grenadines | 03/06/1996 acs |
| Samoa | 09/02/1994 rtf |
| Senegal | 17/10/1994 rtf |
| Serbia & Montenegro (in pipeline) | 01/03/2002 rtf |
| Sierra Leone (in pipeline) | 12/12/1994 acs |
| South Africa | 02/11/1995 rtf |
| Sudan | 30/10/1995 rtf |
| Suriname | 12/01/1996 rtf |
| Swaziland | 09/11/1994 rtf |
| Syrian Arab Republic | 04/01/1996 rtf |
| Tajikistan | 29/10/1997 acs |
| Tanzania, United Republic of (in pipeline) | 08/03/1996 rtf |
| Thailand (in pipeline) | 29/01/2004 rtf |
| Tonga | 19/05/1998 acs |
| Trinidad & Tobago | 01/08/1996 rtf |
| Turkmenistan | 18/09/1996 acs |
| Uruguay | 05/11/1993 rtf |
| Uzbekistan | 19/07/1995 acs |
| Venezuela | 13/09/1994 rtf |
| Yemen | 21/02/1996 rtf |
| Zambia | 28/05/1993 rtf |
| Zimbabwe | 11/11/1994 rtf |

Annex 2: Draft Format for Individual country requests for assistance in the preparation of their Third National Reports on Biodiversity

UNITED NATIONS DEVELOPMENT PROGRAMME

GLOBAL ENVIRONMENT FACILITY

Proposal for preparation of the Third National Report on Biodiversity:
GEF Additional Funding for Biodiversity Enabling Activities

| Summary Project Info: |  |
| --- | --- |
| Country: | Name of country |
| Project Title: | Preparation of Third National Report on Biodiversity |
| GEF Focal Area: | Biodiversity |
| GEF Financing: | US$_________(not to exceed $20,000) |
| Co-financing: |  |
| Country Eligibility/Country Drivenness: |  |
| Date of ratification of CBD: | Date |
| OFP Request letter: | Name of OFP, Date of request letter |
| Implementation Details |  |
| Implementing Agency: | UNDP |
| Executing Agency: | Name of National Executing Agency |
| Duration: | x months |
| Estimated Start date: | Date |

Objective

The main objective of this request is to assist [Country Name] to undertake the preparation of its Third National Report on Biodiversity for submission to the Convention on Biological Diversity. The preparation will be in line with CBD Decision VII/25B and according to the format provided at www.biodiv.org/world/nr-guidelines.asp?t=t.

The Government of [Country Name] is requesting US$ [<20,000] from the Global Environment Facility (GEF) for the preparation of the Third National Report.  The support provided by the GEF will enable [Country Name] to submit its Third National Report to the CBD in a timely manner with respect to the deadline of 15 May 2005.

Status of earlier assistance received under enabling activites

[Please Complete table below]

| National Reporting to CBD | Date of Submission to CBD | Status/Comments |
| --- | --- | --- |
| National Biodiversity Strategy and Action Plan (NBSAP) |  |  |
| First National Report to CBD: |  |  |
| Second National Report to CBD: |  |  |
| Third National Report: | [Provide planned date] |  |

[Please also indicate if the country has received additional funding for undertaking capacity needs assessments in priority areas of the CBD, and/or for establishment and operationalization of the Clearing House Mechanism?  Describe what is the current status of the EA and Add-on projects and any funds remaining?]

Activities to be carried out

The activities foreseen under this request are expected to synthesise biodiversity information, building upon on previous activities, studies, experiences that will be used for the preparation of [Country Name] Third National Report. The preparation process also foresees extensive consultation with the full range of national stakeholders, including local and indigenous groups, in order to ensure perspectives of all national stakeholders are taken into account in the preparation of the Third National Report.  The preparatory activities will include:

- A synthesis of biodiversity information:  [Please refer to relevant BD information that will be drawn upon, such as NBSAP, First and Second National Reports, and other relevant databases and sources of information.]

- Consultations with stakeholders: [Describe specific consultations and participatory activities planned.]

[Include a preliminary list of the government institutions, academia, NGOs, research institutions, private organisations, and others as relevant, which would be invited to participate in the preparation of the Third National Report.]

institutional arrangements

The national lead agency responsible for oversight and implementation of the preparation of the Third National Report is [Name of the institution].  The lead agency will work closely with the National Biodiversity Task Force/Committee [Describe the exact institutional arrangements].

The Director/Coordinator/Manager of [Specify institution/unit as appropriate] will be responsible for the coordination of project activities in close consultation with the UNDP-[Country Office name]. The Director/Coordinator/Manager will provide overall project management and supervision.

A short-term consultant(s) may be recruited to assist in facilitating the review of data and consultations for the preparation of the Third National Report.  [Briefly describe any specific consultants foreseen and their tasks].

UNDP-[Name of Country Office] will monitor the project in accordance with the agreed budget and outputs and disburse funds to facilitate implementation.

Outputs

The outcome of the preparation process will be the Third National Report prepared in accordance with the CBD guidelines.

[List any specific outputs to be achieved during the preparation process if relevant].

Budget breakdown

| Activity | GEF Budget estimate (US $) |
| --- | --- |
| Synthesis of biodiversity information | $ |
| Stakeholder consultations | $ |
| Preparation of draft report | $ |
| Total | $ [not to exceed $20,000] |

- Workplan

[Please provide Workplan and Time-table]

Annex 2A

Country Request Format: Summary of Support Provided to [Country Name]

under the GEF Biodiversity Enabling Activities

[Please complete the following Table indicating the amount of support received by the country for each of the following eligible activities under the GEF Biodiversity Enabling Activities]

| ACTIVITY | TOTAL (US $ 000) |
| --- | --- |
| ORIGINAL ENABLING ACTIVITY |
| Original EA, less costs of CHM activities |  |
| CHM support (provided through add-on module or project itself) |  |
| Total support for EA: |  |
| ADDITIONAL REQUEST |
| 1. Assessment of Capacity-building needs for Implementation of measures for in-situ and ex-situ conservation and sustainable use methodologies to evaluate and mitigate specific threats to biodiversity components Biosafety Initial assessment and monitoring programs, including taxonomy Conservation and sustainable use of biodiversity important for agriculture Incentive measures Access to genetic resources, benefit-sharing and formulation of mechanisms for these purposes Preservation/ maintenance of biodiversity related knowledge of indigenous and local communities with traditional lifestyles Total new request |  |
| 2. Country-driven project for participation in the CHM |  |
| 3. Consultations for the preparation of a second national report |  |
| Sub-total Additional Funding Phase: |  |
| REQUEST FOR THIRD NATIONAL REPORT |  |
| Preparation of the Third National Report |  |
| TOTAL | 0 – 470 |

Annex 2B

Country Request Format:  Sample Total Budget and Work Plan

| Country: |
| --- |
| Title: PIMS 3456 BD: MSP Preparation of Third National Reports on Biodiversity - (3NR) |
| GEF Outcome | Responsible Party | Source of Funds | Budget Description | Amount 2005 (USD) | Amount 2006 (USD) | Total (USD) |
| OUTCOME 1: Third National Report prepared by [Country Name] | CO | GEF |  | International Consultants |  |  |  |
|  |  |  |  | Travel |  |  |  |
|  |  |  |  | Local Consultants |  |  |  |
|  |  |  |  | sub-total |  |  |  |
|  | Min. Envt | Govt. |  | International Consultants |  |  |  |
|  |  |  |  | Travel |  |  |  |
|  |  |  |  | Local Consultants |  |  |  |
|  |  |  |  | sub-total |  |  |  |
|  |  |  |  | TOTAL |  |  |  |
|  |  |  |  | GEF |  |  |  |
|  |  |  |  | Govt |  |  |  |
|  |  |  |  | Others |  |  |  |
|  |  |  |  | TOTAL |  |  |  |
|  |  |  |  | (inclusive of ISS) |  |  |  |

# Annex 2C

# Country Request Format:  Letter of Request from GEF Operational Focal Point

[Please attach OFP letter GEF requesting assistance for preparation of the Third National Report with the individual country request]

Annex 3: Letters of Request Received from GEF Operational Focal Points

See separate PDF file attached.

Annex 4: Terms of Reference

Sub-contract to prepare a Guidance document to assist countries in preparation of their Third National Reports

Background:

Experience from earlier rounds of Biodiversity Enabling Activities, which were assisted through the Biodiversity Planning Support Programme (BPSP), as well as experience in other focal areas which have global projects with central support units, has demonstrated that in addition to financial support some substantive technical support is also be needed by countries.  Therefore, in addition to providing funds to countries in a timely and expedited manner, this project will also commission the development of guidance material to provide substantive assistance to countries. It is expected that substantive guidance will enhance quality and result in greater level of standardization of the Third National Reports preparation process.

Scope of activity:

The guidance material could be developed in the form of a short and user friendly guide that includes some of the following elements:

- a suggested methodology on how countries could manage the “process” of preparation including synthesizing information, undertaking consultations with stakeholders, and validating information to be included in the report,

- draw upon some best practice examples of earlier reporting to the CBD (First and Second National Reports, and NBSAPs), and

- provide links to relevant thematic material available for countries to consult.

The terms of reference for guidance material will be further elaborated at a later stage and circulated to the GEF Secretariat, CBD Secretariat and other GEF Implementing Agencies for their inputs and endorsement.

Qualifications:

The work will be commissioned through a qualified institution or individual(s) with thorough knowledge of the CBD and its requirements, and understanding of consultative and analytical processes.

Time-Frame:

The guidance document is expected to be completed within the first 6 weeks of project implementation.

Annex 5: Draft Template for Framework Service Agreement

Date

Dear Mr/s. ResRep,

Subject: Country: Activity X GEF National Reporting to the CBD: Supporting countries to prepare the Third National Report on Biodiversity “3NR” (PIMS 3456)

The HQ managed project entitled “Global: National Reporting to the CBD: Supporting countries to prepare the Third National Report on Biodiversity (PIMS 3456)” has received its final approval in accordance with the established GEF and UNDP procedures.  As a sub-activity of the aforementioned HQs managed project, please be advised that the attached request for assistance entitled “Proposal for preparation of the Third National Report on Biodiversity:  GEF Additional Funding for Biodiversity Enabling Activities” budget and description of activities planned for 2005 have been approved.  Your office is hereby authorized to charge GEF account below for the usage of US $<20,000 (inclusive of ISS).

In order to ensure agile provision of services to the designated lead agency, kindly note the procedures for the use of the funds.  We are delegating the approval of specific expenditures to your office.  This procedure is effective immediately, and there is no need for separate authorization for each expenditure in Atlas by our unit in New York.

We are hereby issuing your office with the Authorized Spending Limit (ASL) up to US $$<20,000 for 2005.

The Award and Project has been created for your office with the following information:

|  |  |  |  |  | Project |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GLBU | Budgetary Code | Oper. Unit | Fund | Budget Department | Project No. | Activity ID | Impl. Agency | Donor |
| UNDP1 | 72600 | H21 | 62000 | B_ _ _ _ | 00044131 | ACTIVITY X | 001981 | 10003 |

FOR EXPENDITURE: Kindly ensure that expenditure is charged as per information below:

Chart of Account to Charge: GEF BD 3NR –PIMS 3456

|  |  |  |  |  | Project |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GLBU | Expenditure Account | Oper. Unit | Fund | Expenditure Department | Project No. | Activity ID | Impl. Agency | Donor |
| UNDP1 | 72605 | H21 | 62000 | CO to fill-in | 00044131 | ACTIVITY X | 001981 | 10003 |

Mr/s. Name

Resident Representative

UNDP, Country

Kindly note that the above mentioned budget and description of activities will be regarded as the framework service agreement between UNDP/GEF, your Office and the Government of ___ to incur expenditures according to the attached approved “Proposal for preparation of the Third National Report on Biodiversity:  GEF Additional Funding for Biodiversity Enabling Activities.”

In accordance with the approved “Proposal for preparation of the Third National Report on Biodiversity:  GEF Additional Funding for Biodiversity Enabling Activities”, your office shall disburse up to the total amount authorized: (a) to pay for the goods and supplies purchased by your office for the purposes of carrying out the approved activities; (b) to pay for the services contracted by your office for the purposes of carrying out the approved activities; and (c) to pay for any other non administration costs your office incurs for the purposes of carrying out the preparation of the Third National Report on Biodiversity.

Since this is a Global DEX project, the expenditure of the grant amount at the CO level should also be carried out using DEX procedure. In case the Government prefers to have greater flexibility in management of funds (as in the case of NEX projects) the CO should consider subcontracting the entire grant amount to the Government lead agency for them to manage this with greater flexibility and direct supervision. If requested by the Government, and within the limits imposed by the above-mentioned guidelines, your office may carry out the necessary adjustments to the budget and/or activities selected.

Relevant supporting documentation should be maintained by your office in case of future Audit. At the conclusion of the support, kindly confirm the operational completion of this activity and please provide the final report (i.e. the country's Third National Report to the CBD) to UNDP/GEF.

Yours sincerely,

Frank Pinto

Executive Coordinator

UNDP Global Environment Facility

- Mr./s. Name UNDP/GEF Country Office Focal Point
Mr./s Name, GEF Regional Coordinator, Location

#### Mr. Elson Decolongon, UNDP/GEF

Ms. Tehmina Akhtar, UNDP/GEF
	Ms. Cathy Maize, UNDP/GEF

SIGNATURE PAGE

Country: ____Global____

UNDAF Outcome(s)/Indicator(s):

To assist country parties to fulfill national reporting obligations under the global conventions (Convention on Biological Diversity).

Expected Outcome(s)/Indicator (s):

The project is aligned with MYFF 2004-2007 Goals and Service Lines 3.5 “Conservation and sustainable use of biodiversity”.

Expected Output(s)/Indicator(s):

National capacity building of key government institutions, and other stakeholders strengthened and improved with respect to biodiversity conservation.

Implementing partner:

The project will be executed through DEX Execution

Other Partners:

The project will closely involve the GEF Focal Point and CBD Focal Point Institutions (usually Ministries of Environment) in implementing project activities in the countries that are assisted through this global project.

Agreed by (UNDP):_____________________________________________________________

# Footnotes

It is recognized in view of the short time-frame remaining that not all countries will be able to complete these reports by 15 May 2005, in which case they will be encouraged to complete and submit these reports to the CBD by 31 December 2005 if possible.

It is recognized in view of the short time-frame remaining that not all countries will be able to complete these reports by 15 May 2005, in which case they will be encouraged to complete and submit these reports to the CBD by 31 December 2005 if possible.

The countries to be assisted will be drawn from among 94 countries, which have already worked with UNDP in conducting their earlier Biodiversity Enabling Activities and/or Add-on Phases. See Annex 1 for the list of countries. UNDP may prepare a second MSP request if additional demands for assistance are received from countries that may not be covered under the present proposal.

All terms, "ratification" (rtf), "accession" (acs), "approval" (apv) and "acceptance" (acp), signify the consent of a State to be bound by a treaty.

Botswana has already received GEF assistance for the Third National Report as part of a broader Additional Funding request submitted in December 2004. It will therefore not receive funding under this MSP.

Countries which have proposals for larger Add-on phases in the pipeline may also choose to include the Third National Report as an activity within these proposals, in which case they will not receive any funding from this MSP.

Zambia is likely to include the Third National Report preparation as an activity within a broader Additional Funding request to be submitted shortly. It will therefore not receive funding under this MSP.

Indicate the status of plans/reports, whether these are still under finalization or under implementation, and whether these have been endorsement by government or parliament as relevant. Please provide any additional comments.

This synthesis should ensure that preparation of the Third National Report builds upon lessons learned and previous findings and achievements. It should review and draw upon the National Biodiversity Strategy and Action Plan and earlier National Reports submitted to the CBD, as well as new studies or analyses focusing on areas or sectors not previously covered, and take account of more recent and up-to-date biodiversity information where available.

The preparation process is intended to be highly consultative and participatory to ensure a more accurate and comprehensive reflection of the views and priorities of national stakeholders.  Consultations could include national, regional, local level meetings, thematic consultations, questionnaires or other modes of stakeholder participation.

Cost estimates for each line item (for which funding has been requested) to be indicated.

In light of paragraph 4 (c) of the Revised Guidelines for Additional Funding of Biodiversity Enabling Activities (Expedited Procedures) of October 2000.

to be prepared during project preparation for HQs/GEF entry into Atlas . Upon approval of proposal, HQ/GEF will delegate to the CO the approval of specific expenditures to be charged against the project along with ASL details.

Insert 4 digit department code for the country – see GEF Quick Guide to AWP RPF.doc p.6 on digital workspace

# Text boxes

Brief description

This umbrella project is designed to assist at least 49 countries in the preparation of their Third National Reports on Biodiversity in order to meet their national reporting requirements under the Convention on Biological Diversity (CBD).  This project, through its umbrella approach, is intended to provide expedited assistance to countries and reduce transaction costs of individual requests.  Its benefits will include enabling country parties to the CBD to improve the quality and timeliness of their reporting as called for under Decision VII/25B of the CBD.

SECTION I : Elaboration of the Narrative

SECTION III : Total Budget and Workplan

#### SECTION IV : ADDITIONAL INFORMATION

Total budget:		 _$ 1 mil_____

Allocated resources:	 ____________

- Government		 _(in-kind)_tbd_

- Regular 		 ____________

- Other:

  - Donor	___$ 1 mil (GEF)_

  - Donor	_________

  - Donor	_________

- In kind contributions  _______ (govt. contributions expected)____

Programme Period:_ _

Programme Component:_________

Project Title: National Reporting to the CBD: Supporting countries to prepare the Third National Report on Biodiversity

Project ID: _ Atlas: Proposal 00039377, Project: 00044131 _

Project Duration:	__1 year__11 April 2005 – 10 April 2006_

Management Arrangement: __DEX____

[Once the GEF CEO  has approved the MSP proposal, add letter(s) of financial commitment, MOUs with executing agency if relevant, and other official agreements.]

SECTION V : Supplemental annexes

#### SECTION II : STRATEGIC RESULTS FRAMEWORK