# UNDP Project Document

PDF B Project

United Nations Development Programme

International Maritime Organization

Building Partnerships to Assist Developing Countries to Reduce the Transfer of Harmful Aquatic Organisms in Ships’ Ballast Water and Sediments

(GloBallast Partnerships)

Table of Contents

Section										    Page

UNDP Project Document	1

SECTION I   :   ELABORATION OF THE NARRATIVE	4

PART I      :   Situation Analysis	4

PART II    :   Strategy	4

PART III  :   Management Arrangements	5

SECTION II :    STRATEGIC RESULTS FRAMEWORK	7

SECTION III :  TOTAL BUDGET AND WORKPLAN	8

SECTION IV :  ADDITIONAL INFORMATION	9

PART I       :  PDF-B Proposal	9

PART II     :  Organigram of Project	20

PART III :  Terms of Refernce	22

Acronyms

| AA | : | Administrative Assistant |
| --- | --- | --- |
| AC | : | Ad-hoc Consultants |
| FOEI | : | Friends of the Earth International |
| GBP | : | GloBallast Partnerships |
| GEF | : | Global Environmental Facility |
| GloBallast | : | Global Ballast Water Management Project |
| GTF | : | Global Task Force |
| ICS | : | International Chamber of Shipping |
| IFI | : | International Financial Institutions |
| IMO | : | International Maritime Organization |
| INTERTANKO | : | International Association of Independent Tanker Owners |
| IUCN | : | World Conservation Union |
| IW | : | International Waters |
| LC | : | Lead Consultant |
| LPIR | : | Legal, Policy and Institutional Reforms |
| MER | : | Monitoring, Evaluation and Reporting |
| NGO | : | Non-Governmental Organisation |
| OCIMF | : | Oil Companies International Marine Forum |
| PDF-B | : | Project Development Fund-B |
| PIP | : | Project Implementation Plan |
| PM | : | Project Manager |
| PMU | : | Project Management Unit |
| SAP | : | Strategic Action Plan |
| TAG | : | Technical Advisory Group |
| UNDP | : | United Nations Development Programme |

# SECTION I : ELABORATION OF THE NARRATIVE

## PART I: Situation Analysis

GEF, during 2001-2004, funded a pilot phase IW Project (GloBallast Project) to remove the barrier to the effective implementation of ballast water control and management measures in developing countries and to minimise the risk of introduction of alien invasive species through ships’ ballast water and sediments. This project has precipitated an unprecedented momentum of concerted international action and a number of new countries and especially new regions that are potentially vulnerable to marine bioinvasions have expressed strong interest in replicating and building on the GloBallast activities. However, the knowledge base, legal/policy framework and institutional capacity as well as coherent regional approaches required to give effect to an international regime for the control and management of ships’ ballast water remain severe constraints for most of these countries. To sustain the momentum created by GloBallast Project and to assist developing countries to enact, through effective partnerships, the necessary national level policy, legal and institutional reforms, a second GEF intervention is needed in order to support the incremental costs. This will facilitate a logical expansion of the pilot phase, with a focus on national policy, legal and institutional reforms in targeted developing countries with an emphasis on integrated management, partnership and regional cooperation.

Due to the complexity of the ballast water issue, and the broad, multi-disciplinary nature of the proposed follow-up project, it will be necessary to undertake a PDF-B project for an 18 month period to identify the vulnerable and sensitive areas, the most appropriate participants and partners, and to develop the Project Brief for submission to GEF. Considerable effort is needed for consultations with countries, industry and other stakeholders and partners during a PDF-B design phase, to ensure the full project best reflects and addresses stakeholder needs and priorities. A PDF-B is also necessary to identify and secure the substantial co-financing and resourcing that is needed for the full project, over and above the incremental funding being sought from GEF, including from multi-lateral donors, bi-lateral donors, regional organizations, "sister" GEF-IW projects, NGOs such as IUCN and the private sector. The strengths derived from the pilot phase and the extensive communication networks, consultation mechanisms and awareness raising programmes established during the GloBallast Project will significantly help the PDF-B process in achiving the expected outcomes and in ensuring continuity and synergies between the GloBallast Project, the PDF-B and the proposed future project (GloBallast Partnerships). The experience gained by the the six pilot phase countries, the regional task forces that are in place  and the project personnel whose expertise and know-how on the regional issues and needs can all be effectively used  for the PDF-B process to design an optimum full-scale project. Morever, the new International Convention on Ballast Water Management would give the PDF-B process a solid foundation to design a full project aiming at national level legal and policy reforms.

## PART II : Strategy

The Full Project, which will run for about 5 years, will be a logical expansion of the pilot phase, with a greater focus on policy and legal reforms in targeted developing countries and more emphasis on integrated management. The project will be designed to build on the lessons learned during the pilot phase and will be based on the principle of “on the ground” implementation. A number of activities particularly successful in the initial phase, will be replicated in other ports and particularly sensitive areas. The GEF supported activities will focus on assisting specially vulnerable and sensitive countries to enact the reforms to implement the international regime. The project will ensure a globally uniform approach and, to the extent possible, global coverage of the developing regions of the world. The project strategy is to maximize benefits by using a partnership approach, and will aim to establish strategic alliances with other organizations and programmes that are endeavouring to address the problem of invasive aquatic species and will seek to integrate ballast water management activities with other coastal and marine management programmes, thereby increasing cost-effectiveness and creating inter-programme synergies.

This PDF-B project will lay the foundation for the Full Project and develop the Project Brief for presentation to GEF.   To this end, it will assemble a PDF-B development team, develop criteria for identification of vulnerable and sensitive areas by utilizing the relevant previous and parallel works and experiences,  hold full consultations with stakeholders necessary for the preparation of the Project Brief  and to secure “Partners”, collect baseline information on relevant issues, areas and needs, develop stakeholder involvement and communication plans, develop generic Legal, Policy and Institutional Reform plan (LPIR), develop an initial Monitoring, Evaluation and Reporting (MER) plan and prepare a Project Brief conceptualizing the full project and confirming the commitment of the participating countries and partners. The project design, in the form of the LogFrame Matrix will be developed in a participatory manner and adopted by consensus.  Likewise, the Project Brief will be shared with stakeholders and ultimate beneficiaries during its development stages so as to engender a feeling of ownership among the community and a degree of sensitivity towards the goals of the Full Project. The existing regional task forces and communication networks established in the pilot phase will be extensively utilized to facilitate the PDF-B process.

## PART III : Management Arrangements

The PDF-B project will be implemented by UNDP and executed by the International Maritime Organization (IMO). IMO will be responsible for overall coordination and delivery of  all activities under the PDF-B project. The Project Management Unit (PMU) set up by IMO will be responsible for the day to day monitoring and administration of the Project and for project management. The IMO Office for Ballast Water Mangement will work seamlessly with PMU on this project and will provide the technical backstopping for the project. IMO will also provide the project with operational premises and will assist with country coordination when required. It is assumed that most contact will be directly with countries through their IMO focal points.

UNDP will ensure appropriate linkage to the Project with related GEF and other internationally supported projects, notably linkages with International Waters projects involved in marine and coastal zone management. UNDP will also provide the technical and policy backstopping including partcipation in the Global Task Force meetings.

A Global Task Force (GTF) will be established to guide the project development activities. The GTF will consist of representatives of all the countries involved in the project, UNDP/GEF, IMO, the International Financial Institutions (IFI) and other potential donors. The GTF, which will act in the role of a project advisory committee will endorse the Project Implementation Plan, SAPs and major project outputs. The existing cooperation with the International Association of Independent Tanker Owners (INTERTANKO), Oil Companies International Marine Forum (OCIMF), International Chamber of Shipping Limited (ICS), Friends of the Earth International (FOEI), World Conservation Union (IUCN) and other major NGOs with an interest in ballast water and invasive species will be continued and enhanced by inviting their representatives to observe the meetings of the GTF. A Technical Advisory Group (TAG), comprising internationally renowned subject matter experts will be invited to partcipate in the GTF meetings.

An Organigram for the project is given in Section IV.  The PMU will comprise:

•	the current GloBallast Technical Adviser based at IMO in London, who will act as project manager (PM) for the duration of the PDF-B phase; and

•	administrative support personnel;

The PMU will identify and hire a team of consultants to support the Project Development Activities. This team will comprise:

•	a suitably qualified and experienced Lead Consultant (LC) engaged to carry out specific tasks

•	An internationlly recruited legal consultant as well as Ad-hoc Consultants (ACs) and IT experts will be engaged on an as-needed basis throughout the PDF-B period, to assist the PM and LC as required.  The ACs will be drawn, to the extent possible, from the expertise and capacity built in the six Pilot Countries during the GloBallast pilot project.

The PMU supported by the consultant team will be responsible for carrying out the PDF-B and developing the full Project Brief.  The primary role of the PM, who will directly report to the Director, IMO Marine Environment Division, will be to oversee, manage and coordinate the PDF-B process,  to ensure continuity and synergies between the GloBallast pilot project, the PDF and any future project, and to ensure close communication and coordination between the preparatory process and the IMO. The primary role of the LC will be to lead and undertake the core of the PDF activities, in particular the main partner and stakeholder consultations and development of the Project Brief itself. The primary role of the ACs will be to undertake information gathering and to assist, support and facilitate partner and stakeholder consultations in each region, utilising the well-developed communication networks and consultation mechanisms established during the GloBallast pilot project.

In order to accord proper acknowledgement to GEF for providing funding, a GEF logo will appear on all relevant GEF project publications, including among others, project hardware and vehicles purchased with GEF funds. Any citation on publications regarding projects funded by GEF will also accord proper acknowledgment to GEF.

# SECTION II : STRATEGIC RESULTS FRAMEWORK

Table 1: Indicative Outputs, Activities and quarterly workplan

| Outputs | Activities | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 PMU Establishment | 1.1.1 Hiring of PM | X |  |  |  |  |  |
|  | 1.1.2 Hiring of AA | X |  |  |  |  |  |
| 2.1 Vulnerable Area Criteria | 2.1.1 Desk-top Study | X |  |  |  |  |  |
|  | Consultations with IMO States |  | X |  |  |  |  |
| 3.1 1st GPTF Meeting | 3.1.1 Meeting Preparation | X |  |  |  |  |  |
|  | 3.1.2 Hold the Meeting |  | X |  |  |  |  |
|  | 3.1.3 GPTF Report |  | X |  |  |  |  |
| 4.1 Information Gathering | 4.1.1 Global Information gathering | X | X |  |  |  |  |
|  | 4.1.2 Needs Assessment |  |  | X |  |  |  |
|  | 4.1.3 Global Synthesis |  |  |  | X |  |  |
| 5.1 Stakeholder / communication Plans | 5.1.1 Development of Plan | X | X |  |  |  |  |
|  | 5.1.2 Web-site / E-forums | X | X | X | X | X | X |
| 6.1 Partnership analysis and stakeholder engagement | 6.1.1 Consultations with Beneficiary countries |  |  | X | X | X |  |
|  | 6.1.2 Consultations with donors/contributors |  |  | X | X | X |  |
| 7.1 Generic LPIR Plan | 7.1.1 Develop LPIR Plan |  | X | X |  |  |  |
| 8.1 Initial MER Plan | 8.1.1 Develop MER Plan |  |  | X | X |  |  |
| 9.1 Draft Project Brief | 9.1.1 Prepare Draft Project Brief |  |  |  | X | X |  |
| 10.1 2nd GPTF Meeting | 10.1.1 Meeting Preparation |  |  |  | X | X |  |
|  | 10.1.2 Hold the Meeting |  |  |  |  | X |  |
|  | 10.1.3 GPTF Report |  |  |  |  | X |  |
|  | 10.1.4 Preparation and submission of Final Project Document |  |  |  |  |  | X |

# SECTION III : TOTAL BUDGET AND WORKPLAN

| Award ID: |  |
| --- | --- |
| Project Title: | Building Partnerships to Assist Developing Countries to Reduce the Transfer of Harmful Aquatic Organisms in Ships’ Ballast Water (GloBallast Partnerships) |
| GEF Outcome/Atlas Activity | Responsible Party | Source of Funds | Atlas Code | ERP/ATLAS Budget Description/Input | Amount (USD) Year 1 | Amount (USD) Year 2 | Total (USD) |
| Outcome 1: Project Management Unit established | IMO | GEF | 71400 | Project Manager | 120,000 | 60,000 | 180,000 |
|  | IMO | GEF | 71300 | Admin. Assistant | 60,000 | 30,000 | 90,000 |
|  | IMO | GEF | 71300 | Local Consultants | 60,000 | 12,000 | 72,000 |
|  | Sub-Total | 240,000 | 102,000 | 342,000 |
| Outcome 2Vulnerable Area Criteria developed | IMO | GEF | 71200 | Intl. Consultant | 4,000 | 0 | 4,000 |
|  | Sub-Total | 4,000 | 0 | 4,000 |
| Outcome 3.: First GPTF meeting organised | IMO | GEF | 71600 | Travel | 52,000 | 0 | 52,000 |
|  | Sub-Total | 52,000 | 0 | 52,000 |
| Outcome 4: Basic information gathered | IMO | GEF | 71200 | Intl. Consultant | 10,000 | 0 | 10,000 |
|  | Sub-Total | 10,000 | 0 | 10,000 |
| Outcome 5 Stakeholder / communication Plans developed | IMO | GEF | 71400 | Contractual Services-Ind. | 4,000 | 0 | 4,000 |
|  | Sub-Total | 4,000 | 0 | 4,000 |
| Outcome 6: Partner consultations completed | IMO | GEF | 71200 | Intl. consultant | 35,000 | 10,000 | 45,000 |
|  | IMO | GEF | 71600 | Travel | 65,000 | 35,000 | 100,000 |
|  | Sub-Total | 100,000 | 45,000 | 145,000 |
| Outcome 7: Generic LPIR plan developed | IMO | GEF | 71200 | Intl. consultant | 10,000 | 0 | 10,000 |
|  | IMO | GEF | 71600 | Travel | 10,000 | 0 | 10,000 |
|  | Sub-Total | 20,000 | 0 | 20,000 |
| Outcome 8: Initial MER Plan developed | IMO | GEF | 71200 | Intl. consultant | 4,000 | 0 | 4,000 |
|  | Sub-Total | 4,000 | 0 | 4,000 |
| Outcome 9: Draft Project Brief completed | IMO | GEF | 71600 | Intl Consultant | 10,000 | 5,000 | 15,000 |
|  | Sub-Total | 10,000 | 5,000 | 15,000 |
| Outcome 10: 2nd GPTF meeting organised | IMO | GEF | 71600 | Travel | 0 | 52,000 | 52,000 |
|  | Sub-Total | 0 | 52,000 | 52,000 |
| Total | 444,000 | 204,000 | 648,000 |
| Executing Agency Support (8%) | 35,520 | 16,320 | 51,840 |
| Total GEF Funds | 479,520 | 220,320 | 699,840 |

# SECTION IV : ADDITIONAL INFORMATION

## PART I :     PDF-B Proposal

Due to the complexity of the ballast water issue and the broad, multi-disciplinary nature of the proposed Project, it will be necessary to undertake a PDF-B stage for an 18 month period to identify the most appropriate participants, secure co-financing, design the full project and develop the Project Brief.

The immediate objective of the PDF-B will be to carry out preparatory activities for the full scale GEF project that will assist developing countries to implement through effective partnerships the necessary national level policy reforms to prevent, minimize and ultimately eliminate risk to the environment, human health, property and resources arising from the transfer of invasive aquatic species and pathogens in ships’ ballast water. The PDF-B will include, but will not be limited to, the following activities:

Activity 1: PDF-B Development Team:

Given the global scope and complexity of this project, it is necessary to assemble a PDF-B development team.  In order to ensure continuity and optimise benefits from and build upon the strong foundations, excellent knowledge base, significant capacity and well-developed communication networks and consultation mechanisms established during the GloBallast pilot project, this team will comprise:

•	the current GloBallast Technical Adviser based at IMO in London (Dr Jose Matheickal of India), who will act as project manager (PM) for the duration of the PDF-B phase;

•	administrative support personnel;

•	a suitably qualified and experienced Lead Consultant (LC) engaged to carry out specific tasks as described below;

•	An internationally recruited legal consultant and Ad-hoc Consultants (ACs) engaged on an as-needed basis throughout the PDF-B period, to assist the PM and LC as required.  The ACs will be drawn, to the extent possible, from the expertise and capacity built in the six Pilot Countries during the GloBallast pilot project.

This team will be responsible for carrying out the PDF-B and developing the full Project Brief.  The primary role of the PM will be to oversee, manage and coordinate the PDF-B process, from IMO in London, to ensure continuity and synergies between the GloBallast pilot project, the PDF and any future project, and to ensure close communication and coordination between the preparatory process and the IMO.

The primary role of the LC will be to lead and undertake the core of the PDF activities, in particular the main partner and stakeholder consultations and development of the Project Brief itself.

The primary role of the ACs will be to undertake information gathering and to assist, support and facilitate partner and stakeholder consultations in each region, utilising the well-developed communication networks and consultation mechanisms established during the GloBallast pilot project.

Terms of Reference for the PM, LC and ACs are contained in Part III.

Other expert consultants may be engaged as required (e.g. to develop the generic legal / policy reform plan).

IMO will supervise, coordinate and support the PDF-B activities for the duration of the project.

No additional PDF-B funds are required for this Activity.

Activity 2: Vulnerable area ID criteria:

In order to identify sites, countries and/or geographic areas of concentration suitable as potential high-priority beneficiaries under the full-scale Project, it is necessary to develop criteria for the identification of "vulnerable areas" sensitive to aquatic bio-invasions through unmanaged ballast water discharges.

This Activity will be undertaken by the PM and LC with support from the AC's and IMO, and will utilise:

•	the outputs of the pilot project Ballast Water Risk Assessments,

•	relevant guidelines being developed by the IMO Marine Environment Protection Committee (MEPC), under the auspices of the new IMO Ballast Water Management Convention,

•	relevant activities being undertaken by IMO member States, NGOs, IGOs, academia and the private sector.

This approach is cost-effective in that it builds-on and optimises use of relevant previous and parallel work, including the outputs of the GloBallast pilot project.

Inputs to this Activity from IMO, MEPC, individual member States, NGOs, IGOs, academia and the private sector represent significant support-in-kind for the PDF-B.

PDF-B funds are required to recruit the consultants for this activity.

Activity 3: 1st Global Task Force (GTF) meeting:

In order to develop a shared vision for the full Project and a participatory workplan for the PDF-B, and to agree on PDF-B coordination and information sharing mechanisms, it is necessary to organize and convene an initial Global Task Force (GTF) meeting early in the PDF-B time frame, with the direct participation of IMO, UNDP and other major stakeholders. Representatives from the potential beneficiary countries will also be invited.

A venue and meeting facilities will be secured from the host organization as support-in-kind for the PDF-B.

PDF-B funds are required to cover staff time / fees for the attendance of the consultants and the travel and DSA of all GTF members for this meeting.

Activity 4: Information gathering:

In order to support and inform the PDF-B process and development of the full Project Brief, it is necessary to collect basic information on a variety of issues and areas early in the PDF-B time frame. This Activity will be undertaken by the PM and LC with support from the AC's and IMO, utilising:

•	the outputs of the GloBallast pilot project, and

•	relevant activities being undertaken by MEPC, IMO member States, NGOs, IGOs, academia and the private sector.

This approach is cost-effective in that it builds-on and optimises use of relevant previous and parallel work.

Inputs to this Activity from IMO, MEPC, individual member States, NGOs, IGOs, academia and the private sector represent significant support-in-kind for the PDF-B.

PDF-B funds are required to recruit the consultants for this activity.

Activity 5:  Develop stakeholder involvement & communication plan:

In order to ensure cross-sectoral participation in both the PDF-B and the implementation of the full project, it is necessary to develop a stakeholder involvement and communication plan.  This Activity will be undertaken by the PM and LC with support from the AC's and IMO.

During the PDF this Activity will link closely with Activity 6, as well as involve the continuation of the existing stakeholder involvement mechanisms and communication networks established under the GloBallast pilot project.  These include the GloBallast Information Clearing House mechanism (global web-site, directories &  E-Forum and six pilot country web sites), as well as the six Regional Task Forces that have been established and are now functioning as an outcome of the pilot project.  These mechanisms have proven highly effective during the pilot project, and optimising their established success through continuity will also bring major benefits to the PDF-B and the full Project.

IMO will continue to host, manage and maintain the GloBallast Information Clearing House mechanism (web-site, directories, E-Forum etc). The six initial pilot countries will be encouraged to do the same for their national web sites and information systems, as support-in-kind to the PDF-B (and later the full Project).

PDF-B funds are required to recruit the consultant for this activity.

Activity 6: Partner & stakeholder consultations & engagement:

A major objective of the PDF-B is to identify and secure "Partners" for the full Project.  Potential partners can be divided into three main groups as follows:

•	the beneficiary countries / groups of countries (regions), which must be GEF-eligible developing countries;

•	donors and other "contributors"; that are sources of co-financing, support-in-kind and other forms of support for the Project, over-and above the incremental support being sought from GEF;

•	other GEF or regional projects with an interest in invasive species (e.g. LMEs, UNEP regional sees programmes, etc.)

Activity 6.1: Consultations / engagement with beneficiary countries / regional mechanisms

During the GloBallast pilot project many developing countries have expressed strong interest in being included as beneficiary countries under the proposed GloBallast Partnerships project, both through direct representations to IMO and through regional Inter-governmental Organizations (IGO's), including through the formation of Regional Task Forces and formal adoption of regional ballast water management plans.

During the PDF-B it will be necessary to enter into detailed consultations with potential beneficiary countries / regional mechanisms to provide coordinated national inputs from relevant stakeholders, effect resources mobilization and confirm and secure full project co-funding commitments. Standardised MoUs or Letters of Agreement will be used to confirm the interest of potential beneficiaries.  The PDF-B will select suitable beneficiary countries / regions for inclusion in the full Project Brief based on:

•	the criteria developed under Activity 2,

•	the degree of country / region commitment (including formal sign-on and commitment of national / regional resources and co-finance), and

•	other relevant GEF criteria.

For cost-effectiveness, national consultations will be undertaken:

•	during attendance of IMO member States at MEPC meetings,

•	through consultation missions by the PM / LC / ACs to meetings of the Regional Task Forces that have been established / are now functioning as an outcome of the pilot project, in-conjunction with inter-governmental meetings of relevant IGOs (e.g. ROPME, SPREP,  CEP, MAP, PERSGA, CPPS etc), and

•	through consultation missions by the PM / LC / ACs to selected individual high priority countries.

PDF-B funds will be required to cover travel, DSA and consultants fees for the missions under this Activity (combined with 6.2 below).

Activity 6.2: Consultations / engagement with donors / contributors:

Many potential donors / contributors / other groups have expressed interest in becoming partners in the GloBallast Partnerships Project.  These include multi-lateral donors such as the European Union and regional development banks, bi-lateral donors (developed-country aid agencies), regional organizations such as APEC, ASEAN, HELCOM etc, "sister" GEF-IW projects (especially the LME projects), NGOs such as IUCN and the private sector.

During the PDF-B the PM, LC and ACs, supported by the IMO, will undertake consultation missions to these potential partners to secure their involvement and formal commitment in the full Project Brief.  For cost-effectiveness, these missions will be undertaken in conjunction / coordination with those for beneficiary countries / regions under Activity 6.1.

A draft workplan and timeline for the 6.1 and 6.2 missions will be developed at the 1st GTF meeting.

PDF-B funds will be required to cover travel, DSA and consultants fees for the missions under this Activity (combined with 6.1 above).

Activity  7: Develop generic Legal, Policy and Institutional Reform (LPIR) plan:

A major objective of the full Project will be to enable the beneficiary countries to enact the necessary national-level legal, policy and institutional reforms in order to achieve sustainable management and control of ships' ballast water, so as to minimize harmful aquatic bio-invasions.

The full Project Brief must therefore include a generic Legal, Policy and Institutional Reform (LPIR) plan.  Development of this generic plan will be undertaken during the PDF-B through engagement of a relevant expert (legal consultant), building on the outputs of the Legislative Review undertaken during the GloBallast pilot project and supported by the PM and IMO.

PDF-B funds will be required to cover travel, DSA and LPIR consultant fees under this Activity.

Activity 8: Develop initial Monitoring, Evaluation and Reporting (MER) plan:

An important component of the full Project Brief will be a monitoring, evaluation and reporting (MER) plan with process, environmental status and stress reduction indicators. Development of an initial MER plan will be undertaken during the PDF-B by the PM and LC supported by IMO and with inputs from MER experts at UNDP and GEF-SEC.

PDF-B funds are required to recruit the consultants for this activity.

Activity 9:  Prepare a first draft Project Brief:

The primary output of the PDF-B is of-course the Project Brief that will conceptualise the full Project and confirm the commitment of the participating countries and partners. The LC will be engaged to develop the draft Project Brief, incorporating the outputs of Activities 2 to 8, for submission to IMO, UNDP, GEF and other stakeholders for review and comment, prior to review, finalisation and adoption by the GTF at its second meeting.

PDF-B funds are required to recruit the consultants for this activity.

Activity 10: 2nd GTF Meeting:

The 2nd GTF meeting will review, finalise and adopt the Full Project Brief for submission to GEF Council.

A venue and meeting facilities will be secured from the host organization as support-in-kind for the PDF-B.

PDF-B funds are required to cover staff time / fees for the attendance of the consultants and the travel and DSA of all GTF members for this meeting.

Project Brief for full project

The ultimate output of the PDF-B will be from Activities 9 and 10 - the final Project Brief for the full GloBallast Partnerships project, for submission to the GEF Council for consideration for funding.

Detailed design of the full Project, including its development objectives, immediate objectives, components, outputs, outcomes and activities, as well as workplan and budget, and coordination, management and institutional arrangements, are vital outputs of Activities 6 to 9 that will be included in the Project Brief. The full project will assist developing countries to implement the necessary national level reforms, through effective partnerships, to prevent, minimize and ultimately eliminate risks to the environment, human health, property and resources arising from the transfer of invasive aquatic species and pathogens in ships’ ballast water.

Vulnerable Area Criteria

In order to identify sites, countries and/geographic areas of concentration suitable as potential high-priority beneficiaries under the full-scale Project, Activity 2 will develop, criteria for the identification of "vulnerable areas" sensitive to aquatic bio-invasions through unmanaged ballast water discharges. This output will not only be useful in the PDF-B, but to the general global community in developing, prioritising and targeting its responses to the ballast water and aquatic invasive species issue.

Identifying / securing partners, commitment & co-financing

Significant and vital outputs of the PDF-B that must be part of the Project Brief include the outputs of Activity 6 - identification and securing of the most appropriate participants and partners (beneficiaries, donors/other and other contributors), with incremental cost analysis and commitment and co-finance documentation.

Stakeholder Involvement and Communication Plan, Generic LPR Plan and MER Plan

Additional outputs of the PDF-B, also to be included in the Project Brief, will be the Stakeholder Involvement and Communication Plan (Activity 5), the generic Legal, Policy and Institutional Reform Plan (needed to effect the necessary national-level reforms in the beneficiary countries) (Activity 7), and the Monitoring, Evaluation and Review Plan (including process, environmental status and stress reduction indicators) (Activity 8).

Outcomes

In addition to these outputs, the activities carried out under the PDF-B will produce a number of important and valuable outcomes.  These include further developing, replicating, strengthening and building upon the foundations, excellent knowledge-base, significant capacity, well-developed communication networks and consultation mechanisms, as well as the national and regional institutional arrangements, established during the GloBallast pilot project, by ensuring continuity and synergies between the pilot project, the PDF-B and the proposed future project.

Utilising and building upon the highly successful pilot project communication campaign and infrastructure, by maintaining and further developing these under Activity 5, will continue to ensure significant increases in awareness and understanding of ballast water as a vector for the transfer of aquatic invasive species.  This is considered to be fundamental and vital to effectively addressing the issue, especially in developing countries.

A major outcome of the GloBallast pilot project has been to stimulate a significant increase in investment in a range of responses to the issue globally, both in developing and developed economies, by governments and industry. Its is highly likely that the communication, awareness and stakeholder engagement and partner consultation activities under the PDF-B, will continue to produce this outcome, over and above co-financing secured directly for the full project.  Over time, the impact of this will be to actually begin to reduce the rate of harmful aquatic bio-invasions.

C – JUSTIFICATION

In the last ten years or so, scientists, governments and the shipping industry have come to recognize aquatic invasive species, including the transfer of harmful organisms in ships’ ballast water and sediments, as one of the greatest threats to global marine bio-diversity and ecosystems, and also a significant threat to coastal economies and even public health. Global economic impacts from invasive aquatic species, including through disruption to fisheries, fouling of coastal industry and infrastructure and interference with human amenity, are estimated to exceed tens of billions of US dollars per year. The United Nations Environment Programme (UNEP) and World Conservation Union (IUCN), announced at the World Summit on Sustainable Development (WSSD) in Johannesburg in 2002, that invasive species are the second greatest threat to global bio-diversity after habitat loss. The US General Accounting Office (2003) has identified biological invasions as one of the greatest environmental threats of the 21st Century.

The impacts are set to aggravate in coming years with a three-fold increase in shipping activity predicted in the next decade.  Developing and transitional economies in Africa, Asia, South America and Eastern Europe, as well as Small Island Developing States, are at particular risk as globalisation of the world economy continues and new markets, trading patterns and therefore ports and shipping routes are opened in these areas.

Every major international conference and several international Conventions on the environment in the last decade, including the United Nations Conference on Environment and Development in 1992, the United Nations Convention on the Law of the Sea (UNCLOS), the Conferences of Parties to the Convention on Biological Diversity (CBD), the World Summit on Sustainable Development in 2002 and the 5th World Congress on Protected Areas in 2003, have highlighted the issue of invasive species, and called upon governments and industry to act.  Several international Conventions contain specific provisions relating to invasive species, including UNCLOS and the CBD, as well as several regional intergovernmental Conventions and Protocols.  IMO of-course has adopted various guidelines and the International Convention for the Control and Management of Ships’ Ballast Water and Sediments.  Virtually all of these international instruments contain provisions requiring technical cooperation and assistance programmes, skills and technology transfer between developed and developing countries, as well as the provision of funding mechanisms for these.

Responding to the ballast-mediated aquatic bio-invasions poses enormous scientific, technological, institutional, socio-economic, legal and political challenges.  This highly complex and multi-disciplinary problem encompasses biology, chemistry, physics, engineering, law, economics and ecology, not to mention ship design, construction and operation and interactions between flag, port and coastal States.

Due to the complexity of the ballast water / invasive species issue, and the broad, multi-disciplinary nature of the proposed GloBallast Partnerships project, it will be necessary to undertake a PDF-B stage for an 18 month period to identify the most appropriate participants, design the Project and develop the Project Brief.  The complexities of the issue, as outlined above, pose even greater challenges for developing countries.  Carrying out a thorough PDF-B is vital to ensure that the full-project is optimally designed, so as to best assist these countries to meet these challenges, and maximise returns from deployment of the GEF incremental funding.  Proceeding directly with a full project, without the PDF-B phase, may not ensure that all of the complexities are properly considered and reflected in project design.  Considerable effort must be put into consultations with countries, industry and other stakeholders and partners during a PDF-B design phase, to ensure the full project best reflects and addresses stakeholder needs and priorities.

A PDF-B is of-course necessary in order to identify the vulnerable and sensitive sites, countries and/or regions suitable as potential high-priority beneficiaries for inclusion in the full-scale Project.  As this is a truly global issue and because an extremely large number of countries have expressed strong interest in being involved in GloBallast Partnerships, this ‘selection’ process requires close attention and the application of objective, fair, equitable and transparent criteria, which is best achieved through a PDF-B.

A PDF-B is also necessary to identify and secure the substantial co-financing and resourcing that is needed for the full project, over and above the incremental funding being sought from GEF, including from multi-lateral donors, bi-lateral donors, regional organizations, "sister" GEF-IW projects, NGOs such as IUCN and the private sector.  This is of-course vital to the success of the full project, and cannot be achieved without a PDF-B.

Finally, the GloBallast pilot project has achieved significant outputs and outcomes, including inter alia: effective institutional and management arrangements, major increases in capacity, substantially improved understanding and awareness, development and demonstration of best-practices and management tools, significant increases in investment in responding to the issue globally and well-developed communication networks and consultation mechanisms, as well as functioning National and Regional Task Forces and formally-adopted national and regional action plans for ballast water management in the main developing regions of the world.  It is highly desirable that the outputs and outcomes of the GEF investment in the pilot phase are not lost, that additional developing countries are able to benefit from these achievements, through ensuring sustainability and continuity between the pilot phase and the proposed future project.  The PDF-B is vital for bridging the gap between the end of the pilot phase (Dec 04) and the proposed start of the future project (late 06).  Without a bridging and continuity mechanism, the significant global momentum and increased engagement of developing countries that has been catalysed by the pilot phase will be lost, and the results, impacts and other benefits from the initial GEF intervention will be substantially reduced.

## PART II : Organigram of Project

SIGNATURE PAGE

Country:

UNDAF Outcome(s)/Indicator(s):

(Link to UNDAF outcome., If no UNDAF, leave blank)

Strengthening Decentralization

Expected Outcome(s)/Indicator (s):

(CP outcomes  linked t the SRF/MYFF goal and service line)

Expected Output(s)/Indicator(s):

(CP outcomes  linked t the SRF/MYFF goal and service line)

Implementing partner:	International Maritime Organization

(designated institution/Executing agency)

Other Partners:

(formerly implementing agencies )

Agreed by (Government): _____________________________________________________________

Agreed by (International Maritime Organization):

_____________________________________________________________

Agreed by (UNDP):

_____________________________________________________________

# Text boxes

Brief description:  The PDF-B Project will develop the Project Document for a full scale GEF project (GloBallast Partnerships) that will aim to expand and build on a successfully completed global project on removing barriers to the effective implementation of ballast water control and management measures in developing countries (GloBallast Project).

The GloBallast Partnerships will aim to assist developing countries to enact, through effective partnerships, the necessary national level policy, legal and institutional reforms to prevent, minimize and ultimately eliminate the risk arising from the transfer of invasive aquatic species and pathogens in ships’ ballast water and sediments and to develop sustainable mechanisms for the control and management of ballast water and sediments. GloBallast Partnerships, will focus on assisting specially vulnerable and sensitive countries and will emphasis on integrated management. The partnerships will ensure a globally uniform approach and, to the extent possible, global coverage of the developing regions of the world.

The PDF-B project, over an eighteen month period, will develop criteria for identification of “vulnerable areas”, secure project partners and co-financing, develop stakeholder involvement and communication plans, and generic LPR and MER plans. In addition, the PDF-B activities will also help sustaining the interest and momentum precipitated by the Pilot Phase and will act as a bridge between GloBallast Project and GloBallast Partnerships. The project will be executed by IMO and managed by a Project Management Unit established under IMO. The project will be advised by a Global Task Force.

GEF

(Funding Agency)

UNDP

(Implementing Agency)

IMO

(Executing Agency)

PMU

(Project Management)

Lead Consultant

(International)

Legal Consultant

(International)

Ad-hoc Consultants

(Local)

IT Expert

(Local)

Technical Committee

(Technical Advise)

GTF

(Advisory Committee)

Programme Period:

Programme Component_________

Project Title:____GloBallast Partnerships___________

Project ID: _________________

Project Duration:	1 April 2005 – 30 September 2006

Management Arrangement: The project will be executed by IMO and managed by a Project Management Unit established under IMO. The project will be advised by a Global Task Force. International Consultants will be engaged to carry out major activities.

Budget	US $ 648,000

General Management Support Fee  US $ 51,8400

Total budget:	US$699, 840

Allocated resources:	 ____________

- Government		 ____________

- Regular 		 ____________

- Other:

  - Donor   GEF US $ 699,840

  - Donor	_________

  - Donor	_________

- In kind contributions US$ 2,010,000