## Fiji Project Work Plan
India Funded Project Consolidated Work Plan and Budget
Project details | [5 empty] | Total amount approved
Project Name | Developing Climate Disaster Risk Financing Framework and Parametric Insurance in Fiji |  |  |  |  | Approved Grant |  | 850000
Country | Fiji |  |  |  |  | UNDP GMS (3%) |  | 24757.2816
IP | UNCDF
IP support cost % | 7% |  |  |  |  | Total amount to be included in the AWP |  | 825242.7184
Starting date | 2020-09-01 |  |  |  |  | Programmable |  | 771254.8771
Ending date | 2021-12-31 |  |  |  |  | IP support Cost (max 7%) |  | 53987.8414
Year: | 2021
Project (former Award)
Output 1 - Improved Government’s disaster responsiveness financial policies creating an enabling environment for deploying market-based instruments. | Key Activities | Timeframe |  | Responsible Party | Planned Budget
|  | Start | End |  | Fund | Donor | Budget Account | Budget Descr | Unit Price | Quantity | Unit Measure (rate,days,month,lump sum, etc.) | Annual Budget
| 1.1 CDRF instruments overview developed and presented to stakeholders & CDRF Strategies developed | 2020-09-01 | 2021-12-31 | UNCDF | 59012 | India-UN Development Partnersh | 71200 | International Consultants |  |  | lump sum | 47000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 71300 | Local Consultants |  |  | lump sum | 23000
| 1.2 Awareness workshop on CDRF strategies and enabling environment |  |  | UNCDF | 59012 | India-UN Development Partnersh | 75700 | Training and Workshops |  |  | lump sum | 28000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 71600 | Travel |  |  | lump sum | 12000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 74100 | UNCDF GMS - 7% |  |  | lump sum | 7700
TOTAL Output 1 | [11 empty] | 117700
Output 2 - Individuals, communities, and MSMEs respond and recover more quickly from disasters with the support of CDRF instruments, including accessing through digital linkages. | Key Activities | Timeframe |  | Responsible Party | Planned Budget
|  | Start | End |  | Fund | Donor | Budget Account | Budget Descr | Unit Price | Quantity | Unit Measure (rate,days,month,lump sum, etc) | Annual Budget
| 2.1 Identify suitable FinTech/InsurTech providers, develop digital interfaces for client onboarding. | 2020-09-01 | 2021-12-31 | UNCDF | 59012 | India-UN Development Partnersh | 72100 | Contractual Services |  |  | lump sum | 40000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 72600 | Grants |  |  | lump sum | 45000
|  |  |  | UNCDF | 59012 | India-UN Development Partners | 71200 | International Consultants |  |  | lump sum | 15000
| 2.2 Development and testing of digital payment solutions for premium by individuals, cooperatives and MSME |  |  | UNCDF | 59012 | India-UN Development Partners | 71300 | Local Consultants |  |  | lump sum | 10000
|  |  |  | UNCDF | 59012 | India-UN Development Partners | 72100 | Contractual Services |  |  | lump sum | 15000
|  |  |  | UNCDF | 59012 | India-UN Development Partners | 72600 | Grants |  |  | lump sum | 25000
| 2.3 Establish digital linkage for last mile delivery of CDRF solutions, beneficiary payments |  |  | UNCDF | 59012 | India-UN Development Partners | 72600 | Grants |  |  | lump sum | 50000
|  |  |  | UNCDF | 59012 | India-UN Development Partners | 72100 | Contractual Services |  |  | lump sum | 20000
|  |  |  | UNCDF | 59012 | India-UN Development Partners | 74100 | UNCDF GMS - 7% |  |  | lump sum | 15400
TOTAL Output 2 | [11 empty] | 235400
Output 3 - Individuals, communities, and MSMEs can respond and recover quicker with access to and usage of market based CDRF instruments | Key Activities | Timeframe |  | Responsible Party | Planned Budget
|  | Start | End |  | Fund | Donor | Budget Account | Budget Descry | Unit Price | Quantity | Unit Measure (rate,days,month,lump sum, etc) | Annual Budget
| 3.1 Market based CDRF products developed for pilot testing - including Product Concepts development, field surveys to validate concepts, focus groups discussions with beneficiary groups to co-create solutions | 2020-09-01 | 2021-12-31 | UNCDF | 59012 | India-UN Development Partnersh | 71300 | Local Consultants |  |  | lump sum | 12000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 71200 | International Consultants |  |  | lump sum | 10000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 75700 | Training and Workshops |  |  | lump sum | 8000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 71600 | Travel |  |  | lump sum | 8000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 72600 | Grants |  |  | lump sum | 52000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 74100 | UNCDF GMS - 7% |  |  | lump sum | 6300
TOTAL Output 3 | [11 empty] | 96300
Output 4 - Individuals and communities have better understanding of, accessibility, and usage of market-based CDRF instruments. Improved awareness through digital tools and e-learning interfaces. | Key Activities | Timeframe |  | Responsible Party | Planned Budget
|  | Start | End |  | Fund | Donor | Budget Account | Budget Descr | Unit Price | Quantity | Unit Measure (rate,days,month,lump sum, etc) | Annual Budget
| 4.1 CDRF Training for partners | 2020-09-01 | 2021-12-31 | UNCDF | 59012 | India-UN Development Partnersh | 75700 | Training and Workshops |  |  | lump sum | 50000
| 4.2 CDRF product awareness material development |  |  | UNCDF | 59012 | India-UN Development Partnersh | 72500 | Supplies |  |  | lump sum | 35000
| 4.3 CDRF campaigns in communities and for MSMEs |  |  | UNCDF | 59012 | India-UN Development Partnersh | 71600 | Travel |  |  | lump sum | 31000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 72400 | Communications |  |  | lump sum | 14000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 74100 | UNCDF GMS - 7% |  |  | lump sum | 9100
TOTAL Output 4 | [11 empty] | 139100
Output 5 - Ensuring and enabling effective Monitoring, Evaluation, Accountability and Learning (MEAL) and Knowledge Management | Key Activities | Timeframe |  | Responsible Party | Planned Budget
|  | Start | End |  | Fund | Donor | Budget Account | Budget Descr | Unit Price | Quantity | Unit Measure (rate,days,month,lump sum, etc) | Annual Budget
| 5.1 MEAL | 2020-09-01 | 2021-12-31 | UNCDF | 59012 | India-UN Development Partnersh | 71300 | Local Consultants |  |  | lump sum | 45000
| 5.2 Knowledge Management |  |  | UNCDF | 59012 | India-UN Development Partnersh | 72500 | Supplies |  |  | lump sum | 25000
| 5.3 Program Operations and Office Cost |  |  | UNCDF | 59012 | India-UN Development Partnersh | 77100 | Staff Salaries |  |  | lump sum | 115255
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 73100 | Rental and Maintenance |  |  | lump sum | 16000
| 5.4 South/South Cooperation and Travel |  |  | UNCDF | 59012 | India-UN Development Partnersh | 75700 | Training and Workshops |  |  | lump sum | 20000
|  |  |  | UNCDF | 59012 | India-UN Development Partnersh | 74100 | UNCDF GMS - 7% |  |  | lump sum | 15487.85
TOTAL Output 5 | [11 empty] | 236742.85
[9 empty] | Matches Programmable + IP Costs |  |  | 825242.85
Instructions: | Please complete only the cells highlighted in yellow
Complete Project details information
Enter Approved Grant amount
Add Output description
Add Activity ID and description
Additional outputs can be created under the same Project
| Additional activities can be created under the same output | [5 empty] | Krishnan Narasimhan
| An AWP need to be prepared for each year | [5 empty] | Programme Advisor