Quarterly Progress Report

| Country | JAMAICA |
| --- | --- |
| Reporting period | January –March 2017. No.00075375. ACP-EU Development Minerals Programme: Capacity development of institutions and small-scale private operations in mineral production in ACP countries. September 1, 2014 to 31st August, 2017. UNDP and Mines & Geology Division (M&GD), Ministry of Transport & Mining. UNDP Ruth Clarke USD:431,638 JMD:56,112,940.00 Revised Approved Budget USD: JMD: UJanSD: JMD: Current Quarter Expenditure by IP: USD: JMD: USD: JMD: Direct Payments by UNDP: USD: 78,556.98 JMD: 10,212,407.40 USD:78,556.98 JMD:10,212,407.40 Current Year Delivery to Date Annual exp/approved budget x 100%18% |
| Project number and title | No.00075375. ACP-EU Development Minerals Programme: Capacity development of institutions and small-scale private operations in mineral production in ACP countries. |
| Project Duration | September 1, 2014 to 31st August, 2017. UNDP and Mines & Geology Division (M&GD), Ministry of Transport & Mining. |
| Implementing Partner | UNDP and Mines & Geology Division (M&GD), Ministry of Transport & Mining. |
| Responsible Parties | UNDP Ruth Clarke |
| Overall Project Coordinator | UNDP |
| Initial Approved Budget | Ruth Clarke | Revised Approved Budget | USD: JMD: |
| Balance Brought Forward from Previous Quarter | USD:431,638 JMD:56,112,940.00 | Revised Approved Budget | USD: JMD: |
| Current Quarter Advance (IF NO ADVANCE, put $0.00) | USD: JMD: | Current Quarter Expenditure by IP: | USD: JMD: |
| Annual Expenditure to Date | USD: JMD: | Direct Payments by UNDP: | USD: 78,556.98 JMD: 10,212,407.40 |
|  | USD:78,556.98 JMD:10,212,407.40 | Current Year Delivery to Date | Annual exp/approved budget x 100%18% |

| Description of In Kind Contribution (attach any supporting documents, e.g. cost of Project Manager, other). Timesheets for Richard, Ava, Shelly, Stacy to be submitted. (January-March 2017) | Total Estimated Value of In Kind Contribution (Monetary Value) |
| --- | --- |

project Expenditure for Reporting Period (Month- month, year)

| Output # / Activity Result # | Authorised amount on AWP | Q1 2017 JMD$ | Q2 2017 JMD$ | Q3 2017 JMD$ | Q4 2017 JMD$ | Balance JMD$ A-(B+C+D+E) |
| --- | --- | --- | --- | --- | --- | --- |
|  | A | B | C | D | E | F |
| OUTCOME 1 Output 2 Environmental Health and Safety Standards, improved and human and labour rights better protected in small-scale mining through enhanced technical and legal knowledge of the small-scale private sector, associations/chambers and public institutions. Activity 2.3Prepare training materials -Conduct country level training and sensitization on environment, health, safety and labour standards for operators in St. Catherine -E. Jamaica. (20 persons). |  | 78,556.98 34608.48 |  |  |  |  |
| Activity 3.2. Site visits to selected artisanal centres. Publication and promotion of activities (video and photography). Training course fee, air-fare, daily subsistence allowance for 8-9 persons to attend out of country training in Africa. |  | 39311.93 |  |  |  |  |
| Total |  |  |  |  |  |  |
| Cash in hand @ end of reporting period |  |  |  |  |  |  |

- indicator tracking table

(The Indicator tracking sheet given below is a useful Performance Monitoring tool which can serve as a valuable source of readily available information on project progress. Values of indicators in each quarter show the progress towards achieving their corresponding annual targets. Summarize all the Outputs with their respective indicators and annual targets into the following table as per the example)

| OUTPUT# | INDICATOR(S) | Baseline | Overall Project Target | Indicator Status Q1 2016 (insert previous year) | Current Year Progress | Annual Target (DEC 2017) | Means of verification/Data Source | Date data source uploaded to PMM/filed |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |  |
| Output 2: Environmental, health, safety standards improved and human and labour rights better protected in small-scale mining through enhanced technical and legal knowledge of the small scale private sector, associations/chambers and public institutions. Activity Activity 2.3 Conduct country training and sensitisation on environmental, health, safety and labour standards;(including UN guiding principles for business and labour rights; UN declaration on the rights of indigenous peoples ;certification schemes). Activity2.5: Sector promotion: Small Grants | 1 Sensitisation seminar planned. 1 Agenda and presentations submitted to UNDP 30 Environmental Handbooks circulated including promotional items – Calendars, thumbdrives. 1 Presentation uploaded to website- UNDP Brussels (Programme website) and UNDP, Ministry of Transport and Mining and Mines and Geology Division. | 0 0 | 1 300 | 0 0 | 1 30 | 0 0 | 1 0 | 0 0 | 1 30 | 1 Sensitisation Seminar 30 Handbooks | August 31 2017 |
|  | Not done |  |  |  |  |  |  |  |  |  |  |
| Output 3: Productivity, access to markets and working capital of the small-scale private sector in development minerals mining increased through enhanced entrepreneurial skills of mining enterprises. Activity 3.2 Conduct regional training on entrepreneurial skills (value-added processes, accounting, marketing, sales promotion, purchasing, market analysis, identifying potential value chain entry points). | 1 Training Workshop planned by African Minerals and Geoscience Centre (AMGC) in Tanzania for 4 weeks. 1 Study Tour itinerary for Related agencies planned by UNDP Jamaica in Tanzania for 2 weeks. 1 Course outline and training report submitted to UNDP 1 Course outline and video footage of presentation to EU monitors and presentation ceremony uploaded to website- UNDP Brussels (Programme website) and UNDP, Ministry of Transport and Mining and Mines and Geology Division. Number of small grant applications submitted by companies and associations. | 0 0 0 0 0 | 1 1 1 1 5 | 0 0 0 | 0 0 0 | 1 1 1 | 1 1 1 | 0 1 1 | 2 2 2 2 2 | 2 Training Reports by AMGC – ceramic pottery and semi precious stone jewellery. Study Tour Mission Report by UNDP Course outline and training report. Video footage of presentation to EU monitors and Presentation ceremony. Small grant applications submitted by June | March 28th – April 24th May 6th |

- Planned Outputs, Activity Results and Achieved Results for the quarter (Based on AWP) [Completion status coded as:  Fully=activity result accomplished; partially=activity started but incomplete/not finished; not started=no activity has started during this quarter]

INSTRUCTIONS (delete upon completion of report):

This section is intended to present an assessment of the extent to which the project has progressed in relation to the outputs/targets expected for the year. The review should be concise, based on the Annual Work Plan (AWP) of the project and follow the format below. The progress review should only cover the reporting period.

| PLANNED OUTPUT (based on project document) | Planned Activity Results | Completion Status [Achieved Activity Result] | Remarks on completion status of planned activities | Progress Towards Achieving Output |
| --- | --- | --- | --- | --- |
|  |  | Fully | Partially/Not Finished | Not Started |  |  |
| Output # 2: Environmental, health, safety standards improved and human and labour rights better protected in small-scale mining through enhanced technical and legal knowledge of the small scale private sector, associations/chambers and public institutions. Activity Activity 2.3 Conduct country training and sensitisation on environmental, health, safety and labour standards;(including UN guiding principles for business and labour rights; UN declaration on the rights of indigenous peoples ;certification schemes). Sector Promotion: Output 3: Productivity, access to markets and working capital of the small-scale private sector in development minerals mining increased through enhanced entrepreneurial skills of mining enterprises. Activity 3.2 Conduct regional training on entrepreneurial skills (value-added processes, accounting, marketing, sales promotion, purchasing, market analysis, identifying potential value chain entry points). | Activity 2.3. Sensitisation Seminar on environmental, health and safety and labour standards to be held on March 7th. 20 quarry operators were sensitised. | X |  |  | Sensitization seminars on environmental, health and safety and labour standards Targeting St. Catherine operators was held on March 7th; topics included quarry legislation, rehabilitation of quarried lands, health and environmental issues. | This output is completed. All sensitisation seminars were held island-wide – Western, Central, Eastern and St. Catherine for 220 quarry operators. The final one was held on March 7th. The sector was promoted by the distribution of calendars. The progress towards achieving this output will be outlined in the next quarterly report. |
|  | Printing of 1,000 wall and 100 desk calendars on Development Minerals | X |  |  | Publication of calendars were done in March and distributed to major stakeholders. 100 desk calendars are to be printed and distributed in Quarter 2 |  |
|  | A four week training workshop and 2 week study tour to Dal El Salaam is being organized. |  | X |  | Preparatory work was done to register artisans (9) for the Jamaican Artisan Training Workshop in Tanzania and planning of itinerary for (6) study tour participants in Tanzania. Visa application, processing of daily subsistence allowance, airline ticket purchasing, hotel accommodation were procured in preparation for the visit March 26th – April 24th. |  |

- UNPLANNED ACTIVITIES during quarter (if Applicable)

Activities  undertaken during the quarter but were not included in AWP .

There were no unplanned activities undertaken during the quarter.

| Output# | DATE | UNPLANNED ACTIVITY |  | Comments/Justification |
| --- | --- | --- | --- | --- |

VI. Risk Log

There were no risks to the project during the period.

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |  |  |  |

VII. Implementation Constraints and Lessons Learned

| Implementation Constraint | Measures/Action Taken | Recommendation for follow-up (If implementation constraints persist after measures taken) | Issues resolved (yes/no) |
| --- | --- | --- | --- |
| The support from UNDP Tanzania was limited and un-co-operative at times. The hotel charged VAT and UNDP Jamaica paid for this tax. This should be reimbursed as UNDP Tanzania is eligible for VAT exemption. | Micro grant agreement was prepared and executed by UNDP Jamaica. Several emails were written to UNDP Tanzania requesting their help in getting the letter authorizing tax refund but there was no response. The hotel is to be approached to see if they can get the verification from Tanzania Revenue Authority to submit letter granting VAT exemption for UNDP Tanzania. | UNDP Tanzania needs to be more pro-active and provide more assistance. Continue trying to get assistance from UNDP Tanzania and the hotel in Tanzania. | No No |

Lessons Learnt from implementation constraints noted above

There were no lessons learnt from implementation constraints noted above. Resolution of this issue is still outstanding.

Status of Project at the end of this quarter

INSTRUCTIONS (delete upon completion of report):

This section is intended to provide a narrative/summary detailing the progress of the outputs of the project in the period under review. This section is best completed

after the completion of the other parts of the report

The following activities were completed during January to March. The project continued with the following activities which were planned to be undertaken during the first quarter of 2017. Jamaican Sensitisation Seminar for Quarry Operators (St. Catherine) and Preparation for Jamaican Artisans Training Workshop on Ceramic Technology and Pottery, Tanzania. The main activities in the work plan included Jamaican Sensitisation Seminar for Quarry Operators in St. Catherine (Central) in March and preparation for the activities associated with the Jamaican Artisans’ Training Worksop on Ceramic Technology and Pottery, Tanzania in March. The training commenced March 28th and continued until April. Consultancy – Baseline Study SLR Environmental Consulting, from Ireland was selected to conduct a baseline assessment of the Development Minerals Sector. The consultancy commenced on March 15th, 2017, and runs until July 15th, 2017. The procurement for this consultancy was undertaken by UNDP Brussels with UNDP Jamaica assisting in the selection of the successful candidate. The team visited Jamaica on a mission between the 22nd and 29th March, 2017, and met with major stakeholders and relevant organizations. Dr. Deirdre Lewis, visited and worked alongside local consultants – Dr. Arthur Geddes and Ms. Yolanda Drakapoulous. The consultants visited the island in order to plan the activities which would be required to conduct the baseline study as well as meet with major stakeholders as an introduction to the field work related to the baseline study. The consultant met with PIOJ, NEPA, M&QA, Commissioner of Mines, EXIM Bank and DBJ. Quarterly Meetings of Country Working Group (CWG) The first quarterly meeting of the Country Working Group was held on January 16th at Mines and Geology Division Conference Room. Approximately fourteen (14) Committee members of CWG attended and the Annual Work Plan and Budget for 2017, 2018 was presented and discussed. Other activities discussed included Minerals Fair, November 19th to 25th, future training seminars, exhibitions and filed trips being planned by Ministry of Transport and Mining, Mines and Geology Division, JAMPRO, JBDC and UNDP. Jamaican Sensitisation Seminar for Quarry Operators in St. Catherine A sensitisation seminar on health, environment, safety and gender issues was held on March 7th at Terra Nova Hotel for quarry operators in the St. Catherine area. Approximately 20 operators attended. Presentation were made by representatives of UNDP, Mines and Geology Division. Rehabilitation of Mined out quarried lands as well as changes in the legislation were presented. This seminar is the final in the series of seminars presented to all quarry operators. To date, a total of 221 operators were sensitised. Jamaican Artisans Training Workshop on Ceramic Technology and Pottery, Dar es Salaam, Tanzania A group of 15 participants, including 9 artisans and 6 study tour participants attended a month long training workshop, from March 26th to April 21st, and from March 28th to April 6th respectively. The study tour participants represented attendees from JBDC, UWI Sustainable Development Unit, Ministry of Transport & Mining, Private business consultant, ProTrade Consult, Mines and Geology Division, UNDP. The objective of this trip in Tanzania is to hone their skills in ceramic technology and pottery. It is expected that they will visit related agencies to observe synergies in training, collection of raw material, and marketing of finished products. Preparatory work in airline reservations, tuition/course fees, hotel accommodation and daily subsistence allowance were completed in March.

how is the project performing overall

Should include a description of the achievements towards the accomplishment of the project outputs in the reporting period.

has there been any major developments that impacted the project this QUARTER (challenges or opportunities)

A description of the challenges and major developments (internal) towards the accomplishment of the project outputs in the reporting period. (E.g., delays in consultant recruitment; identification of new sources for co-funding, etc.)

There have been no major developments that impacted the project this quarter.

has there been any developments in the country context or thematic area that has

had an impact on the project this quarter

A description of the challenges and major developments (external to the project) towards the accomplishment of the project outputs in the reporting period. (E.g., natural disaster, national elections, fiscal space challenges, etc.)

There have been no developments in the country context that impacted the project this quarter.

VIII. Planned Activities (Next Quarter – mth-mth, year)

| Expected Outputs | Planned Activities | Timeframe | Responsible Party | Planned Budgets |
| --- | --- | --- | --- | --- |
|  |  | M1 | M2 | M 3 |  | Source of Funds | Budget Description | Amount |
| OUTCOME 1 Output 3: Productivity, access to markets and working capital of the small-scale private sector in development minerals mining increased through enhanced entrepreneurial skills of mining enterprises. Activity 3.2 Conduct regional training on entrepreneurial skills (value-added processes, accounting, marketing, sales promotion, purchasing, market analysis, identifying potential value chain entry points). |  |  |  |  |  |  |  |  |
|  | Activity 3.2. Site visits to selected artisanal centres. Publication and promotion of activities (video and photography). Training course fee, air-fare, daily subsistence allowance for 8-9 persons to attend out of country training in Africa. |  |  | March/April March/April March/April | UNDP,MGD, JBDC, MT&M | EU | 71600 - Travel | US$60,000 |

# Annex I:  Assets Inventory

| Project Title: ACP-EU Development Minerals Programme: Capacity development of institutions and small-scale private operations in mineral production in ACP countries. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Award Number: 00075375(previously 00099852 |  |  |  |  |  |  |  |  |  |
| Project Number: 00075375(previously 00099852 |  |  |  |  |  |  |  |  |  |
| Date of Report: September 3, 2017. |  |  |  |  |  |  |  |  |  |  |
| Asset Profile 1 – Vehicles |
| S/N | Country Code | Business Unit | Item Description | Make & Model | Quantity | Location | Tag Number | Date acquired | Value | Custodian | Remarks |
| 1 | JAM10 |  | Vehicle |  |  |  |  |  |  |  |  |
| 2 |  |  | Vehicle |  |  |  |  |  |  |  |  |
| 3 |  |  | Vehicle |  |  |  |  |  |  |  |  |
| 4 |  |  | Vehicle |  |  |  |  |  |  |  |  |
| Asset Profile 2 – Furniture |
| 5 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| 6 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| 7 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| 8 |  |  | Furniture or Fixture |  |  |  |  |  |  |  |  |
| Asset Profile 3 - Electrical |
| 9 |  |  | Electrical Equip. or Computer | Digicel DL 910 (Gray) Mobile Phone (loaner until request is available). | 1 | Mobile |  | November 26, 2016 |  | Ruth Clarke, Tel.:322-6314 or 403555 (mobile company) |  |
| 10 | JAM 10 | UNDP1 | Electrical Equip. or Computer | 1 DELL Computer Ultrabook Latitude E7470. Serial No. M100093/1 RL8MC2 | 1 | M&GD, Kingston, Jamaica | 1RL8MC2M100093 | September 23, 2016 | US$2,000 | Ruth Clarke, Tel.:322-6314 or 403555 (company mobile phone). Equipment is at M&GD, Hope Gardens, Kingston 7. |  |
| 11 |  |  | Electrical Equip. or Computer | Dongle (Mobile) | 1 | Mobile |  | Not yet acquired |  |  |  |
| 12 |  |  | Electrical Equip. or Computer | Digital Camera. Canon Power Shot EPH180 (RE) No. 272063000828 | 1 | Mobile |  | November 26,2016 | 180US |  |  |
| Asset Profile 4 - Heavy Machinery |
| 13 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| 14 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| 15 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| 16 |  |  | Heavy Equip. or Generator |  |  |  |  |  |  |  |  |
| Asset Profile 5 - Non Capitalized Items |
| 17 |  |  | Other (less than 1,000 $) | Flash Drive Data-traveler G4 128GB | 1 | Mobile |  | September 23rd, 2016 | 31.76US |  |  |
| 18 |  |  | Other (less than 1,000 $) | Printer/Copier/Scanner | 1 | MGD, Kingston Jamaica |  | September 23, 2016 | 484US |  | Equipment is at Mines and Geology Division |
| 19 |  |  | Other (less than 1,000 $) | UPS | 1 | MGD ,Kingston Jamaica |  | September 23 2016 | 158US |  | Equipment is at Mines and Geology Division |
| 20 |  |  | Other (less than 1,000 $) |  |  |  |  |  |  |  |  |
| Project Manager: Ruth Clarke |  | Programme Officer |  |  |  | Deputy Resident Representative: Elsie Laurence-Chounoune, PhD |  |
| Date and Signature |  | Date and Signature |  |  |  | Date and Signature |  |  |  |

Completion checklist:

Prior to submission of final draft to undp, please check the following:

□ Asset Inventory log completed with signature (See Annex I: Asset Inventory template)

□X Report reviewed by PSC ((Yes/NO)

□All sections of Quarterly Report completed

| Summary of Progress towards Outputs Project Expenditure for Reporting Period Indicator Tracking Table Planned Outputs, Activity Results, and Achieved Results for the quarter | 5. Unplanned activities during quarter 6. Risk Log 7. Implementation Constraints and Lessons Learned 8. Planned Activities |
| --- | --- |

□ Any new deliverable(s) for this quarter?

Yes X□     No 	□

Has deliverable(s) been submitted to UNDP

Yes X□      No □

□Signed Asset inventory

□Signed report by Project Management

Project Management: (This should be the persons whose name is in the Signatory Registry) Prepared by: ______ __Ruth Clarke____________________ Date: __3rd September 2017___________________ Reviewed & Approved by: ___________ _________ Date: _______________________

UNDP Resource Person: Accepted by: _________________________________________ Date: ___________________ _________________________________________ (Signature)