## ELECTORAL SYSTEM
GRANT NO.: AID-522-IO-11-00001
ANNUAL WORK PLAN - OBJECTIVE 1 "HONDURAS ELECTORAL SYSTEM STRENGHTHENED"
Result | PMP Indicator | Activities | Narrative of the Activity | Actions | Timeframe Jul.2016-Jun 2017 |  |  |  | Responsible party | Budget for period July 2016 - June 2017
[5 empty] | Jul-Sep 2016 | Oct - Dec 2016 | Jan - Mar 2017 | Apr - Jun 2017 |  | Source of Funds
[10 empty] | UNDP | USAID | Total budget
Result 1: Electoral Legal and Regulatory Framework Improved | OUTCOME INDICATOR 1.1.Number of Electoral legal reform proposals supported by UNDP/USG presented to the National Congress. | ACTIVITY 1.1: Technical and Legal Assistance to Support Discussion on Electoral Reforms. (POLITICAL PARTIES & ELECTORAL TECHNICAL ASSISTENCE) | Political Parties and Civic Society Organizations Component: The main purpose of these activities is monitoring and following up the discussion and implementation of electoral reforms, eventually passed by parliament in 2016 legislature and supported by the project. Therefore, UNDP will continue working with Civil Society Organizations and Political Parties to develop strategies and skills, to advocate for implement key electoral reform issues (legislative and/or regulatory), such as electoral campaing funding, citizen participation in polling stations, parity and alternation. For that reason, it's important to develop several workshops in other important cities, in order to involve regional civil society. Additionally, workshops, seminars, working meetings, and a forum on political systems and electoral reform will be coordinated with national and international experts for CSOs, National Congress members, political parties, and electoral authorities. Furthermore, working papers will be elaborate in order to enrich the implementation on electoral reforms and media will be invited in order to raise public awareness. | Technical assistance:
|  |  |  | Working Meetings (5) for the Multiparty Commision to strenghtening the democratic dialogue on political system and electoral reforms. |  |  |  |  | Unit coordinator UNDP |  | 2000 | 2000
|  |  |  | Working Meetings (3) to discuss the Advocacy Plan on Electoral Processes with CSO. |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 2000 | 2000
|  |  |  | Working meetings (3) to follow up the Electoral Reform Proposals from CSO. |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 1500 | 1500 |  | 11500
|  |  |  | Working meetings (5) for monitoring the Advocacy Plan on Electoral Processes with regional stakeholders. |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 2000 | 2000 |  | 28937
40437
|  |  |  | Working meetings (3) to promote a dialogue between CSO and Political Parties on electoral topics. |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 2000 | 2000
|  |  |  | Support CSO proposals for regulations of electoral legal reforms (passed in 2016) |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 2000 | 2000 | 10000 | 12000
|  |  |  | Grant CARITAS for the proposal and socialization for legal reforms and social society |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 6500 | 6500
Technical Missions:
|  |  |  | Technical mission to knowing the functioning of citizen polling stations in Guatemala. |  |  |  |  | Electoral Specialist |  | 20000 | 20000 | 9292 | 10000
|  |  |  | Technical mission for monitoring the Advocacy Plan on Electoral Processes with regional stakeholders. |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 20000 | 20000 | 37000
Personnel:
|  |  |  | International consulting to facilitate the Multiparty Dialogue on electoral reforms.. |  |  |  |  | Unit Coordinator UNDP |  | 27668.4 | 27668.4
|  |  |  | National Consultants | [6 empty] | 8000 | 8000
|  |  |  | Project team, in charge of the implementation of the activities of the annual work plan (July 2016 - June 2017 AWP) and will among other things, draft the ToR of the experts and conduct the monitoring, evaluation and reporting. | [6 empty] | 101968.41 | 101968.41
Workshops and/or seminars
|  |  |  | Training and seminars for representatives of Political Parties on electoral topics such as: citizen polling stations, electoral campaign funding, regulation on parity and alternation, vote counting and voting procedures. |  |  |  |  | Unit Coordinator UNDP |  | 6000 | 6000
|  |  |  | Support to Academy of Women Candidates |  |  |  |  | Program Officer UNDP |  | 7000 | 7000
|  |  |  | Training for CSO and Political Parties on electoral topics such as: citizen polling stations, electoral campaign funding systems, regulation on parity and alternation and voting procedures. |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 6000 | 6000
Publications:
|  |  |  | Publication and distribution of lesson learned on electoral reforms. |  |  |  |  | Unit Coordinator UNDP |  | 4500 | 4500
|  |  |  | Publications of experiencies on civil society participation in electoral processes. |  |  |  |  | Unit Coordinator UNDP PP-CSO Specialist |  | 2409.35 | 2409.35 |  |  |  | 50392.32 | 363980.29
|  |  |  | Operative Costs | [6 empty] | 142434.13 | 142431.24 | 40462.83 | 0.46594
|  |  |  | TOTAL ACTIVITY 1.1 (Political Parties) | [7 empty] | 363977.4 | 305683.84 | -58293.56 | 457977.34 | 363980.29 | 2.89
|  |  | Tecnical Electoral Assistence Component: Workshops will be coordinated to discuss electoral topics for a widest range of actors such as the Supreme Electoral Court (TSE), civil society organizations (CSOs), general public, political parties, and the National Congress, including the Congressional Commission on Electoral Affairs. The main purpose of these activities is to place the issue of electoral reform on the agenda for public discussion, so it may lead to a formal debate and promulgation of electoral reforms in the National Congress (the Congressional Commission for Electoral Affairs and parliamentary members of the National Congress). Importantly, UN Electoral Assistance Division of the Department of Political Affairs (EAD/DPA) through its 2014 Needs Assessment Mission (NAM) recommended that the UNDP technical assistance provided to reforms efforts should not discuss the entire law, but specific aspects of it. In contrast to previous approach, UNDP will be able to work with other key stakeholders from the political-electoral arena aside from the TSE, such as Civil Society Organizations and Political Parties. Thus, UNDP will make efforts to discuss the issues of electoral reform in a participatory and inclusive manner so that once the environment is conducive to formally discuss electoral reforms in Congress, key stakeholders will be ready. | Technical assistance for the discussion of electoral reforms: | [13 empty] | Nuevo POA | DIF
|  |  |  | Recruiting an international expert on e-voting. |  |  |  |  | ATE/RNP Component Coordinator |  | 10000 | 10000 | [5 empty] | 24000 | -14000
Technical Missions:
|  |  |  | A technical missions to the TSE/Guatemala inorder to obtain an exchange of ideas and best practices on citizens polling stations and electoral technilogy for scrutiny. This mission might have the participation of TSE’s magistrates, members of the Congressional Commission on Electoral Affairs & political parties’ representatives. (*) |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 5000 | 5000
Workshops, seminars and a forum:
|  |  |  | Two workshops for the discussion of e-voting and new electoral technologies (one workshop will be for the public and the other will be exclusively for the TSE). |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 3840 | 3840 | [5 empty] | 3840
|  |  |  | TOTAL ACTIVITY 1.1 (Technical Assistence) | [5 empty] | 0 | 18840 | 18840
| OUTCOME INDICATOR '1.2.Number of reforms to the electoral regulatory framework supported by UNDP/USG adopted by the Electoral Supreme Court (TSE). | ACTIVITY 1.2: Technical and Legal Assistance to Formulate and Implement Electoral Regulations for the Primary and General Elections. | Given the complexity of the political environment, it is important that the ATE Component continue carrying out parallel work focusing on the revision and formulation of non-constitutional and legal reforms such as electoral regulations in order to address the problematic aspects on the current electoral law. A workshop with national and international electoral reform experts will be developed in order to identify electoral issues that could be resolved through regulatory amendments. Possible issues might include the electoral calendar, consistency among the regulations and with the Constitution, electoral dispute resolutions, registration of political movements, gender equity, among others. Based on the findings of this workshop, UNDP will technically support the TSE in the development and approval of new electoral regulations to ensure that management of 2017 primary and general elections are smooth and efficient. Once electoral regulation are fully revised and in some cases share with stakeholders, the ATE Component will assist the TSE in the publication of those electoral regultaion approved so that it can be reached to all stakeholders involve in the electoral process. Additionally, the ATE Component will provide its technical expertise during the whole process from revision and implementarion of such electoral regulation. | Workshops for the discussion and formulation of TSE electoral regulations:
|  |  |  | > At least four Workshops to present approved electoral regulations by TSE to key stakeholders (Political Parties, CSOs, Target groups of the society i.e. organizations working on gender issues) |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 4000 | 4000
Publication of TSE electoral regulations on press media:
|  |  |  | > Approximately 4 publications in the main four newspapers of the country. |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 2000 | 2000
|  |  |  | TOTAL ACTIVITY 1.2 | [5 empty] | 0 | 6000 | 6000
|  |  |  | TOTAL ACTIVITY 1.1 (Technical Electoral Assitence) | [7 empty] | 24840 | [5 empty] | 43680
TOTAL RESULT 1 (Activities from Political Parties & Technical Electoral Assistence) | [11 empty] | 388817.4
Result 2: Electoral institutions’ administration improved | OUTCOME INDICATOR 2.1. At least three initiatives to update the National Electoral Census. | ACTIVITY 2.1: Support for the training process of Directors and Technical Staff of the TSE | As recommended by the 2014 UN Needs Assessment Mission, it is important to continue supporting the profesionalization process of TSE' staff through training programs and technical missions to Electoral Management Bodies (EMBs) in the region; therefore, activities such as short-term trainings will be implemented to promote capacity-building and skills required to improve TSE staff abilities. Based on previous relations between TSE Honduras and other EMBs in the region, ATE Component will also facilitate a technical mission for exchange of experiences, ideas and best practices in the framework of TSE's institutional strengthening and personnel capacity building, especificaly in the topic of mapping and census issues. In the framework of South-South/Horizontal cooperation, this mission will establish a collaborating network so that TSE can receive visits from experts of regional EMBs and other electoral authorities and share their knowledge and experience with personnel of the TSE. UNDP will also contribute to implement a BRIDGE training to improve management and/or skills on electoral processes-related topics. BRIDGE stands for “Building Resources in Democracy, Governance and Elections.” It is a methodology for training related to electoral processes that has been jointly developed by International IDEA, IFES, UNDP, the UN and the Australian Electoral Commission, and includes workshops in various issues concerning electoral processes. | Personnel:
|  |  |  | > Recruitment of a BRIDGE expert on managerial and technical skills and/or electoral issues to deliver workshops for TSE staff. |  |  |  |  | ATE/RNP Component Coordinator |  | 10000 | 10000
Technical Missions:
|  |  |  | > A technical mission to Colombia in order to have an exchange of ideas and better practices in cartography and census matter. |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 15000 | 15000 | [5 empty] | 15000 | 0
Workshops:
|  |  |  | > A BRIDGE workshop on management and/or technical skills on electoral-related topics. |  |  |  |  | ATE Component Team & TSE |  | 12000 | 12000
|  |  |  | TOTAL ACTIVITY 2.1 | [5 empty] | 0 | 37000 | 37000
| OUTCOME INDICATOR 2.1. At least three initiatives to update the National Electoral Census. | ACTIVITY 2.2: Technical Assistance to Contribute to the Strengthening of the Operational Units of the TSE | Since 2009, UNDP has been assisting the TSE in its internal re-organization and modernization. As a result of the support from UNDP, the institutional structure of the TSE now includes new units such as IT, Gender, Mapping and Census, and Planning and Monitoring, and there has been an overall improvement in the effectiveness and efficiency of the TSE as well as the quality of electoral management. Therefore, ATE Component will assist the TSE to improve and deepen this organizational reform process and to strengthen its operational units (in particular Electoral Training and Civic Education, Census and Mapping, IT and Planning and Monitoring) in view of the upcoming 2017 primary and general elections. Although technical assistance provided by UNDP though the ATE Component has strengthened the area of information technology of the TSE and it is now able to best meet the requirements of the electoral body, operational units still need to be consolidated. ATE Component will recruit an international expert on information technologies (IT) to work on the consolidation of the IT Unit and on IT-related issues such as the use of new technologies or improvement of existing ones employed by the TSE (system for transmission of preliminary electoral results (SIEDE/TREP, development of intranet, etc.). With the assistance of ATE component, the TSE recently created a Planning and Monitoring Unit that as well as the Census and Mapping Unit both depending on the Electoral Directorate. The TSE Magistrates have identified these two units (Planning and Monitoring Unit & Census and Mapping Unit) as essential for the effective functioning of the Tribunal, and therefore, ATE Component will support the consolidation and strengthening of capacities of both units. In particular, ATE Component will hire IT consultants to provide technical assistance to the Planning and Monitoring Unit in designing and developing an informatic application to monitor and following up the electoral projects contemplating in the 2017 Primary Election Plan. These two IT experts may also assist the TSE in developing another informatic application of one of the 22 electoral projects of the 2017 Primary Election Plan. As for the Census and Mapping Unit, ATE Component will continue working to support the implementation of the interconnection system between TSE and RNP databases for sharing information to permanently update and verify the information in the National Electoral Census. Furthermore, the recruitment of an international consultant on Census data verification will be supported by the ATE Component. The aim of this consultancy is to verify the consistency of the data of the National Electoral Census (NEC) and contrast that information through field missions. The places to be visited during the field visit will be determined by statistical methods so that the sample will be sufficiently significant and representative considering the data in the NEC. Regarding support to the Electoral Training and Civic Education Unit of the TSE, which ATE Component has been supporting intensively in several areas. The ATE Component will support the TSE in the publication of civic and voter education materials since it has aided in the design of initiatives such as voter education campaigns, women empowerment political rights and duties amongst others, and the support on the elaboration of promotional material based on the democratic values campaign. These initiatives aim at promoting a true democratic culture and responsible behavior by Hondurans not only during elections but in all facets of their lives. Finally, ATE will work with the TSE on issues related to women political participation and inclusion of minorities into political processes (the physically challenged, indigenous and afro descendants). As for the issue of gender in politics, ATE Comopnent through the work of a gender expert hired will continue implementing the ATENEA initiative, a Monitoring System for Political Participation of Women, a tool that allows for a more comprehensive, permanent and comparative political participation of women in the context of Honduras. It is also a generator of more strategic guidelines for the development of advocacy and policy reform to achieve equal exercise of political rights of women at national and regional level. It will continue working on developing a Political Parity Index to properly measure the political participation of women in Honduras. Additionally, It will assist the TSE in the reactivation of the TSE´s Gender Unit. | Personnel:
|  |  |  | > Recruitment of two IT expert in order to develop the Electoral Planning and Monitoring System of the TSE Planning and Monitoring Unit. |  |  |  |  | ATE Component Team & TSE's Planning and Monitoring Unit |  | 9000 | 9000 | [6 empty] | 9000
| OUTCOME INDICATOR 2.2 Number of civic-electoral outreach initiatives led by TSE |  |  | > Recruitment of an IT consultant (international) to support the IT initiatives of the TSE. |  |  |  |  | ATE Component Team & TSE's Magistrates |  | 55000 | 55000 | [5 empty] | 0 | 55000
|  |  |  | > Recruitment of UNVs for software development and registration on trained MMER |  |  |  |  | ATE Component Team & TSE's Magistrates |  | 18000 | 18000 | [5 empty] | 18000 | 0
|  |  |  | > Recruitment of a social inclusion consultant to support the social inclusion initiatives of the TSE. |  |  |  |  | ATE Component Team & TSE's Social Inclusion Unit |  | 5000 | 5000 | [5 empty] | 5000 | 0
| OUTCOME INDICATOR 2.3 Percentage of actions executed of three electoral projects of the 2017 Primary Election Plan implemented by the TSE. |  |  | > Recruitment of an international cosultant on Census data verification. |  |  |  |  | ATE Component Team & TSE's Census Unit |  | 7000 | 7000 | [5 empty] | 7000 | 0
|  |  |  | > Recruitment of an national cosultant on Census data verification. |  |  |  |  | ATE Component Team & TSE's Census Unit |  | 3000 | 3000 | [5 empty] | 3000 | 0
|  |  |  | > Recruitment of an IT Expert to develop the TSE-RNP Interconection System. |  |  |  |  | ATE Component Team, TSE & RNP |  | 4600 | 4600 | [5 empty] | 4600 | 0
Events & Workshops:
|  |  |  | > Four workshops to discuss the design and implementation of TSE-RNP Interconnection System. |  |  |  |  | ATE Component Team, TSE & RNP |  | 1500 | 1500
|  |  |  | > 1 event to socialize the implementation of Interconnection System TSE-RNP among authorities, legal and technical staff from TSE and RNP. |  |  |  |  | ATE Component Team, TSE & RNP |  | 3000 | 3000
|  |  |  | > Five workshops on eletoral topics such as: social inclusion, gender mainstreaming, polling stations integrations, electoral technologies, electoral observation. |  |  |  |  | PNUD & ATE/RNP Component Coordinator |  | 3413.55 | 3413.55
|  |  |  | > 2 workshops to socialize the findings of the diagnosis of the census data verification for RNP and TSE autorities. |  |  |  |  | ATE Component Team, TSE & RNP |  | 3000 | 3000
Publications:
|  |  |  | Publications of experiencies on civil society participation in electoral processes. |  |  |  |  | ATE Component Team, TSE & RNP |  | 3000 | 3000
Missions:
|  |  |  | > Missions to update the electoral cartography |  |  |  |  | ATE Component Team, TSE & RNP |  | 55000 | 55000
|  |  |  | TOTAL ACTIVITY 2.2 | [5 empty] | 0 | 112513.55 | 170513.55
| OUTCOME INDICATOR 2.1. At least three initiatives to update the National Electoral Census. | ACTIVITY 2.3.: Improve the quality of information provided by the RNP to TSE for the generation of a Census reliable and transparent, in order to strengthen the image of these institutions to the citizen. | Determine and update inconsistent data in the RNP’s Databases in order to investigate the cases with inconsistencies in the RNP’s civil registration and identification databases. UNDP will recruit researchers to visit the Municipal Civil Registries and review the original records in order to determine the correct citizen data that should be included in both databases. The information collected will then be analyzed and the RNP will form a committee to review each case and correct the database errors. | > Technical Assistance: Recruiting an Operations and Quality Control Officer for Assistance in all technical aspects of databases updating; Data Researchers (4 people), Project Personnel. > The Tecchnical Assistance will Visit 20 Municipal Civil Registers to verify, update and resolve census data. The Municipal Civil Registries selected for this activity are in the 20 largest cities in the country in relation to its population, so they generate the greatest burden of information to the National Census. The cities are: La Ceiba, Tela, Santa Rosa de Copán, San Pedro Sula, Choloma, Tegucigalpa,Copán Ruinas, Sabanagrande, San Antonio de Oriente, Chiloma, Valle de Angeles, Comayagua, Santa Lucia, Ojojona, San Juan de Flores, Cabañas, San Buenaventura,Tatumbla, Santa Rita, Santa Ana y Talanga. |  |  |  |  | RNP Committe of Civil Records, personnel Technical assistance for citizen Identification |  | 55589.0242 | 55589.0242
|  |  |  | TOTAL ACTIVITY 2.3 | [5 empty] | 0 | 55589.0242 | 55589.0242
| OUTCOME INDICATOR 2.4 Percentage of decrease in the delivery time of the identity card in selected municipalities. | ACTIVITY 2.4: Support institutional strengthening of RNP and G-fort (Group Institutional strengthening and transparency) to ensure better service to citizens and increase the confidence that they have in the institution. | In order to promote transparency within the RNP , efficiency and equity in their processes, 4 workshops with NGOs , international organizations , political parties, churches etc ... in which the following topics among which stand out will be made : Modernization RNP , Generation inputs the National Electoral Census (CNE ) , application and delivery of identity cards before the elections , agreements , protocols and commitments to the Supreme Electoral Tribunal ( TSE) on the issue of the creation of CNE , death registration and control of shipments of election addresses. | > Workshops: 4 workshop will be delivered, which will include representatives from the RNP and other state agencies such as the Institute for Access to Public Information (IAIP) and the National Commission for Human Rights (CONADEH), civil society organizations including the 'Hagamos Democracia' Consortium, the Evangelical and Catholic Churches, and international organizations such as the Spanish Agency for International Development Cooperation (AECID), NIMD, NDI, the OAS, UNDP. Workshops will be held on a monthly basis and will cover topics such as: • renewal of the new identity card, • modernization of the RNP, • inter-agency agreements, • generating inputs for the CNE, • request and delivery of identity cards before the elections, • agreements, protocols, and commitments of the TSE in the creation of the CNE, • registration of deaths, and • control of electoral address changes. |  |  |  |  | RNP, Technical assistance for citizen Identification, UNDP |  | 6745.1616 | 6745.1616
|  |  |  | Technical Assistance: Consultant in processes of RNP for strengthening and ensuring transparency within the RNP in the process of citizen identification. Supporting the right to identification and democracy in order to build confidence among the Honduran population |  |  |  |  | RNP, Technical assistance for citizen Identification |  | 7559.0808 | 7559.0808
|  |  |  | TOTAL ACTIVITY 2.4 | [5 empty] | 0 | 14304.2424 | 14304.2424
| OUTCOME INDICATOR 2.4 Percentage of decrease in the delivery time of the identity card in selected municipalities. | ACTIVITY 2.5: Ensure data security of citizens that are stored in data bases RNP, through strengthening technological Municipal Civil Registries, | In order to ensure the integrity and the complete privacy or confidentiality of information RNP, it is being implemented ISO: 27002 : 2013 in order to increase the rate of data security RNP ; additionally , it will be provided to 4 CRICS equipment that enables encrypting communications. | Data Security: Purchase IT equipment to ensure the integrity and privacy or confidentiality of the main transactions of 12 Municipal Civil Registries (MCRs) that are on-line with the center data base of the RNP. The Municipal Civil Registries (MCRs) that will be equipped are: La Ceiba, Tela, San Pedro Sula, Choloma, Villanueva, Danli, Choluteca, Juticalpa, Catacamas, El Progreso, Olanchito, Puerto Córtes. Community selection will be informed for discussion to USAID. |  |  |  |  | RNP, Technical assistance for citizen Identification |  | 11745.1616 | 11745.1616
|  |  |  | Workshops: 4 Meetings with the purpose of monitoring the measures taken to increase security data index . |  |  |  |  | RNP Department of Information Technology , Technical assistance for citizen Identification, |  | 11059.0808 | 11059.0808
|  |  |  | TOTAL ACTIVITY 2.5 | [5 empty] | 0 | 22804.2424 | 22804.2424
| N/A | ACTIVITY 2.6 Project Implementation Unit | The ATE Component team will include a coordinator/international technical advisor, national technical assistant, financial administrator, and a designated driver and vehicle. Additionally, the team will include a program associate, M&E specialist, Communication specialist, Gender specialist & procurement specialist The Project team will be in charge of the implementation of the activities of the annual work plan (July 2016 - June 2017 AWP) and will among other things, draft the ToR of the experts and conduct the monitoring, evaluation and reporting. Finally, the Project Implementation Unit will require resources for travel expenses, operational costs (rental and maintenance, IT, communication expenses, petty cash fund and fuel cash fund), supplies (power, water) and administration cost (GMS). | > Conformation of Electoral Technical Assistance Team |  |  |  |  | ATE/RNP Project Coordinator |  | 189246 | 189314.94 | [5 empty] | 359828.49
|  |  |  | TOTAL ACTIVITY 2.6 | [5 empty] | 0 | 189246 | 189314.94 | [5 empty] | 403508.49
TOTAL RESULT 2 & ACTIVITY 2 | [9 empty] | 0 | 431457.059 | 489525.999
TOTAL OBJECTIVE 1 | [11 empty] | 878343.399
#REF!
|  |  | ATE | 421668.49 | 244263.91 |  |  |  | 421668.49
-177404.58
|  |  | RNP | #REF!
|  |  | output 2 | #REF!
|  |  | OUTPUT 1 | 92697.509
#REF!
#REF!
|  |  | ATE | 421668.49
|  |  | RNP | 502804.37

## ATE
GRANT NO.: AID-522-IO-11-00001
PLANOPERATIVO ANUAL- Componente Asistencia Técnica Electoral "Sistema Electoral Hondureño Fortalecido"
| Acciones | Linea de Tiempo |  |  |  | Parte Responsable | Presupuesto Julio 2016-Junio 2017
|  | Jul-Sep 2016 | Oct - Dec 2016 | Jan - Mar 2017 | Apr - Jun 2017 | [5 empty] | USAID
Tecnical Electoral Assistence Component: Workshops will be coordinated to discuss electoral topics for a widest range of actors such as the Supreme Electoral Court (TSE), civil society organizations (CSOs), general public, political parties, and the National Congress, including the Congressional Commission on Electoral Affairs. The main purpose of these activities is to place the issue of electoral reform on the agenda for public discussion, so it may lead to a formal debate and promulgation of electoral reforms in the National Congress (the Congressional Commission for Electoral Affairs and parliamentary members of the National Congress). Importantly, UN Electoral Assistance Division of the Department of Political Affairs (EAD/DPA) through its 2014 Needs Assessment Mission (NAM) recommended that the UNDP technical assistance provided to reforms efforts should not discuss the entire law, but specific aspects of it. In contrast to previous approach, UNDP will be able to work with other key stakeholders from the political-electoral arena aside from the TSE, such as Civil Society Organizations and Political Parties. Thus, UNDP will make efforts to discuss the issues of electoral reform in a participatory and inclusive manner so that once the environment is conducive to formally discuss electoral reforms in Congress, key stakeholders will be ready. | Asistencia Técnica para discusiones sobre reforma electoral | [10 empty] | Diferencia
| Consultor intrenacional experto en voto electrónico |  |  |  |  | ATE/RNP Component Coordinator |  | 10000 | 10000 |  | 24000 | 14000
| Misiones Técnicas | [10 empty] | 0
| Misión técnica a Guatemala para intercambiar experiencias y mejores prácticas en temas de ciudadanización de las mesas electorales y tecnologías de automatización de escrutinio. |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 5000 | 5000 |  | 12000 | 7000
| Talleres, Seminarios y Foros | [10 empty] | 0
| Dos talleres para discusión de temas de voto electrónico y nuevas tecnologías. |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 3840 | 3840 |  | 3875 | 35
| TOTAL ACTIVIDAD 1.1 (Asistencia Electoral) | [5 empty] | 0 | 18840 | 18840 |  | 39875 | 21035
Given the complexity of the political environment, it is important that the ATE Component continue carrying out parallel work focusing on the revision and formulation of non-constitutional and legal reforms such as electoral regulations in order to address the problematic aspects on the current electoral law. A workshop with national and international electoral reform experts will be developed in order to identify electoral issues that could be resolved through regulatory amendments. Possible issues might include the electoral calendar, consistency among the regulations and with the Constitution, electoral dispute resolutions, registration of political movements, gender equity, among others. Based on the findings of this workshop, UNDP will technically support the TSE in the development and approval of new electoral regulations to ensure that management of 2017 primary and general elections are smooth and efficient. Once electoral regulation are fully revised and in some cases share with stakeholders, the ATE Component will assist the TSE in the publication of those electoral regultaion approved so that it can be reached to all stakeholders involve in the electoral process. Additionally, the ATE Component will provide its technical expertise during the whole process from revision and implementarion of such electoral regulation. | Talleres para discusión de regamentos electorales del TSE | [10 empty] | 0
| Al menos cuatro talleres para presentar reglamentos electorales aprobados por el TSE a contrapartes (partidos políticos, OSC, grupos de género, etc) |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 4000 | 4000 |  | 4890 | 890
| Publicaciones de reglamentos electorales en medios de comunicación escrita | [10 empty] | 0
| 4 publicaciones en los principales periodicos del país |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 2000 | 2000 |  | 2500 | 500
| TOTAL ACTIVIDAD 1.2 | [5 empty] | 0 | 6000 | 6000 |  | 7390 | 1390
| TOTAL ACTIVIDAD 1 (ASISTENCIA TÉCNICA ELECTORAL) | [7 empty] | 24840 |  | 47265 | 22425
[6 empty] | GMS |  | GMS |  |  | 2822.07 | 2822.07
TOTAL RESULTADO 1 | [8 empty] | 24840 |  | 50087.07 | 25247.07
As recommended by the 2014 UN Needs Assessment Mission, it is important to continue supporting the profesionalization process of TSE' staff through training programs and technical missions to Electoral Management Bodies (EMBs) in the region; therefore, activities such as short-term trainings will be implemented to promote capacity-building and skills required to improve TSE staff abilities. Based on previous relations between TSE Honduras and other EMBs in the region, ATE Component will also facilitate a technical mission for exchange of experiences, ideas and best practices in the framework of TSE's institutional strengthening and personnel capacity building, especificaly in the topic of mapping and census issues. In the framework of South-South/Horizontal cooperation, this mission will establish a collaborating network so that TSE can receive visits from experts of regional EMBs and other electoral authorities and share their knowledge and experience with personnel of the TSE. UNDP will also contribute to implement a BRIDGE training to improve management and/or skills on electoral processes-related topics. BRIDGE stands for “Building Resources in Democracy, Governance and Elections.” It is a methodology for training related to electoral processes that has been jointly developed by International IDEA, IFES, UNDP, the UN and the Australian Electoral Commission, and includes workshops in various issues concerning electoral processes. | Personal | [10 empty] | 0
| Consultor experto en BRIDGE ( modulo capacitación electoral ) para facilitar taller a personal del TSE ( Gastos de viaje) |  |  |  |  | ATE/RNP Component Coordinator |  | 10000 | 10000 |  | 6000 | -4000
| Misiones Técnicas | [10 empty] | 0
| Misión técnica a Colombia para intercambiar experiencias en temas reclacionados con cartografía y censo |  |  |  |  | ATE/RNP Component Coordinator & TSE's Magistrates |  | 15000 | 15000 |  | 15000 | 0
| Talleres | [10 empty] | 0
| Talleres BRIDGE |  |  |  |  | ATE Component Team & TSE |  | 12000 | 12000 |  | 12000 | 0
| TOTAL ACTIVIDAD 2.1 | [5 empty] | 0 | 37000 | 37000 |  | 33000 | -4000
Since 2009, UNDP has been assisting the TSE in its internal re-organization and modernization. As a result of the support from UNDP, the institutional structure of the TSE now includes new units such as IT, Gender, Mapping and Census, and Planning and Monitoring, and there has been an overall improvement in the effectiveness and efficiency of the TSE as well as the quality of electoral management. Therefore, ATE Component will assist the TSE to improve and deepen this organizational reform process and to strengthen its operational units (in particular Electoral Training and Civic Education, Census and Mapping, IT and Planning and Monitoring) in view of the upcoming 2017 primary and general elections. Although technical assistance provided by UNDP though the ATE Component has strengthened the area of information technology of the TSE and it is now able to best meet the requirements of the electoral body, operational units still need to be consolidated. ATE Component will recruit an international expert on information technologies (IT) to work on the consolidation of the IT Unit and on IT-related issues such as the use of new technologies or improvement of existing ones employed by the TSE (system for transmission of preliminary electoral results (SIEDE/TREP, development of intranet, etc.). With the assistance of ATE component, the TSE recently created a Planning and Monitoring Unit that as well as the Census and Mapping Unit both depending on the Electoral Directorate. The TSE Magistrates have identified these two units (Planning and Monitoring Unit & Census and Mapping Unit) as essential for the effective functioning of the Tribunal, and therefore, ATE Component will support the consolidation and strengthening of capacities of both units. In particular, ATE Component will hire IT consultants to provide technical assistance to the Planning and Monitoring Unit in designing and developing an informatic application to monitor and following up the electoral projects contemplating in the 2017 Primary Election Plan. These two IT experts may also assist the TSE in developing another informatic application of one of the 22 electoral projects of the 2017 Primary Election Plan. As for the Census and Mapping Unit, ATE Component will continue working to support the implementation of the interconnection system between TSE and RNP databases for sharing information to permanently update and verify the information in the National Electoral Census. Furthermore, the recruitment of an international consultant on Census data verification will be supported by the ATE Component. The aim of this consultancy is to verify the consistency of the data of the National Electoral Census (NEC) and contrast that information through field missions. The places to be visited during the field visit will be determined by statistical methods so that the sample will be sufficiently significant and representative considering the data in the NEC. Regarding support to the Electoral Training and Civic Education Unit of the TSE, which ATE Component has been supporting intensively in several areas. The ATE Component will support the TSE in the publication of civic and voter education materials since it has aided in the design of initiatives such as voter education campaigns, women empowerment political rights and duties amongst others, and the support on the elaboration of promotional material based on the democratic values campaign. These initiatives aim at promoting a true democratic culture and responsible behavior by Hondurans not only during elections but in all facets of their lives. Finally, ATE will work with the TSE on issues related to women political participation and inclusion of minorities into political processes (the physically challenged, indigenous and afro descendants). As for the issue of gender in politics, ATE Comopnent through the work of a gender expert hired will continue implementing the ATENEA initiative, a Monitoring System for Political Participation of Women, a tool that allows for a more comprehensive, permanent and comparative political participation of women in the context of Honduras. It is also a generator of more strategic guidelines for the development of advocacy and policy reform to achieve equal exercise of political rights of women at national and regional level. It will continue working on developing a Political Parity Index to properly measure the political participation of women in Honduras. Additionally, It will assist the TSE in the reactivation of the TSE´s Gender Unit. | Personal y Consultorías | [10 empty] | 0
| Dos expertos para apoyar a la UPEG con el sistema de monitoreo y planificación electoral |  |  |  |  | ATE Component Team & TSE's Planning and Monitoring Unit |  | 9000 | 9000 |  | 9000 | 0
| Canal de transferencia de datos para el sistema de intreconexión RNP-TSE (iniciativa en conjunto con RNP) |  |  |  |  | ATE Component Team & TSE's Magistrates |  | 55000 | 55000 |  | 0 | -55000
| UNVS para desarrollar sietma de carnetización de custodios electorales |  |  |  |  | ATE Component Team & TSE's Magistrates |  | 18000 | 18000 |  | 18000 | 0
| Consultor experto en inclusión para apoyar iniciativas del TSE |  |  |  |  | ATE Component Team & TSE's Social Inclusion Unit |  | 5000 | 5000 |  | 5000 | 0
| Consultor internacional experto en analisis y verificación de datos y censo ( iniciativa en conjunto con RNP) |  |  |  |  | ATE Component Team & TSE's Census Unit |  | 7000 | 7000 |  | 0 | -7000
| Consultor Nacional experto en analisis y verificación de datos y censo ( iniciativa en conjunto con RNP) |  |  |  |  | ATE Component Team & TSE's Census Unit |  | 3000 | 3000 |  | 3000 | 0
| Consultor experto en IT para desaarollar sistema de interconexión ( TSE-RNP) |  |  |  |  | ATE Component Team, TSE & RNP |  | 4600 | 4600 |  | 4600 | 0
| Talleres, Seminarios y Foros | [10 empty] | 0
| Cuatro talleres para implementar pruebas y validar funcionamiento de sistema de intreconexión RNP-TSE |  |  |  |  | ATE Component Team, TSE & RNP |  | 1500 | 1500 |  | 1500 | 0
| 1 evento para socializar con autoridades de las instituciones, la implementación del sistema de interconexión |  |  |  |  | ATE Component Team, TSE & RNP |  | 3000 | 3000 |  | 3000 | 0
| Cinco talleres relacionados con diferentes temas electorales, entre ellos: Inclusión social, transversalización de género, mesas electorales recepctoras, tecnologías electorales y/o custodios, obervadores electorales, |  |  |  |  | PNUD & ATE/RNP Component Coordinator |  | 3413.55 | 3413.55 |  | 3300 | -113.55
| Dos talleres para socializar hallazgos del diagnostico de censo y verificación de datos ( Iniciativa conjunta RNP-TSE) |  |  |  |  | ATE Component Team, TSE & RNP |  | 3000 | 3000 |  | 3000 | 0
| Publicaciones | [10 empty] | 0
| Producción de cadena nacional para lanzamiento del proceso electoral primario |  |  |  |  | ATE Component Team, TSE & RNP |  | 3000 | 3000 |  | 5000 | 2000
| Misiones Técnicas | [10 empty] | 0
| Misiones para actualización cartografica |  |  |  |  | ATE Component Team, TSE & RNP |  | 55000 | 55000 |  | 55000 | 0
| TOTAL ACTIVIDAD 2.2 | [5 empty] | 0 | 112513.55 | 170513.55 |  | 110400 | -60113.55
The ATE Component team will include a coordinator/international technical advisor, national technical assistant, financial administrator, and a designated driver and vehicle. Additionally, the team will include a program associate, M&E specialist, Communication specialist, Gender specialist & procurement specialist The Project team will be in charge of the implementation of the activities of the annual work plan (July 2016 - June 2017 AWP) and will among other things, draft the ToR of the experts and conduct the monitoring, evaluation and reporting. Finally, the Project Implementation Unit will require resources for travel expenses, operational costs (rental and maintenance, IT, communication expenses, petty cash fund and fuel cash fund), supplies (power, water) and administration cost (GMS). | Equipo Técnico de Asistencia Electoral |  |  |  |  | ATE/RNP Project Coordinator |  | 189246 | 189314.94 |  | 163650.83 | -25664.11
| TOTAL ACTIVIDAD 2.6 | [5 empty] | 0 | 106513.55 | 189314.94 |  | 163650.83 | -25664.11
[7 empty] | GMS | GMS |  |  | 27530.59 | 27530.59
TOTAL RESULTADO 2 | [8 empty] | 396828.49 |  | 301581.42 | -95247.07
TOTAL OBJECTIVO 1 ASISTENCIA TECNICA ELECTORAL | [8 empty] | 421668.49 | 0 | 351668.49 | -70000

## Sheet2
Objetivos | Resultados Proyecto | Presupuesto por resultados | Ejecutado septiembre - diciembre 2015 | Ejecutado enero - septiembre 2016 | Ejecutado septiembre 2015 – agosto 2016 | % ejecución | Presupuesto por ejecutar octubre 2016 – junio 2017
Fortalecida la administración de las Instituciones Electorales | Resultado 1. Incrementado el nivel de seguridad de la información que se resguardan en las bases de datos del RNP a nivel central y en las áreas municipales de intervención. | $ 73,129.74 | $ 22,412.95 | $ 16,667.87 | $39,080.82 | 5.55% | $47,696.74
Resultado 2. Implementados procesos y mecanismos en el TSE y RNP para la creación de un Censo Nacional Electoral confiable y actualizado.
Mejorado el acceso a datos más seguros y confiables | Resultado 3. Entregado documento de identificación del RNP a personas que habitan en zonas vulnerables | $ 381,847.90 | $ 22,205.14 | $ 110,107.55 | 132312.69 | 18.82% | $382,643.82
Incrementada la calidad de las políticas y servicios públicos para mejorar la seguridad ciudadana | Resultado 4. Establecidos y en funcionamiento Centros de Registro e Inscripción Ciudadana (CRIC)
|  | $ 248,152.10 | $ 7,176.86 | $ 84,428.53 | 91605.39 | 13.03% | $9,790.28
| TOTAL | $ 703,129.74 | $ 51,794.95 | $211,203.95 | $262,998.90 | 37.4% | $440,130.84

## Sheet1
Objective | Results | Budget Year 1 July 2015-June 2016 (a) | Budget Year 2 July 2016-June 2017 (b) | Total budget July 2015-Jun 2017 ( c ) = (a+b) | Expenditure July 2015-Junio 2016 (d) | % execution budget year 1 | % execution total budget | Balance New AWP july 2016-june 2017 | % Delivery Year 1 (Expenditures as at June 2016/Budget Year 1) ( e ) = (d/a)
Honduras Electoral System Strengthened | Result 1: Electoral Legal and Regulatory Framework Improved
| Electoral Technical Assistance | 131114.93 | 24840 | 155954.93 | 105867.86 | 80.74% | 67.88% | 50087.07 | 80.74%
Result 2: Electoral institutions’ administration improved
| Electoral Technical Assistance | 405612.99 | 290459.55 | 696072.54 | 394491.12 | 97.26% | 56.67% | 301581.42 | 97.26%
TOTAL |  | 536727.92 | 315299.55 | 852027.47 | 500358.98 | 93.22% | 58.73% | 351668.49 | 178%

## INCLUSIVE MECHANISMS
ANNUAL WORK PLAN - OBJECTIVE 2 "INCLUSIVE MECHANISMS THAT RESPOND TO CITIZEN SECURITY NEEDS IMPROVED"
Result | PMP Indicators | Activities | Narrative of the Activity | Actions | Timeframe Jul 16 to June 17 |  |  |  | Responsible party | Budget for period July 2016 - June 2017
[5 empty] | Jul-Sep 2016 | Oct - Dec 2016 | Jan - Mar 2017 | Apr - Jun 2017 |  | Source of Funds US$
[10 empty] | UNDP | USAID | Total budget
Result 1: Access to secure and reliable data improved | OUTCOME INDICATOR 1.1 Number of bulletins published by the University Institute Democracy, Peace and Security (Insituto Universitario Democracia, Paz y Seguridad), IUDPAS with UNDP/USG support. | 1.1.1 Process of validation and updating data on crime. Create charts, analyze and disseminate information and publish newsletters. | Each observatory will publish quarterly and annual bulletins, analyzing the statistics of violence that are collected. Also will publish special bulletins on specific topics. | Technical Assistance by a Letter of Agreement betwen UNDP and UNAH:
|  |  |  | Selection and recruitment of national consultants on systems engineers, analysts and local assistant to develop of the validation process, layout and analysis of 30 bulletins of the 5 municipalities. |  |  |  |  | UNDP/ IUDPAS - UNAH |  | 97636.65 | 97636.65
|  |  |  | National validation: Process of validation and geocoding of statistical data with official sources on crime. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Local validation: Process of validation and geocoding of statistical data on crime (2015-2016) in 5 municipalities. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Debugging and consolidation of the database at local and national level. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Elaborate charts, graphs and geo-referenced maps needed for the production of quarterly, semiannual and annual bulletins. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Analysis and writing of 24 local and national bulletins for the years 2015 to 2017 and 6 special bulletins. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Review, quality control, editing, design and printing newsletters. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Presentation and preliminary data analysis with official sources and coexistence and security councils of 5 municipalities. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Socialization of results in 5 municipalities. |  |  |  |  | UNDP/ IUDPAS - UNAH
| OUTPUT INDICATOR 1.1.2 Number of people trained in policy and security plan formulation for local actors and justice operators. | 1.1.2 Develop an university diploma on citizen security targetted at members of municipal councils of prevention and safety, as well as officials of the five municipalities. Results based on evidence for decision-making: (Workshops and an university diploma). | Strengthening of violence observatories, UNDP will also work with local technicians to improve their ability to use statistical data and information provided by the observatories to formulate policies and plans on crime prevention. Specifically, UNDP will develop a university diploma in citizen security for local governments and community leaders focused on improving their analytical capacity. | Development of the conceptual and methodological proposal of the diploma in citizen security |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Teacher recruitment process to facilitate the diploma modules. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Identify volunteer teachers to facilitate 3 modules |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Implementation of citizen security program addressed to different actors in 5 municipalities (includes folders, ink, notebooks, stationery, labels, envelopes, paper, cards, etc.) |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Defense final research paper and completion of the modular program. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Systematization of security councils and prevention committees of Tela and La Ceiba: interviews, document review and focus groups. |  |  |  |  | UNDP/ IUDPAS - UNAH
|  |  |  | Operating costs. |  |  |  |  | UNDP/ IUDPAS - UNAH |  | 10830.53 | 10830.53
|  |  |  | Specialized consultancy on national observatories of violence. |  |  |  |  | UNDP/ IUDPAS - UNAH |  | 57139.18 | 57139.18
| TOTAL ACTIVITIES UNAH/IUDPAS | [10 empty] | 165606.36
| OUTCOME INDICATOR 1.2 Number of people registered or identified in RNP records in areas prioritized by the project during identification brigades. | 1.3. Reduced Levels of Under-registration of Civil Acts and Under-identification in Prioritized Areas | This activity is divided into two actions: Conduct an Assessment of Under-registration of Civil Acts and Under-identification Conduct an assessment in order to ascertain who are and where the people in the priority zones who are not included in the civil registry and/or do not have identity cards,are located. This information will then be used to create effective registration and identification strategies. With the understanding that involvement of the community is the starting point to combat social exclusion, this assessment will be conducted based on cooperation agreements between the RNP and well-established social organizations which members come from the communities where capacities will be installed. Using the information collected by the social organizations, data analysts will assess the communities’ issues regarding under-registration of civil acts and under-identification, which will help UNDP and the RNP design appropriate strategies. Create and Deploy Mobile RNP Brigades To reduce the number of under-registrations and under-identifications in the priority areas, UNDP will help the RNP create and deploy mobile RNP brigades to travel across the country and bring the services of the RNP directly to the people. The mobile RNP brigades will be tasked with registering civil acts and submitting identification requests in the target communities. Based on the information gleaned from the assessment of under-registration and under-identification in each community, UNDP and the RNP will develop an intervention strategy defining the places and dates for the visits of mobile RNP brigades. In order to register and provide identification for citizens who have not previously registered or received identification cards, UNDP will help the RNP make the processes more flexible so that these people can be registered and receive identification cards more easily and promptly. | Technical Assistance:
|  |  |  | Data Analysts 1 analyst for 2 months), to tabulate data obtained by organizations about the cases of under-registration and under-identification in their communities, an IT Expert (5 months) to create the necessary information systems to conduct an assessment of under-registration and under-identification and a part of the Technical Assistance Team (Programme Associate, Comunicator,Gender specialist, Municipal strengthening manager, Technical Advisor on registration topics, an Administrative / Financial RNP/TSE Acquisitions Associate, Field Strategy Specialist, Civil Registry and Citizen Identification Specialist , Chauffeur) |  |  |  |  | Department of Information Technology , Technical assistance for citizen Identification, |  | 312264.4692 | 312264.4692
Missions:
|  |  |  | Travel Mission( 8 Municipalities): Trip 1: Training Organizations as Registration Promotors Create and Deploy Mobile RNP Brigades to Municipalities to increase the database of birth, death and identity. Trip 2: Create and Deploy Mobile RNP Brigades 8 municipalities: San Pedro Sula, Ceiba, Choloma, Corquín, Nueva Aracdía, Las Vegas, Quimistán, Nueva Frontera |  |  |  |  | RNP Department of Information Technology , Civil Registry and Identification Technical, Technical assistance for citizen Identification, |  | 59572.6056 | 59572.6056
|  | 1.4 Conduct Training Workshops for Institutions and Organizations to Train Registration Promoters and Form a Network for Timely Registration (Red de Inscripción Oportuna or RIO) | Workshop topics will address issues related to civil registration such as relevant laws, procedures, and time-periods in which the RNP must complete registrations and identity card requests.After the trainings, the Registration Promoters will be expected to return to their communities and hold talks and/or informally disseminate information about registration and identification, their importance, and the necessary requirements. In accordance with RNP’s strategy, these workshops will support the formation of a Network of Timely Registration (Red de Inscripción Oportuna or RIO), composed of municipal institutions and organizations. Workshop participants will learn about the Network’s mission, objectives, and functions, among other things, and will be invited to join the Network. Staff of the MCRs will also be invited to participate in these workshops to keep them updated on the issues of civil registration and citizen identification and to raise awareness of under-registration and under-identification so that they can play a key role in the processes designed to reduce these levels. Overall, the goal of the network will be to promote a culture of registration that is inclusive and encourages citizens’ rights. The network will also collect information about under-registration of civil acts and under-identification in each municipality and will monitor and follow-up on actions that promote timely registration. | Workshops:
|  |  |  | Workshops: Conduct 4 workshops in the target municipalities to train the Civil Organization and other public institutions as “Registration Promoters”. One workshop is expected to be held in each of the eight target municipalities with at least 20 participants each. ( Food and supplies for the participants) |  |  |  |  | RNP Department of Information Technology , Civil Registry and Identification Technical, Technical assistance for citizen Identification, |  | 12205.2636 | 12205.2636
|  | 1.5 Organize a Public Awareness Campaign | Create and implement a campaign to raise public awareness about the importance of registering civil acts and obtaining official identification for the priority zone. The campaign will disseminate information about the RNP mobile brigades, advising citizens on when and where to meet them. | Publications:
|  |  |  | Media Campaign: Recruit an advertising company to develop and implement a local campaign to inform and raise awareness among citizens to promote the registration of all civil acts at the RNP. The advertising company will be responsible for designing spots for radios and make alliances with non-profit organizations such as religious radio stations; as well as designing the artwork for the written posters and brochures. The message of the media campaign will be defined jointly with the authorities of RNP, and advertisements will be broadcast in the local media at the municipalities where the mobile RNP brigades will be. |  |  |  |  | Protocol and Press RNP Departament , Communication and Gender UNDP specialist , Technical assistance for citizen Identification |  | 25440 | 25440
TOTAL ACTIVITIES RNP 1.3; 1.4; 1.5 | [9 empty] | 0 | 409482.3384 | 410106.8584
TOTAL ACITIVITIES RESULT 1: UNAH/IUDPAS & RNP | [11 empty] | 575713.2184
Result 2: Quality and inclusive public policies and services that improve citizen security enhanced | 2.1 LOCAL MANAGEMENT OUTPUT INDICATOR 2.1.2 Number of municipalities that articulate dialogue spaces with the national level. | 2.1.1 Strengthening of municipal offices for prevention management, logistics, equipment and human resources to develop actions that promote coexistence and security. | UNDP will provide technical assistance to the prevention offices for the formulation and evaluation of local policies, plans, programs and projects related to coexistence and security with a gender perspective. At the same time, UNDP will arrange meetings, workshops and seminars with key actors at local and national level on participatory management of violence prevention. | Technical assistance
|  |  |  | Recruiting an expert for the functioning of the Municipal Prevention Offices. |  |  |  |  | UNDP and local governments |  | 35124.28 | 35124.28
|  |  |  | Inauguration of the Municipal Prevention Offices. |  |  |  |  | UNDP Local Management Area |  | 662.66 | 662.66
|  |  |  | Meetings to socialize the proposal with the municipal prevention offices. |  |  |  |  | UNDP Local Management Area |  | 441.78 | 441.78
Equipment and Furniture
|  |  |  | Equipment for the Municipal Prevention Offices. |  |  |  |  | UNDP Local Management Area |  | 71491.72 | 71491.72
Publications:
|  |  |  | Publishing and socialization of the Operating Manual of the Municipal Office of Prevention. |  |  |  |  | UNDP Local Management Area |  | 8000 | 8000
GRANTS
|  |  |  | Grant for the CAC-UNAH. |  |  |  |  | UNDP Local Management Area |  | 25000 | 25000
|  |  |  | Grant for microcapital support for small business initiative. |  |  |  |  | UNDP Local Management Area |  | 10000 | 10000
| 2.1 LOCAL MANAGEMENT OUTCOME INDICATOR 2.1 Percentage of actions executed increased from the Annual Operatives Plans in each target Municipality. | 2.1.2 Annual work plan for coexistence and citizen security with a gender perspective designed, implemented and appropriately evaluated. | The annual work plans (AWPs) are a highly valued tool for the articulation of local institutional offer and a mechanism for measuring results and compliance with the objectives and follow up actions, facilitating an analysis of their effectiveness and improving interventions. Resources have not yet been approved for the Central District so UNDP and the municipal government will implement a work plan in 2016. | Technical assistance for the discussion of AWP and its progress:
|  |  |  | Accountability sessions with different municipal actors. |  |  |  |  | UNDP Local Management Area |  | 11856.06 | 11856.06
|  |  |  | Meetings of municipal authorities in their local contexts |  |  |  |  | UNDP Local Management Area |  | 3714.02 | 3714.02
|  |  |  | Workshop to strengthen capacities for georeferencing of community interventions. |  |  |  |  | UNDP Local Management Area |  | 2135.12 | 2135.12
|  |  |  | Intermunicipal workshop on results-based management. |  |  |  |  | UNDP Local Management Area |  | 15000 | 15000
|  |  |  | Event for the presentation of project results. |  |  |  |  | UNDP Coordination Unit |  | 30000 | 30000
|  |  |  | Monitoring and Evaluation of all actions/ activities. |  |  |  |  | UNDP Coordination Unit |  | 42473 | 42473
Publications:
|  |  |  | Publications of community interventions. |  |  |  |  | UNDP Local Management Area |  | 9000 | 9000
|  |  |  | Operating costs: including GMS and service contracts 71400 | [6 empty] | 257182.9 | 257182.9 | 371361.1
| TOTAL ACTIVITY 2.1: | [10 empty] | 522081.54
| 2.2 CPTED OUTCOME INDICATOR 2.2 Number of infrastructure projects using CPTED methodology implemented in selected communities led by municipal officials. | 2.2.1 Support IDECOAS/FHIS so that they can provide technical assistance to the project municipalities for the implementation of the CPTED methodology. | UNDP and IDECOAS sign aLetter of Agreement commeting to a) Strengthen the capacities of the municipalities to apply the CPTED methodology instruments i) diagnosis ii) community assembly iii) discussion on priorities and the design of projects iv) presentation of projects for grants funding v) implementation of infrastructure projects vi) evaluation. b) Carry out 2 processes for the implementation of 2 local policies. c) Study visit to a country in the region with experience in preventation and the recuperation of public spaces. | Technical Assistance by a Letter of Agreement betwen UNDP and IDECOAS/FHIS
|  |  |  | CPTED diagnoses, community assemblies for prioritization and project design. |  |  |  |  | UNDP - IDECOAS / FHIS |  | 139622.07 | 139622.07
|  |  |  | Design and implementation of social infrastructure projects applying the CPTED-PEC and final reception of the works. |  |  |  |  | UNDP - IDECOAS / FHIS
|  |  |  | GRANT IDECOAS-FHIS |  |  |  |  | UNDP - IDECOAS / FHIS
| 2.2 CPTED OUTPUT INDICATOR: 2.2.1 Number of municipal employees trained on the CPTED methodology that are able to implement project adopting this methofology | 2.2.2 Strenghtening of the municipal instances' capacity to apply the CPTED metholodogy through local policies. | Design and implementation of 2 municipal policies for situational prevention, including the design and review of municipal norms. The metholodogy will include a gender perspective. | Personnel
|  |  |  | Recruitment of a national consultancy for the development of two municipal policies for situational prevention. |  |  |  |  | UNDP, Municipalities & IDECOAS / FHIS |  | 30000 | 30000
|  |  |  | Recruitment of a gender consultancy to advise local policy processes and ensure the presence of a gender perspective. |  |  |  |  | UNDP - IDECOAS / FHIS |  | 13000 | 13000
Workshops:
|  |  |  | Implementation of workshops on the local policy development methodologies. |  |  |  |  | UNDP - IDECOAS / FHIS |  | 10000 | 10000
|  |  |  | Exchange of experiences with one country in the region for personnel from IDECOAS/FHIS and the municipal instances |  |  |  |  | UNDP - IDECOAS / FHIS |  | 27000 | 27000
|  |  |  | Travel and missions |  |  |  |  | UNDP |  | 6650 | 6650
Publications:
|  |  |  | Publications of the systematization of experiences (300). |  |  |  |  | UNDP |  | 4000 | 4000
|  |  |  | Publication of promotional materials. |  |  |  |  | UNDP |  | 6000 | 6000
|  |  |  | Operating costs, including GMS and service contracts 71400. |  |  |  |  | UNDP |  | 274082.96 | 274082.96
| TOTAL ACTIVITY 2.2: | [10 empty] | 510355.03
| 2.3 UMC OUTCOME INDICATOR 2.3 Number of instruments formulated to use alternative conflict resolution mechanisms. | 2.3.1 Interinstitutional Committee for alternative mechanisms for conflict resolution organized and up and running. | Specialized technical assistance for the Judicial and Executive branches for the installation of the Interinstitutional Committee on alternative mechanisms for conflict resolution and the development of a work plan and public policy proposal on the same. A proposal for the academic curricula on AMCR will be prepared and a course on advanced mediation will be carried out. A study on the judicial status of the AMCR in Honduran legislation will be carried out and a information system for the MCU will be developed. | Personnel
|  |  |  | Recruitment of an international consultant specialized in mediation and conciliation. |  |  |  |  | Mediation and Conciliation Area |  | 97300 | 97300
|  |  |  | Recruitment of a consultancy for the analysis of the judicial situation of the AMCR. |  |  |  |  | UNDP |  | 12000 | 12000
|  |  |  | Recruitment of a consultancy for the development of the information system with work and statistical modules for the UMC. |  |  |  |  | UNDP |  | 18000 | 18000
|  |  |  | Recruitment of consultancies for the municipal mediation and conciliation units |  |  |  |  | UNDP |  | 53683.25 | 53683.25
Equipment
|  |  |  | Purchase of hardware for the UMC information system. |  |  |  |  | UNDP |  | 25000 | 25000
|  |  |  | Equipment and physical improvements to the UMC in San Pedro Sula and Tela. |  |  |  |  | UNDP |  | 8261.21 | 8261.21
| 2.3 UMC OUTCOME INDICATOR 2.4 Number of people that access alternative conflict resolution mechanisms in targeted municipalities. | 2.3.2 Mediation and Conciliation Units, Points and Networks for community coexistence strengthened in human resources, logistics and equipment in order to promote coexistence and conflict mediation. | Material and human resource support will be provided in order to support the work of the UMC and the community points in 5 municipalities | Travel costs
|  |  |  | Transportation and mobilization costs for UMC and PCC personnel. |  |  |  |  | UNDP |  | 9427.5 | 9427.5
Equipment
|  |  |  | Equipment for the five target municipalities and purchase of office equipment for the UMC offices. |  |  |  |  | UNDP - UMC - PCC |  | 10000 | 10000
|  | 2.3.3 Educational processes; meetings and trainings in mediation and promoting coexistence in a participatory manner with gender perspective in five municipalities implemented. | Continue to providing training for coexistence promoters and community mediators in 5 municipalities. Give support with publications and materials for training processes. Hold the opening of new points of community coexistence in the municipalities. Provide a training to Garifuna peoples on the rules of Brasilia. | Trainings and Workshops
|  |  |  | Animation Workshops for Volunteers in Coexistence. |  |  |  |  | UNDP - UMC - PCC |  | 1082.76 | 1082.76
|  |  |  | Awareness Raising Workshops for new AVCC. |  |  |  |  | UNDP - UMC - PCC |  | 13240.89 | 13240.89
|  |  |  | Training module for Mediators. |  |  |  |  | UNDP - UMC - PCC |  | 6065.78 | 6065.78
|  |  |  | Training Module for Promotors. |  |  |  |  | UNDP - UMC - PCC |  | 6065.78 | 6065.78
|  |  |  | Workshop on Code of Ethics for new AVCC. |  |  |  |  | UNDP - UMC - PCC |  | 2662.22 | 2662.22
|  |  |  | Workshop for Mediators and Promotors. |  |  |  |  | UNDP - UMC - PCC |  | 9860 | 9860
|  |  |  | Workshop for Community Coexistence Volunteers |  |  |  |  | UNDP - UMC - PCC |  | 4539 | 4539
|  |  |  | Workshops on mediation and conciliation to UMC officials of the five municipalities. |  |  |  |  | UNDP - UMC |  | 6234 | 6234
|  |  |  | Coordinators meeting of UMC in different municipalities |  |  |  |  | UNDP - UMC |  | 7840 | 7840
|  |  |  | Actors National Meeting of Volunteers in Coexistence |  |  |  |  | UNDP - UMC - PCC |  | 50000 | 50000
|  |  |  | Graduation and certification of volunteer hours (AVCC) |  |  |  |  | UNDP - UMC - PCC |  | 15188.89 | 15188.89
|  |  |  | Workshop for certification of hours worked by AVCCs. |  |  |  |  | UNDP - UMC - PCC |  | 9000 | 9000
|  |  |  | Opening on Community Coexistence Points |  |  |  |  | UNDP - UMC - PCC |  | 17973.33 | 17973.33
|  |  |  | Support materials for the PCC. |  |  |  |  | UNDP - UMC - PCC |  | 4626.08 | 4626.08
|  |  |  | Workshops with Garifuna populations - Brasilia Rules. |  |  |  |  | UNDP - UMC - PCC |  | 1000 | 1000
Publications
|  |  |  | Publication of promotional materials. |  |  |  |  | UNDP - UMC - PCC |  | 15000 | 15000
|  |  |  | Operating costs (including GMS and service contracts 71400) |  |  |  |  | UNDP |  | 257182.9 | 257182.9
| TOTAL ACTIVITY 2.3 | [10 empty] | 661233.59
| 2.4 Women´s Municipal Office WMO OUTCOME INDICATOR 2.5Number of women in selected municipalities that access services offered by the Women Municipal Offices (WMO). | 2.4.1 Strengthen the capacities of municipal women's offices to promote effective action through the implementation of innovative activities. | Technical assistance to women's municipal offices according to the annual work plan, provide equipment, furniture, materials, publications, promotional, seed capital, etc. that will be delivered according to the work plan with each WMO. In addition, provide capacity strengthening through workshops, conferences, forums, meetings and exchanges between WMOs. Follow up the information system of the WMO, particularly the module of violence against women in order to generate information locally for decision-making. | Personnel
|  |  |  | Central District: Design of "Handbook for Women Entrepreneurship" and training employees for use of the municipal government for further replication groups of entrepreneurs. |  |  |  |  | UNDP-WMO |  | 7000 | 7000
|  |  |  | Consultancyto design a module on gender and security. |  |  |  |  | UNDP |  | 8000 | 8000
|  |  |  | Consultancy to facilitate two specialized workshops for WMO. |  |  |  |  | UNDP-WMO |  | 4000 | 4000
Equipment
|  |  |  | San Pedro Sula: Provision of equipment to support training processes offered by the Women Municipal Office (WMO). |  |  |  |  | UNDP-WMO |  | 7000 | 7000
|  |  |  | Tela: Delivery of computer equipment to the WMO. |  |  |  |  | UNDP-WMO |  | 1300 | 1300
|  |  |  | Grants | [8 empty] | 124575.47
|  |  |  | La Ceiba: Delivery of seed capital through the Chamber of Commerce. |  |  |  |  | UNDP-Chamber Commerce-WMO |  | 7000 | 7000
|  |  |  | Choloma: Delivery of seed capital through the Chamber of Commerce. |  |  |  |  | UNDP-WMO |  | 7000 | 7000
Workshops
|  |  |  | Tours every 2 months for monitoring of the Information System of the WMO. |  |  |  |  | UNDP |  | 7185 | 7185
|  |  |  | Exchanges with Municipal Women's Offices of the five municipalities. |  |  |  |  | UNDP-WMO |  | 29216 | 29216
|  |  |  | Accompanying to activities of the work plans of the women municipal offices. |  |  |  |  | UNDP-WMO |  | 21874.47 | 21874.47
|  |  |  | Intermunicipal forum for experiences exchange between WMO. |  |  |  |  | UNDP-WMO |  | 12515 | 12515
|  |  |  | Priority activities of work plans of the WMO for each municipality. |  |  |  |  | UNDP-WMO |  | 12485 | 12485
| 2.4 Women´s Municipal Office WMO OUTPUT INDICATOR 2.5.3 Number of proposals on culture of peace presented by youth to decision-makers. | 2.4.2 Design and implementation of awareness campaigns in schools and taxi associations in three municipalities (Choloma, La Ceiba and Tela). | Implementation of an awareness campaign on prevention of domestic violence and sexual harassment that includes training at various local actors and developing protocols in ten schools in priority areas of the project and taxi associations in the municipalities of Choloma, Tela and La Ceiba . | Publications
|  |  |  | Assistance in the implementation of awareness campaigns on prevention of domestic violence and sexual harassment for each selected municipality in accompaniment to the Women Municipal Offices. |  |  |  |  | UNDP-WMO |  | 35000 | 35000
|  |  |  | Operating costs (including GMS and service contracts 71400) |  |  |  |  | UNDP |  | 257182.9 | 257182.9
| TOTAL ACTIVITY 2.5 | [10 empty] | 416758.37
| 2.5 Culture and Youth OUTCOME INDICATOR 2.6 Number of proposals on culture of peace presented by youth to decision-makers. | 2.5.1 Formulation of a plan of community strengthening for managing protective environments in each municipality. | Provide processes in areas of the 5 municipalities for promoting protective environments for young people, such as family, school and community, all through the realization of recreational activities and realization of youth participatory plans. Formulation of a communication strategy including the creation of youth groups in two municipalities, producing communication materials and alternative products to promote life, peace and coexistence. These groups will be strengthened in coordination with the PMIAJ / COMVIDA to be responsible for monitoring of processes that are carried out. | Personnel
|  |  |  | Hiring a consultant to facilitate local youth agendas and develop workshops on social organization and strategic planning. |  |  |  |  | UNDP-PMIAJ | 16500 |  | 16500
|  |  |  | Hiring a consultant to formulate a plan of community strengthening for managing protective environments in each municipality in coordination with PMIAJ. |  |  |  |  | UNDP-PMIAJ | 9000 |  | 9000
Technical Missions
|  |  |  | Tracking and monitoring of creative and recreational holidays methodology. |  |  |  |  | UNDP-PMIAJ | 8500 |  | 8500
Workshop
|  |  |  | Develop a communication strategy for life that includes 2 youth groups to promote community radio online and local cables, as well as creating blogs linked to social networks in coordination with project communication area. |  |  |  |  | UNDP-PMIAJ | 12500 |  | 12500
|  | 2.5.2 Review and formulation of the draft law to promote culture in consultation with local and cultural actors. | A participatory review of the draft of Law to promote culture with local and cultural actors through municipal / regional workshops to update and have a new proposal to present to making decision. | Personnel
|  |  |  | Recruitment of national consultant to review the draft law on promoting culture through local and regional consultation workshops. |  |  |  |  | UNDP-PMIAJ | 5500 |  | 5500
Publications
|  |  |  | Publications |  |  |  |  | UNDP | 5000 |  | 5000
|  | TOTAL ACTIVITY 2.6 | [9 empty] | 57000
| TOTAL ACTIVITY 2 USAID FUNDS | [10 empty] | 2110428.53
| TOTAL ACTIVITY 2 UNDP FUNDS | [10 empty] | 57000
| TOTAL ACTIVITY 2 | [10 empty] | 2167428.53
[9 empty] | RNP Project (activity 1 & 2) |  |  | 502804.3674 | #REF!
[9 empty] | Security and Citizen Coexistence Project |  |  | 2276034.89
| TOTAL OBJECTIVE 2 (ACTIVITY 1 & ACTIVITY 2) USAID FUNDS |  |  | 2686141.7484
502804.37
| TOTAL PROJECT (OBJECTIVE 1 & OBJECTIVE 2) |  |  | 3564485.1474 | [8 empty] | RNP | #REF!
|  |  | TOTAL | 3,564,485.15 | comprimos incluidos en nuevo AWP
|  |  | ATE | 421668.49
|  |  | RNP | 502804.37
|  |  | Seguridad | 2276034.89
|  |  | Partidos Políticos | 363977.4
|  |  | TOTAL | 3564485.15
|  |  | DIFERENCIA | 0.00264