## Plan 2014
Procurement Plan 2014
Data to be provided/completed by Programme/Project
Project Name | Project ID | Type of Supply (service, goods, Individual consultant, civil work) | High Level Categorizaton | Description of goods, services or works | Quantity/ Duration | Estimated Total Price in USD for 2014 | * Available budget in USD/Total Contract Amount | EstimatedCompletion of Activity | Requesting Unit/Focal Point | Comments
Shell - VTC-MSME | 82551 | Civil Civil Works | High, due to complexity of expected services and high value of LTA | Turn-key design and construction of Vocational Training Center (Shell/SOC) | 1 to 4 Quarter | 2000000 | 5000000 | 2015-02-01 |  | Turn key design and BOQ will be development by engineers and it expected that construction will be lasted for 2 years with total amount of 5 million, considering complexity of construciton and provision of training EQPs.
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | English Language Trainings | 1 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | Project Management Trainings | 1 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | LTA Quality Assurance-Trainings | 1 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | Health and Safety Environment-Trainings | 1 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | Assets Management & Computer Skills -Trainings | 1 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | HR and Financial Management and Auditing Trainings | 3 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | Developing Standards Trainings | 3 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
Shell - VTC-MSME | 82551 | Services | High, due to complexity of expected services and high value of LTA | ISO Standards Trainings | 3 Quarter | 225000 | 450000 | 2014-12-01 |  | LTA over two years (450,000/2)
[6 empty] | 3800000 | 8600000
*Available budget covers the total contracts' amounts more than one year