## 2016
Atlas PROJECT Award ID: 66352 | Annual Work Plan (AWP) 2016: Version A
Atlas OUTPUT ID: 82552
ATLAS Project/Programme Title: | Development Partnership Programme
Atlas OUTPUT Name | Area Based Development Programme
UNDAF Outcome: | Outcome 5: Enabling policy and frameworks for rapid economic recovery, inclusive and diversified growth and private sector development
Applicable Key Result Area (from 2015-17 Strategic Plan):
CPAP Outcome: | Outcome 5: Enabling policy and frameworks for rapid economic recovery, inclusive and diversified growth and private sector development
CPAP Output(s): | Output 7.6: Innovations enabled for development solutions, partnerships and other collaborative arrangements
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount ($) | SIDA | KRG | Shell | TRAC
Output 1 (Output 2 - KRG): Production of 18 Development Plans with district level inputs through enhanced national, regional, and governorate capacity and mechanisms and mainstreaming NDP social priorities/MDG strategies into Local Development and Service Delivery (LDSD), and through integrated knowledge management and public access to information. Indicators: 1. Institutionalised mechanisms/ processes operating at regional, governorate and district levels to manage integrated, multi-sectoral information and findings 3. KRG Vision social priorities and MDG targets , vulnerability assessments/ strategies and district plans are incorporated into Governorate-level planning processes Baseline 1. No assessment of baseline local situation on available Government information regarding local development and service delivery 2. No Provincial Development Strategies for any of KR governorates Target: 1. Three (3) Provincial Development Strategies for KR three governorates that respond to KRG Vision. 2. Provincial Annual Planning Manual, that documents major processes and techniques in preparing provincial annual plans for KR governorates. 3. Provincial Development Strategy Manual, that documents major processes and techniques for formulating provincial development strategies. | Activity.1.1 |  |  |  |  | UNDP | 30000 | SIDA | 00555 | 61300 | Personnel - Int | 42747 | 46166.76 | 153644.8662 | 264510.7542 | 150000 | 614322.3804
| 1.1.1 Review and finalize drafted PDSs for KR provincies (Erbil, Suli and Dohuk). |  |  |  |  | UNDP | 30071 | KRG | 00135 | 61100 | Personnel - Nat |  | 46167 | 189145 | 434511 | 150000 | 819823
| 1.1.2 Translate PDSs into Kurdish and English |  |  |  |  | UNDP | 30071 | KRG | 00135 | 61300 | Personnel - Int | 119288 | 0.24 | 35500.1338 | 170000.2458 | 0
| 1.1.3. Design and print PDSs for future referrence |  |  |  |  | UNDP | 30071 | KRG | 00135 | 71600 | Travel - missions | 14293 |  |  | 264512
1.1.4. Discuss and plan launching event with KRG MoP for PDSs
1.1.5. Review and finazlie drafted PDS manual
1.1.6. Review and finalzie drafted PAP manual
Total of Output 1 | [11 empty] | 176328
Output 2 (Output 1 - Shell): Inclusive participatory processes in local area planning and decision-making are institutionalized. Local communities are given a key role in influencing development priorities and in turn contribute to further stability and reconciliation Indicators - Sucessfull implimentation of development projects under Shell Partnership - Technical assistance provided to the planning of sub-districts Baseline: Needs identified in the consultation process are reflected in the local district plan for public funding consideration, Community priorities and needs are addressed Target • Completion of School Rehabilitation Project • Conducting the Partnership reveiw Exercise • Formulated proposals and discussions for partnership future based on Review report | Activity 2.1 |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61300 | Personnel - Int | 61521
| 2.1.1 Full complete School Rehabilitation Project |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61100 | Personnel - Nat
| 2.1.2 Opening cermoney with communication plan for the school project |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 71600 | Travel | 5000
| 2.1.3 Finalize concept note on vocational training and employability for donors' consideration |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 72100 | Contracts | 10000
| 2.1.4 Conduct related Partnership Review evaluation for area based component of Shell partnership |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 74500 | Miscellaneous | 500
| 2.1.5 Conduct defect liability assessment for school and playgrounds projects |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 74500 | Miscellaneous
Total of Output 2 | [11 empty] | 77021
Output 3 (Output 2 - Shell): Institutional capacity and technical capability at national and sub national level to support local inclusive development and service delivery established Indicators - Sucessfull implimentation of development projects under Shell Partnership - Technical assistance provided to the planning of sub-districts Baseline: Governorate Steering Committee and District Technical Committee are able to perform their functions and advise on institutionalisation of process Target • Follow up on formulated sub-district development strategies for targeted sub-districts • Follow up on Area Profiles for targeted sub-districts • Finalizing and presenting organizational assessments for key national institutions | Activity 3.1: |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61300 | Personnel - Int | 86000
| 3.1.1 Conduct follow up meetings on formulated sub-district development planning |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61100 | Personnel - Nat
| 3.1.2 Follow up and conduct meetings on area profiles in Al-Dair and Al-Nashwa sub-districts |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 71600 | Travel | 5000
| 3.1.3 Conduct related Partnership review Exercise |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 72100 | Contracts | 15000
3.1.4 Conduct stakeholders consultation for national partners, on the conclusions of UNDP-Shell Partnership review evaluation
3.1.5 Formulate concept notes and discussions for future cooperation based on Review Exercise recommendations
3.1.6 Finalize translated organizational assessments for BOTI and SOC
Total of Output 3 | [11 empty] | 106000
Output 4 (Output 1 - Basra Compactl): Improved capacities at district level to develop and implement strategies for accelerated achievement of localised National Development Plan (NDP) social priorities and Millennium Development Goals (MDG) targets. Indicators - Number of projects agreed with teh governorate based on cost sharing - Technical assistance provided to the governorate supporting teh thematic areas of teh compact agreement Baseline: UNDP signed a Compact Agreement with Basra Goevrnorate in May 2015, to supoprt the governorate under several tehmatic areas based on their priorities and needs. Target • One concept note submitted to teh governorate covering one of teh thematic areas udner teh compact. • One project apporved by the governorate based on cost sharing | Activity 4.1: |  |  |  |  | UNDP | 00012 | TRAC | 04000 | 72100 | Contracts | 125000
| 4.1.1 Produce one concept note to initiate a PFM project with Basra Provincial Council, in preparation for a Project based on cost sharing |  |  |  |  | UNDP | 00012 | TRAC | 04000 | 74200 | Miscellaneous | 20000
| 4.1.2 Support activities to initiate projects under the Basra Compact Agreement, responding to the several tehmatic areas and priorities under the agreement. |  |  |  |  | UNDP | 00012 | TRAC | 04000 | 74500 | Miscellaneous | 5000
Total of Output 4 | [11 empty] | 150000
Management Cost | Management Cost
| Common Premises | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 73120 | Common Premises | 50000 | It needs to be calsulated as a lump sum ($6,196.37 * staff No.)
| Life Support | X | X | X | X | UNDP |  |  |  | 73120 | Life Support | 0 | It is not percentage, it has 3 different calsulation: - Baghdad Intrnational Staff= $33.42 per staff * 264 days - Baghdad Local Staff= $18.75 per staff * 264 days - Erbil (Int. & Local) Staff= $17.41 per staff * 264 days
| Communications (2.5%) | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 72400 | Communic & Audio Visual Equip | 4575.525
|  | X | X | X | X | UNDP | 30071 | KRG | 00135 | 72400 | Communic & Audio Visual Equip | 3339.525
| Security (4%) | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 74300 | CO Common Security | 7320.84
|  | X | X | X | X | UNDP | 30071 | KRG | 00135 | 74300 | CO Common Security | 5343.24
| Monitoring and Evaluation (2%) | X | X | X | X | UNDP |  |  |  | 74100 | Professional Services | 0
| GMS (8%) | X | X | X | X | UNDP | 30000 | SIDA | 00555 | 75100 | General Management Services | 3419.76
|  | X | X | X | X | UNDP | 30071 | KRG | 00135 | 75100 | General Management Services | 11381.1012
|  | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 75100 | General Management Services | 19593.3892
Total of Management Cost | [11 empty] | 104973.3804
Total Project Budget for 2016 | [11 empty] | 614322.3804
This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partner, the plan authorizes the responsible parties and project management to manage available resources and achieve set results.
Project Manager: Thair Shraideh | 16/2/2016 | [6 empty] | UNDP Country Director
Signature & Date | [7 empty] | Signature and Date

## 2017
Atlas PROJECT Award ID: 66352 | Annual Work Plan (AWP) 2016: Version A
Atlas OUTPUT ID: 82552
ATLAS Project/Programme Title: | Development Partnership Programme
Atlas OUTPUT Name | Area Based Development Programme
UNDAF Outcome: | Outcome 5: Enabling policy and frameworks for rapid economic recovery, inclusive and diversified growth and private sector development
Applicable Key Result Area (from 2015-17 Strategic Plan):
CPAP Outcome: | Outcome 5: Enabling policy and frameworks for rapid economic recovery, inclusive and diversified growth and private sector development
CPAP Output(s): | Output 7.6: Innovations enabled for development solutions, partnerships and other collaborative arrangements
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount ($) | SIDA | KRG | Shell | TRAC
Output 1 (Output 2 - KRG): Production of 18 Development Plans with district level inputs through enhanced national, regional, and governorate capacity and mechanisms and mainstreaming NDP social priorities/MDG strategies into Local Development and Service Delivery (LDSD), and through integrated knowledge management and public access to information. Indicators: 1. Institutionalised mechanisms/ processes operating at regional, governorate and district levels to manage integrated, multi-sectoral information and findings 3. KRG Vision social priorities and MDG targets , vulnerability assessments/ strategies and district plans are incorporated into Governorate-level planning processes Baseline 1. No assessment of baseline local situation on available Government information regarding local development and service delivery 2. No Provincial Development Strategies for any of KR governorates Target: 1. Finalized printed provincial strategies with manuals handed over to MoP. 2. Finalized programmatic reporting for project closure. | Activity.1.1 |  |  |  |  | UNDP | 30071 | KRG | 00135 | 61300 | Personnel - Int | 20000 |  | 35500.167 | 169999.9704 | #REF! | #REF!
| 1.1.1 Handover of printed PDSs for KR MoP and provincies (Erbil, Suli and Dohuk). |  |  |  |  | UNDP | 30071 | KRG | 00135 | 72100 | Contracts | 8000 | 46167 | 189145 | 434511 | 150000 | 819823
| 1.1.2 Handover of PDS manual and PAP manuals |  |  |  |  | UNDP | 30071 | KRG | 00135 | 71600 | Travel - missions | 4085 | 46167 | 153644.833 | 264511.0296 | #REF!
1.1.3.Final Project Board Meeting for project closure
1.1.4. Final programme reporting
Total of Output 1 | [11 empty] | 32085
Output 2 (Output 1 - Shell): Inclusive participatory processes in local area planning and decision-making are institutionalized. Local communities are given a key role in influencing development priorities and in turn contribute to further stability and reconciliation Indicators - Sucessfull implimentation of development projects under Shell Partnership - Technical assistance provided to the planning of sub-districts Baseline: Needs identified in the consultation process are reflected in the local district plan for public funding consideration, Community priorities and needs are addressed Target • Establish new MoU with Shell • Enter cost-sharing agreements with Shell for new projects • Sustainbility assessment to be conducted for executed projects | Activity 2.1 |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61300 | Personnel - Int | 45000
| 2.1.1 Negotiate new MoU with Shell for areas of cooperation |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61100 | Personnel - Nat
| 2.1.2 Due delegence process for entering new MoU |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 71600 | Travel | 4000
| 2.1.3 Draft project documents under new partnership |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 72100 | Contracts | 2500
| 2.1.4 Conduct sustainability assessment for executed projects |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 74500 | Miscellaneous | 352
Total of Output 2 | [11 empty] | 51852
Output 3 (Output 2 - Shell): Institutional capacity and technical capability at national and sub national level to support local inclusive development and service delivery established Indicators - Sucessfull implimentation of development projects under Shell Partnership - Technical assistance provided to the planning of sub-districts Baseline: Governorate Steering Committee and District Technical Committee are able to perform their functions and advise on institutionalisation of process Target • Follow up on formulated sub-district development strategies for targeted sub-districts • Conceptual notes of programmatic intervention to be proposed to national institutions based on conducted organizational assessments | Activity 3.1: |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61300 | Personnel - Int | 45000
| 3.1.1 Integrate formulated sub-district development planning with Provincial Annual Plan |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61100 | Personnel - Nat
| 3.1.2 Prepare concept note for BOTI with MOU draft for future cooperation |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 71600 | Travel | 1000
| 3.1.2 Presentation of organizational assessment for South Oil Company, with concept note for providing technical assistance |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 72100 | Contracts | 3000
[6 empty] | UNDP | 30000 | SHELL | 11790 | 74500 | Miscellaneous
Total of Output 3 | [11 empty] | 49000
Management Cost | Management Cost
| Common Premises | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 73120 | Common Premises | 50000 | It needs to be calsulated as a lump sum ($6,196.37 * staff No.)
| Life Support | X | X | X | X | UNDP |  |  |  | 73120 | Life Support | 0 | It is not percentage, it has 3 different calsulation: - Baghdad Intrnational Staff= $33.42 per staff * 264 days - Baghdad Local Staff= $18.75 per staff * 264 days - Erbil (Int. & Local) Staff= $17.41 per staff * 264 days
| Communications (2.5%) | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 72400 | Communic & Audio Visual Equip | 2521.3
|  | X | X | X | X | UNDP | 30071 | KRG | 00135 | 72400 | Communic & Audio Visual Equip | 302.125
| Security (4%) | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 74300 | CO Common Security | 4034.08
|  | X | X | X | X | UNDP | 30071 | KRG | 00135 | 74300 | CO Common Security | 483.4
| Monitoring and Evaluation (2%) | X | X | X | X | UNDP |  |  |  | 74100 | Professional Services | 0
| GMS (8%) | X | X | X | X | UNDP | 30071 | KRG | 00135 | 75100 | General Management Services | 2629.642
|  | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 75100 | General Management Services | 12592.5904
Total of Management Cost | [11 empty] | 72563.1374
Total Project Budget for 2016 | [11 empty] | 205500.1374
This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partner, the plan authorizes the responsible parties and project management to manage available resources and achieve set results.
Project Manager: Thair Shraideh | 16/2/2016 | [6 empty] | UNDP Country Director
Signature & Date | [7 empty] | Signature and Date