## 2017
Atlas PROJECT Award ID: 66352 | Annual Work Plan (AWP) 2017: Version A
Atlas OUTPUT ID: 82552
ATLAS Project/Programme Title: | Development Partnership Programme
Atlas OUTPUT Name | Area Based Development Programme
UNDAF Outcome: | Outcome 5: Enabling policy and frameworks for rapid economic recovery, inclusive and diversified growth and private sector development
Applicable Key Result Area (from 2015-17 Strategic Plan):
CPAP Outcome: | Outcome 5: Enabling policy and frameworks for rapid economic recovery, inclusive and diversified growth and private sector development
CPAP Output(s): | Output 7.6: Innovations enabled for development solutions, partnerships and other collaborative arrangements
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
And baseline, associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Fund Code | Donor Name | Donor Code | Account Code | Budget Description | Amount ($) | SIDA | KRG | Shell | TRAC
Output 1 (Output 2 - KRG): Production of 18 Development Plans with district level inputs through enhanced national, regional, and governorate capacity and mechanisms and mainstreaming NDP social priorities/MDG strategies into Local Development and Service Delivery (LDSD), and through integrated knowledge management and public access to information. Indicators: 1- Number of PSDs developed and handed over to counterparts 2- Number of website constructed Baseline 1- 3 PSDs have been developed and endorsed by counterparts 2- No website is constructed for provincial development strategies Target: 1. 3 Finalized printed provincial strategies with manuals handed over to MoP. 2. Website established for formulated strategies. | Activity.1.1 |  |  |  |  | UNDP | 30071 | KRG | 00135 | 61300 | Personnel - Int | 49602.5 | 70 | 76703.9625 | 219881.0799 | 0 | 296655.0424
| 1.1.1 Handover of printed PDSs for KR MoP and provinces (Erbil, Suli and Dohuk). |  |  |  |  | UNDP | 30071 | KRG | 00135 | 72100 | Contracts | 12000 | 70 | 76704 | 219881 | 0 | 296655
| 1.1.2 Handover of PDS manual and PAP manuals |  |  |  |  | UNDP | 30071 | KRG | 00135 | 71600 | Travel - missions | 5085 | 0 | 0.0375 | -0.0799 | 0
| 1.1.3. Construct a website for formulated provincial strategies. |  |  |  |  | UNDP | 30000 | SIDA | 00555 | 74500 | Miscellaneous | 70
Total of Output 1 | [11 empty] | 66757.5
Output 2 (Output 1 - Shell): Inclusive participatory processes in local area planning and decision-making are institutionalized. Local communities are given a key role in influencing development priorities and in turn contribute to further stability and reconciliation Indicators - Number of updated sub-districts profiles - Number of draft concept notes for potential partnership with private sector developed - Number of sustainability assessment for executed projects conducted Baseline: - Two sub-districts profiles have been formulated in previous years - No sustainability assessment for executed projects have been conducted in previous years Target • Updated sub-districts profiles for Al-Dair and Al-Nashwa sub-districts • Sustainability assessment for playgrounds and school projects tp be conducted. | Activity 2.1 |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61300 | Personnel - Int | 44000
| 2.1.1 Conduct an update for sub-districts profiles |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61100 | Personnel - Nat
| 2.1.2 Approach private sector entities for potential partnerships |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 71600 | Travel | 4000
| 2.1.3 Draft concept notes and possible interventions for needs based on consultative processes |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 72100 | Contracts | 25574
| 2.1.4 Conduct sustainability assessment for executed projects |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 74500 | Miscellaneous | 1000
Total of Output 2 | [11 empty] | 74574
Output 3 (Output 2 - Shell): Institutional capacity and technical capability at national and sub national level to support local inclusive development and service delivery established Indicators - Follow-up activities on subdistrict planning to be conducted. - Number of concept notes for programatic interventions with SOEs Baseline: - Sub-district development plan formulated in previous year. - Organizational assessment for SOC was conducted in previous year. Target • Consideration of formulated sub-district planning within provincial planning to be acheived. • One concept note of programmatic intervention to be proposed to SOC based on on conducted organizational assessment | Activity 3.1: |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61300 | Personnel - Int | 33950.5
| 3.1.1 Conduct working sessions with sub-district local council and Basra Provincial Council for considering sub-district development planning within Provincial Annual Plan for 2018 |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 61100 | Personnel - Nat
| 3.1.2 Presentation of organizational assessment for senior management of South Oil Company |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 71600 | Travel | 1000
| 3.1.2 Provide technical assistance for the Training Department of SOC |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 72100 | Contracts | 30000
| 3.1.3 Draft concept note for SOC for possible interventions based on conducted organizational assessment |  |  |  |  | UNDP | 30000 | SHELL | 11790 | 74500 | Miscellaneous
Total of Output 3 | [11 empty] | 64950.5
Management Cost | Management Cost
| Common Premises | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 73120 | Common Premises | 55000 | It needs to be calculated as a lump sum ($6,196.37 * staff No.)
| Life Support | X | X | X | X | UNDP |  |  |  | 73120 | Life Support | 0 | It is not percentage, it has 3 different calculation: - Baghdad International Staff= $33.42 per staff * 264 days - Baghdad Local Staff= $18.75 per staff * 264 days - Erbil (Int. & Local) Staff= $17.41 per staff * 264 days
| Communications (2.5%) | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 72400 | Communic & Audio Visual Equip | 3488.1125
|  | X | X | X | X | UNDP | 30071 | KRG | 00135 | 72400 | Communic & Audio Visual Equip | 1667.1875
| Security (4%) | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 74300 | CO Common Security | 5580.98
|  | X | X | X | X | UNDP | 30071 | KRG | 00135 | 74300 | CO Common Security | 2667.5
| Monitoring and Evaluation (2%) | X | X | X | X | UNDP |  |  |  | 74100 | Professional Services | 0
| GMS (8%) | X | X | X | X | UNDP | 30071 | KRG | 00135 | 75100 | General Management Services | 5681.775
|  | X | X | X | X | UNDP | 30000 | SHELL | 11790 | 75100 | General Management Services | 16287.4874
Total of Management Cost | [11 empty] | 90373.0424
Total Project Budget for 2017 | [11 empty] | 296655.0424
This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partner, the plan authorizes the responsible parties and project management to manage available resources and achieve set results.
Project Manager: Thair Shraideh | [7 empty] | UNDP Country Director
Signature & Date | [7 empty] | Signature and Date

## Procurement Plan
Project Title: Development Partnership Programme
Project ID: 82552
Modality of Project Execution (DIM /NIM): DIM
# | **Expected date for specification/TOR/SOW to be finalized | Type of Supply* | Description of goods (per item), services or works (per milestone/output) | Quantities | Estimated Unit Price in USD | Estimated total price in USD | Available budget in USD | Expected completion date of contract
1 | Consulting services, Q1 | IC | Consultant for vocational training assessment | 1 | 5500 | 5500 | 5574 | Q2 2017
2 | National Consultant, Q1 | LTA | National consultants for coordination and IT | 1 | 12000 | 12000 | 12000 | Q2 2017
3
4
5
[5 empty] | Total | 17500 | 17574
REQUISTION PLAN: During the definition stage of the project cycle, all relevant activities will need to be identified and budgeted. Among these activities, considerations must be taken for the acquisition of goods, services and works in order to achieve the project objectives. Required services identified should also include any individual consultant services necessary for the successful implementation of the project (including services for complex/highly technical specifications development, if applicable). This information will be the groundwork for the establishment of the Requisition Plan.
The Requisition Plan shall be developed at the project definition stage, and must be shared with the Procurement Unit.
The requisitioner is responsible for developing the Requisition Plan, including the following minimum information:
*Type of Supply: Service from company (RFP), Individual consultnat (IC), Works (EOI then ITB), Goods (ITB/RFQ), etc.
**Expected date for specification/ToRs/SOW to be finalized: Q1, Q2, Q3 or Q4

## Recruitment Plan
Project Title: Development Partnership Programme
Project ID: 82552
Modality of Project Execution (DIM /NIM): DIM
# | Job Title | Type of position (New or Replacement) | SC/FT Level | Budgeted Monthly Pay Range | Type of contract | Duration of Employment | Month position needed to be filled | When ToR are expected to be issued
1
2
3
4
5
6
7
8
9
10
No recruitment is planned