United Nations Development Programme Iraq

[Support for Private Sector Development in Iraq – No. 00087253]

Quarterly Progress Report

Q3 2014

| Project Title: | Support for Private Sector Development in Iraq |
| --- | --- |
| UNDP Project #: | 00087253 |
| Project Duration: | 12 months |
| Project Resources: | UNDP TRAC |
| UNDP Iraq Focal Point: | Shigeru Handa, Team Leader, Loan Management Maan Al Maree, UNGC Iraq Focal Point, Private Sector Development Programme |

| UNDAF Outcome(s) | Inclusive, more equitable and sustainable economic growth |
| --- | --- |
| CP Outcome(s): | Enabling policy and frameworks for rapid economic recovery, inclusive and diversified growth and private sector development |
| Output(s): | Establishment and Implementation of Private Sector Development Strategy of Iraq |
| Implementing Partner: | United Nations Development Programme Iraq |
| Responsible Partner: | United Nations Development Programme Iraq |
| Project Location(s): | Nationwide |

Table of Contents

Executive Summary	3

Context	4

Implementation Progress	5

Output 1	5

5

Challenges	6

Issues	7

Lessons Learned	7

Future Plans	8

Financial Section	10

Table 1. Funding Overview	10

Table 2: Expenditure Status (by activity)	10

Table 3. Expenditure Status (by donor)	11

Annexes	12

Annex I:  Performance Tracking Matrix	12

Annex II: Risk Log	13

# Executive Summary

The project is to formulate the Private Sector Development Strategy of Iraq (2014-2030) (PSDS), to support the GoI in implementing the PSDS at the transitional period until an official entity in charge of PSDS is established.

In the beginning of Q3 of 2014, UNDP invited Dr.Hameed Al Anbari, Advisor and Director of the Office of services and reconstruction in PMAC and point of contact between PMAC and UNDP to participate in a miniature workshop to discuss the developments of the PSDS after endorsement by the CoM and the executive steps to launch activities for transition period, particularly structural implementation. This workshop held over 3 days 7-9 July 2014 in Amman. The WS results and recommendations are as following:

- Emphasis on joint cooperation between PMAC and the UNDP in Iraq.

- Workshop focused to maintain the momentum and push for the implementation of PSDS.

- Agreed on a mechanism to proposed management of the strategy.

- Agreed to adopt co-sharing of the planned activities based on a cost-sharing mechanism.

- Set up awareness raising workshop includes all players of the strategy.

In coordination between UNDP/PMAC and MoP, UNDP focal point finished the printing of 150 copies of the Arabic and 100 copies of English version of the PSDS in addition to 100 CDs. These copies of PSDS will be distributed to the Line Ministries, Embassies, CoR/Economic Committee and Iraqi and International Business Associations.

Many meetings took place in August and September 2014 between PMAC, line ministries and UNDP/PSDS team to keep the momentum and discuss the progress on the implementation pillar.

Before the end of 2014, PMAC/UNDP will organize a general meeting with all line ministries, business associations and academia to discuss the interim arrangement for awareness raising and how to implement the strategy until the official entity will be established.

Prior to this endorsement, the CoMs initially reviewed the PSDS in its 21st Session held on 27 May and referred it to the Economic Committee to provide detailed opinion and recommendations.  The Economic Committee (EC) is chaired by the Deputy Prime Minister (Economic Affairs) and has the ministers of finance, oil, planning, industry and minerals, trade as members in addition to the Governor of the Central Bank of Iraq, the President of the Board of Supreme Audit and PMAC. The EC recommended the strategy as comprehensive and solid to CoMs on 2 June.  Then, CoMs endorsed the strategy and the PMAC shall follow up with the development of the early stages required to establish the organizational structure.

Upon finalizing of the PSDS, Ministry of Planning took an initiative in designing the cover page of PSDS and printing required copies both in Arabic and English version in addition to digital copies on CDs with their contributions.

# Context

Recognition of the importance of the private sector and the need to support its development emerged in the past years as a major and urgent requirement to ensure economic and social growth as well as peace and stability in Iraq. The National Development Plan (NDP) for 2013-2017 recognizes this role emphasizing as a key challenge faced by private sector the ‘lack of clarity on the private sector’s role in effective development’ and the need to address this challenge as success factor for Iraqi wellbeing.

Furthermore UNDAF 2015-2018 states this commitment by dedicating special attention to the role of the private sector and empowerment of civil society, with particular attention to women, children, youth, and the most vulnerable. And the project meets UNDAF key result area on restoring the Foundations for Development (CPAP outcome and output) and it addresses priority #2 on Inclusive, more equitable and sustainable economic growth, under the UNDAF as well as the CPD 2011-2015.

The PSDS aims to create a proactive responsible private sector, also enhance the contribution of businesses to the MDGs; in view of the approaching end of MDGs timeframe (2015) and the ongoing efforts by the international community to define a post-2015 development agenda in line with the Rio+20 outcomes focused on sustainable development. Strengthening the Iraqi private sector will help integrating Iraqi economic players into this global framework of action, with benefits both at country and international level.

The PSDS will provide a road map for the Government of Iraq, to follow over the period of 2014-2030; PSDS implementation will lead to score higher on international indices that measure Iraq’s business environment, also implementing PSDS will work on private sector in Iraq to become more productive, more competitive, and able to provide an increasingly larger number of new job opportunities to Iraq’s work force.

Implementation of the PSDS will allow GoI to find solutions that address the priority needs of the business community and to diversify the economy for its inclusive growth. And gradually, the implementation role of PSDS will be transferred to the private sector in Iraq. The Government of Iraq will achieve the objectives of the Strategy using a three-pronged approach:

- Understanding Iraq’s Private Sector

- Improving Iraq’s Business Environment

- The SME Support Programme

The fourth approach will carry out the work on the three development pillars; the objective of this project is to support GoI establishing the enabling, predictable, easy business environment for the Private Sector development of Iraq.

MDG(s) being addressed in the PSDS:

Goal 1: Eradicate extreme poverty and hunger

Goal 3: Promote gender equality and empower women

Goal 7: Ensure environmental sustainability

Goal 8: Develop global partnerships for development

National Development Plan goal(s) being addressed in PSDS:

- Enhancing the Private Sector’s Developmental Role

- Partnership between the Private and Public Sectors

- Promoting an Environment that Encourages Investment

- Strengthening the Private Sector’s Role in Regional Development

# Implementation Progress

# As a cumulative outcome, the Private Sector Development Strategy of Iraq was developed, including inputs from Iraqi businesses and endorsed by the Council of Ministers on 24 June 2014. This was a significant achievement to move forward.

# In coordination with Ministry of Planning/ Central Statistical Organization/ Printing Press Department through an official letter issued by PMAC, UNDP printed out the Arabic and English versions of the PSDS in MoP. 150 Arabic version copies were shared with COMSEC, PMO/Economic Committee, Line Ministries, CoR/Economic Committee and Iraqi Business Associations. 100 English version copies were recently received from MoP/ 25 copies to PMAC and 75 to UNDP Iraq office to be distributed to the Embassies, International counterparts and International Business Entities. 100 copies of CDs were printed in MoP and received by UNDP and shared with PMAC.

# From 7-9 July 2014, UNDP/PSDS team held a roundtable meeting in Amman with Dr.Al Anbari/PMAC Advisor for Reconstruction and Services Committee.

# The following recommendations have been achieved in the roundtable meeting:

# - Emphasis put on joint cooperation between PMAC and UNDP in Iraq at the level of implementation of the Private Sector Development Strategy (PSDS) in Iraq and at all levels and sectors.

# - Workshop focused to maintain the momentum and push for the implementation of the PSDS forward.

# - Agreed on a mechanism to proposed management of the strategy during the transitional period and the establishment of the Task Force and six working groups to implement the PSDS.

# - Agreed to adopt co-sharing of the planned activities based on a cost-sharing mechanism, where the Iraqi government allocated a sum of money in addition to what has been allocated by UNDP for the implementation of the strategy to develop the private sector. Dr.Al Anbari will present the proposed mechanism to the President of PMAC within the year 2014 and then work on getting written consent in this regard.

# - Setting up a workshop including all players of the strategy for the purpose of raising their awareness and to initiate the implementation of the strategy by the agreed upon timings and place commensurate with the workshop schedule.

# Many meetings took place in Baghdad in August and September after the roundtable meeting in Amman between PSDS focal point and PMAC to keep the momentum of the programme and maintain communication with the PSDS counterparts.

# The PSDS will contribute to an efficient, predictable and transparent business enabling environment that will eventually lead to economic growth, diversification and job creation in Iraq.

# Challenges

# One of the challenges facing the project is the communication with GoI and private sector entities is sometimes ineffective due to the security situation and the large number of official holidays, which have caused delays in achieving the goals on time. Also, the slow response of GoI and the private sector in providing inputs which was affected the timeline of project work plan.

# The second challenge is the time required for certain operational procedures at the UN level and the operational arrangements for the UNDP staff.

# The main implementation challenges from an operational point of view, is the difficulty and impossibility to work side by side with beneficiaries located in the Red Zone of Baghdad. Security restrictions and extremely limited number of Red Zone movements made it difficult to travel to field locations and to organize meetings with Iraqi counterparts and to interact with UNGC Iraq Local Network and Steering Committee members on the ground outside the International Zone. The complicated procedures for getting Iraqi counterparts into the International Zone and the limited number of escorts available to handle visitors' requests caused more problems and delays.

# Furthermore, in the second quarter of 2014 there was CoR election held in 30 April and the possibility of changing the cabinet will affect the PSDS coordination and work plan. This should be avoiding by direct coordination with PMAC to sustain the momentum of the strategy.

# One of the most effecting challenges was the decision of SRSG to remove the UNCT from Baghdad issued on 15th June 2014 because of the security incidents that took place in many provinces in Iraq and edict for national staff to work from home and restricted movement decision which affected the implementation of the programme. Despite of the UNCT decisions, PSDS team kept direct communication with PSDS counterparts.

Some risks identified in the project implementation:

- The political affiliation of key Government counterparts, which materialized particularly at local level where in some cases the counterparts delayed or impeded activities for political reasons.

- UNDP team, in coordination with GoI, CoR, Private Sector Representative, Civil Society Leaders, had to first support the endorsement of the PSDS by the CoM and second to adopt and implement the Private Sector Laws by CoR.

- Security situation (as envisaged, progresses in the programme implementation were undermined by the volatile security situation, which often led to changes and re-planning of the activities). This situation led the UNDP team to authorize the programme coordinator to meet Private Sector Counterparts in any convenient time and place.

-  The escalation of security situation when ISIS invaded Nineveh, Salahuddin and Anbar which affected all UN and Iraqi Government programmes. After 10th June the security situation deteriorated and ISIS threatened Baghdad, resulting in an UNAMI imposed edict for UN agencies to request national staff to restricted their movement and work from home until further notice. These measures led to miscommunication with all counterparts and delayed most of the programme activities and changing the time frame of private sector development strategy in Iraq.

Issues

Due to the security situation in Baghdad, the project team couldn`t gather the GoI, NGOs, Line Ministries Representatives, Local and International Business Associations and Business Women. UNDP held a roundtable meeting in Amman gathering all stakeholders in onetime and place to facilitate the consultation process among the GoI, the Private Sector and the international community includes wide range of female stakeholders to endorse the PSDS.

Lessons Learned

In terms of relations with the GoI, the PSDS was implemented through a management mechanism agreed upon with the GoI that aims to strengthen the country’s ownership in the process of reforms for private sector development. PSDS’s activities are identified, planned for and regularly reviewed in a joint work plan with the Programme Management Team (PMT). All activities were planned for and implemented in close consultation with the relevant GoI bodies and other stakeholders by order of the Council of Minister Secretariat (COMSEC) and UNDP. This management mechanism has been very successful.

The Integrated Management Structure of PSDS was introduced building upon the joint capacity and coordination of UNDP team that was physically present in Baghdad. The PSDS team was working under the overall coordination of the UNDP Programme Director who has a physical presence in Baghdad and other locations on the ground. The programme team proved to be an essential element for proper coordination of joint activities and constant follow-up with relevant counterparts. The presence of the UNDP team in Baghdad was to ensure effective interaction and participation of our main partners, PMAC, MoP, Private Sector Representatives to ensure achievement of the outcomes of this programme, mainly those related to the social dialogue issues, especially their roles in the establishment of the Corporate Social Responsibility CSR.

Since the project assured the inclusive approach, MoP took the lead of designing the cover page and printing required copies both in Arabic and English. Through this inclusive approach, the project managed to enhance the GoI’s ownership on the PSDS.

Another lesson learnt is the establishment of partnerships with relevant organizations and donors, which emerged to cope with challenges such as unexpected inability or withdrawal of organizations initially assigned to conduct the planned activities, Even if not planned in the project design these partnerships, such as the partnership established by UNDP with the USAID, served to advance progress towards common goals.

Dealing with the security situation, especially in terms of movement for UN programme team which caused limited interactions with local counterparts, were solved to some extent by recruiting more national staff instead of international ones, as originally planned. This proofed to be a useful practice for the assignment where national staff whereas in a better position to move forward PSDS activities through closer coordination with local government and private sector counterparts.

The timeframe of major institutional changes sought for in PSDS proved unrealistic for a country suffering from great degrees of political instability, poor capacities, and where the interaction with the Iraqi counterparts is severely restrained by restrictions of movement. In some cases, the rationale for some of the reforms and bylaws proposed could have been discussed more in depth and agreed upon in clearer terms, if time had allowed it. Some institutions did not fully buy-in from the start, and consequently did not take the lead of the proposed reforms, leaving these policies and bylaws mid-way.

# Future Plans

# PSDS will enhance collaborative decision-making by streamlining the sharing and timely exchange of information among UNDP and GoI, Line Ministries and Private Sector Entities to facilitate a real multiple dialogue on policy issues.

# Coordination and management arrangements in multi-administrative efforts of several counterparts should be given close attention, especially when the programme is operating at a number of levels, and when it involves many institutions and stakeholders. The participating institutions should ensure that appropriate work arrangements are made to improve the implementation.  It is also important to note that such projects should operate with less ambition and more realistic expectations, even if this requires a longer inception/preparation period. This would allow for a better understanding of the context and for more realistic expectations in terms of project impacts.

# Institutional and legislative changes have to be understood, owned and politically committed to by the national and provincial decision makers, before drafts of Policies and Laws can be successfully implemented. This can be achieved when there is direct and regular interaction with decision makers and when well-connected National staff assists in the liaison.

# Financial Section: 
Note: All financial data presented in this report are provisional. From UNDP Bureau of Management/Office of Finance and Administration, an annual certified financial statement as of 31 December will be submitted every year no later than 30 June of the following year.

## Table 1: Funding Overview

| Donor | Commitment (Currency of the Agreement) | Received (Currency of the Agreement) | Received (USD) | UNORE | Balance (Currency of the Agreement) |
| --- | --- | --- | --- | --- | --- |
| TRAC | USD 500,000 | - | USD 500,000 | - | - |
| Total |  |  | USD 500,000 |  |  |

The table on funding overview will cover funding since inception of the project, and will include only those contributions for which legal basis i.e. agreement/ letters exchange, exist.   Column 1:  will include the name of the donor, with a new adjacent cell created for every different agreement signed with the same donor.  Column 2, commitment, will include the amount of the commitment as stated in the agreement in the same currency as in the agreement.  Column 3: shows the amount of the money received against every commitment. If the currency in the agreement is denominated in USD, this slot can be left blank.  Column 4: provides for the US equivalent of the received amount of the local currency, with Column 5: providing the United Nations Operational Rate of Exchange at the date of the receipt of funds. Column 6: provides for the balance of the contribution expected to be received from the donor.  This is arrived at through subtraction of total received amount from the commitments.

## Table 2: Expenditure Status (by activity)

| Activity | Budget (A) | Donor | Cumulative Expenditure Status at End of June, 2014 | Expenditure in Reporting from July to End of September , 2014 | 3rd Quarter Expenditure (F=D+E) | Total Expenditure (G=B+C+F) | Budget Balance (H=A-G) | Delivery Rate (%I =G/A) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Commitment (B) | -Expenses + full asset cost (C) | Commitment (D) | Expenses + full asset cost (E) |  |  |  |  |
|  | USD 500,000 | 12 | 1,067.69 | 459,466.70 | 1,113.00 | 4,372.37 | 5,485.37 | 466,019.76 | 33,980.24 | 93% |
| GMS | NA |  |  |  |  |  |  |  |  |  |
| Total | USD 500,000 | 12 | 1,067.69 | 459,466.70 | 1,113.00 | 4,372.37 | 5,485.37 | 466,019.76 | 33,980.24 | 93% |

## With regards, to GMS, projects should reflect only ATLAS records as GMS is expected to be posted on time this year.  Columns 1, 2 and 3 which respectively indicate activity, budget and donor of the project reflect the planned budget as in the AWP.  Column 4/5, which indicates Expenditure Status at date of closure of the last reporting phase, will show commitments and disbursement   up to that point. It is advised to use the IPSAS project resource management reports - fund resource overview; project resource overview; project budget balance; project transaction detail. This section has been re-aligned with these reports to make the reporting meaningful and easy.  Commitments are the written contractual obligations which the project has signed out, while disbursements indicate the amount of money which was actually paid for the obligations. In UNDP corporate terms: OPEN REPORTED COMMITMENTS as at the reporting period ARE UNRECEIPTED POs ONLY.    Columns 6/7 similarly indicate commitments and disbursements, however only for the reporting quarter.  Column 8, Quarterly expenditure, will sum up the commitments and disbursements in the reporting quarter.  Column 9, on total expenditures will add the quarter expenditure (column 8) to the expenditure status at the end of the last reporting quarter (columns 4/5).  Column 10, the Balance, is arrived at through subtracting, total expenditure (column 9), from the budget (column 2).  Finally the last column, Column 11, delivery, will be expressed in percentage terms, and is calculated by dividing total expenditure (column 9) by the budget (column2).

## Table 3: Expenditure Status (by donor)

| Donor | Budget | Activity | Expenditure Status at [Date] | Expenditure in Reporting Quarter | Quarter Expenditure | Total Expenditure | Balance | Delivery |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Commitment | Disbursement | Commitment | Disbursement |  |  |  |  |
| GMS |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |

The explanation under this section is similar to the above section, however here the difference is that on this table expenditure is categorized as per source of funding/donor.

# Annexes

## Annex I:  Performance Tracking Matrix

| Result/Goals | Performance Indicators | Baseline Info | Performance Benchmark and Targets | Implementation Progress in reporting quarter |
| --- | --- | --- | --- | --- |
| Private Sector Development Strategy of Iraq (PSDS) established and its associated action plans initiated with optimal institutional arrangement | Number of Inclusive consultations to refine the PSDS; PSD strategy endorsed; Action Plan Endorsed; Institutional arrangement in place for implementation of PSD Strategy | No PS Strategy endorsed by GOI (a draft is available but not endorsed) | At least 2 meetings/workshops taking place in a participatory process PSDS endorsed through wide consultative mechanism ensuring inclusive and fair representation based on gender, geographic areas, sectors, typology of enterprises criteria Private Sector council established for implementing the PSDS strategy Institutional arrangement in place with ToR Project Document developed to support implementation stage | PSDS endorsed by the Council of Ministers through wide consultative mechanism |

## Annex II: Risk Log:

| Project Title: Support for Private Sector Development in Iraq | Award ID: | Date: Dec 2013 |
| --- | --- | --- |
| # | Description | Date Identified | Type | Impact and Probability | Countermeasures / Management response | Owner | Submitted, updated by | Last Update | Status |
| 1 | Endorsement of PSDS takes longer Possible prolonged legislative process within the GoI | Dec 2013 | Political/ Operational | Could affect the delay of private sector development in Iraq as well as better business environment. P = 2 / I =2 | Continuous follow up with the consultation meetings with GoI and the Private Sector with clear milestones | Project Manager | Project Manager | Dec 2013 |  |
| 2 | Due to complicated functions among relevant government authorities, establishment or assignment of a single entity in charge of PSDS implementation may create prolonged internal discussions | Dec 2013 | Political/ Organizational | Could affect the project implementation schedule as well as the overall PSDS implementation P=2 / I=2 | Continuous engagement in the senior GoI officials during the strategy formulation process to keep them aware of the importance of implementation of the strategy | Project Manager | Project Manager | Dec 2013 |  |
| 3 | Security situation in Iraq preventing movements / meetings with the private sector | Dec 2013 | Operational | Could affect the project implementation schedule P= 4 / I= 4 | Increase virtual technological platforms usage for holding meetings. | Project Manager | Project Manager | Dec 2013 |  |