## Sheet1
Data to be provided/completed by Programme/Project
Project Name | Project ID | Type of Supply (service, goods, Individual consultant, civil work) | High Level Categorizaton (Low, Medium, High) | Description of goods, services or works | Quantity/ Duration | Estimated Total Price in USD | Available budget in USD | Estimated Completion of Activity | Requesting Unit/Focal Point | Date for Procurement Unit to Receive the TOR | Case Officer to be assigned | Comments
KRG | 69415 | Goods |  | Office Furnature - UNDP |  | 5000 | 5000 | April | Nimal | April | Samer
KRG | 69415 | Goods |  | Office IT Equipment - UNDP |  | 38000 | 38000 | April | Nimal | April | Samer
KRG | 69415 | Goods |  | Vehicle - MOE |  | 120000 | 120000 | April | Nimal | April | Samer
KRG | 69415 | Goods |  | Stationary - UNDP |  | 7000 | 7000 | April | Nimal | April | Samer
KRG | 69415 | Services |  | Driver / cleaner - UNDP |  | 10000 | 10000 | April | Nimal | April | Samer
KRG | 69415 | Services |  | National consultant - Civil Engineer / Architec/ Erbil |  |  |  |  | Nimal |  | Samer | done
KRG | 69415 | Services |  | 2National Consultants - Civil Engineer for Erbil and Duhok | 5 months | 55000 | 55000 | end of 2014 | Nimal | May | Samer
KRG | 69415 | Services |  | National Consultant - Electrical Engineer for Sulaimaniyeh | 6 month | 28000 | 28000 | end of 2014 | Nimal | May | Samer
KRG | 69415 | Services |  | Contract Extension - Bava till end of May 2014 | 1 month | 28000 | 28000 | end of May | Nimal | April | Samer
KRG | 69415 | Services |  | Contract Extension - Takeda till end of Nov. 2014 | 5 months | 80000 | 80000 | end of November | Nimal | May | Samer
EECC |  | Services |  | INC-High level meeting - Baghdad |  | 5000 |  |  | Sarmad | 2014-05-01 | events focal point
EECC |  | Services |  | INC-High level meeting - Erbil |  | 7000 |  |  | Sarmad | 2014-05-04 | events focal point
EECC |  | Services |  | INC validation workshop - Baghdad |  | 10000 |  |  | Sarmad | 2014-05-01 | events focal point
EECC |  | Services |  | KRG-OD meeting - Erbil |  | 10000 |  |  | Sarmad | 2014-04-15 | events focal point
EECC |  | Services |  | DRM/ training courses and workshops - TBD |  | 50000 |  |  | Seiichi |  | events focal point
EECC |  | Services |  | Unsteady flow Analysis with HEC-RAS with case study on TIGRIS River (workshop) - Istanbul |  | 10000 |  |  | Seiichi |  | events focal point
EECC |  | Services |  | Introductory course-groundwater management/GMS - Istanbul |  | 10000 |  |  | Seiichi |  | Samer
EECC |  | Services |  | Local consultant / Developing Disaster Risk Management capacities in Iraq |  | 10000 |  |  | Manal | 2014-10-01 | Samer
EECC |  | Services |  | Drought Risk Management workshop - Amman |  | 17000 |  |  | Seiichi |  | events focal point
EECC |  | Services |  | International consultants / US DOS Water |  | 30000 |  |  | Seiichi |  | Samer
EECC |  | Services |  | UD DOS Water workshop - Baghdad |  | 4000 |  |  | Seiichi |  | events focal point
KRG | 69415 | Services / Goods | Middle | Transmission system Planning Software / hardware and training and other office equipment required to establish transmission study unit |  | 300000 | 300000 | May | Nimal | April | Samer
SS | 87255 | Services | Middle | Study tour in Indonesia |  | 18000 | 18000 | end of June | Shigeru | May | events focal point
SS | 87255 | Services | Middle | Study tour in India |  | 18000 | 18000 | end of July | Shigeru | June | events focal point
FMA | 72135 | Services | Middle | Capacity Building Training on Procurement and Project Managementfor PMTs | 1.5 year | 200000 | 300000 | end of May | Shiori | 2014-04-06 | Samer
FMA | 72135 | Goods | Middle | Equipment and furniture for setting up the office in Basra |  | 10000 |  |  | Shiori |  | Samer
FMA | 72135 | Services | Middle | Workshop for Project Management in Dubai | 6 days | 46484.27 | 50000 | 19-24 April 2014 | Shiori | Ongoing | events focal point
FMA | 72135 | Services | Middle | Workshop for Project Management | 6 days | 50000 | 50000 | September | Shiori |  | events focal point
FMA | 72135 | Services | Middle | Workshop for Project Management | 6 days | 50000 | 50000 | September | Shiori |  | events focal point
FMA | 72135 | Services | Middle | Procurement Training for PMTs (Basra) | 5 days | 25000 | 30000 | End of June | Shiori |  | events focal point
FMA | 72135 | Services | Middle | Procurement Training for PMTs (Basra) | 5 days | 25000 | 30000 | August | Shiori |  | events focal point
FMA | 72135 | Services | Middle | Procurement Training for PMTs (Basra) | 5 days | 25000 | 30000 | August | Shiori |  | events focal point
| 72135 | Services | Middle | Travel Arrangement for Training in Japan | 7 days | 25000 | 30000 | End of June
FMA | 72135 | Services | Middle | Knowledge Sharing Workshop | 6 days | 100000 | 120000 | End of May | Shiori |  | events focal point
FMA | 72135 | Services | Middle | Financial Management Training | 7 days | 50000 | 50000 | October | Shiori | August | Samer
FMA | 72135 | Services | Middle | Financial Management Training | 7 days | 50000 | 50000 | October | Shiori |  | Samer
FMA | 72135 | Services | Middle | Video Production for the Project | 2 months | 15000 | 20000 | October | Shiori | August | Samer
FMA | 72135 | Services | Middle | Contract Extension | 6 months | 150000 | 200000 | Beginning of May | Shiori | 2014-04-10 | Samer
FMA | 72135 | Services | High | System for monitoring tool | 4 months | TBD | 300000 |  | Shiori | September | Samer
EECC |  | Services |  | inception workshop / Developing Disaster Risk Management capacities in Iraq |  | 25000 |  |  | Manal | 2014-03-10 | events focal point
EECC |  | Services |  | INC-Translation of Report |  | 20000 |  |  | Sarmad | 2014-07-01 | Samer
EECC |  | Services |  | INC Launch- Baghdad |  | 10000 |  |  | Sarmad | 2014-08-15 | events focal point
EECC |  | services |  | Water Diplomacy Training/Workshop |  | 60000 |  |  | seiichi | Apr | events focal point
EECC |  | services |  | Transboundary Water Training/Workshop |  | 45000 |  |  | seiichi | May | events focal point
EECC |  | services |  | Contract Extension-Seiichi Sasaki |  |  |  |  | seiichi | May | Samer
EECC |  | services |  | Contract -National Water Advisor |  | 70000 |  |  | seiichi | May | Samer
EECC |  | services |  | GEF Solar PV consultants |  |  |  |  | seiichi | July | Samer